## Tabs Index
S.No. | Tab Index | Remarks
1 | MTO Input | Input required from Client; Let us know if you need us to prepare MTOs from your 3D Model/Drawings
2 | MTO Input Pipe Class | Input required from Client
3 | LF & Wage Rate Input | Preliminary input from Client - can be refined later as necessary
4 | Field Construction Plan | Preliminary input from Client - can be refined later as necessary
5 | Module Construction Plan | Preliminary input from Client - can be refined later as necessary
6 | Spool Fabrication Plan | Preliminary input from Client - can be refined later as necessary
7 | PP or IWP Mapping | Preliminary input from Client - can be refined later as necessary
8 | Allowances | Output from EstiResource
9 | WBS_L-Summary By Isometric | Output from EstiResource
10 | WBS1-Project Level Summary | Output from EstiResource
11 | WBS2-Summary By Area | Output from EstiResource
12 | WBS3-Summary By Service | Output from EstiResource
13 | WBS4-Summary By Line No | Output from EstiResource
14 | Output-Labor Detail | Output from EstiResource
15 | Piping Labor Summary Overview | Overviews, analysis and metrics from EstiResource
16 | Metrics by Location | Overviews, analysis and metrics from EstiResource
17 | Spool Fab Summary | Overviews, analysis and metrics from EstiResource
18 | Module Piping Summary | Overviews, analysis and metrics from EstiResource
19 | Field Piping Summary | Overviews, analysis and metrics from EstiResource
20 | Labor Codes | EstiResource COA for information
Tabs Index - Click to navigate to desired tab

## MTO Input
MTO_ID | WBS1 | WBS2/Area | WBS3/Sub-Area/Module No./ Service | WBS4/Line Number | WBS_L/Isometric | Pipe Class | Description | Size | Units | Quantity | Shop Prefab/Stick Built | Location | Rack/Off-Rack
1500001 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 10 | EA | 1 | Stick Built | Field | Off Rack
1500002 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | CLAMP PIPE SHOE - S4 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500003 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500004 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.352 | Spool Fabrication | Field | Off Rack
1500005 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500006 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500007 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500008 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | SWAGE, ECCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500009 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500010 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500011 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500012 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | SWAGE, ECCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500013 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.152 | Spool Fabrication | Field | Off Rack
1500014 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500015 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500016 | Project A | Area_1 | TR | TR-YP01-8087 | ISO4009 | YP01 | CONTROL VALVE, GLOBE BODY, CL300, RF, (BY INSTRUMENTATION) | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1500017 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1500018 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500019 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500020 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500021 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500022 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500023 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500024 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500025 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1500026 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500027 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500028 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500029 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500030 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | VARIABLE LENGTH SUPPORT - SP36 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500031 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | VARIABLE LENGTH SUPPORT - SP36 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500032 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.166 | Spool Fabrication | Field | Off Rack
1500033 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500034 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500035 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500036 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500037 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500038 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 35.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500039 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.249 | Spool Fabrication | Field | Off Rack
1500040 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500041 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | SPECTACLE BLIND, ASME B16.48, CL300, RF, 9.7mm THK, ASTM A516 GR. 70N | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500042 | Project A | Area_1 | IA | IA-XP02-9003 | ISO2044 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1500043 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | GUIDE FOR PIPE SHOE - G6 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500044 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | GUIDE FOR PIPE SHOE - G6 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500045 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1500046 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1500047 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500048 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500049 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500050 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500051 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500052 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | PIPE GUIDE - G4 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500053 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | PIPE GUIDE - G4 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500054 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 4 | EA | 1 | Stick Built | Field | Off Rack
1500055 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | PIPE GUIDE - G4 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500056 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE GUIDE - G4 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500057 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE GUIDE - G4 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500058 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 4 | EA | 1 | Stick Built | Field | Off Rack
1500059 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE GUIDE - G4 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500060 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500061 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500062 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500063 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500064 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500065 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 10 | EA | 1 | Stick Built | Field | Off Rack
1500066 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | DIRECTIONAL ANCHOR - A6 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500067 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | PIPE SHOE - S2L | 10 | EA | 1 | Stick Built | Field | Off Rack
1500068 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 10 | EA | 1 | Stick Built | Field | Off Rack
1500069 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500070 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500071 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500072 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH 80 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500073 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 8.635 | Spool Fabrication | Field | Off Rack
1500074 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.289 | Spool Fabrication | Field | Off Rack
1500075 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500076 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1500077 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | PIPE GUIDE - G4 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500078 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | PIPE GUIDE - G4 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500079 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 4 | EA | 1 | Stick Built | Field | Off Rack
1500080 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 4 | EA | 1 | Stick Built | Field | Off Rack
1500081 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | DIRECTIONAL ANCHOR - A6 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500082 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500083 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | PIPE SHOE - S1L | 6 | EA | 1 | Stick Built | Field | Off Rack
1500084 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500085 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500086 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500087 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500088 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500089 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500090 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | DIRECTIONAL ANCHOR - A6 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500091 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | PIPE SHOE - S1L | 6 | EA | 1 | Stick Built | Field | Off Rack
1500092 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500093 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500094 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1500095 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500096 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500097 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500098 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 6 | EA | 1 | Stick Built | Field | Off Rack
1500099 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500100 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500101 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500102 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500103 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500104 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500105 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 6 | EA | 1 | Stick Built | Field | Off Rack
1500106 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500107 | Project A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500108 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.406 | Spool Fabrication | Field | Off Rack
1500109 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.192 | Spool Fabrication | Field | Off Rack
1500110 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.399 | Spool Fabrication | Field | Off Rack
1500111 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500112 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500113 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500114 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.079 | Spool Fabrication | Field | Off Rack
1500115 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500116 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500117 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | General Support | 4 | EA | 1 | Stick Built | Field | Off Rack
1500118 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500119 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.564 | Spool Fabrication | Field | Off Rack
1500120 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500121 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500122 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 15.7mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500123 | Project A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.664 | Spool Fabrication | Field | Off Rack
1500124 | Project A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500125 | Project A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500126 | Project A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 15.7mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500127 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500128 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500129 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | DUMMY EXTENSION SUPPORT - D3 (L=840mm) | 4 | EA | 1 | Stick Built | Field | Off Rack
1500130 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | DUMMY EXTENSION SUPPORT - D3 (L=340mm) | 4 | EA | 1 | Stick Built | Field | Off Rack
1500131 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500132 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500133 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500134 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500135 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500136 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.21 | Spool Fabrication | Field | Off Rack
1500137 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500138 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.21 | Spool Fabrication | Field | Off Rack
1500139 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 4x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500140 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 4x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500141 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.015 | Spool Fabrication | Field | Off Rack
1500142 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.265 | Spool Fabrication | Field | Off Rack
1500143 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500144 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500145 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.266 | Spool Fabrication | Field | Off Rack
1500146 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.266 | Spool Fabrication | Field | Off Rack
1500147 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500148 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500149 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500150 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 13.916 | Stick Built | Field | Off Rack
1500151 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500152 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500153 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500154 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.983 | Spool Fabrication | Field | Off Rack
1500155 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500156 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500157 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500158 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500159 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500160 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500161 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500162 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500163 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.41 | Spool Fabrication | Field | Off Rack
1500164 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 4x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500165 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.415 | Spool Fabrication | Field | Off Rack
1500166 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500167 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500168 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | CONTROL VALVE, BUTTERFLY BODY, CL600, RF WAFER, (BY INSTRUMENTATION) | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500169 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.166 | Spool Fabrication | Field | Off Rack
1500170 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500171 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500172 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500173 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500174 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 4x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500175 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.41 | Spool Fabrication | Field | Off Rack
1500176 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500177 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.165 | Spool Fabrication | Field | Off Rack
1500178 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500179 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500180 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500181 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1500182 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.306 | Spool Fabrication | Field | Off Rack
1500183 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500184 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500185 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.299 | Spool Fabrication | Field | Off Rack
1500186 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500187 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500188 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 8.48 | Spool Fabrication | Field | Off Rack
1500189 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.276 | Spool Fabrication | Field | Off Rack
1500190 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500191 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 6x4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500192 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500193 | Project A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 15.7mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500194 | Project A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500195 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500196 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 4.197 | Spool Fabrication | Field | Off Rack
1500197 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500198 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500199 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 4.109 | Spool Fabrication | Field | Off Rack
1500200 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500201 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500202 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.353 | Spool Fabrication | Field | Off Rack
1500203 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500204 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.175 | Spool Fabrication | Field | Off Rack
1500205 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500206 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500207 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500208 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.7 | Spool Fabrication | Field | Off Rack
1500209 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500210 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.1 | Spool Fabrication | Field | Off Rack
1500211 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500212 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500213 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 6.266 | Spool Fabrication | Field | Off Rack
1500214 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500215 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500216 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 15.319 | Stick Built | Field | Off Rack
1500217 | Project A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 4x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500218 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500219 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500220 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 4.18 | Spool Fabrication | Field | Off Rack
1500221 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 4x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500222 | Project A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500223 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500224 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.079 | Spool Fabrication | Field | Off Rack
1500225 | Project A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500226 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500227 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500228 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500229 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.863 | Spool Fabrication | Field | Off Rack
1500230 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.429 | Spool Fabrication | Field | Off Rack
1500231 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500232 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500233 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500234 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1500235 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500236 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500237 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500238 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500239 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500240 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500241 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500242 | Project A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500243 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500244 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500245 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500246 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500247 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500248 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500249 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500250 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500251 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500252 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500253 | Project A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500254 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500255 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500256 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500257 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1500258 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500259 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500260 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500261 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500262 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500263 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500264 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500265 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500266 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500267 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500268 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500269 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500270 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500271 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500272 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500273 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500274 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500275 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500276 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500277 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500278 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500279 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500280 | Project A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500281 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500282 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500283 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500284 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500285 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | CLAMP PIPE SHOE - SP18 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500286 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.404 | Spool Fabrication | Field | Off Rack
1500287 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500288 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 1.408 | Spool Fabrication | Field | Off Rack
1500289 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500290 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500291 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500292 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500293 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500294 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500295 | Project A | Area_1 | FL | FL-XP01-8123 | ISO2040 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500296 | Project A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500297 | Project A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500298 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500299 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500300 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500301 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500302 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500303 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500304 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500305 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1500306 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.711 | Spool Fabrication | Field | Off Rack
1500307 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.142 | Spool Fabrication | Field | Off Rack
1500308 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500309 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500310 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500311 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500312 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500313 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500314 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500315 | Project A | Area_1 | DL | DL-XP01-8002 | ISO2006 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500316 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500317 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500318 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500319 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.142 | Spool Fabrication | Field | Off Rack
1500320 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500321 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.507 | Spool Fabrication | Field | Off Rack
1500322 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500323 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500324 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500325 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1500326 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.711 | Spool Fabrication | Field | Off Rack
1500327 | Project A | Area_1 | DL | DL-XP01-8001 | ISO2036 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500328 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500329 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500330 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500331 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500332 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500333 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500334 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500335 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500336 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 10x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500337 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500338 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500339 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500340 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500341 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 10x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500342 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | CLAMP PIPE SHOE - S4 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500343 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500344 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500345 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500346 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500347 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | CLAMP PIPE SHOE - SP28 | 10 | EA | 1 | Stick Built | Field | Off Rack
1500348 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.4 | Spool Fabrication | Field | Off Rack
1500349 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 4.117 | Spool Fabrication | Field | Off Rack
1500350 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500351 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 2.03 | Spool Fabrication | Field | Off Rack
1500352 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500353 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 10x4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500354 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500355 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 10.457 | Spool Fabrication | Field | Off Rack
1500356 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500357 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500358 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 2.367 | Spool Fabrication | Field | Off Rack
1500359 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500360 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 3.367 | Spool Fabrication | Field | Off Rack
1500361 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500362 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 10x4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500363 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500364 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500365 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500366 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.324 | Spool Fabrication | Field | Off Rack
1500367 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500368 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 4.102 | Spool Fabrication | Field | Off Rack
1500369 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500370 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1.814 | Spool Fabrication | Field | Off Rack
1500371 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500372 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500373 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500374 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500375 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500376 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500377 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500378 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500379 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500380 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1 | Spool Fabrication | Field | Off Rack
1500381 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.3 | Spool Fabrication | Field | Off Rack
1500382 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500383 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 35.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500384 | Project A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500385 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1.713 | Spool Fabrication | Field | Off Rack
1500386 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500387 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500388 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.3 | Spool Fabrication | Field | Off Rack
1500389 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.701 | Spool Fabrication | Field | Off Rack
1500390 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500391 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500392 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1.353 | Spool Fabrication | Field | Off Rack
1500393 | Project A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1500394 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500395 | Project A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 15.7mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500396 | Project A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500397 | Project A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.8 | Spool Fabrication | Field | Off Rack
1500398 | Project A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.3 | Spool Fabrication | Field | Off Rack
1500399 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | FLANGE, BLIND, ASME B16.5, CL300, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500400 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02A | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500401 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500402 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500403 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 3x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500404 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500405 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.608 | Spool Fabrication | Field | Off Rack
1500406 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500407 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500408 | Project A | Area_1 | FL | FL-YP01-8121 | ISO1055 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500409 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500410 | Project A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500411 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500412 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500413 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500414 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 15.7mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500415 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500416 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500417 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.354 | Spool Fabrication | Field | Off Rack
1500418 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 11.499 | Spool Fabrication | Field | Off Rack
1500419 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500420 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500421 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500422 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500423 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500424 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 15.7mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500425 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500426 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500427 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | CLAMP PIPE SHOE - S3 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500428 | Project A | Area_1 | IA | IA-XP02-9003 | ISO2044 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.462 | Spool Fabrication | Field | Off Rack
1500429 | Project A | Area_1 | IA | IA-XP02-9003 | ISO2044 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500430 | Project A | Area_1 | IA | IA-XP02-9003 | ISO2044 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.505 | Spool Fabrication | Field | Off Rack
1500431 | Project A | Area_1 | IA | IA-XP02-9003 | ISO2044 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500432 | Project A | Area_1 | IA | IA-XP02-9003 | ISO2044 | XP02 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02B | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500433 | Project A | Area_1 | IA | IA-XP02-9003 | ISO2044 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500434 | Project A | Area_1 | IA | IA-XP02-9003 | ISO2044 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500435 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500436 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500437 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500438 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500439 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 6x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500440 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500441 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500442 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500443 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500444 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 6x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500445 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500446 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 15.353 | Stick Built | Field | Off Rack
1500447 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500448 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500449 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 15.953 | Stick Built | Field | Off Rack
1500450 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500451 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500452 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 16.742 | Stick Built | Field | Off Rack
1500453 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500454 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500455 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 16.742 | Stick Built | Field | Off Rack
1500456 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500457 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500458 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 16.742 | Stick Built | Field | Off Rack
1500459 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500460 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 16.742 | Stick Built | Field | Off Rack
1500461 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500462 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500463 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500464 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500465 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500466 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500467 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500468 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500469 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500470 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500471 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500472 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500473 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500474 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500475 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500476 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500477 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500478 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500479 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500480 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 4.441 | Spool Fabrication | Field | Off Rack
1500481 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 3.841 | Spool Fabrication | Field | Off Rack
1500482 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500483 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500484 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 14.583 | Stick Built | Field | Off Rack
1500485 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500486 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500487 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500488 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500489 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500490 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 15.183 | Stick Built | Field | Off Rack
1500491 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500492 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500493 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.036 | Spool Fabrication | Field | Off Rack
1500494 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500495 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500496 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500497 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500498 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1500499 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500500 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500501 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500502 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500503 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500504 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500505 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500506 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500507 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.274 | Spool Fabrication | Field | Off Rack
1500508 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500509 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.318 | Spool Fabrication | Field | Off Rack
1500510 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.274 | Spool Fabrication | Field | Off Rack
1500511 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500512 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.318 | Spool Fabrication | Field | Off Rack
1500513 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500514 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500515 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500516 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 7.586 | Spool Fabrication | Field | Off Rack
1500517 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500518 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.436 | Spool Fabrication | Field | Off Rack
1500519 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.436 | Spool Fabrication | Field | Off Rack
1500520 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500521 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500522 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500523 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500524 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 3.444 | Spool Fabrication | Field | Off Rack
1500525 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500526 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.761 | Spool Fabrication | Field | Off Rack
1500527 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 3.444 | Spool Fabrication | Field | Off Rack
1500528 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500529 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.761 | Spool Fabrication | Field | Off Rack
1500530 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500531 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500532 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500533 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500534 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.036 | Spool Fabrication | Field | Off Rack
1500535 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500536 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500537 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 7.786 | Spool Fabrication | Field | Off Rack
1500538 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500539 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500540 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.836 | Spool Fabrication | Field | Off Rack
1500541 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 9.136 | Spool Fabrication | Field | Off Rack
1500542 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 9.936 | Spool Fabrication | Field | Off Rack
1500543 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 4.004 | Spool Fabrication | Field | Off Rack
1500544 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 3.104 | Spool Fabrication | Field | Off Rack
1500545 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500546 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.836 | Spool Fabrication | Field | Off Rack
1500547 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500548 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500549 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500550 | Project A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.709 | Spool Fabrication | Field | Off Rack
1500551 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | ZL01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 6x4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500552 | Project A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500553 | Project A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500554 | Project A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500555 | Project A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500556 | Project A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500557 | Project A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500558 | Project A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500559 | Project A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500560 | Project A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500561 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.289 | Spool Fabrication | Field | Off Rack
1500562 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500563 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.21 | Spool Fabrication | Field | Off Rack
1500564 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500565 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 6x4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500566 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500567 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500568 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500569 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500570 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 11.499 | Spool Fabrication | Field | Off Rack
1500571 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500572 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 10.093 | Spool Fabrication | Field | Off Rack
1500573 | Project A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.425 | Spool Fabrication | Field | Off Rack
1500574 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500575 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.158 | Spool Fabrication | Field | Off Rack
1500576 | Project A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500577 | Project A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500578 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500579 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 8.755 | Spool Fabrication | Field | Off Rack
1500580 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | CLAMP PIPE SHOE - S3 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500581 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | CLAMP PIPE SHOE - S3 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500582 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | CLAMP PIPE SHOE - S3 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500583 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | CLAMP PIPE SHOE - S3 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500584 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | CLAMP PIPE SHOE - S3 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500585 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | CLAMP PIPE SHOE - S3 | 4 | EA | 1 | Stick Built | Field | Off Rack
1500586 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.361 | Spool Fabrication | Field | Off Rack
1500587 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 6x4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500588 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500589 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500590 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500591 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500592 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500593 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 1.175 | Spool Fabrication | Field | Off Rack
1500594 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500595 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 0.158 | Spool Fabrication | Field | Off Rack
1500596 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500597 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 4 | M | 7.955 | Spool Fabrication | Field | Off Rack
1500598 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500599 | Project A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500600 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500601 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500602 | Project A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500603 | Project A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1500604 | Project A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500605 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500606 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500607 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500608 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500609 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500610 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500611 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500612 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500613 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500614 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500615 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500616 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500617 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500618 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500619 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1500620 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500621 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500622 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500623 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500624 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500625 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500626 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE GUIDE - G4 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500627 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PIPE GUIDE - G4 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500628 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500629 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500630 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1500631 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1500632 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1500633 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1500634 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500635 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | FLANGE, RED, SW, ASME B16.5, CL300, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500636 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500637 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | FLANGE, RED, SW, ASME B16.5, CL300, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500638 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500639 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | ORIFICE PLATE, CL300, RF, (BY INSTRUMENTATION) | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500640 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500641 | Project A | Area_2 | TR | TR-YP01-8099 | ISO4024 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500642 | Project A | Area_2 | TR | TR-YP01-8099 | ISO4024 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500643 | Project A | Area_2 | TR | TR-YP01-8099 | ISO4024 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500644 | Project A | Area_2 | TR | TR-YP01-8100 | ISO4026 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500645 | Project A | Area_2 | TR | TR-YP01-8100 | ISO4026 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500646 | Project A | Area_2 | TR | TR-YP01-8100 | ISO4026 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500647 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.112 | Spool Fabrication | Field | Off Rack
1500648 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500649 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, RED, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 3x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500650 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | FLANGE, RED, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 3x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500651 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.083 | Spool Fabrication | Field | Off Rack
1500652 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2052 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.083 | Spool Fabrication | Field | Off Rack
1500653 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1500654 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1500655 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1500656 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Module | Rack
1500657 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1500658 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500659 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1500660 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Module | Rack
1500661 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1500662 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500663 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500664 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500665 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.625 | Spool Fabrication | Module | Rack
1500666 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500667 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02B | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500668 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500669 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500670 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500671 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1500672 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | YP01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Module | Rack
1500673 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.205 | Spool Fabrication | Module | Rack
1500674 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1500675 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500676 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500677 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500678 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.198 | Spool Fabrication | Field | Off Rack
1500679 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500680 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500681 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500682 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500683 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1500684 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | YP01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Module | Rack
1500685 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.205 | Spool Fabrication | Module | Rack
1500686 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.198 | Spool Fabrication | Field | Off Rack
1500687 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500688 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500689 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500690 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500691 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1500692 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500693 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2060 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.441 | Spool Fabrication | Field | Off Rack
1500694 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.441 | Spool Fabrication | Field | Off Rack
1500695 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.88 | Spool Fabrication | Field | Off Rack
1500696 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.88 | Spool Fabrication | Field | Off Rack
1500697 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500698 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.88 | Spool Fabrication | Field | Off Rack
1500699 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.88 | Spool Fabrication | Field | Off Rack
1500700 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.634 | Spool Fabrication | Field | Off Rack
1500701 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.634 | Spool Fabrication | Field | Off Rack
1500702 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500703 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | GUIDE FOR PIPE SHOE - G6 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500704 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | CLAMP PIPE SHOE - SP18 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500705 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | GUIDE FOR PIPE SHOE - G6 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500706 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | CLAMP PIPE SHOE - SP18 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500707 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | U-BOLT (ANCHOR) - A10 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500708 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500709 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500710 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500711 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 3x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500712 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500713 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500714 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500715 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 3x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1500716 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | U-BOLT (ANCHOR) - A10 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500717 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500718 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500719 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500720 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500721 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500722 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500723 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | FLANGE, RED, SW, ASME B16.5, CL300, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3x3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500724 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500725 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500726 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500727 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500728 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | FLANGE, RED, SW, ASME B16.5, CL300, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3x3/4 | EA | 1 | Spool Fabrication | Module | Rack
1500729 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500730 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500731 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500732 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500733 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | SPECTACLE BLIND, ASME B16.48, CL300, RF, 9.7mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500734 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500735 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500736 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.279 | Spool Fabrication | Field | Off Rack
1500737 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500738 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500739 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500740 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500741 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.844 | Spool Fabrication | Field | Off Rack
1500742 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500743 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.2 | Spool Fabrication | Field | Off Rack
1500744 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1500745 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.897 | Spool Fabrication | Field | Off Rack
1500746 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500747 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.279 | Spool Fabrication | Field | Off Rack
1500748 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500749 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500750 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | U-BOLT (GUIDE) - G1 | 3/4 | EA | 1 | Stick Built | Field | Off Rack
1500751 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500752 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500753 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500754 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500755 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.964 | Spool Fabrication | Field | Off Rack
1500756 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500757 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500758 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500759 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500760 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | SPECTACLE BLIND, ASME B16.48, CL300, RF, 9.7mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500761 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500762 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500763 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.279 | Spool Fabrication | Field | Off Rack
1500764 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500765 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500766 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500767 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500768 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.844 | Spool Fabrication | Field | Off Rack
1500769 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.15 | Spool Fabrication | Module | Rack
1500770 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500771 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1500772 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 10 | EA | 1 | Spool Fabrication | Module | Rack
1500773 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 35.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 10 | EA | 1 | Spool Fabrication | Module | Rack
1500774 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.15 | Spool Fabrication | Module | Rack
1500775 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500776 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1500777 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 10 | EA | 1 | Spool Fabrication | Module | Rack
1500778 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 35.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 10 | EA | 1 | Spool Fabrication | Module | Rack
1500779 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500780 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL300, RF, 38.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500781 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500782 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.2 | Spool Fabrication | Field | Off Rack
1500783 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 1.058 | Spool Fabrication | Field | Off Rack
1500784 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1500785 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.897 | Spool Fabrication | Field | Off Rack
1500786 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500787 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | U-BOLT (ANCHOR) - A10 | 2 | EA | 1 | Stick Built | Module | Rack
1500788 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1500789 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1500790 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1500791 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | U-BOLT (ANCHOR) - A10 | 2 | EA | 1 | Stick Built | Module | Rack
1500792 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1500793 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1500794 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1500795 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | U-BOLT (GUIDE) - G1 | 1+1/2 | EA | 1 | Stick Built | Field | Off Rack
1500796 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1+1/2 | M | 0.423 | Spool Fabrication | Field | Off Rack
1500797 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500798 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1+1/2 | M | 0.236 | Spool Fabrication | Field | Off Rack
1500799 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1+1/2 | M | 0.452 | Spool Fabrication | Field | Off Rack
1500800 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.369 | Spool Fabrication | Field | Off Rack
1500801 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500802 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | U-BOLT (GUIDE) - G1 | 1+1/2 | EA | 1 | Stick Built | Field | Off Rack
1500803 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1+1/2 | M | 0.423 | Spool Fabrication | Field | Off Rack
1500804 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1+1/2 | M | 0.452 | Spool Fabrication | Field | Off Rack
1500805 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 1.058 | Spool Fabrication | Field | Off Rack
1500806 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500807 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1+1/2 | M | 0.236 | Spool Fabrication | Field | Off Rack
1500808 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500809 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500810 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500811 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500812 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500813 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | GUIDE FOR PIPE SHOE - G6 | 3 | EA | 1 | Stick Built | Field | Off Rack
1500814 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.112 | Spool Fabrication | Field | Off Rack
1500815 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500816 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.097 | Spool Fabrication | Field | Off Rack
1500817 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.33 | Spool Fabrication | Field | Off Rack
1500818 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500819 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500820 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.116 | Spool Fabrication | Field | Off Rack
1500821 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500822 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500823 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500824 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500825 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500826 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500827 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500828 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.097 | Spool Fabrication | Field | Off Rack
1500829 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.33 | Spool Fabrication | Field | Off Rack
1500830 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500831 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500832 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.116 | Spool Fabrication | Field | Off Rack
1500833 | Project A | Area_2 | DL | DL-YP01-8012 | ISO2063 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500834 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500835 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2052 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500836 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2052 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500837 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500838 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500839 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500840 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500841 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500842 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500843 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500844 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Module | Rack
1500845 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH STD, ASTM A350 GR. LF2 CL. 1 | 16x3 | EA | 1 | Spool Fabrication | Module | Rack
1500846 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Module | Rack
1500847 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH STD, ASTM A350 GR. LF2 CL. 1 | 16x3 | EA | 1 | Spool Fabrication | Module | Rack
1500848 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, BLIND, ASME B16.5, CL300, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500849 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500850 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500851 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1500852 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 16 | M | 0.4 | Spool Fabrication | Module | Rack
1500853 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 24x2 | EA | 1 | Spool Fabrication | Module | Rack
1500854 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500855 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500856 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500857 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500858 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500859 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500860 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500861 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500862 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1500863 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500864 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500865 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500866 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500867 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Module | Rack
1500868 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1500869 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500870 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500871 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1500872 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500873 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Module | Rack
1500874 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500875 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Module | Rack
1500876 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500877 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Module | Rack
1500878 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500879 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500880 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Module | Rack
1500881 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500882 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500883 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Module | Rack
1500884 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Module | Rack
1500885 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Module | Rack
1500886 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Module | Rack
1500887 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Module | Rack
1500888 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Module | Rack
1500889 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | DIRECTIONAL ANCHOR - A11 | 24 | EA | 1 | Stick Built | Module | Rack
1500890 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | CLAMP PIPE SHOE - S4L | 24 | EA | 1 | Stick Built | Module | Rack
1500891 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Module | Rack
1500892 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Module | Rack
1500893 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500894 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500895 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500896 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500897 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | STRAINER, PLATE TYPE, CL300, RF, ASTM A516 GR. 70N, IMPACT TEST TO M45C, SP-AN-302 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500898 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | STRAINER, BASKET TYPE, CL300, RF, 304 SS, SP-AG-618 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500899 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500900 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500901 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | STRAINER, BASKET TYPE, CL300, RF, 304 SS, SP-AG-618 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500902 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500903 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500904 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | STRAINER, PLATE TYPE, CL300, RF, ASTM A516 GR. 70N, IMPACT TEST TO M45C, SP-AN-302 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1500905 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.151 | Spool Fabrication | Module | Rack
1500906 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.75 | Spool Fabrication | Field | Off Rack
1500907 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.3 | Spool Fabrication | Field | Off Rack
1500908 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500909 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500910 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500911 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500912 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500913 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500914 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500915 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500916 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.279 | Spool Fabrication | Field | Off Rack
1500917 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500918 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500919 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | U-BOLT (GUIDE) - G1 | 3/4 | EA | 1 | Stick Built | Field | Off Rack
1500920 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500921 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500922 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500923 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500924 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500925 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500926 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500927 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 3/4 | M | 0.964 | Spool Fabrication | Field | Off Rack
1500928 | Project A | Area_2 | DL | DL-YP01-8014 | ISO1036 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500929 | Project A | Area_2 | TR | TR-ZL01-8101 | ISO4027 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500930 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500931 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500932 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.369 | Spool Fabrication | Field | Off Rack
1500933 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500934 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500935 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.621 | Spool Fabrication | Field | Off Rack
1500936 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500937 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500938 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500939 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500940 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500941 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500942 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500943 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.579 | Spool Fabrication | Field | Off Rack
1500944 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500945 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500946 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500947 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500948 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.254 | Spool Fabrication | Module | Rack
1500949 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500950 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500951 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500952 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 3x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500953 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 1.386 | Spool Fabrication | Field | Off Rack
1500954 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.073 | Spool Fabrication | Module | Rack
1500955 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.745 | Spool Fabrication | Module | Rack
1500956 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500957 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500958 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500959 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500960 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500961 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 3x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1500962 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.097 | Spool Fabrication | Field | Off Rack
1500963 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500964 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500965 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.75 | Spool Fabrication | Field | Off Rack
1500966 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.3 | Spool Fabrication | Field | Off Rack
1500967 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, BLIND, ASME B16.5, CL300, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500968 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500969 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500970 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500971 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 1.386 | Spool Fabrication | Field | Off Rack
1500972 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-3" | 3 | EA | 1 | Stick Built | Field | Off Rack
1500973 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-3" | 3 | EA | 1 | Stick Built | Field | Off Rack
1500974 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | FLANGE, BLIND, ASME B16.5, CL300, RF, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500975 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500976 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 7.622 | Spool Fabrication | Field | Off Rack
1500977 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500978 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500979 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500980 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500981 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500982 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500983 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500984 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500985 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-3" | 3 | EA | 1 | Stick Built | Field | Off Rack
1500986 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-3" | 3 | EA | 1 | Stick Built | Field | Off Rack
1500987 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 8.544 | Spool Fabrication | Field | Off Rack
1500988 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500989 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.227 | Spool Fabrication | Field | Off Rack
1500990 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1500991 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.202 | Spool Fabrication | Module | Rack
1500992 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500993 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500994 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | SPECTACLE BLIND, ASME B16.48, CL300, RF, 9.7mm THK, ASTM A516 GR. 70N | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1500995 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500996 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500997 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500998 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1500999 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501000 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501001 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501002 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501003 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.577 | Spool Fabrication | Module | Rack
1501004 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.176 | Spool Fabrication | Module | Rack
1501005 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.621 | Spool Fabrication | Field | Off Rack
1501006 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501007 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501008 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501009 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 6.069 | Spool Fabrication | Field | Off Rack
1501010 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501011 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501012 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501013 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501014 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501015 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501016 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501017 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501018 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501019 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501020 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.662 | Spool Fabrication | Module | Rack
1501021 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501022 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501023 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501024 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.662 | Spool Fabrication | Module | Rack
1501025 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501026 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501027 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501028 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501029 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501030 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501031 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1.284 | Spool Fabrication | Module | Rack
1501032 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501033 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501034 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501035 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501036 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1501037 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501038 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 16 | M | 1.16 | Spool Fabrication | Module | Rack
1501039 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1501040 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501041 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501042 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1501043 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501044 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 13.388 | Spool Fabrication | Module | Rack
1501045 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501046 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501047 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501048 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501049 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.966 | Spool Fabrication | Field | Off Rack
1501050 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501051 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501052 | Project A | Area_2 | DL | DL-YP01-8006 | ISO2057 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501053 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501054 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501055 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501056 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1+1/2 | M | 0.619 | Spool Fabrication | Field | Off Rack
1501057 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501058 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501059 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501060 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501061 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501062 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501063 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501064 | Project A | Area_2 | DL | DL-YP01-8080 | ISO2071 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501065 | Project A | Area_2 | DL | DL-YP01-8081 | ISO2001 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501066 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501067 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501068 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501069 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501070 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501071 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501072 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2060 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501073 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2060 | YP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501074 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2060 | YP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501075 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501076 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501077 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2059 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501078 | Project A | Area_2 | DL | DL-YP01-8007 | ISO2059 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501079 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Module | Rack
1501080 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501081 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501082 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501083 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501084 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501085 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501086 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501087 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501088 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501089 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501090 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501091 | Project A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501092 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501093 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 16 | M | 1.458 | Spool Fabrication | Module | Rack
1501094 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 16 | M | 0.714 | Spool Fabrication | Module | Rack
1501095 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501096 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501097 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501098 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 10 | M | 1.2 | Spool Fabrication | Module | Rack
1501099 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH STD, ASTM A420 GR. WPL6, SMLS | 16x10 | EA | 1 | Spool Fabrication | Module | Rack
1501100 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501101 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501102 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501103 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501104 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501105 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501106 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501107 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501108 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501109 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501110 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 10 | M | 1.461 | Spool Fabrication | Module | Rack
1501111 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH STDxSCH STD, ASTM A420 GR. WPL6, SMLS | 10x8 | EA | 1 | Spool Fabrication | Module | Rack
1501112 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Module | Rack
1501113 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501114 | Project A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | YP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501115 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501116 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501117 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501118 | Project A | Area_2 | TR | TR-ZL01-8101 | ISO4025 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501119 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.632 | Spool Fabrication | Field | Off Rack
1501120 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2052 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501121 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501122 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | CHECK VALVE, WAFER, LONG PATTERN, CL600, RF LUG, ASTM A352 GR. LCC, CH-C02B | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501123 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501124 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501125 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.902 | Spool Fabrication | Module | Rack
1501126 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.175 | Spool Fabrication | Field | Off Rack
1501127 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501128 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501129 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501130 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501131 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501132 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1.284 | Spool Fabrication | Module | Rack
1501133 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501134 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501135 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1501136 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501137 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501138 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501139 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501140 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1501141 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1501142 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501143 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 13.108 | Spool Fabrication | Module | Rack
1501144 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501145 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501146 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501147 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501148 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.966 | Spool Fabrication | Field | Off Rack
1501149 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501150 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501151 | Project A | Area_2 | DL | DL-YP01-8009 | ISO2068 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501152 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501153 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501154 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1+1/2 | M | 0.619 | Spool Fabrication | Field | Off Rack
1501155 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501156 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501157 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501158 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1+1/2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501159 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501160 | Project A | Area_2 | DL | DL-YP01-8010 | ISO2066 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501161 | Project A | Area_2 | DL | DL-YP01-8011 | ISO2070 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501162 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501163 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501164 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501165 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501166 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | PIPE, ASME B36.10, SCH 40, ASTM A333 GR. 6, SMLS | 24 | M | 0.698 | Spool Fabrication | Module | Rack
1501167 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501168 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL300, RF, 38.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501169 | Project A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02MT | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501170 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501171 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH 40, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501172 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH 40, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501173 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 40xSCH XS, ASTM A420 GR. WPL6, SMLS | 24x16 | EA | 1 | Spool Fabrication | Module | Rack
1501174 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501175 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501176 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | PIPE, ASME B36.10, SCH 40, ASTM A333 GR. 6, SMLS | 24 | M | 13.762 | Spool Fabrication | Module | Rack
1501177 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501178 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501179 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501180 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501181 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501182 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501183 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501184 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2061 | YP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501185 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501186 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501187 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2062 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501188 | Project A | Area_2 | DL | DL-YP01-8008 | ISO2062 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501189 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Module | Rack
1501190 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501191 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501192 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | FLANGE, SW, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501193 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501194 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501195 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501196 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501197 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501198 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501199 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501200 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501201 | Project A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501202 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501203 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 16 | M | 1.458 | Spool Fabrication | Module | Rack
1501204 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 16 | M | 0.714 | Spool Fabrication | Module | Rack
1501205 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501206 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501207 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501208 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 10 | M | 1.2 | Spool Fabrication | Module | Rack
1501209 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH STD, ASTM A420 GR. WPL6, SMLS | 16x10 | EA | 1 | Spool Fabrication | Module | Rack
1501210 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501211 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 16 | M | 1.16 | Spool Fabrication | Module | Rack
1501212 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501213 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL300, RF, 38.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501214 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02MT | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501215 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501216 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501217 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501218 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501219 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501220 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501221 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501222 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501223 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501224 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501225 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 10 | M | 1.461 | Spool Fabrication | Module | Rack
1501226 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH STDxSCH STD, ASTM A420 GR. WPL6, SMLS | 10x8 | EA | 1 | Spool Fabrication | Module | Rack
1501227 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Module | Rack
1501228 | Project A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501229 | Project A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | YP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501230 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH 40, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501231 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH 40, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501232 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02MT | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501233 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501234 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501235 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501236 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.633 | Spool Fabrication | Field | Off Rack
1501237 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501238 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501239 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.737 | Spool Fabrication | Field | Off Rack
1501240 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501241 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.562 | Spool Fabrication | Field | Off Rack
1501242 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501243 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 2.114 | Spool Fabrication | Field | Off Rack
1501244 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501245 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501246 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501247 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501248 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1501249 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.256 | Spool Fabrication | Field | Off Rack
1501250 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501251 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501252 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501253 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1501254 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.249 | Spool Fabrication | Field | Off Rack
1501255 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501256 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501257 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501258 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501259 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501260 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501261 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501262 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | CHECK VALVE, WAFER, LONG PATTERN, CL600, RF LUG, ASTM A352 GR. LCC, CH-C02B | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501263 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501264 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1501265 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1501266 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1501267 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501268 | Project A | Area_2 | FL | FL-YP01-8122 | ISO2005 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.626 | Spool Fabrication | Field | Off Rack
1501269 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501270 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501271 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501272 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Module | Rack
1501273 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501274 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501275 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501276 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501277 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501278 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501279 | Project A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501280 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501281 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501282 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501283 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501284 | Project A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501285 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501286 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501287 | Project A | Area_2 | DL | DL-YP01-8004 | ISO2053 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501288 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 7.666 | Spool Fabrication | Module | Rack
1501289 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501290 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1.5 | Spool Fabrication | Module | Rack
1501291 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501292 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2054 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.777 | Spool Fabrication | Field | Off Rack
1501293 | Project A | Area_2 | DL | DL-YP01-8005 | ISO2055 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501294 | Project A | Area_2 | IA | IA-XP02-9005 | ISO2074 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501295 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501296 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501297 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.902 | Spool Fabrication | Module | Rack
1501298 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH 40xSCH XS, ASTM A420 GR. WPL6, SMLS | 24x16 | EA | 1 | Spool Fabrication | Module | Rack
1501299 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH 40xSCH XS, ASTM A420 GR. WPL6, SMLS | 24x16 | EA | 1 | Spool Fabrication | Module | Rack
1501300 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | TEE, STR, ASME B16.9, BW, SCH 40, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501301 | Project A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 40, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501302 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501303 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501304 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Module | Rack
1501305 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501306 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1.5 | Spool Fabrication | Module | Rack
1501307 | Project A | Area_2 | IA | IA-XP02-9004 | ISO2073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501308 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501309 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501310 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 8.374 | Spool Fabrication | Module | Rack
1501311 | Project A | Area_2 | IA | IA-XP02-9002 | ISO2072 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501312 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 15.191 | Spool Fabrication | Module | Rack
1501313 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 12.448 | Spool Fabrication | Module | Rack
1501314 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 14.664 | Spool Fabrication | Module | Rack
1501315 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 14.664 | Spool Fabrication | Module | Rack
1501316 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 12.062 | Spool Fabrication | Module | Rack
1501317 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 7.63 | Spool Fabrication | Module | Rack
1501318 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 4.431 | Spool Fabrication | Module | Rack
1501319 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 16.664 | Spool Fabrication | Module | Rack
1501320 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 17.664 | Spool Fabrication | Module | Rack
1501321 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 5.324 | Spool Fabrication | Module | Rack
1501322 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501323 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501324 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 2.674 | Spool Fabrication | Module | Rack
1501325 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501326 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501327 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501328 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501329 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501330 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501331 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501332 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501333 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501334 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501335 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.305 | Spool Fabrication | Module | Rack
1501336 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501337 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501338 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501339 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501340 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501341 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 12x1 | EA | 1 | Spool Fabrication | Module | Rack
1501342 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 2.699 | Spool Fabrication | Module | Rack
1501343 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501344 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.176 | Spool Fabrication | Module | Rack
1501345 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501346 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501347 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501348 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501349 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501350 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501351 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501352 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 3.42 | Spool Fabrication | Module | Rack
1501353 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501354 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501355 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501356 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501357 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501358 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501359 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.319 | Spool Fabrication | Module | Rack
1501360 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501361 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501362 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501363 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501364 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501365 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501366 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501367 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 5.696 | Spool Fabrication | Module | Rack
1501368 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 14.664 | Spool Fabrication | Module | Rack
1501369 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501370 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501371 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 15.564 | Spool Fabrication | Module | Rack
1501372 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501373 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501374 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501375 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501376 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 10.512 | Spool Fabrication | Module | Rack
1501377 | Project A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501378 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501379 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | TEE, RED, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 12x10 | EA | 1 | Spool Fabrication | Module | Rack
1501380 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 2.749 | Spool Fabrication | Module | Rack
1501381 | Project A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501382 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Module | Rack
1501383 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | TEE, RED, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 12x10 | EA | 1 | Spool Fabrication | Module | Rack
1501384 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.075 | Spool Fabrication | Module | Rack
1501385 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501386 | Project A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501387 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501388 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501389 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501390 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 5.166 | Spool Fabrication | Field | Off Rack
1501391 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501392 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501393 | Project A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | ZL02 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501394 | Project A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | ZL02 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501395 | Project A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | ZL02 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501396 | Project A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | ZL02 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501397 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.172 | Spool Fabrication | Field | Off Rack
1501398 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501399 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.342 | Spool Fabrication | Field | Off Rack
1501400 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501401 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.142 | Spool Fabrication | Field | Off Rack
1501402 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501403 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.725 | Spool Fabrication | Field | Off Rack
1501404 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 1.719 | Spool Fabrication | Field | Off Rack
1501405 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.752 | Spool Fabrication | Field | Off Rack
1501406 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.129 | Spool Fabrication | Field | Off Rack
1501407 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | PIPE GUIDE - G5 | 3 | EA | 1 | Stick Built | Field | Off Rack
1501408 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501409 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | U-BOLT (GUIDE) - G1 | 4 | EA | 1 | Stick Built | Field | Off Rack
1501410 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501411 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | CONTROL VALVE, GLOBE BODY, CL150, RF, (BY INSTRUMENTATION) | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501412 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501413 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501414 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, BA-C10ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501415 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 15.742 | Spool Fabrication | Module | Rack
1501416 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 1.32 | Spool Fabrication | Module | Rack
1501417 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, BA-C10ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501418 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, BA-C10ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501419 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501420 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501421 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 24x2 | EA | 1 | Spool Fabrication | Module | Rack
1501422 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501423 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501424 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 24x2 | EA | 1 | Spool Fabrication | Module | Rack
1501425 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | DIRECTIONAL ANCHOR - A20-SCH STD | 8 | EA | 1 | Stick Built | Field | Off Rack
1501426 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501427 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501428 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501429 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.225 | Spool Fabrication | Field | Off Rack
1501430 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501431 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501432 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501433 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501434 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501435 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501436 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501437 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501438 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501439 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501440 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501441 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501442 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501443 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501444 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501445 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501446 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501447 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501448 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501449 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501450 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501451 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501452 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501453 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501454 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501455 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501456 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 3x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501457 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | DIRECTIONAL ANCHOR - A11 | 3 | EA | 1 | Stick Built | Field | Off Rack
1501458 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501459 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1501460 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 24x16 | EA | 1 | Spool Fabrication | Module | Rack
1501461 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501462 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501463 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501464 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501465 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501466 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501467 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501468 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501469 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 24x2 | EA | 1 | Spool Fabrication | Module | Rack
1501470 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501471 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501472 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501473 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501474 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501475 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501476 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501477 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501478 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501479 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501480 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501481 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501482 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501483 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501484 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501485 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501486 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501487 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501488 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501489 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501490 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501491 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | DIRECTIONAL ANCHOR - A20-SCH STD | 8 | EA | 1 | Stick Built | Field | Off Rack
1501492 | Project A | Area_3 | TR | TR-ZL01-8116 | ISO3026 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501493 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.264 | Spool Fabrication | Field | Off Rack
1501494 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501495 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501496 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501497 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1501498 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1501499 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.143 | Spool Fabrication | Field | Off Rack
1501500 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501501 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501502 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.744 | Spool Fabrication | Field | Off Rack
1501503 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501504 | Project A | Area_3 | DL | DL-XP01-8076 | ISO3025 | XP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501505 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501506 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02D | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501507 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501508 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1501509 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.305 | Spool Fabrication | Field | Off Rack
1501510 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501511 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501512 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501513 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501514 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501515 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501516 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 24x2 | EA | 1 | Spool Fabrication | Module | Rack
1501517 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501518 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501519 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501520 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1501521 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501522 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501523 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | U-BOLT (GUIDE) - G1 | 4 | EA | 1 | Stick Built | Field | Off Rack
1501524 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | U-BOLT (ANCHOR) - A10 | 4 | EA | 1 | Stick Built | Field | Off Rack
1501525 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501526 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501527 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 4 | M | 0.4 | Spool Fabrication | Field | Off Rack
1501528 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501529 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501530 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501531 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501532 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501533 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 4 | M | 2.747 | Spool Fabrication | Field | Off Rack
1501534 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 4 | M | 5.211 | Spool Fabrication | Field | Off Rack
1501535 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501536 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 4 | M | 1.249 | Spool Fabrication | Field | Off Rack
1501537 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501538 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501539 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 4 | M | 0.934 | Spool Fabrication | Field | Off Rack
1501540 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 4 | M | 0.29 | Spool Fabrication | Field | Off Rack
1501541 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501542 | Project A | Area_3 | BD | BD-XP01-6003 | ISO2075 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501543 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | U-BOLT (ANCHOR) - A10 | 8 | EA | 1 | Stick Built | Field | Off Rack
1501544 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1501545 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1501546 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | PIPE GUIDE - G5 | 3 | EA | 1 | Stick Built | Field | Off Rack
1501547 | Project A | Area_3 | IA | IA-XP02-9010 | ISO2051 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1501548 | Project A | Area_3 | TR | TR-XP01-8097 | ISO4022 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501549 | Project A | Area_3 | TR | TR-XP01-8097 | ISO4022 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501550 | Project A | Area_3 | TR | TR-XP01-8097 | ISO4022 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501551 | Project A | Area_3 | TR | TR-XP01-8097 | ISO4022 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501552 | Project A | Area_3 | TR | TR-XP01-8097 | ISO4022 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501553 | Project A | Area_3 | TR | TR-XP01-8098 | ISO4023 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501554 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501555 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501556 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501557 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | DIRECTIONAL ANCHOR - A21-SCH STD | 16 | EA | 1 | Stick Built | Module | Rack
1501558 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501559 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501560 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501561 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 24 | EA | 1 | Stick Built | Module | Rack
1501562 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501563 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501564 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501565 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501566 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501567 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501568 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501569 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 24 | EA | 1 | Stick Built | Module | Rack
1501570 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501571 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501572 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501573 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501574 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | CLAMP PIPE SHOE - S4L | 24 | EA | 1 | Stick Built | Module | Rack
1501575 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | GUIDE FOR PIPE SHOE - G11 | 24 | EA | 1 | Stick Built | Module | Rack
1501576 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | DIRECTIONAL ANCHOR - A11 | 24 | EA | 1 | Stick Built | Module | Rack
1501577 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | PIPE GUIDE - G4 | 24 | EA | 1 | Stick Built | Module | Rack
1501578 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 20 | EA | 1 | Stick Built | Module | Rack
1501579 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Module | Rack
1501580 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 20 | EA | 1 | Stick Built | Module | Rack
1501581 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Module | Rack
1501582 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Module | Rack
1501583 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Module | Rack
1501584 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501585 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501586 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501587 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501588 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501589 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501590 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501591 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501592 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501593 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501594 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501595 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501596 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501597 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501598 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501599 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501600 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE SHOE - S1L | 2 | EA | 1 | Stick Built | Field | Off Rack
1501601 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501602 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501603 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501604 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501605 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501606 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE SHOE - S1L | 2 | EA | 1 | Stick Built | Field | Off Rack
1501607 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501608 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501609 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501610 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501611 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501612 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501613 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501614 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE SHOE - S1L | 2 | EA | 1 | Stick Built | Field | Off Rack
1501615 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501616 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501617 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501618 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501619 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501620 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE SHOE - S1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501621 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 16 | EA | 1 | Stick Built | Module | Rack
1501622 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501623 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501624 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501625 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501626 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501627 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501628 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501629 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501630 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 16 | EA | 1 | Stick Built | Module | Rack
1501631 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Module | Rack
1501632 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 0.636 | Spool Fabrication | Module | Rack
1501633 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 24x2 | EA | 1 | Spool Fabrication | Module | Rack
1501634 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Module | Rack
1501635 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Module | Rack
1501636 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Module | Rack
1501637 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Module | Rack
1501638 | Project A | Area_3 | IA | IA-XP02-9010 | ISO2051 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501639 | Project A | Area_3 | IA | IA-XP02-9010 | ISO2051 | XP02 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501640 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501641 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL600, RF, 50.8mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501642 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501643 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501644 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | CHECK VALVE, WAFER, LONG PATTERN, CL150, RF LUG, ASTM A352 GR. LCC, CH-A02B | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501645 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501646 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 14.687 | Stick Built | Field | Off Rack
1501647 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.729 | Spool Fabrication | Field | Off Rack
1501648 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501649 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501650 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501651 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 0.597 | Spool Fabrication | Field | Off Rack
1501652 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501653 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Module | Rack
1501654 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02D | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501655 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Module | Rack
1501656 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Module | Rack
1501657 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.2 | Spool Fabrication | Module | Rack
1501658 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501659 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501660 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.292 | Spool Fabrication | Module | Rack
1501661 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501662 | Project A | Area_3 | IA | IA-XP02-9006 | ISO2045 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501663 | Project A | Area_3 | IA | IA-XP02-9010 | ISO2051 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501664 | Project A | Area_3 | IA | IA-XP02-9010 | ISO2051 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501665 | Project A | Area_3 | IA | IA-XP02-9010 | ISO2051 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501666 | Project A | Area_3 | IA | IA-XP02-9010 | ISO2051 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.297 | Spool Fabrication | Module | Rack
1501667 | Project A | Area_3 | IA | IA-XP02-9010 | ISO2051 | XP02 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501668 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501669 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501670 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 2.807 | Spool Fabrication | Module | Rack
1501671 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 3.666 | Spool Fabrication | Module | Rack
1501672 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501673 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501674 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1501675 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501676 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL600, RF, 50.8mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C, CSA CERTIFIED TO Z662 AND RATED TO PN100 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501677 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501678 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, CH-C10D | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501679 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 16.613 | Spool Fabrication | Module | Rack
1501680 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501681 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501682 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 17.124 | Spool Fabrication | Module | Rack
1501683 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501684 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501685 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 17.373 | Stick Built | Field | Off Rack
1501686 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.312 | Spool Fabrication | Field | Off Rack
1501687 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 0.636 | Spool Fabrication | Module | Rack
1501688 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1501689 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Module | Rack
1501690 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501691 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501692 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501693 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 5.882 | Spool Fabrication | Field | Off Rack
1501694 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501695 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501696 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.233 | Spool Fabrication | Field | Off Rack
1501697 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3032 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501698 | Project A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501699 | Project A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501700 | Project A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | ZL02 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Module | Rack
1501701 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501702 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501703 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Module | Rack
1501704 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 10.085 | Spool Fabrication | Module | Rack
1501705 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501706 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501707 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, RED, THD, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Module | Rack
1501708 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501709 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501710 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 3.822 | Spool Fabrication | Module | Rack
1501711 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501712 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.997 | Spool Fabrication | Module | Rack
1501713 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501714 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501715 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 13.402 | Spool Fabrication | Module | Rack
1501716 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501717 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501718 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.997 | Spool Fabrication | Module | Rack
1501719 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501720 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 4.699 | Spool Fabrication | Module | Rack
1501721 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501722 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501723 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501724 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501725 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501726 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501727 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 12.711 | Spool Fabrication | Module | Rack
1501728 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501729 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.978 | Spool Fabrication | Module | Rack
1501730 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501731 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501732 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501733 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 8.899 | Spool Fabrication | Module | Rack
1501734 | Project A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501735 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501736 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501737 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501738 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501739 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 1.179 | Spool Fabrication | Module | Rack
1501740 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501741 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.71 | Spool Fabrication | Module | Rack
1501742 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501743 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.633 | Spool Fabrication | Module | Rack
1501744 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501745 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 5.78 | Spool Fabrication | Module | Rack
1501746 | Project A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501747 | Project A | Area_3 | TR | TR-ZL01-8088 | ISO4010 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501748 | Project A | Area_3 | TR | TR-XP01-8092 | ISO4012 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501749 | Project A | Area_3 | TR | TR-XP01-8095 | ISO4015 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501750 | Project A | Area_3 | TR | TR-ZL01-8091 | ISO4017 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501751 | Project A | Area_3 | TR | TR-ZL02-8094 | ISO4014 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501752 | Project A | Area_3 | TR | TR-ZL02-8090 | ISO4016 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501753 | Project A | Area_3 | TR | TR-ZL02-8093 | ISO4013 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501754 | Project A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501755 | Project A | Area_3 | TR | TR-ZL02-8089 | ISO4011 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501756 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501757 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501758 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501759 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501760 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501761 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501762 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1501763 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | CLAMP PIPE SHOE - SP18 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501764 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501765 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501766 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.811 | Spool Fabrication | Field | Off Rack
1501767 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501768 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501769 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.425 | Spool Fabrication | Field | Off Rack
1501770 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501771 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.354 | Spool Fabrication | Field | Off Rack
1501772 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501773 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501774 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.255 | Spool Fabrication | Field | Off Rack
1501775 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501776 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 1.305 | Spool Fabrication | Field | Off Rack
1501777 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.255 | Spool Fabrication | Field | Off Rack
1501778 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501779 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501780 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501781 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501782 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501783 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501784 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3027 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501785 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501786 | Project A | Area_3 | DL | DL-XP01-8045 | ISO3034 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501787 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501788 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501789 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501790 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.205 | Spool Fabrication | Field | Off Rack
1501791 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501792 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1501793 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.391 | Spool Fabrication | Field | Off Rack
1501794 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501795 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.141 | Spool Fabrication | Field | Off Rack
1501796 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501797 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.009 | Spool Fabrication | Field | Off Rack
1501798 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501799 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.738 | Spool Fabrication | Field | Off Rack
1501800 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501801 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501802 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 0.6 | Spool Fabrication | Field | Off Rack
1501803 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501804 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501805 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501806 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501807 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501808 | Project A | Area_3 | BD | BD-XP01-6001 | ISO2076 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 12.7mm THK, ASTM A516 GR. 70N | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1501809 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1501810 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501811 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501812 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501813 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501814 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.143 | Spool Fabrication | Field | Off Rack
1501815 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501816 | Project A | Area_3 | DL | DL-XP01-8047 | ISO3024 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1501817 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 5.167 | Spool Fabrication | Field | Off Rack
1501818 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501819 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501820 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501821 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501822 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501823 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501824 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501825 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501826 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501827 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501828 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 5.097 | Spool Fabrication | Field | Off Rack
1501829 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 11.666 | Spool Fabrication | Field | Off Rack
1501830 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501831 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501832 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 17.862 | Stick Built | Field | Off Rack
1501833 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501834 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501835 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 16.096 | Stick Built | Field | Off Rack
1501836 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501837 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501838 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501839 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501840 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501841 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501842 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501843 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501844 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501845 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501846 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501847 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1501848 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 10.662 | Spool Fabrication | Field | Off Rack
1501849 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.266 | Spool Fabrication | Field | Off Rack
1501850 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501851 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501852 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501853 | Project A | Area_3 | DL | DL-XP01-8043 | ISO3033 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501854 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501855 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501856 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 16 | M | 3.652 | Spool Fabrication | Module | Rack
1501857 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501858 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501859 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 16 | M | 1.943 | Spool Fabrication | Module | Rack
1501860 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | TEE, STR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501861 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501862 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501863 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 16 | M | 1.824 | Spool Fabrication | Module | Rack
1501864 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501865 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 16 | M | 17.595 | Spool Fabrication | Module | Rack
1501866 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501867 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501868 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 16 | M | 2.152 | Spool Fabrication | Module | Rack
1501869 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501870 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501871 | Project A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 16 | M | 16.594 | Spool Fabrication | Module | Rack
1501872 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 16 | EA | 1 | Spool Fabrication | Module | Rack
1501873 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | REDUCER, ECCENTRIC, CSA Z245.11, BW, SCH XSxSCH STD, GR. 359 CAT II M45C, SMLS | 24x16 | EA | 1 | Spool Fabrication | Module | Rack
1501874 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501875 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501876 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501877 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Module | Rack
1501878 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501879 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 20 | M | 1.971 | Spool Fabrication | Module | Rack
1501880 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH XS, GR. 359 CAT II M45C, SMLS | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501881 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 24 | M | 0.73 | Spool Fabrication | Module | Rack
1501882 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 20 | M | 0.443 | Spool Fabrication | Module | Rack
1501883 | Project A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501884 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501885 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | TEE, RED, CSA Z245.11, BW, SCH XSxSCH XS, GR. 359 CAT II M45C, SMLS | 24x20 | EA | 1 | Spool Fabrication | Module | Rack
1501886 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 24 | M | 1.769 | Spool Fabrication | Module | Rack
1501887 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 17.596 | Spool Fabrication | Module | Rack
1501888 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501889 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501890 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 17.596 | Spool Fabrication | Module | Rack
1501891 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501892 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501893 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.535 | Spool Fabrication | Module | Rack
1501894 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501895 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501896 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501897 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CH-C02C | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501898 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501899 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.052 | Spool Fabrication | Module | Rack
1501900 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501901 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CH-C02C | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501902 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501903 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.052 | Spool Fabrication | Module | Rack
1501904 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501905 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CH-C02C | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501906 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501907 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.052 | Spool Fabrication | Module | Rack
1501908 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501909 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501910 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Module | Rack
1501911 | Project A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501912 | Project A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | M | 12.589 | Spool Fabrication | Module | Rack
1501913 | Project A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501914 | Project A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | M | 0.851 | Spool Fabrication | Module | Rack
1501915 | Project A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501916 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 12 | EA | 1 | Spool Fabrication | Module | Rack
1501917 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | TEE, RED, CSA Z245.11, BW, SCH XSxSCH STD, GR. 359 CAT II M45C, SMLS | 24x12 | EA | 1 | Spool Fabrication | Module | Rack
1501918 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 24 | M | 7.455 | Spool Fabrication | Module | Rack
1501919 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH XS, GR. 359 CAT II M45C, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501920 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 24 | M | 0.738 | Spool Fabrication | Module | Rack
1501921 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH XS, GR. 359 CAT II M45C, SMLS | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501922 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 24 | M | 1.707 | Spool Fabrication | Module | Rack
1501923 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501924 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501925 | Project A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 24 | EA | 1 | Spool Fabrication | Module | Rack
1501926 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 2.136 | Spool Fabrication | Module | Rack
1501927 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501928 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1501929 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.432 | Spool Fabrication | Module | Rack
1501930 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.432 | Spool Fabrication | Module | Rack
1501931 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 2.027 | Spool Fabrication | Module | Rack
1501932 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3027 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501933 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501934 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 16.619 | Stick Built | Field | Off Rack
1501935 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501936 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501937 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501938 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501939 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501940 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501941 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501942 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501943 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501944 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501945 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501946 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501947 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 15.002 | Stick Built | Field | Off Rack
1501948 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501949 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501950 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501951 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501952 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501953 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501954 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.726 | Spool Fabrication | Field | Off Rack
1501955 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501956 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3028 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501957 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.719 | Spool Fabrication | Field | Off Rack
1501958 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 10.004 | Spool Fabrication | Field | Off Rack
1501959 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501960 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501961 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 14.72 | Stick Built | Field | Off Rack
1501962 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501963 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501964 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501965 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501966 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 12.666 | Stick Built | Field | Off Rack
1501967 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501968 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501969 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501970 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501971 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 11.029 | Spool Fabrication | Field | Off Rack
1501972 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.769 | Spool Fabrication | Field | Off Rack
1501973 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501974 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501975 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501976 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501977 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501978 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 13.862 | Stick Built | Field | Off Rack
1501979 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501980 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501981 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501982 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501983 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.764 | Spool Fabrication | Field | Off Rack
1501984 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501985 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501986 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501987 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501988 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501989 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 15.962 | Stick Built | Field | Off Rack
1501990 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501991 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501992 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501993 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1501994 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501995 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501996 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 12.994 | Stick Built | Field | Off Rack
1501997 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.457 | Spool Fabrication | Field | Off Rack
1501998 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1501999 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502000 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.768 | Spool Fabrication | Field | Off Rack
1502001 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 0.766 | Spool Fabrication | Module | Rack
1502002 | Project A | Area_3 | DL | DL-XP01-8046 | ISO3030 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502003 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502004 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 11.466 | Spool Fabrication | Field | Off Rack
1502005 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502006 | Project A | Area_3 | DL | DL-XP01-8079 | ISO3031 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502007 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 6.771 | Spool Fabrication | Module | Rack
1502008 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.374 | Spool Fabrication | Module | Rack
1502009 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502010 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502011 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Module | Rack
1502012 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 1.094 | Spool Fabrication | Module | Rack
1502013 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502014 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502015 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502016 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502017 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 13.313 | Spool Fabrication | Module | Rack
1502018 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502019 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502020 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502021 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502022 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 13.313 | Spool Fabrication | Module | Rack
1502023 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502024 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502025 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502026 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502027 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 21.021 | Spool Fabrication | Module | Rack
1502028 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 24 | M | 19.021 | Spool Fabrication | Module | Rack
1502029 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502030 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502031 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.65 | Spool Fabrication | Module | Rack
1502032 | Project A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502033 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502034 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502035 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 24 | EA | 1 | Spool Fabrication | Module | Rack
1502036 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.65 | Spool Fabrication | Module | Rack
1502037 | Project A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502038 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502039 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.205 | Spool Fabrication | Module | Rack
1502040 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.205 | Spool Fabrication | Module | Rack
1502041 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.205 | Spool Fabrication | Module | Rack
1502042 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.47 | Spool Fabrication | Module | Rack
1502043 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502044 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502045 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502046 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502047 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502048 | Project A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Module | Rack
1502049 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502050 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502051 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3043 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502052 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.493 | Spool Fabrication | Field | Off Rack
1502053 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502054 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502055 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502056 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502057 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502058 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502059 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502060 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502061 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502062 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502063 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502064 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502065 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502066 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502067 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502068 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502069 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502070 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502071 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502072 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502073 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502074 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502075 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502076 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502077 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502078 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502079 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502080 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502081 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502082 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502083 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | FLANGE, RED, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502084 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1502085 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x3 | EA | 1 | Spool Fabrication | Field | Off Rack
1502086 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502087 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502088 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502089 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | FLANGE, RED, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502090 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1502091 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x3 | EA | 1 | Spool Fabrication | Field | Off Rack
1502092 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502093 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502094 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502095 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | FLANGE, RED, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502096 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1502097 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x3 | EA | 1 | Spool Fabrication | Field | Off Rack
1502098 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3039 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502099 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502100 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502101 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502102 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502103 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.148 | Spool Fabrication | Field | Off Rack
1502104 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502105 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.145 | Spool Fabrication | Field | Off Rack
1502106 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502107 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.148 | Spool Fabrication | Field | Off Rack
1502108 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502109 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.148 | Spool Fabrication | Field | Off Rack
1502110 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502111 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502112 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502113 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502114 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502115 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502116 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502117 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502118 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502119 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502120 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502121 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502122 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502123 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502124 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502125 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502126 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502127 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502128 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502129 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3048 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502130 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO2047 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502131 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502132 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502133 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502134 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.487 | Spool Fabrication | Field | Off Rack
1502135 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.487 | Spool Fabrication | Field | Off Rack
1502136 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502137 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502138 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502139 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502140 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 16x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502141 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502142 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502143 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502144 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502145 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 16x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502146 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502147 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502148 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502149 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502150 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 16x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502151 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502152 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502153 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502154 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502155 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502156 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.458 | Spool Fabrication | Field | Off Rack
1502157 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502158 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502159 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1502160 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502161 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.102 | Spool Fabrication | Field | Off Rack
1502162 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502163 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502164 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502165 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502166 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.102 | Spool Fabrication | Field | Off Rack
1502167 | Project A | Area_4 | DL | DL-XP01-8042 | ISO3055 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502168 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502169 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.323 | Spool Fabrication | Field | Off Rack
1502170 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.323 | Spool Fabrication | Field | Off Rack
1502171 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1502172 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502173 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502174 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502175 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502176 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.968 | Spool Fabrication | Field | Off Rack
1502177 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502178 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502179 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502180 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502181 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502182 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502183 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502184 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502185 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502186 | Project A | Area_4 | DL | DL-XP01-8040 | ISO3050 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502187 | Project A | Area_4 | DL | DL-XP01-8040 | ISO3050 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502188 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502189 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502190 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502191 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502192 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502193 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502194 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502195 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502196 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502197 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.624 | Spool Fabrication | Field | Off Rack
1502198 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502199 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502200 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1502201 | Project A | Area_4 | DL | DL-XP01-8034 | ISO3044 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502202 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502203 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502204 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502205 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502206 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502207 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502208 | Project A | Area_4 | DL | DL-XP01-8032 | ISO3041 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502209 | Project A | Area_4 | DL | DL-XP01-8032 | ISO3041 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502210 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.624 | Spool Fabrication | Field | Off Rack
1502211 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502212 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.458 | Spool Fabrication | Field | Off Rack
1502213 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502214 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502215 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1502216 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502217 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.102 | Spool Fabrication | Field | Off Rack
1502218 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502219 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502220 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502221 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502222 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.102 | Spool Fabrication | Field | Off Rack
1502223 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502224 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502225 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502226 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502227 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502228 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502229 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502230 | Project A | Area_4 | DL | DL-XP01-8027 | ISO3035 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502231 | Project A | Area_4 | DL | DL-XP01-8027 | ISO3035 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502232 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502233 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502234 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502235 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502236 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502237 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502238 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502239 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502240 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 16x14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502241 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502242 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502243 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502244 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502245 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502246 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502247 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 16x14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502248 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502249 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502250 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502251 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502252 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502253 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502254 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502255 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502256 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502257 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502258 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502259 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502260 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502261 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502262 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502263 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502264 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502265 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502266 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502267 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502268 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502269 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502270 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502271 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502272 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502273 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502274 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502275 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502276 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502277 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502278 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502279 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502280 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502281 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502282 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502283 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502284 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.419 | Spool Fabrication | Field | Off Rack
1502285 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502286 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502287 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502288 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502289 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502290 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502291 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.624 | Spool Fabrication | Field | Off Rack
1502292 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502293 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.458 | Spool Fabrication | Field | Off Rack
1502294 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502295 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502296 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1502297 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502298 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.102 | Spool Fabrication | Field | Off Rack
1502299 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502300 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502301 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502302 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502303 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.102 | Spool Fabrication | Field | Off Rack
1502304 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502305 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502306 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502307 | Project A | Area_4 | DL | DL-XP01-8029 | ISO1049 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502308 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502309 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502310 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502311 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502312 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502313 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502314 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502315 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502316 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502317 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502318 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.464 | Spool Fabrication | Field | Off Rack
1502319 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502320 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502321 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502322 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502323 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502324 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502325 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.464 | Spool Fabrication | Field | Off Rack
1502326 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502327 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502328 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502329 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502330 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502331 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502332 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.464 | Spool Fabrication | Field | Off Rack
1502333 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502334 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502335 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502336 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502337 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502338 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502339 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.464 | Spool Fabrication | Field | Off Rack
1502340 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502341 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502342 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502343 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502344 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502345 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502346 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.464 | Spool Fabrication | Field | Off Rack
1502347 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502348 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502349 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502350 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502351 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502352 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502353 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.464 | Spool Fabrication | Field | Off Rack
1502354 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502355 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502356 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502357 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502358 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502359 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502360 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502361 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502362 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502363 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502364 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502365 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.701 | Spool Fabrication | Field | Off Rack
1502366 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.338 | Spool Fabrication | Field | Off Rack
1502367 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502368 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502369 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.544 | Spool Fabrication | Field | Off Rack
1502370 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 1.399 | Spool Fabrication | Field | Off Rack
1502371 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502372 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502373 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502374 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502375 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502376 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502377 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502378 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.184 | Spool Fabrication | Field | Off Rack
1502379 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502380 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502381 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.24 | Spool Fabrication | Field | Off Rack
1502382 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502383 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502384 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.272 | Spool Fabrication | Field | Off Rack
1502385 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502386 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502387 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502388 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502389 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502390 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502391 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502392 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.108 | Spool Fabrication | Field | Off Rack
1502393 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502394 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502395 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502396 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.121 | Spool Fabrication | Field | Off Rack
1502397 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502398 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502399 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502400 | Project A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502401 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.701 | Spool Fabrication | Field | Off Rack
1502402 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.338 | Spool Fabrication | Field | Off Rack
1502403 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502404 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502405 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.544 | Spool Fabrication | Field | Off Rack
1502406 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 1.399 | Spool Fabrication | Field | Off Rack
1502407 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502408 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502409 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502410 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502411 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502412 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502413 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502414 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.184 | Spool Fabrication | Field | Off Rack
1502415 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502416 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502417 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.24 | Spool Fabrication | Field | Off Rack
1502418 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502419 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502420 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.272 | Spool Fabrication | Field | Off Rack
1502421 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502422 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502423 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502424 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502425 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502426 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502427 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502428 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.108 | Spool Fabrication | Field | Off Rack
1502429 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502430 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502431 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502432 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.121 | Spool Fabrication | Field | Off Rack
1502433 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502434 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502435 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502436 | Project A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502437 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.701 | Spool Fabrication | Field | Off Rack
1502438 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.338 | Spool Fabrication | Field | Off Rack
1502439 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502440 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502441 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.544 | Spool Fabrication | Field | Off Rack
1502442 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 1.399 | Spool Fabrication | Field | Off Rack
1502443 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502444 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502445 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502446 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502447 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502448 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502449 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502450 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.184 | Spool Fabrication | Field | Off Rack
1502451 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502452 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502453 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.24 | Spool Fabrication | Field | Off Rack
1502454 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502455 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502456 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502457 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502458 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502459 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.272 | Spool Fabrication | Field | Off Rack
1502460 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502461 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502462 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502463 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502464 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502465 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502466 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502467 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | PIPE GUIDE - G4 | 14 | EA | 1 | Stick Built | Field | Off Rack
1502468 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | PIPE GUIDE - G4 | 14 | EA | 1 | Stick Built | Field | Off Rack
1502469 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 14x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502470 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 14x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502471 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.419 | Spool Fabrication | Field | Off Rack
1502472 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502473 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502474 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.275 | Spool Fabrication | Field | Off Rack
1502475 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502476 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 16x14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502477 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 16x14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502478 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502479 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502480 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.275 | Spool Fabrication | Field | Off Rack
1502481 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502482 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | PIPE GUIDE - G4 | 14 | EA | 1 | Stick Built | Field | Off Rack
1502483 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 14x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502484 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.419 | Spool Fabrication | Field | Off Rack
1502485 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 16x14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502486 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502487 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502488 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.275 | Spool Fabrication | Field | Off Rack
1502489 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502490 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502491 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502492 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502493 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502494 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502495 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502496 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502497 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502498 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502499 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502500 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502501 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502502 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502503 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502504 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502505 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502506 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502507 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502508 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | DIRECTIONAL ANCHOR - A11 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502509 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502510 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502511 | Project A | Area_4 | DL | DL-XP01-8040 | ISO3050 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502512 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502513 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502514 | Project A | Area_4 | DL | DL-XP01-8027 | ISO3035 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502515 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502516 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | DIRECTIONAL ANCHOR - A11 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502517 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502518 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502519 | Project A | Area_4 | DL | DL-XP01-8032 | ISO3041 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502520 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502521 | Project A | Area_4 | DL | DL-XP01-8029 | ISO1049 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.257 | Spool Fabrication | Field | Off Rack
1502522 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502523 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502524 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Field | Off Rack
1502525 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502526 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502527 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502528 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502529 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502530 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502531 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502532 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | PIPE GUIDE - G4 | 2 | EA | 1 | Stick Built | Field | Off Rack
1502533 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Field | Off Rack
1502534 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Field | Off Rack
1502535 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | PIPE GUIDE - G4 | 14 | EA | 1 | Stick Built | Field | Off Rack
1502536 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | PIPE GUIDE - G4 | 14 | EA | 1 | Stick Built | Field | Off Rack
1502537 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | PIPE GUIDE - G4 | 14 | EA | 1 | Stick Built | Field | Off Rack
1502538 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Field | Off Rack
1502539 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1502540 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1502541 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1502542 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Field | Off Rack
1502543 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | PIPE GUIDE - G4 | 20 | EA | 1 | Stick Built | Field | Off Rack
1502544 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1502545 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1502546 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1502547 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 16x14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502548 | Project A | Area_4 | DL | DL-XP01-8034 | ISO3044 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.257 | Spool Fabrication | Field | Off Rack
1502549 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.136 | Spool Fabrication | Field | Off Rack
1502550 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.511 | Spool Fabrication | Field | Off Rack
1502551 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502552 | Project A | Area_4 | DL | DL-XP01-8040 | ISO3050 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.144 | Spool Fabrication | Field | Off Rack
1502553 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502554 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502555 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502556 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502557 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502558 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502559 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502560 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 14x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502561 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502562 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502563 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 14x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502564 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502565 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502566 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502567 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502568 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502569 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502570 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502571 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 14x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502572 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502573 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502574 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502575 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502576 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502577 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502578 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502579 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502580 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.109 | Spool Fabrication | Field | Off Rack
1502581 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502582 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502583 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502584 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502585 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502586 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502587 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | STRAINER, BASKET TYPE, CL600, RF, 304 SS, SP-AG-617 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502588 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502589 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | STRAINER, BASKET TYPE, CL600, RF, 304 SS, SP-AG-617 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502590 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502591 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | STRAINER, BASKET TYPE, CL600, RF, 304 SS, SP-AG-617 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502592 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.53 | Spool Fabrication | Field | Off Rack
1502593 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.53 | Spool Fabrication | Field | Off Rack
1502594 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502595 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502596 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 1.075 | Spool Fabrication | Field | Off Rack
1502597 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.418 | Spool Fabrication | Field | Off Rack
1502598 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502599 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502600 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 1.075 | Spool Fabrication | Field | Off Rack
1502601 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.418 | Spool Fabrication | Field | Off Rack
1502602 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502603 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 16x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502604 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 1.075 | Spool Fabrication | Field | Off Rack
1502605 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.418 | Spool Fabrication | Field | Off Rack
1502606 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502607 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502608 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.157 | Spool Fabrication | Field | Off Rack
1502609 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502610 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502611 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.716 | Spool Fabrication | Field | Off Rack
1502612 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.716 | Spool Fabrication | Field | Off Rack
1502613 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502614 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502615 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502616 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502617 | Project A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502618 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502619 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502620 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502621 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502622 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502623 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502624 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502625 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502626 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502627 | Project A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502628 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502629 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 20x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502630 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.911 | Spool Fabrication | Field | Off Rack
1502631 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502632 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502633 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.466 | Spool Fabrication | Field | Off Rack
1502634 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502635 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.673 | Spool Fabrication | Field | Off Rack
1502636 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.448 | Spool Fabrication | Field | Off Rack
1502637 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.377 | Spool Fabrication | Field | Off Rack
1502638 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502639 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502640 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502641 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.673 | Spool Fabrication | Field | Off Rack
1502642 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.278 | Spool Fabrication | Field | Off Rack
1502643 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.255 | Spool Fabrication | Field | Off Rack
1502644 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502645 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502646 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502647 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.673 | Spool Fabrication | Field | Off Rack
1502648 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.34 | Spool Fabrication | Field | Off Rack
1502649 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502650 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502651 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.54 | Spool Fabrication | Field | Off Rack
1502652 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502653 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 20x16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502654 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502655 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL600, RF, 63.5mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502656 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502657 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502658 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.6 | Spool Fabrication | Field | Off Rack
1502659 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 20x16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502660 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502661 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL600, RF, 63.5mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502662 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502663 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502664 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 20x16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502665 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502666 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL600, RF, 63.5mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502667 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502668 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502669 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.6 | Spool Fabrication | Field | Off Rack
1502670 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 20x16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502671 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502672 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL600, RF, 63.5mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502673 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502674 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502675 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 20x16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502676 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502677 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL600, RF, 63.5mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502678 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502679 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.8 | Spool Fabrication | Field | Off Rack
1502680 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.6 | Spool Fabrication | Field | Off Rack
1502681 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 20x16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502682 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502683 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | PADDLE BLIND C/W PADDLE SPACER, ASME B16.48, CL600, RF, 63.5mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502684 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502685 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502686 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.673 | Spool Fabrication | Field | Off Rack
1502687 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502688 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502689 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502690 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | STRAINER, PLATE TYPE, CL600, RF, ASTM A516 GR. 70N, IMPACT TEST TO M45C, SP-AN-602 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502691 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502692 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502693 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | STRAINER, PLATE TYPE, CL600, RF, ASTM A516 GR. 70N, IMPACT TEST TO M45C, SP-AN-602 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502694 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502695 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502696 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | STRAINER, PLATE TYPE, CL600, RF, ASTM A516 GR. 70N, IMPACT TEST TO M45C, SP-AN-602 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502697 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502698 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.266 | Spool Fabrication | Field | Off Rack
1502699 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502700 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502701 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.866 | Spool Fabrication | Field | Off Rack
1502702 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502703 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502704 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.866 | Spool Fabrication | Field | Off Rack
1502705 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 4.564 | Spool Fabrication | Field | Off Rack
1502706 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502707 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502708 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.736 | Spool Fabrication | Field | Off Rack
1502709 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502710 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502711 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.126 | Spool Fabrication | Field | Off Rack
1502712 | Project A | Area_4 | DL | DL-XP01-8040 | ISO3050 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.712 | Spool Fabrication | Field | Off Rack
1502713 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502714 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502715 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.136 | Spool Fabrication | Field | Off Rack
1502716 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502717 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502718 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502719 | Project A | Area_4 | DL | DL-XP01-8040 | ISO3050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502720 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502721 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502722 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.736 | Spool Fabrication | Field | Off Rack
1502723 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502724 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502725 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.126 | Spool Fabrication | Field | Off Rack
1502726 | Project A | Area_4 | DL | DL-XP01-8032 | ISO3041 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.712 | Spool Fabrication | Field | Off Rack
1502727 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.8 | Spool Fabrication | Field | Off Rack
1502728 | Project A | Area_4 | DL | DL-XP01-8027 | ISO3035 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.712 | Spool Fabrication | Field | Off Rack
1502729 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | FLANGE, RED, THD, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502730 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502731 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502732 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | FLANGE, RED, THD, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502733 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502734 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502735 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | FLANGE, RED, THD, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502736 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502737 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502738 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502739 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502740 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502741 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502742 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | FLANGE, RED, THD, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502743 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502744 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502745 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502746 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502747 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.32 | Spool Fabrication | Field | Off Rack
1502748 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.32 | Spool Fabrication | Field | Off Rack
1502749 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.538 | Spool Fabrication | Field | Off Rack
1502750 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 5.515 | Spool Fabrication | Field | Off Rack
1502751 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.408 | Spool Fabrication | Field | Off Rack
1502752 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502753 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502754 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502755 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.108 | Spool Fabrication | Field | Off Rack
1502756 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502757 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502758 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502759 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.655 | Spool Fabrication | Field | Off Rack
1502760 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502761 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502762 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502763 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502764 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502765 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502766 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.114 | Spool Fabrication | Field | Off Rack
1502767 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502768 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502769 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | CHECK VALVE, CL800, SW, ASTM A350 GR. LF2 CL. 1, CH-G02A | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502770 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502771 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502772 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502773 | Project A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502774 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.121 | Spool Fabrication | Field | Off Rack
1502775 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502776 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502777 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502778 | Project A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502779 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502780 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502781 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502782 | Project A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502783 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.257 | Spool Fabrication | Field | Off Rack
1502784 | Project A | Area_4 | DL | DL-XP01-8042 | ISO3055 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.257 | Spool Fabrication | Field | Off Rack
1502785 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502786 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502787 | Project A | Area_4 | DL | DL-XP01-8041 | ISO3052 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502788 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502789 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502790 | Project A | Area_4 | DL | DL-XP01-8042 | ISO3055 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502791 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.8 | Spool Fabrication | Field | Off Rack
1502792 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.884 | Spool Fabrication | Field | Off Rack
1502793 | Project A | Area_4 | DL | DL-XP01-8040 | ISO3050 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502794 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.837 | Spool Fabrication | Field | Off Rack
1502795 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502796 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502797 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.156 | Spool Fabrication | Field | Off Rack
1502798 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502799 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502800 | Project A | Area_4 | DL | DL-XP01-8039 | ISO3049 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502801 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502802 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502803 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502804 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502805 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502806 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502807 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3047 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502808 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502809 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502810 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502811 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502812 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502813 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502814 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502815 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502816 | Project A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502817 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502818 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502819 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.617 | Spool Fabrication | Field | Off Rack
1502820 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.658 | Spool Fabrication | Field | Off Rack
1502821 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502822 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502823 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502824 | Project A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502825 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502826 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502827 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.8 | Spool Fabrication | Field | Off Rack
1502828 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502829 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 0.85 | Spool Fabrication | Field | Off Rack
1502830 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502831 | Project A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502832 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.228 | Spool Fabrication | Field | Off Rack
1502833 | Project A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.22 | Spool Fabrication | Field | Off Rack
1502834 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502835 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502836 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502837 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502838 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502839 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502840 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502841 | Project A | Area_4 | DL | DL-XP01-8032 | ISO3041 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502842 | Project A | Area_4 | DL | DL-XP01-8032 | ISO3041 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.144 | Spool Fabrication | Field | Off Rack
1502843 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502844 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502845 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | FLANGE, RED, THD, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502846 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502847 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502848 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502849 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502850 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.32 | Spool Fabrication | Field | Off Rack
1502851 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.32 | Spool Fabrication | Field | Off Rack
1502852 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.538 | Spool Fabrication | Field | Off Rack
1502853 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 5.515 | Spool Fabrication | Field | Off Rack
1502854 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.408 | Spool Fabrication | Field | Off Rack
1502855 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502856 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1502857 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502858 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502859 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502860 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502861 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.656 | Spool Fabrication | Field | Off Rack
1502862 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502863 | Project A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502864 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502865 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502866 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502867 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502868 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.114 | Spool Fabrication | Field | Off Rack
1502869 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502870 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502871 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502872 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502873 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502874 | Project A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502875 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.257 | Spool Fabrication | Field | Off Rack
1502876 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502877 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502878 | Project A | Area_4 | DL | DL-XP01-8033 | ISO3043 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502879 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502880 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502881 | Project A | Area_4 | DL | DL-XP01-8034 | ISO3044 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502882 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.8 | Spool Fabrication | Field | Off Rack
1502883 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.884 | Spool Fabrication | Field | Off Rack
1502884 | Project A | Area_4 | DL | DL-XP01-8032 | ISO3041 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502885 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.837 | Spool Fabrication | Field | Off Rack
1502886 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502887 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502888 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.156 | Spool Fabrication | Field | Off Rack
1502889 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502890 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502891 | Project A | Area_4 | DL | DL-XP01-8031 | ISO3040 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502892 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502893 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502894 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502895 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502896 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502897 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502898 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502899 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502900 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502901 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502902 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502903 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502904 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502905 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502906 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502907 | Project A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502908 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502909 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502910 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.617 | Spool Fabrication | Field | Off Rack
1502911 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.658 | Spool Fabrication | Field | Off Rack
1502912 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502913 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502914 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502915 | Project A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1502916 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502917 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502918 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.8 | Spool Fabrication | Field | Off Rack
1502919 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502920 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 0.85 | Spool Fabrication | Field | Off Rack
1502921 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502922 | Project A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1502923 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.228 | Spool Fabrication | Field | Off Rack
1502924 | Project A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.22 | Spool Fabrication | Field | Off Rack
1502925 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502926 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502927 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502928 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502929 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502930 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502931 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502932 | Project A | Area_4 | DL | DL-XP01-8027 | ISO3035 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502933 | Project A | Area_4 | DL | DL-XP01-8027 | ISO3035 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.144 | Spool Fabrication | Field | Off Rack
1502934 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502935 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502936 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | FLANGE, RED, THD, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502937 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502938 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502939 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502940 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 20 | EA | 1 | Spool Fabrication | Field | Off Rack
1502941 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.32 | Spool Fabrication | Field | Off Rack
1502942 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.32 | Spool Fabrication | Field | Off Rack
1502943 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.538 | Spool Fabrication | Field | Off Rack
1502944 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 1.487 | Spool Fabrication | Field | Off Rack
1502945 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 5.515 | Spool Fabrication | Field | Off Rack
1502946 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 4.408 | Spool Fabrication | Field | Off Rack
1502947 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502948 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502949 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502950 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1502951 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.655 | Spool Fabrication | Field | Off Rack
1502952 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502953 | Project A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502954 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502955 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502956 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502957 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502958 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.114 | Spool Fabrication | Field | Off Rack
1502959 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502960 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502961 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502962 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502963 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502964 | Project A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502965 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.257 | Spool Fabrication | Field | Off Rack
1502966 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502967 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502968 | Project A | Area_4 | DL | DL-XP01-8028 | ISO1048 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502969 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502970 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502971 | Project A | Area_4 | DL | DL-XP01-8029 | ISO1049 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502972 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.884 | Spool Fabrication | Field | Off Rack
1502973 | Project A | Area_4 | DL | DL-XP01-8027 | ISO3035 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502974 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.837 | Spool Fabrication | Field | Off Rack
1502975 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502976 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502977 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.156 | Spool Fabrication | Field | Off Rack
1502978 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502979 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502980 | Project A | Area_4 | DL | DL-XP01-8074 | ISO2048 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502981 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502982 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502983 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.228 | Spool Fabrication | Field | Off Rack
1502984 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.22 | Spool Fabrication | Field | Off Rack
1502985 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502986 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502987 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502988 | Project A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502989 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502990 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502991 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502992 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502993 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502994 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502995 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502996 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502997 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1502998 | Project A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1502999 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503000 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1503001 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.617 | Spool Fabrication | Field | Off Rack
1503002 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 20 | M | 0.658 | Spool Fabrication | Field | Off Rack
1503003 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503004 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503005 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1503006 | Project A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1503007 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503008 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503009 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 1.8 | Spool Fabrication | Field | Off Rack
1503010 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1503011 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 14 | M | 0.85 | Spool Fabrication | Field | Off Rack
1503012 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1503013 | Project A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 14 | EA | 1 | Spool Fabrication | Field | Off Rack
1503014 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503015 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503016 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503017 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, RED, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503018 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503019 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503020 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503021 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503022 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503023 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, RED, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 3x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503024 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503025 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503026 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503027 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503028 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.109 | Spool Fabrication | Field | Off Rack
1503029 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503030 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503031 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503032 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503033 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503034 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503035 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503036 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503037 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503038 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503039 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503040 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503041 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503042 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 8 | EA | 1 | Stick Built | Field | Off Rack
1503043 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503044 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503045 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | CORIOLIS METER, CL600 RF, (BY INSTRUMENTATION) | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503046 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 8 | EA | 1 | Stick Built | Field | Off Rack
1503047 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.282 | Spool Fabrication | Field | Off Rack
1503048 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.266 | Spool Fabrication | Field | Off Rack
1503049 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.21 | Spool Fabrication | Field | Off Rack
1503050 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503051 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503052 | Project A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.241 | Spool Fabrication | Field | Off Rack
1503053 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | CORIOLIS METER, CL600 RF, (BY INSTRUMENTATION) | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503054 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.781 | Spool Fabrication | Field | Off Rack
1503055 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503056 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 1.394 | Spool Fabrication | Field | Off Rack
1503057 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503058 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.814 | Spool Fabrication | Field | Off Rack
1503059 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503060 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503061 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503062 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.984 | Spool Fabrication | Field | Off Rack
1503063 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503064 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503065 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503066 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.248 | Spool Fabrication | Field | Off Rack
1503067 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | DIRECTIONAL ANCHOR - A11 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503068 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503069 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503070 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503071 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503072 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503073 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503074 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503075 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503076 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503077 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503078 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503079 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503080 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503081 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503082 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.123 | Spool Fabrication | Field | Off Rack
1503083 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503084 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.443 | Spool Fabrication | Field | Off Rack
1503085 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503086 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503087 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503088 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | ORIFICE PLATE, CL600, RF, (BY INSTRUMENTATION), RO-9400 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503089 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.883 | Spool Fabrication | Field | Off Rack
1503090 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503091 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.763 | Spool Fabrication | Field | Off Rack
1503092 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1503093 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1503094 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | GUIDE FOR PIPE SHOE - G11 | 12 | EA | 1 | Stick Built | Field | Off Rack
1503095 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | CLAMP PIPE SHOE - S4L | 12 | EA | 1 | Stick Built | Field | Off Rack
1503096 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | DIRECTIONAL ANCHOR - A11 | 12 | EA | 1 | Stick Built | Field | Off Rack
1503097 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 8.543 | Spool Fabrication | Field | Off Rack
1503098 | Project A | Area_5 | FL | FL-XP01-8124 | ISO3061 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503099 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | DIRECTIONAL ANCHOR - A11 | 6 | EA | 1 | Stick Built | Field | Off Rack
1503100 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503101 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.235 | Spool Fabrication | Field | Off Rack
1503102 | Project A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.162 | Spool Fabrication | Field | Off Rack
1503103 | Project A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503104 | Project A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.152 | Spool Fabrication | Field | Off Rack
1503105 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503106 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.613 | Spool Fabrication | Field | Off Rack
1503107 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3069 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503108 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503109 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503110 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503111 | Project A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503112 | Project A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503113 | Project A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503114 | Project A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503115 | Project A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503116 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.166 | Spool Fabrication | Field | Off Rack
1503117 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.166 | Spool Fabrication | Field | Off Rack
1503118 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503119 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503120 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503121 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503122 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.166 | Spool Fabrication | Field | Off Rack
1503123 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503124 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503125 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503126 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503127 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503128 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.908 | Spool Fabrication | Field | Off Rack
1503129 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503130 | Project A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503131 | Project A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.559 | Spool Fabrication | Field | Off Rack
1503132 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3062 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503133 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503134 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.628 | Spool Fabrication | Field | Off Rack
1503135 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503136 | Project A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.971 | Spool Fabrication | Field | Off Rack
1503137 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503138 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.214 | Spool Fabrication | Field | Off Rack
1503139 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503140 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.559 | Spool Fabrication | Field | Off Rack
1503141 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3067 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503142 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503143 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.572 | Spool Fabrication | Field | Off Rack
1503144 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503145 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.242 | Spool Fabrication | Field | Off Rack
1503146 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503147 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.292 | Spool Fabrication | Field | Off Rack
1503148 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.996 | Spool Fabrication | Field | Off Rack
1503149 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.672 | Spool Fabrication | Field | Off Rack
1503150 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503151 | Project A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503152 | Project A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503153 | Project A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503154 | Project A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503155 | Project A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503156 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503157 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503158 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503159 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503160 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503161 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.632 | Spool Fabrication | Field | Off Rack
1503162 | Project A | Area_5 | DL | DL-ZL01-8059 | ISO3066 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503163 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503164 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503165 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503166 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503167 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503168 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503169 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503170 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503171 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503172 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503173 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503174 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503175 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503176 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503177 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503178 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503179 | Project A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503180 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503181 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503182 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503183 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.604 | Spool Fabrication | Field | Off Rack
1503184 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503185 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503186 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503187 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503188 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503189 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503190 | Project A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503191 | Project A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503192 | Project A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503193 | Project A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503194 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.527 | Spool Fabrication | Field | Off Rack
1503195 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503196 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503197 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.166 | Spool Fabrication | Field | Off Rack
1503198 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503199 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503200 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503201 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503202 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503203 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503204 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503205 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.834 | Spool Fabrication | Field | Off Rack
1503206 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503207 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503208 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.796 | Spool Fabrication | Field | Off Rack
1503209 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503210 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503211 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.386 | Spool Fabrication | Field | Off Rack
1503212 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503213 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503214 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503215 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.472 | Spool Fabrication | Field | Off Rack
1503216 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.472 | Spool Fabrication | Field | Off Rack
1503217 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.525 | Spool Fabrication | Field | Off Rack
1503218 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503219 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503220 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503221 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503222 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503223 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503224 | Project A | Area_5 | DL | DL-ZL01-8063 | ISO3011 | ZL01 | CLAMP PIPE SHOE - SP18 | 6 | EA | 1 | Stick Built | Field | Off Rack
1503225 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503226 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503227 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503228 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.9 | Spool Fabrication | Field | Off Rack
1503229 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503230 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503231 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 7.599 | Spool Fabrication | Field | Off Rack
1503232 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | CLAMP PIPE SHOE - SP18 | 6 | EA | 1 | Stick Built | Field | Off Rack
1503233 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503234 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503235 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503236 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1503237 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503238 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503239 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503240 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503241 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503242 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503243 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503244 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503245 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503246 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503247 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503248 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503249 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503250 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503251 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503252 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503253 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503254 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503255 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503256 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503257 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503258 | Project A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503259 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503260 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503261 | Project A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503262 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503263 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503264 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 9.7mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503265 | Project A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503266 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503267 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503268 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503269 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503270 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.603 | Spool Fabrication | Field | Off Rack
1503271 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.603 | Spool Fabrication | Field | Off Rack
1503272 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503273 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503274 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503275 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503276 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503277 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503278 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503279 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503280 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503281 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503282 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503283 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503284 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503285 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503286 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.9 | Spool Fabrication | Field | Off Rack
1503287 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503288 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503289 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503290 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503291 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503292 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503293 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503294 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503295 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503296 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503297 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503298 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503299 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503300 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 3.631 | Spool Fabrication | Field | Off Rack
1503301 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503302 | Project A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503303 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503304 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503305 | Project A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503306 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503307 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503308 | Project A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503309 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503310 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503311 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503312 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503313 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.643 | Spool Fabrication | Field | Off Rack
1503314 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.643 | Spool Fabrication | Field | Off Rack
1503315 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.33 | Spool Fabrication | Field | Off Rack
1503316 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503317 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503318 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503319 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503320 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503321 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503322 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503323 | Project A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1503324 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503325 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503326 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503327 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503328 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503329 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503330 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503331 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503332 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503333 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503334 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503335 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503336 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503337 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503338 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503339 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503340 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503341 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503342 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503343 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503344 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503345 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503346 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503347 | Project A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503348 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503349 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 3.631 | Spool Fabrication | Field | Off Rack
1503350 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 1.348 | Spool Fabrication | Field | Off Rack
1503351 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503352 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.628 | Spool Fabrication | Field | Off Rack
1503353 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503354 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503355 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 1.348 | Spool Fabrication | Field | Off Rack
1503356 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503357 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503358 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.628 | Spool Fabrication | Field | Off Rack
1503359 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503360 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503361 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503362 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503363 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503364 | Project A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503365 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503366 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503367 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503368 | Project A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503369 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503370 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503371 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503372 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503373 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503374 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503375 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503376 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503377 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503378 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.543 | Spool Fabrication | Field | Off Rack
1503379 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503380 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503381 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503382 | Project A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503383 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503384 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503385 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503386 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.144 | Spool Fabrication | Field | Off Rack
1503387 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.21 | Spool Fabrication | Field | Off Rack
1503388 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.695 | Spool Fabrication | Field | Off Rack
1503389 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.782 | Spool Fabrication | Field | Off Rack
1503390 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503391 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503392 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503393 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1503394 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503395 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503396 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503397 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503398 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503399 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503400 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503401 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503402 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503403 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503404 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503405 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | CONTROL VALVE, BUTTERFLY BODY, CL600, RF LUG, (BY INSTRUMENTATION) | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503406 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503407 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503408 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503409 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503410 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503411 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503412 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503413 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | GUIDE FOR PIPE SHOE - G6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503414 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503415 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503416 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503417 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Field | Off Rack
1503418 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.851 | Spool Fabrication | Field | Off Rack
1503419 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503420 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503421 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.142 | Spool Fabrication | Field | Off Rack
1503422 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503423 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503424 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.959 | Spool Fabrication | Field | Off Rack
1503425 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.653 | Spool Fabrication | Field | Off Rack
1503426 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503427 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503428 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503429 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.166 | Spool Fabrication | Field | Off Rack
1503430 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503431 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503432 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.206 | Spool Fabrication | Field | Off Rack
1503433 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503434 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503435 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.657 | Spool Fabrication | Field | Off Rack
1503436 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503437 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503438 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503439 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503440 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503441 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503442 | Project A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503443 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.269 | Spool Fabrication | Field | Off Rack
1503444 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503445 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503446 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.425 | Spool Fabrication | Field | Off Rack
1503447 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503448 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503449 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503450 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503451 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503452 | Project A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503453 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503454 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503455 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.483 | Spool Fabrication | Field | Off Rack
1503456 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503457 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503458 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.782 | Spool Fabrication | Field | Off Rack
1503459 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503460 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503461 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503462 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503463 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503464 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503465 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503466 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.202 | Spool Fabrication | Field | Off Rack
1503467 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.202 | Spool Fabrication | Field | Off Rack
1503468 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503469 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503470 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503471 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503472 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503473 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503474 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503475 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503476 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503477 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.149 | Spool Fabrication | Field | Off Rack
1503478 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.156 | Spool Fabrication | Field | Off Rack
1503479 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503480 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503481 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1503482 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503483 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503484 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503485 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503486 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.58 | Spool Fabrication | Field | Off Rack
1503487 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.937 | Spool Fabrication | Field | Off Rack
1503488 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503489 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503490 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503491 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503492 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 41.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503493 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503494 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02B | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503495 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503496 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503497 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503498 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CH-C02C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503499 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.954 | Spool Fabrication | Field | Off Rack
1503500 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503501 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.952 | Spool Fabrication | Field | Off Rack
1503502 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503503 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503504 | Project A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503505 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.674 | Spool Fabrication | Field | Off Rack
1503506 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503507 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 6.686 | Spool Fabrication | Field | Off Rack
1503508 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503509 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503510 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503511 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 2.051 | Spool Fabrication | Field | Off Rack
1503512 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503513 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503514 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503515 | Project A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503516 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503517 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503518 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503519 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503520 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503521 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503522 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503523 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503524 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503525 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503526 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503527 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503528 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503529 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503530 | Project A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503531 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503532 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503533 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503534 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503535 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503536 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.7 | Spool Fabrication | Field | Off Rack
1503537 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.15 | Spool Fabrication | Field | Off Rack
1503538 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | TEE, RED, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503539 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503540 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503541 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503542 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02C | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503543 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503544 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503545 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503546 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503547 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503548 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 4.53 | Spool Fabrication | Field | Off Rack
1503549 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503550 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503551 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 4.087 | Spool Fabrication | Field | Off Rack
1503552 | Project A | Area_6 | IA | IA-XP02-9001 | ISO3073 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503553 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503554 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503555 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503556 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503557 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503558 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503559 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503560 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 8.543 | Spool Fabrication | Field | Off Rack
1503561 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503562 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503563 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503564 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503565 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503566 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503567 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503568 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.302 | Spool Fabrication | Field | Off Rack
1503569 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.309 | Spool Fabrication | Field | Off Rack
1503570 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503571 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503572 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503573 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503574 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503575 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503576 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503577 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503578 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503579 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503580 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503581 | Project A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503582 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503583 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503584 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503585 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503586 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503587 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503588 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503589 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503590 | Project A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503591 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503592 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503593 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503594 | Project A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503595 | Project A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.667 | Spool Fabrication | Field | Off Rack
1503596 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | CORIOLIS METER, CL600 RF, (BY INSTRUMENTATION) | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503597 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | CORIOLIS METER, CL600 RF, (BY INSTRUMENTATION) | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503598 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503599 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503600 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503601 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503602 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503603 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503604 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503605 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503606 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503607 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503608 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503609 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503610 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503611 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503612 | Project A | Area_7 | DL | DL-XP01-8071 | ISO1041 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.255 | Spool Fabrication | Field | Off Rack
1503613 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503614 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.934 | Spool Fabrication | Field | Off Rack
1503615 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503616 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503617 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503618 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503619 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503620 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503621 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503622 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503623 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503624 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503625 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503626 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503627 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.259 | Spool Fabrication | Field | Off Rack
1503628 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503629 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503630 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503631 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503632 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503633 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503634 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503635 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503636 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503637 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503638 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503639 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503640 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503641 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503642 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503643 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503644 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503645 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503646 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503647 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503648 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503649 | Project A | Area_7 | DL | DL-XP01-8019 | ISO1039 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.487 | Spool Fabrication | Field | Off Rack
1503650 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.996 | Spool Fabrication | Field | Off Rack
1503651 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503652 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.739 | Spool Fabrication | Field | Off Rack
1503653 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.739 | Spool Fabrication | Field | Off Rack
1503654 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503655 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.974 | Spool Fabrication | Field | Off Rack
1503656 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503657 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503658 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503659 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.487 | Spool Fabrication | Field | Off Rack
1503660 | Project A | Area_7 | DL | DL-XP01-8072 | ISO1038 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.255 | Spool Fabrication | Field | Off Rack
1503661 | Project A | Area_7 | DL | DL-XP01-8072 | ISO1038 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503662 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503663 | Project A | Area_7 | DL | DL-XP01-8019 | ISO1039 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503664 | Project A | Area_7 | DL | DL-XP01-8071 | ISO1041 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.642 | Spool Fabrication | Field | Off Rack
1503665 | Project A | Area_7 | DL | DL-XP01-8072 | ISO1038 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.642 | Spool Fabrication | Field | Off Rack
1503666 | Project A | Area_7 | DL | DL-XP01-8018 | ISO1044 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.22 | Spool Fabrication | Field | Off Rack
1503667 | Project A | Area_7 | DL | DL-XP01-8018 | ISO1044 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503668 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503669 | Project A | Area_7 | DL | DL-XP01-8018 | ISO1044 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.442 | Spool Fabrication | Field | Off Rack
1503670 | Project A | Area_7 | DL | DL-XP01-8018 | ISO1044 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503671 | Project A | Area_7 | DL | DL-XP01-8018 | ISO1044 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503672 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503673 | Project A | Area_7 | DL | DL-XP01-8017 | ISO1043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.917 | Spool Fabrication | Field | Off Rack
1503674 | Project A | Area_7 | DL | DL-XP01-8017 | ISO1043 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503675 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503676 | Project A | Area_7 | DL | DL-XP01-8017 | ISO1043 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.142 | Spool Fabrication | Field | Off Rack
1503677 | Project A | Area_7 | DL | DL-XP01-8017 | ISO1043 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503678 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503679 | Project A | Area_7 | DL | DL-XP01-8019 | ISO1039 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.802 | Spool Fabrication | Field | Off Rack
1503680 | Project A | Area_7 | DL | DL-XP01-8019 | ISO1039 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.157 | Spool Fabrication | Field | Off Rack
1503681 | Project A | Area_7 | DL | DL-XP01-8019 | ISO1039 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503682 | Project A | Area_7 | DL | DL-XP01-8019 | ISO1039 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503683 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503684 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503685 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.886 | Spool Fabrication | Field | Off Rack
1503686 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503687 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503688 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503689 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503690 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 4.507 | Spool Fabrication | Field | Off Rack
1503691 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 8 | EA | 1 | Stick Built | Field | Off Rack
1503692 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 8 | EA | 1 | Stick Built | Field | Off Rack
1503693 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1503694 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1503695 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1503696 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1503697 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.477 | Spool Fabrication | Field | Off Rack
1503698 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503699 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.42 | Spool Fabrication | Field | Off Rack
1503700 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503701 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.694 | Spool Fabrication | Field | Off Rack
1503702 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503703 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.187 | Spool Fabrication | Field | Off Rack
1503704 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503705 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503706 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503707 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503708 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503709 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.143 | Spool Fabrication | Field | Off Rack
1503710 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503711 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503712 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503713 | Project A | Area_7 | DL | DL-XP01-8073 | ISO1035 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503714 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.729 | Spool Fabrication | Field | Off Rack
1503715 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503716 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503717 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503718 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503719 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503720 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503721 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503722 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503723 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.135 | Spool Fabrication | Field | Off Rack
1503724 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503725 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503726 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.302 | Spool Fabrication | Field | Off Rack
1503727 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503728 | Project A | Area_7 | DL | DL-XP01-8024 | ISO1037 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503729 | Project A | Area_7 | DL | DL-XP01-8072 | ISO1038 | XP01 | CLAMP PIPE SHOE - SP18 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503730 | Project A | Area_7 | DL | DL-XP01-8072 | ISO1038 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503731 | Project A | Area_7 | DL | DL-XP01-8072 | ISO1038 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503732 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.366 | Spool Fabrication | Field | Off Rack
1503733 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503734 | Project A | Area_7 | DL | DL-XP01-8071 | ISO1041 | XP01 | CLAMP PIPE SHOE - SP18 | 2 | EA | 1 | Stick Built | Field | Off Rack
1503735 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.043 | Spool Fabrication | Field | Off Rack
1503736 | Project A | Area_7 | DL | DL-XP01-8071 | ISO1041 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503737 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1031 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503738 | Project A | Area_7 | DL | DL-XP01-8071 | ISO1041 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503739 | Project A | Area_7 | DL | DL-XP01-8071 | ISO1041 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503740 | Project A | Area_7 | DL | DL-XP01-8019 | ISO1039 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503741 | Project A | Area_7 | DL | DL-XP01-8019 | ISO1039 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503742 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503743 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503744 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503745 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503746 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503747 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503748 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503749 | Project A | Area_7 | DL | DL-XP01-8017 | ISO1043 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503750 | Project A | Area_7 | DL | DL-XP01-8017 | ISO1043 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503751 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.766 | Spool Fabrication | Field | Off Rack
1503752 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.846 | Spool Fabrication | Field | Off Rack
1503753 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.704 | Spool Fabrication | Field | Off Rack
1503754 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503755 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503756 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503757 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503758 | Project A | Area_7 | DL | DL-XP01-8018 | ISO1044 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503759 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1503760 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.845 | Spool Fabrication | Field | Off Rack
1503761 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503762 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503763 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503764 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1032 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503765 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503766 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503767 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503768 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503769 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 3.481 | Spool Fabrication | Field | Off Rack
1503770 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.419 | Spool Fabrication | Field | Off Rack
1503771 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.49 | Spool Fabrication | Field | Off Rack
1503772 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503773 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | STRAINER, PLATE TYPE, CL600, RF, ASTM A516 GR. 70N, IMPACT TEST TO M45C, SP-AN-602 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503774 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503775 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | STRAINER, PLATE TYPE, CL600, RF, ASTM A516 GR. 70N, IMPACT TEST TO M45C, SP-AN-602 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503776 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503777 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503778 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503779 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503780 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503781 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503782 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503783 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503784 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503785 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503786 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503787 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503788 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503789 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.405 | Spool Fabrication | Field | Off Rack
1503790 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 6.154 | Spool Fabrication | Field | Off Rack
1503791 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503792 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503793 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503794 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503795 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503796 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503797 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503798 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1503799 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503800 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503801 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503802 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503803 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503804 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503805 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.109 | Spool Fabrication | Field | Off Rack
1503806 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503807 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503808 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503809 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503810 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503811 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503812 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503813 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503814 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503815 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503816 | Project A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503817 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503818 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503819 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503820 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503821 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503822 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503823 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503824 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503825 | Project A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503826 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503827 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503828 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.525 | Spool Fabrication | Field | Off Rack
1503829 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503830 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.796 | Spool Fabrication | Field | Off Rack
1503831 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503832 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503833 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.386 | Spool Fabrication | Field | Off Rack
1503834 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503835 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503836 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503837 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503838 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503839 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503840 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503841 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | CLAMP PIPE SHOE - SP18 | 6 | EA | 1 | Stick Built | Field | Off Rack
1503842 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503843 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.9 | Spool Fabrication | Field | Off Rack
1503844 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503845 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503846 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | CLAMP PIPE SHOE - SP18 | 6 | EA | 1 | Stick Built | Field | Off Rack
1503847 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503848 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503849 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.9 | Spool Fabrication | Field | Off Rack
1503850 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503851 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.523 | Spool Fabrication | Field | Off Rack
1503852 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.523 | Spool Fabrication | Field | Off Rack
1503853 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1503854 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.159 | Spool Fabrication | Field | Off Rack
1503855 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503856 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 4.062 | Spool Fabrication | Field | Off Rack
1503857 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503858 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503859 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503860 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503861 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503862 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503863 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503864 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503865 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503866 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503867 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.419 | Spool Fabrication | Field | Off Rack
1503868 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503869 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503870 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.743 | Spool Fabrication | Field | Off Rack
1503871 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503872 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.743 | Spool Fabrication | Field | Off Rack
1503873 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503874 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503875 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503876 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503877 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503878 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503879 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503880 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503881 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503882 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503883 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503884 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503885 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503886 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503887 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503888 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503889 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503890 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503891 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503892 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503893 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503894 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503895 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503896 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503897 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503898 | Project A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503899 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.166 | Spool Fabrication | Field | Off Rack
1503900 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503901 | Project A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503902 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503903 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503904 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503905 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503906 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.49 | Spool Fabrication | Field | Off Rack
1503907 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503908 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503909 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503910 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.628 | Spool Fabrication | Field | Off Rack
1503911 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503912 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.5 | Spool Fabrication | Field | Off Rack
1503913 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503914 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503915 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503916 | Project A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503917 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 3.112 | Spool Fabrication | Field | Off Rack
1503918 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503919 | Project A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503920 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503921 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | TEE, RED, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503922 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 3.481 | Spool Fabrication | Field | Off Rack
1503923 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503924 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503925 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503926 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH XSxSCH XS, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503927 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1503928 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.628 | Spool Fabrication | Field | Off Rack
1503929 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503930 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503931 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 8 | M | 0.5 | Spool Fabrication | Field | Off Rack
1503932 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503933 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503934 | Project A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503935 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503936 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503937 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503938 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503939 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503940 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503941 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503942 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503943 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503944 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503945 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503946 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503947 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503948 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503949 | Project A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503950 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503951 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503952 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503953 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503954 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503955 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503956 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503957 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503958 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503959 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503960 | Project A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503961 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503962 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503963 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503964 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503965 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1503966 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503967 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503968 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503969 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503970 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503971 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1503972 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.543 | Spool Fabrication | Field | Off Rack
1503973 | Project A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1503974 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503975 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503976 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503977 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.209 | Spool Fabrication | Field | Off Rack
1503978 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503979 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.83 | Spool Fabrication | Field | Off Rack
1503980 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH STDxSCH XS, ASTM A420 GR. WPL6, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503981 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503982 | Project A | Area_7 | DL | DL-XP01-8003 | ISO1033 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1503983 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503984 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503985 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503986 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | FLANGE, RED, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1503987 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503988 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503989 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.259 | Spool Fabrication | Field | Off Rack
1503990 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503991 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503992 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503993 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1503994 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503995 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1503996 | Project A | Area_8 | DL | DL-XP01-8003 | ISO1018 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503997 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.784 | Spool Fabrication | Field | Off Rack
1503998 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1503999 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504000 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504001 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504002 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504003 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504004 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504005 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.942 | Spool Fabrication | Field | Off Rack
1504006 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.542 | Spool Fabrication | Field | Off Rack
1504007 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.296 | Spool Fabrication | Field | Off Rack
1504008 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504009 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504010 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504011 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.701 | Spool Fabrication | Field | Off Rack
1504012 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504013 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504014 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504015 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504016 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504017 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504018 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504019 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | CONTROL VALVE, BALL BODY, CL600, RF, (BY INSTRUMENTATION) | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504020 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504021 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504022 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504023 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504024 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504025 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504026 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504027 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504028 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504029 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504030 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504031 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504032 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504033 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | CONTROL VALVE, BUTTERFLY BODY, CL600, RF LUG, (BY INSTRUMENTATION) | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504034 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504035 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.423 | Spool Fabrication | Field | Off Rack
1504036 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.109 | Spool Fabrication | Field | Off Rack
1504037 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504038 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.743 | Spool Fabrication | Field | Off Rack
1504039 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.743 | Spool Fabrication | Field | Off Rack
1504040 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504041 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504042 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504043 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504044 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.367 | Spool Fabrication | Field | Off Rack
1504045 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504046 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.367 | Spool Fabrication | Field | Off Rack
1504047 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504048 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504049 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504050 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504051 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504052 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504053 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504054 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504055 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504056 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504057 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504058 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504059 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | CLAMP PIPE SHOE - SP18 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504060 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.23 | Spool Fabrication | Field | Off Rack
1504061 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504062 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504063 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1504064 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504065 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.495 | Spool Fabrication | Field | Off Rack
1504066 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504067 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.206 | Spool Fabrication | Field | Off Rack
1504068 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.591 | Spool Fabrication | Field | Off Rack
1504069 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504070 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504071 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504072 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.783 | Spool Fabrication | Field | Off Rack
1504073 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504074 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504075 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | ELBOW, 90 DEG, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504076 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504077 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.261 | Spool Fabrication | Field | Off Rack
1504078 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.597 | Spool Fabrication | Field | Off Rack
1504079 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504080 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-2-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1504081 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.783 | Spool Fabrication | Field | Off Rack
1504082 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504083 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504084 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504085 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3 | Spool Fabrication | Field | Off Rack
1504086 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504087 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504088 | Project A | Area_8 | DL | DL-XP01-8021 | ISO1034 | XP01 | CLAMP PIPE SHOE - SP18 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504089 | Project A | Area_8 | DL | DL-XP01-8021 | ISO1034 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.403 | Spool Fabrication | Field | Off Rack
1504090 | Project A | Area_8 | DL | DL-XP01-8021 | ISO1034 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504091 | Project A | Area_8 | DL | DL-XP01-8021 | ISO1034 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504092 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504093 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504094 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.958 | Spool Fabrication | Field | Off Rack
1504095 | Project A | Area_8 | DL | DL-XP01-8021 | ISO1034 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.923 | Spool Fabrication | Field | Off Rack
1504096 | Project A | Area_8 | DL | DL-XP01-8021 | ISO1034 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504097 | Project A | Area_8 | DL | DL-XP01-8021 | ISO1034 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504098 | Project A | Area_8 | DL | DL-XP01-8021 | ISO1034 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504099 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504100 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504101 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | CLAMP PIPE SHOE - SP18 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504102 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504103 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.504 | Spool Fabrication | Field | Off Rack
1504104 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504105 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504106 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.166 | Spool Fabrication | Field | Off Rack
1504107 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504108 | Project A | Area_8 | DL | DL-XP01-8070 | ISO1018 | XP01 | CLAMP PIPE SHOE - SP18 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504109 | Project A | Area_8 | DL | DL-XP01-8070 | ISO1018 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.923 | Spool Fabrication | Field | Off Rack
1504110 | Project A | Area_8 | DL | DL-XP01-8070 | ISO1018 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504111 | Project A | Area_8 | DL | DL-XP01-8070 | ISO1018 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.378 | Spool Fabrication | Field | Off Rack
1504112 | Project A | Area_8 | DL | DL-XP01-8070 | ISO1018 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504113 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.254 | Spool Fabrication | Field | Off Rack
1504114 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504115 | Project A | Area_8 | DL | DL-XP01-8070 | ISO1018 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504116 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504117 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | CLAMP PIPE SHOE (SLOPED) - SP30-1-A-2" | 2 | EA | 1 | Stick Built | Field | Off Rack
1504118 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.519 | Spool Fabrication | Field | Off Rack
1504119 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.465 | Spool Fabrication | Field | Off Rack
1504120 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504121 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504122 | Project A | Area_8 | DL | DL-XP01-8070 | ISO1018 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504123 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504124 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504125 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504126 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.742 | Spool Fabrication | Field | Off Rack
1504127 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504128 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.911 | Spool Fabrication | Field | Off Rack
1504129 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504130 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.642 | Spool Fabrication | Field | Off Rack
1504131 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3075 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504132 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504133 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504134 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | CLAMP PIPE SHOE - SP18 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504135 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504136 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.565 | Spool Fabrication | Field | Off Rack
1504137 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504138 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504139 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504140 | Project A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504141 | Project A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | ZL01 | GLOBE VALVE, T-SHAPE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, GL-C02A | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504142 | Project A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504143 | Project A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504144 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.53 | Spool Fabrication | Field | Off Rack
1504145 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504146 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504147 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CH-C02C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504148 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | BALL VALVE, 2000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-H02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504149 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.815 | Spool Fabrication | Field | Off Rack
1504150 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.3 | Spool Fabrication | Field | Off Rack
1504151 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 2.051 | Spool Fabrication | Field | Off Rack
1504152 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504153 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504154 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504155 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.446 | Spool Fabrication | Field | Off Rack
1504156 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504157 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504158 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.306 | Spool Fabrication | Field | Off Rack
1504159 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504160 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504161 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.306 | Spool Fabrication | Field | Off Rack
1504162 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504163 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504164 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504165 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.256 | Spool Fabrication | Field | Off Rack
1504166 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.249 | Spool Fabrication | Field | Off Rack
1504167 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504168 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504169 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504170 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504171 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504172 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504173 | Project A | Area_8 | DL | DL-XP01-8003 | ISO3074 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504174 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504175 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504176 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504177 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504178 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504179 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504180 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504181 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504182 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504183 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504184 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 1.18 | Spool Fabrication | Field | Off Rack
1504185 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504186 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504187 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504188 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504189 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.45 | Spool Fabrication | Field | Off Rack
1504190 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504191 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.6 | Spool Fabrication | Field | Off Rack
1504192 | Project A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 3.279 | Spool Fabrication | Field | Off Rack
1504193 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.26 | Spool Fabrication | Field | Off Rack
1504194 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504195 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | TEE, RED, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504196 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | TEE, RED, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504197 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.245 | Spool Fabrication | Field | Off Rack
1504198 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.199 | Spool Fabrication | Field | Off Rack
1504199 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.238 | Spool Fabrication | Field | Off Rack
1504200 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.582 | Spool Fabrication | Field | Off Rack
1504201 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504202 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504203 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.26 | Spool Fabrication | Field | Off Rack
1504204 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504205 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504206 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504207 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 12x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504208 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504209 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504210 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504211 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.5 | Spool Fabrication | Field | Off Rack
1504212 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504213 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504214 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504215 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504216 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.7 | Spool Fabrication | Field | Off Rack
1504217 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504218 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504219 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504220 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504221 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | TEE, RED, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504222 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504223 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504224 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504225 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504226 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504227 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504228 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504229 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504230 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504231 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504232 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504233 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1504234 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504235 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504236 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504237 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504238 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504239 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504240 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504241 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504242 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504243 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504244 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504245 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504246 | Project A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504247 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504248 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504249 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504250 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504251 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504252 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504253 | Project A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504254 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504255 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504256 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504257 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504258 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504259 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504260 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504261 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504262 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504263 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504264 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504265 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504266 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504267 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504268 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504269 | Project A | Area_8 | DL | DL-XP01-8025 | ISO3088 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504270 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504271 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504272 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504273 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504274 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504275 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504276 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504277 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504278 | Project A | Area_8 | LG | LG-XP01-4017 | ISO3087 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504279 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504280 | Project A | Area_8 | LG | LG-XP01-4001 | ISO1014 | XP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504281 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504282 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504283 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504284 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504285 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504286 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504287 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504288 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504289 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1504290 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504291 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504292 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504293 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504294 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504295 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504296 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504297 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504298 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504299 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504300 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504301 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504302 | Project A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504303 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504304 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504305 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504306 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504307 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504308 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504309 | Project A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504310 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504311 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504312 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504313 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504314 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 6x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504315 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504316 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504317 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504318 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504319 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504320 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504321 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504322 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1504323 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504324 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504325 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504326 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504327 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504328 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504329 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504330 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504331 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504332 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504333 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504334 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504335 | Project A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504336 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504337 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504338 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504339 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504340 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504341 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504342 | Project A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504343 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504344 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504345 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504346 | Project A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504347 | Project A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.941 | Spool Fabrication | Field | Off Rack
1504348 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504349 | Project A | Area_9 | DL | DL-XP01-8056 | ISO2050 | XP01 | PIPE GUIDE - G4 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504350 | Project A | Area_9 | DL | DL-XP01-8056 | ISO2050 | XP01 | CLAMPED-ON ANCHOR - A17 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504351 | Project A | Area_9 | DL | DL-XP01-8054 | ISO2049 | XP01 | CLAMPED-ON ANCHOR - A17 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504352 | Project A | Area_9 | DL | DL-XP01-8054 | ISO2049 | XP01 | PIPE GUIDE - G4 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504353 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | PIPE SHOE - S1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504354 | Project A | Area_9 | DL | DL-XP01-8055 | ISO2007 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504355 | Project A | Area_9 | DL | DL-XP01-8055 | ISO2007 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504356 | Project A | Area_9 | DL | DL-XP01-8055 | ISO2007 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504357 | Project A | Area_9 | DL | DL-XP01-8055 | ISO2007 | XP01 | FLANGE, RED, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504358 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504359 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504360 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504361 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | CONTROL VALVE, GLOBE BODY, CL150, RF, (BY INSTRUMENTATION) | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504362 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | DIRECTIONAL ANCHOR - A20-SCH STD | 6 | EA | 1 | Stick Built | Field | Off Rack
1504363 | Project A | Area_9 | TR | TR-XP01-8096 | ISO4021 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504364 | Project A | Area_9 | TR | TR-XP01-8096 | ISO4021 | XP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504365 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | SWAGE, ECCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504366 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504367 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 0.779 | Spool Fabrication | Field | Off Rack
1504368 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504369 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 0.736 | Spool Fabrication | Field | Off Rack
1504370 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504371 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504372 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 0.718 | Spool Fabrication | Field | Off Rack
1504373 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 0.736 | Spool Fabrication | Field | Off Rack
1504374 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504375 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 0.208 | Spool Fabrication | Field | Off Rack
1504376 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504377 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 3.601 | Spool Fabrication | Field | Off Rack
1504378 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.847 | Spool Fabrication | Field | Off Rack
1504379 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504380 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504381 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504382 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504383 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | PIPE GUIDE - G5 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504384 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | DIRECTIONAL ANCHOR - A6 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504385 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504386 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504387 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504388 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504389 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | GUIDE FOR PIPE SHOE - G6 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504390 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504391 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | GUIDE FOR PIPE SHOE - G6 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504392 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504393 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504394 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504395 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504396 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504397 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504398 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504399 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504400 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504401 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504402 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504403 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.256 | Spool Fabrication | Field | Off Rack
1504404 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504405 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504406 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504407 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 0.106 | Spool Fabrication | Field | Off Rack
1504408 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH STDxSCH STD, ASTM A420 GR. WPL6, SMLS | 6x3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504409 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504410 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2002 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504411 | Project A | Area_9 | FL | FL-XP01-8118 | ISO1060 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504412 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 0.2 | Spool Fabrication | Field | Off Rack
1504413 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504414 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 6.567 | Spool Fabrication | Field | Off Rack
1504415 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504416 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504417 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504418 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504419 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 4.526 | Spool Fabrication | Field | Off Rack
1504420 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.244 | Spool Fabrication | Field | Off Rack
1504421 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504422 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504423 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 12.024 | Stick Built | Field | Off Rack
1504424 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504425 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504426 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 14.812 | Stick Built | Field | Off Rack
1504427 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504428 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504429 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 14.812 | Stick Built | Field | Off Rack
1504430 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504431 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504432 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 16.629 | Stick Built | Field | Off Rack
1504433 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504434 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504435 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2002 | XP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504436 | Project A | Area_9 | FL | FL-XP01-8118 | ISO1060 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504437 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504438 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504439 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504440 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 12.7mm THK, ASTM A516 GR. 70N | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504441 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504442 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | CHECK VALVE, WAFER, LONG PATTERN, CL150, RF LUG, ASTM A352 GR. LCC, CH-A02B | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504443 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504444 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.2 | Spool Fabrication | Field | Off Rack
1504445 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.444 | Spool Fabrication | Field | Off Rack
1504446 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504447 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504448 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504449 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.166 | Spool Fabrication | Field | Off Rack
1504450 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504451 | Project A | Area_9 | DL | DL-XP01-8054 | ISO2049 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504452 | Project A | Area_9 | DL | DL-XP01-8056 | ISO2050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504453 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504454 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH STD, ASTM A420 GR. WPL6, SMLS | 6x3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504455 | Project A | Area_9 | TR | TR-XP01-8096 | ISO4021 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504456 | Project A | Area_9 | DL | DL-XP01-8056 | ISO2050 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 2.069 | Spool Fabrication | Field | Off Rack
1504457 | Project A | Area_9 | DL | DL-XP01-8056 | ISO2050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504458 | Project A | Area_9 | DL | DL-XP01-8056 | ISO2050 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504459 | Project A | Area_9 | DL | DL-XP01-8054 | ISO2049 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 2.069 | Spool Fabrication | Field | Off Rack
1504460 | Project A | Area_9 | DL | DL-XP01-8054 | ISO2049 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504461 | Project A | Area_9 | DL | DL-XP01-8054 | ISO2049 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504462 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504463 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, SW, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1+1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504464 | Project A | Area_9 | FL | FL-XP01-8117 | ISO2003 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504465 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 6 | M | 4.847 | Spool Fabrication | Field | Off Rack
1504466 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504467 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504468 | Project A | Area_9 | FL | FL-XP01-8120 | ISO2034 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504469 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504470 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504471 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504472 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504473 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504474 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504475 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504476 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504477 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 3.021 | Spool Fabrication | Field | Off Rack
1504478 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 4.619 | Spool Fabrication | Field | Off Rack
1504479 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504480 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 2.619 | Spool Fabrication | Field | Off Rack
1504481 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504482 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504483 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504484 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 4.619 | Spool Fabrication | Field | Off Rack
1504485 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504486 | Project A | Area_9 | FL | FL-XP01-8118 | ISO2004 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 4.146 | Spool Fabrication | Field | Off Rack
1504487 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | CLAMP PIPE SHOE - S3 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504488 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 3 | M | 4.238 | Spool Fabrication | Field | Off Rack
1504489 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504490 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504491 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504492 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504493 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504494 | Project A | Area_9 | FL | FL-XP01-8119 | ISO1060 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504495 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | CLAMP PIPE SHOE - S3 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504496 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504497 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504498 | Project A | Area_9 | DL | DL-XP01-8082 | ISO2022 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 5.018 | Spool Fabrication | Field | Off Rack
1504499 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504500 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504501 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504502 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.765 | Spool Fabrication | Field | Off Rack
1504503 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504504 | Project A | Area_9 | DL | DL-XP01-8055 | ISO2007 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504505 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504506 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504507 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.842 | Spool Fabrication | Field | Off Rack
1504508 | Project A | Area_9 | DL | DL-XP01-8015 | ISO2007 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.381 | Spool Fabrication | Field | Off Rack
1504509 | Project A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.333 | Spool Fabrication | Field | Off Rack
1504510 | Project A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1504511 | Project A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1504512 | Project A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 35.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1504513 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504514 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504515 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504516 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504517 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504518 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | U-BOLT (ANCHOR) - A10 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504519 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504520 | Project A | Area_10 | TR | TR-ZL01-8108 | ISO4003 | ZL01 | DUMMY EXTENSION SUPPORT - D12 (MODIFIED DUMMY EXTENSION PIPE SIZE TO 12", L=310mm) | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504521 | Project A | Area_10 | TR | TR-ZL01-8108 | ISO4003 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504522 | Project A | Area_10 | TR | TR-ZL01-8112 | ISO4007 | ZL01 | DUMMY EXTENSION SUPPORT - D12 (MODIFIED DUMMY EXTENSION PIPE SIZE TO 12", L=310mm) | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504523 | Project A | Area_10 | TR | TR-ZL01-8112 | ISO4007 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504524 | Project A | Area_10 | TR | TR-ZL01-8110 | ISO4005 | ZL01 | DUMMY EXTENSION SUPPORT - D12 (MODIFIED DUMMY EXTENSION PIPE SIZE TO 12", L=310mm) | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504525 | Project A | Area_10 | TR | TR-ZL01-8110 | ISO4005 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504526 | Project A | Area_10 | TR | TR-ZL01-8106 | ISO3097 | ZL01 | DUMMY EXTENSION SUPPORT - D12 (MODIFIED DUMMY EXTENSION PIPE SIZE TO 12", L=310mm) | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504527 | Project A | Area_10 | TR | TR-ZL01-8106 | ISO3097 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504528 | Project A | Area_10 | TR | TR-ZL01-8104 | ISO3095 | ZL01 | DUMMY EXTENSION SUPPORT - D12 (MODIFIED DUMMY EXTENSION PIPE SIZE TO 12", L=310mm) | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504529 | Project A | Area_10 | TR | TR-ZL01-8104 | ISO3095 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504530 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1046 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 2.941 | Spool Fabrication | Field | Off Rack
1504531 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504532 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504533 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504534 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 8x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504535 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 0.734 | Spool Fabrication | Field | Off Rack
1504536 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 1.514 | Spool Fabrication | Field | Off Rack
1504537 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504538 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 2.902 | Spool Fabrication | Field | Off Rack
1504539 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH STDxSCH STD, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504540 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504541 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | GLOBE VALVE, T-SHAPE, CL150, RF, ASTM A352 GR. LCC, GL-A02A | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504542 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504543 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH STDxSCH STD, ASTM A420 GR. WPL6, SMLS | 8x6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504544 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 0.295 | Spool Fabrication | Field | Off Rack
1504545 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504546 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504547 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504548 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504549 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 2.759 | Spool Fabrication | Field | Off Rack
1504550 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504551 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02A | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504552 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504553 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504554 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.165 | Spool Fabrication | Field | Off Rack
1504555 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504556 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504557 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504558 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 9.7mm THK, ASTM A516 GR. 70N, CSA CERTIFIED TO Z662 AND RATED TO PN100 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504559 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 0.9 | Spool Fabrication | Field | Off Rack
1504560 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504561 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504562 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504563 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504564 | Project A | Area_10 | IA | IA-XP02-9001 | ISO3072 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504565 | Project A | Area_10 | IA | IA-XP02-9001 | ISO3072 | XP02 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 6.4mm THK, ASTM A516 GR. 70N | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504566 | Project A | Area_10 | IA | IA-XP02-9001 | ISO3072 | XP02 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02B | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504567 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504568 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504569 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | FLANGE, SW, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504570 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | FLANGE, SW, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504571 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504572 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504573 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504574 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | FLANGE, SW, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504575 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | FLANGE, SW, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504576 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504577 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504578 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I10F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504579 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504580 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504581 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504582 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | FLANGE, SW, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504583 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | FLANGE, SW, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504584 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504585 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504586 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | NIPPLE, ASME B36.10, 152.4 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504587 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504588 | Project A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | ZL02 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, BA-C10ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504589 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | U-BOLT (GUIDE) - G1 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504590 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504591 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504592 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504593 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504594 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | ZL01 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504595 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, BA-C10HT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504596 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504597 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504598 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PLE-TSE | 1x1/2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504599 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, RED, SW, HUBBED, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504600 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 8.85 | Spool Fabrication | Field | Off Rack
1504601 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504602 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504603 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.277 | Spool Fabrication | Field | Off Rack
1504604 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504605 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504606 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, BA-C10HT | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504607 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504608 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504609 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504610 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | M | 2.491 | Spool Fabrication | Field | Off Rack
1504611 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504612 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504613 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | TEE, STR, CSA Z245.11, BW, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504614 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | U-BOLT (ANCHOR) - A10 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504615 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | M | 0.454 | Spool Fabrication | Field | Off Rack
1504616 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504617 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 3 | M | 0.412 | Spool Fabrication | Field | Off Rack
1504618 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504619 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | TEE, RED, CSA Z245.11, BW, SCH STDxSCH XS, GR. 359 CAT II M45C, SMLS | 3x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504620 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 3 | M | 0.273 | Spool Fabrication | Field | Off Rack
1504621 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504622 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 3 | EA | 1 | Spool Fabrication | Field | Off Rack
1504623 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | PIPE GUIDE - G4 | 3 | EA | 1 | Stick Built | Field | Off Rack
1504624 | Project A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 3 | M | 1.106 | Spool Fabrication | Field | Off Rack
1504625 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504626 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504627 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504628 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504629 | Project A | Area_10 | TR | TR-ZL02-8115 | ISO4019 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504630 | Project A | Area_10 | TR | TR-ZL01-8114 | ISO4020 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504631 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504632 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504633 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504634 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504635 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504636 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504637 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504638 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | M | 5.324 | Spool Fabrication | Field | Off Rack
1504639 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504640 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | M | 0.192 | Spool Fabrication | Field | Off Rack
1504641 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504642 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | PIPE, CSA Z245.1, SCH XS, GR. 359 CAT II M45C, SMLS | 2 | M | 0.553 | Spool Fabrication | Field | Off Rack
1504643 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH 160, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504644 | Project A | Area_10 | TR | TR-ZL01-8102 | ISO2009 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504645 | Project A | Area_10 | IA | IA-XP02-9001 | ISO3072 | XP02 | U-BOLT (ANCHOR) - A10 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504646 | Project A | Area_10 | IA | IA-XP02-9007 | ISO3071 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504647 | Project A | Area_10 | IA | IA-XP02-9007 | ISO3071 | XP02 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504648 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | PIPE GUIDE - G4 | 10 | EA | 1 | Stick Built | Field | Off Rack
1504649 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 12 | EA | 1 | Stick Built | Field | Off Rack
1504650 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | BASE SUPPORT - BS1 (L= 500 mm) | 10 | EA | 1 | Stick Built | Field | Off Rack
1504651 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | CLAMP PIPE SHOE - S4L | 12 | EA | 1 | Stick Built | Field | Off Rack
1504652 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | DIRECTIONAL ANCHOR - A11 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504653 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 1.907 | Spool Fabrication | Field | Off Rack
1504654 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504655 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504656 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504657 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504658 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504659 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504660 | Project A | Area_10 | TR | TR-ZL01-8107 | ISO4002 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504661 | Project A | Area_10 | TR | TR-ZL01-8086 | ISO2039 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504662 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504663 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 6 | EA | 1 | Stick Built | Field | Off Rack
1504664 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504665 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504666 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1504667 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | DIRECTIONAL ANCHOR - A11 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504668 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | PIPE SHOE - S1L | 6 | EA | 1 | Stick Built | Field | Off Rack
1504669 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1504670 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1504671 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504672 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504673 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504674 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504675 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504676 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504677 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | DIRECTIONAL ANCHOR - A20-SCH XS | 6 | EA | 1 | Stick Built | Field | Off Rack
1504678 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | PIPE GUIDE - G4 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504679 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504680 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1504681 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504682 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504683 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1504684 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504685 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | DIRECTIONAL ANCHOR - A6 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504686 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | PIPE SHOE - S1L | 6 | EA | 1 | Stick Built | Field | Off Rack
1504687 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1504688 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504689 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | GUIDE FOR PIPE SHOE - G15 (TYPE A) | 6 | EA | 1 | Stick Built | Field | Off Rack
1504690 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504691 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1504692 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | PIPE GUIDE - G4 | 16 | EA | 1 | Stick Built | Field | Off Rack
1504693 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 16 | EA | 1 | Stick Built | Field | Off Rack
1504694 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504695 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504696 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504697 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504698 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504699 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504700 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504701 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | DIRECTIONAL ANCHOR - A21-SCH STD | 12 | EA | 1 | Stick Built | Field | Off Rack
1504702 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504703 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504704 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504705 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504706 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504707 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504708 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504709 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504710 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504711 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504712 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504713 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504714 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504715 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | DIRECTIONAL ANCHOR - A21-SCH 80 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504716 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504717 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1504718 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1504719 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE GUIDE - G4 | 8 | EA | 1 | Stick Built | Field | Off Rack
1504720 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | PIPE GUIDE - G4 | 12 | EA | 1 | Stick Built | Field | Off Rack
1504721 | Project A | Area_10 | TR | TR-ZL01-8111 | ISO4006 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504722 | Project A | Area_10 | TR | TR-ZL01-8106 | ISO4001 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504723 | Project A | Area_10 | TR | TR-ZL01-8109 | ISO4004 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504724 | Project A | Area_10 | TR | TR-ZL01-8105 | ISO3096 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504725 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504726 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.614 | Spool Fabrication | Field | Off Rack
1504727 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 4.68 | Spool Fabrication | Field | Off Rack
1504728 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504729 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 2.676 | Spool Fabrication | Field | Off Rack
1504730 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.867 | Spool Fabrication | Field | Off Rack
1504731 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.438 | Spool Fabrication | Field | Off Rack
1504732 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.719 | Spool Fabrication | Field | Off Rack
1504733 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.306 | Spool Fabrication | Field | Off Rack
1504734 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.894 | Spool Fabrication | Field | Off Rack
1504735 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504736 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504737 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 6.788 | Spool Fabrication | Field | Off Rack
1504738 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504739 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504740 | Project A | Area_10 | TR | TR-ZL01-8113 | ISO4018 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504741 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | U-BOLT (GUIDE) - G1 | 2 | EA | 1 | Stick Built | Field | Off Rack
1504742 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504743 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 2.322 | Spool Fabrication | Field | Off Rack
1504744 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504745 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.233 | Spool Fabrication | Field | Off Rack
1504746 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504747 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.247 | Spool Fabrication | Field | Off Rack
1504748 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.24 | Spool Fabrication | Field | Off Rack
1504749 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504750 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504751 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | U-BOLT (ANCHOR) - A10 | 1 | EA | 1 | Stick Built | Field | Off Rack
1504752 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.206 | Spool Fabrication | Field | Off Rack
1504753 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.199 | Spool Fabrication | Field | Off Rack
1504754 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | M | 2.7 | Spool Fabrication | Field | Off Rack
1504755 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | M | 2.701 | Spool Fabrication | Field | Off Rack
1504756 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | M | 1.662 | Spool Fabrication | Field | Off Rack
1504757 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504758 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504759 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504760 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504761 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | TEE, STR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504762 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | M | 0.856 | Spool Fabrication | Field | Off Rack
1504763 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | REDUCER, ECCENTRIC, CSA Z245.11, BW, SCH STDxSCH STD, GR. 359 CAT II M45C, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504764 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | TEE, STR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504765 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH XS, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504766 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504767 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 8x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504768 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | M | 0.45 | Spool Fabrication | Field | Off Rack
1504769 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504770 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504771 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504772 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.657 | Spool Fabrication | Field | Off Rack
1504773 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I10B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504774 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504775 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I10B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504776 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504777 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I10B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504778 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504779 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1504780 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504781 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504782 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I10F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504783 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | SWAGE, CONCENTRIC, MSS SP-95, SCH 160xSCH 160, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504784 | Project A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | ZL02 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504785 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504786 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XSxSCH XXS, ASTM A350 GR. LF2 CL. 1, BLE-PSE | 2x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504787 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504788 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504789 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504790 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504791 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | PIPE, ASME B36.10, SCH 160, ASTM A333 GR. 6, SMLS | 1 | M | 0.455 | Spool Fabrication | Field | Off Rack
1504792 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504793 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504794 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | SWAGE, CONCENTRIC, MSS SP-95, SCH XXSxSCH XXS, ASTM A350 GR. LF2 CL. 1, PBE | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504795 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504796 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | BALL VALVE, 3000 psi CWP, SW, ASTM A350 GR. LF2 CL. 1, BA-I02B | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504797 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504798 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504799 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504800 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | RELIEF VALVE, D ORIFICE, FNPT, (BY INSTRUMENTATION) | 1x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504801 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, POE-TOE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504802 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504803 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504804 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504805 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504806 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | BALL VALVE, 3000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-I02F | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504807 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504808 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | TEE, RED, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504809 | Project A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504810 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504811 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504812 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504813 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | TEE, STR, ASME B16.11, CL3000, SW, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504814 | Project A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504815 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504816 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504817 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504818 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1504819 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1504820 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504821 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.321 | Spool Fabrication | Field | Off Rack
1504822 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.657 | Spool Fabrication | Field | Off Rack
1504823 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504824 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CH-C02C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504825 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504826 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 41.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504827 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504828 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 41.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504829 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504830 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504831 | Project A | Area_10 | IA | IA-XP02-9001 | ISO3072 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.225 | Spool Fabrication | Field | Off Rack
1504832 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.165 | Spool Fabrication | Field | Off Rack
1504833 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.507 | Spool Fabrication | Field | Off Rack
1504834 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504835 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.959 | Spool Fabrication | Field | Off Rack
1504836 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.207 | Spool Fabrication | Field | Off Rack
1504837 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 2.043 | Spool Fabrication | Field | Off Rack
1504838 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504839 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504840 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504841 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.871 | Spool Fabrication | Field | Off Rack
1504842 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.519 | Spool Fabrication | Field | Off Rack
1504843 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504844 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 4.182 | Spool Fabrication | Field | Off Rack
1504845 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504846 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504847 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | BALL VALVE, 2000 psi CWP, FTE, ASTM A350 GR. LF2 CL. 1, BA-H02D | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504848 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, TBE | 3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504849 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | THREADOLET, MSS SP-97, CL3000, IRExFTE, ASTM A350 GR. LF2 CL. 1 | 2x3/4 | EA | 1 | Spool Fabrication | Field | Off Rack
1504850 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 1.096 | Spool Fabrication | Field | Off Rack
1504851 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504852 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504853 | Project A | Area_10 | IA | IA-XP02-9009 | ISO3092 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504854 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504855 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504856 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 5.415 | Spool Fabrication | Field | Off Rack
1504857 | Project A | Area_10 | IA | IA-XP02-9008 | ISO2058 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504858 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504859 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504860 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504861 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504862 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504863 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504864 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504865 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504866 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | CHECK VALVE, DOUBLE-FLANGED, CL150, RF, ASTM A352 GR. LCC, CH-A02C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504867 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504868 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.45 | Spool Fabrication | Field | Off Rack
1504869 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504870 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.327 | Spool Fabrication | Field | Off Rack
1504871 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504872 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | CHECK VALVE, DOUBLE-FLANGED, CL150, RF, ASTM A352 GR. LCC, CH-A02C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504873 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504874 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504875 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CH-C02C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504876 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504877 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | CHECK VALVE, DOUBLE-FLANGED, CL600, RF, ASTM A352 GR. LCC, CH-C02C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504878 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504879 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 8.124 | Spool Fabrication | Field | Off Rack
1504880 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | TEE, RED, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 16x12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504881 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504882 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504883 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504884 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504885 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504886 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.2 | Spool Fabrication | Field | Off Rack
1504887 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | BALL VALVE, LONG PATTERN, CL300, RF, ASTM A352 GR. LCC, BA-B02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504888 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504889 | Project A | Area_10 | GH | GH-YP01-3004 | ISO3093 | YP01 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504890 | Project A | Area_10 | BD | BD-XP01-6002 | ISO3094 | XP01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 0.14 | Spool Fabrication | Field | Off Rack
1504891 | Project A | Area_10 | BD | BD-XP01-6002 | ISO3094 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504892 | Project A | Area_10 | BD | BD-XP01-6002 | ISO3094 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504893 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504894 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | WELDOLET, MSS SP-97, IRExBE, SCH STDxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504895 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 10x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504896 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504897 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504898 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504899 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 1.523 | Spool Fabrication | Field | Off Rack
1504900 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504901 | Project A | Area_10 | IA | IA-XP02-9001 | ISO3072 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504902 | Project A | Area_10 | IA | IA-XP02-9001 | ISO3072 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 3.625 | Spool Fabrication | Field | Off Rack
1504903 | Project A | Area_10 | IA | IA-XP02-9001 | ISO3072 | XP02 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504904 | Project A | Area_10 | IA | IA-XP02-9007 | ISO3071 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504905 | Project A | Area_10 | IA | IA-XP02-9007 | ISO3071 | XP02 | TEE, STR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504906 | Project A | Area_10 | IA | IA-XP02-9007 | ISO3071 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 5.125 | Spool Fabrication | Field | Off Rack
1504907 | Project A | Area_10 | IA | IA-XP02-9007 | ISO3071 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504908 | Project A | Area_10 | IA | IA-XP02-9007 | ISO3071 | XP02 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 2 | M | 6.607 | Spool Fabrication | Field | Off Rack
1504909 | Project A | Area_10 | IA | IA-XP02-9007 | ISO3071 | XP02 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504910 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504911 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 15.742 | Stick Built | Field | Off Rack
1504912 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504913 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504914 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 11.742 | Spool Fabrication | Field | Off Rack
1504915 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504916 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504917 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 5.366 | Spool Fabrication | Field | Off Rack
1504918 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.453 | Spool Fabrication | Field | Off Rack
1504919 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504920 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504921 | Project A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.137 | Spool Fabrication | Field | Off Rack
1504922 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PLUG, HEX HEAD, ASME B16.11, MTE, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504923 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | BALL VALVE, 2000 psi CWP, FSWxFTE, ASTM A350 GR. LF2 CL. 1, BA-H02E | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504924 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504925 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 12x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1504926 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504927 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504928 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 8 | M | 0.435 | Spool Fabrication | Field | Off Rack
1504929 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504930 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504931 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.446 | Spool Fabrication | Field | Off Rack
1504932 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | TEE, RED, ASME B16.9, BW, SCH STDxSCH STD, ASTM A420 GR. WPL6, SMLS | 12x8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504933 | Project A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504934 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504935 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504936 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504937 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 1.043 | Spool Fabrication | Field | Off Rack
1504938 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504939 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504940 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 11.271 | Spool Fabrication | Field | Off Rack
1504941 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504942 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504943 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504944 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 7.749 | Spool Fabrication | Field | Off Rack
1504945 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504946 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 1.809 | Spool Fabrication | Field | Off Rack
1504947 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504948 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504949 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504950 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 1.694 | Spool Fabrication | Field | Off Rack
1504951 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504952 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.435 | Spool Fabrication | Field | Off Rack
1504953 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504954 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504955 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504956 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504957 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02MT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504958 | Project A | Area_10 | LG | LG-XP01-4013 | ISO1050 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 19.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504959 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504960 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.4 | Spool Fabrication | Field | Off Rack
1504961 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504962 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, BLIND, ASME B16.5, CL150, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504963 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02GT | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504964 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1504965 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.722 | Spool Fabrication | Field | Off Rack
1504966 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | BALL VALVE, LONG PATTERN, CL150, RF, ASTM A352 GR. LCC, BA-A02MT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504967 | Project A | Area_10 | LG | LG-XP01-4010 | ISO2029 | XP01 | SPECTACLE BLIND, ASME B16.48, CL150, RF, 19.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504968 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504969 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | TEE, STR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504970 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504971 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504972 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504973 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 16.021 | Stick Built | Field | Off Rack
1504974 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 10.479 | Spool Fabrication | Field | Off Rack
1504975 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504976 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | FLANGE, WN, ASME B16.5, CL150, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504977 | Project A | Area_10 | LG | LG-XP01-4001 | ISO1015 | XP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504978 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504979 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.941 | Spool Fabrication | Field | Off Rack
1504980 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504981 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.453 | Spool Fabrication | Field | Off Rack
1504982 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 4.306 | Spool Fabrication | Field | Off Rack
1504983 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 11.742 | Spool Fabrication | Field | Off Rack
1504984 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 15.742 | Stick Built | Field | Off Rack
1504985 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504986 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504987 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504988 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504989 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504990 | Project A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504991 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 15.742 | Stick Built | Field | Off Rack
1504992 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 17.742 | Stick Built | Field | Off Rack
1504993 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 5.245 | Spool Fabrication | Field | Off Rack
1504994 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1504995 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504996 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1504997 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1504998 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1504999 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1505000 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 15.742 | Stick Built | Field | Off Rack
1505001 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1505002 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1505003 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1505004 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 17.742 | Stick Built | Field | Off Rack
1505005 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1505006 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 4.418 | Spool Fabrication | Field | Off Rack
1505007 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505008 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505009 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505010 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505011 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505012 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505013 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505014 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505015 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505016 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505017 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.453 | Spool Fabrication | Field | Off Rack
1505018 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | CLAMP PIPE SHOE - S3 | 6 | EA | 1 | Stick Built | Field | Off Rack
1505019 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505020 | Project A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 1.537 | Spool Fabrication | Field | Off Rack
1505021 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505022 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505023 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.453 | Spool Fabrication | Field | Off Rack
1505024 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH XS, ASTM A420 GR. WPL6, SMLS | 6 | EA | 1 | Spool Fabrication | Field | Off Rack
1505025 | Project A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | ZL01 | PIPE, ASME B36.10, SCH XS, ASTM A333 GR. 6, SMLS | 6 | M | 0.741 | Spool Fabrication | Field | Off Rack
1505026 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.43 | Spool Fabrication | Field | Off Rack
1505027 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505028 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505029 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | FLANGE, WN, ASME B16.5, CL300, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505030 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.84 | Spool Fabrication | Field | Off Rack
1505031 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505032 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH STD, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505033 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | PIPE, ASME B36.10, SCH STD, ASTM A333 GR. 6, SMLS | 12 | M | 0.416 | Spool Fabrication | Field | Off Rack
1505034 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505035 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | SPECTACLE BLIND, ASME B16.48, CL600, RF, 41.1mm THK, ASTM A516 GR. 70N, IMPACT TEST TO M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505036 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505037 | Project A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | YP01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH STD, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505038 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505039 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505040 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505041 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505042 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.894 | Spool Fabrication | Field | Off Rack
1505043 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505044 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505045 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505046 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505047 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505048 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 12x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505049 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 3.403 | Spool Fabrication | Field | Off Rack
1505050 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | REDUCER, CONCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 16x12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505051 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505052 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505053 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505054 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505055 | Project A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505056 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505057 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505058 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505059 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505060 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1505061 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.687 | Spool Fabrication | Field | Off Rack
1505062 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1505063 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 2.074 | Spool Fabrication | Field | Off Rack
1505064 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505065 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505066 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505067 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 17.002 | Stick Built | Field | Off Rack
1505068 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505069 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505070 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505071 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505072 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 17.009 | Stick Built | Field | Off Rack
1505073 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505074 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505075 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505076 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505077 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 12x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505078 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 3.43 | Spool Fabrication | Field | Off Rack
1505079 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505080 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.155 | Spool Fabrication | Field | Off Rack
1505081 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505082 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505083 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505084 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 15.664 | Stick Built | Field | Off Rack
1505085 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505086 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505087 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505088 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.524 | Spool Fabrication | Field | Off Rack
1505089 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505090 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505091 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505092 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505093 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 4.188 | Spool Fabrication | Field | Off Rack
1505094 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505095 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.447 | Spool Fabrication | Field | Off Rack
1505096 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505097 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 6.804 | Spool Fabrication | Field | Off Rack
1505098 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1505099 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1505100 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505101 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | REDUCER, ECCENTRIC, ASME B16.9, BW, SCH 80xSCH 80, ASTM A420 GR. WPL6, SMLS | 12x10 | EA | 1 | Spool Fabrication | Field | Off Rack
1505102 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 10 | M | 0.577 | Spool Fabrication | Field | Off Rack
1505103 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1505104 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1505105 | Project A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 10 | EA | 1 | Spool Fabrication | Field | Off Rack
1505106 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505107 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505108 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505109 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505110 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505111 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505112 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | M | 1.77 | Spool Fabrication | Field | Off Rack
1505113 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, BLIND, CSA Z245.12, PN100, RF, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505114 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, BA-C10ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505115 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH XS, GR. 359 CAT II M45C | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505116 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | WELDOLET, MSS SP-97, IRExBE, SCH XSxSCH XS, ASTM A350 GR. LF2 CL. 1 | 12x2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505117 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1505118 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1505119 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | M | 6.532 | Spool Fabrication | Field | Off Rack
1505120 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505121 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, CERTIFIED TO CSA Z245.15 PN100, CAT II M45C, BA-C10M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505122 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, SW, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505123 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH 160, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505124 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | SOCKOLET, MSS SP-97, CL3000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 12x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505125 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505126 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | M | 9.112 | Spool Fabrication | Field | Off Rack
1505127 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505128 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505129 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505130 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505131 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.3 | Spool Fabrication | Field | Off Rack
1505132 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505133 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505134 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 4.6 | Spool Fabrication | Field | Off Rack
1505135 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 2.382 | Spool Fabrication | Field | Off Rack
1505136 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505137 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505138 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | M | 8.022 | Spool Fabrication | Field | Off Rack
1505139 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | ELBOW, 90 DEG, LR, CSA Z245.11, BW, SCH STD, GR. 359 CAT II M45C, SMLS | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1505140 | Project A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 8 | EA | 1 | Spool Fabrication | Field | Off Rack
1505141 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | PIPE, CSA Z245.1, SCH STD, GR. 359 CAT II M45C, SMLS | 12 | M | 1.117 | Spool Fabrication | Field | Off Rack
1505142 | Project A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | ZL02 | FLANGE, WN, CSA Z245.12, PN100, RF, SCH STD, GR. 359 CAT II M45C | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505143 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.6 | Spool Fabrication | Field | Off Rack
1505144 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505145 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505146 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505147 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505148 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505149 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 12x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505150 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505151 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.812 | Spool Fabrication | Field | Off Rack
1505152 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505153 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505154 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 2.021 | Spool Fabrication | Field | Off Rack
1505155 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 16.949 | Stick Built | Field | Off Rack
1505156 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.827 | Spool Fabrication | Field | Off Rack
1505157 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505158 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505159 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505160 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505161 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505162 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.676 | Spool Fabrication | Field | Off Rack
1505163 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | ELBOW, 45 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505164 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 13.661 | Stick Built | Field | Off Rack
1505165 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 7.224 | Spool Fabrication | Field | Off Rack
1505166 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 1.077 | Spool Fabrication | Field | Off Rack
1505167 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02M | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505168 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, SW, ASME B16.5, CL600, RF, SCH 160, ASTM A350 GR. LF2 CL. 1 | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505169 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | NIPPLE, ASME B36.10, 101.6 mm LG, SCH XXS, ASTM A333 GR. 6, SMLS, PBE | 1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505170 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | SOCKOLET, MSS SP-97, CL6000, IRExSW, ASTM A350 GR. LF2 CL. 1 | 12x1 | EA | 1 | Spool Fabrication | Field | Off Rack
1505171 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505172 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505173 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505174 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505175 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505176 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505177 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505178 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505179 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, BLIND, ASME B16.5, CL600, RF, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505180 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02ET | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505181 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH XS, ASTM A350 GR. LF2 CL. 1 | 2 | EA | 1 | Spool Fabrication | Field | Off Rack
1505182 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 9.078 | Spool Fabrication | Field | Off Rack
1505183 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505184 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505185 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 12 | M | 0.5 | Spool Fabrication | Field | Off Rack
1505186 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505187 | Project A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505188 | Project A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | ZL01 | TEE, STR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505189 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505190 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505191 | Project A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | ZL01 | BALL VALVE, LONG PATTERN, CL600, RF, ASTM A352 GR. LCC, BA-C02KT | 12 | EA | 1 | Spool Fabrication | Field | Off Rack
1505192 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 6.025 | Spool Fabrication | Field | Off Rack
1505193 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1505194 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | ELBOW, 90 DEG, LR, ASME B16.9, BW, SCH 80, ASTM A420 GR. WPL6, SMLS | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
1505195 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | PIPE, ASME B36.10, SCH 80, ASTM A333 GR. 6, SMLS | 16 | M | 0.624 | Spool Fabrication | Field | Off Rack
1505196 | Project A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | ZL01 | FLANGE, WN, ASME B16.5, CL600, RF, SCH 80, ASTM A350 GR. LF2 CL. 1 | 16 | EA | 1 | Spool Fabrication | Field | Off Rack
Piping Labor - MTO Input Required (Let us know if you need us to prepare MTOs from your 3D Model or Drawings)
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## MTO Input Pipe Class
Pipe Class | X-Ray | PWHT
ZL01 | 0.15 | 0
XP01 | 1 | 0
YP01 | 1 | 0
XP02 | 1 | 0
ZL02 | 0.15 | 0
Pipe Class info. for X-Ray and PWHT Requirements
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## LF & Wage Rate Input
WBS2 | Location | PF | Wage Rate
Area_1 | Spool Fabrication | 1 | 110
Area_1 | Module | 1 | 110
Area_1 | Field | 0.75 | 78
Area_2 | Spool Fabrication | 1 | 110
Area_2 | Module | 1 | 110
Area_2 | Field | 0.75 | 78
Area_3 | Spool Fabrication | 1 | 110
Area_3 | Module | 1 | 110
Area_3 | Field | 0.75 | 78
Area_4 | Spool Fabrication | 1 | 110
Area_4 | Module | 1 | 110
Area_4 | Field | 0.75 | 78
Area_5 | Spool Fabrication | 1 | 110
Area_5 | Module | 1 | 110
Area_5 | Field | 0.75 | 78
Area_6 | Spool Fabrication | 1 | 110
Area_6 | Module | 1 | 110
Area_6 | Field | 0.75 | 78
Area_7 | Spool Fabrication | 1 | 110
Area_7 | Module | 1 | 110
Area_7 | Field | 0.75 | 78
Area_8 | Spool Fabrication | 1 | 110
Area_8 | Module | 1 | 110
Area_8 | Field | 0.75 | 78
Area_9 | Spool Fabrication | 1 | 110
Area_9 | Module | 1 | 110
Area_9 | Field | 0.75 | 78
Area_10 | Spool Fabrication | 1 | 110
Area_10 | Module | 1 | 110
Area_10 | Field | 0.75 | 78
Productivity/Location Factor and Wage Rate Basis:
* Productivity/Location Factors used in this Example Imaginary Project reflect adjustment from typical US Gulf Coast Oil & Gas/Refinery projects based USGC Hours to the simple project with open access and single level rack and small contractor adjustment
* See page "Piping Labor FAQs" on EstiResource website for project complexity and project size considerations in setting the productivity/location factor
Indicative Productivity/Location Factor for the project need to be provided by the project construction team, by Area if necessary, which can be refined during/after review of the first pass estimate
Wage Rate for Module Labor is to be provided by the project team as an all-inclusive rate (supervision, plant & equipment and overheads included) to be applied to the module craft labor hours as applicable in the proposed location for module contract
Wage Rate for Field Labor is to be provided by the project team based on the proposed execution strategy, either as all-in rate or as direct field labor rate if Indirect field costs and supervision will be included separately
Piping Productivity/Location Factor and Wage Rate Input Required
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## Field Construction Plan
Field Construction | Book Ends for Planning |  |  |  | Calculated Finsh Date and Duration based on the Detail Planning
Construction Plan | Start | Finish | Duration (Days) | Total Field Hours | Start | Calculated Finish | Calculated Days | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9
Field | 2026-06-01 | 2026-09-19 | 110 | 6356 | 2026-06-01 | 2026-09-13 | 104
from the detail planning table below
Proposed Work-Week Cycle: 5 days x 10 hrs/day + 2 days off (50 hour work-week)
Effective hours per calendar day (adjusted for off days): =50/7 = 7.143 per worker
Field Construction Planning Basis
Field Construction Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Planned piping crew size | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Planned work hours/day | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Planned work-week cycle | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off
Work days/week | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Total crew hrs/calendar day | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429
Use for planning purposes | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55
Choose different crew size and/or work week basis for any intermedite periods to allow for either pause of construction or reduced activity level due to seasonal weather or any other constraints; change the planned crew hours per calendar day in the detail planning to firm up the detail construction plan
Detail Construction Planning based on Estimated Field Hours by IWP
IWP Number | Estimated Hours | Planned crew hrs/Calendar Day | Work Days | Start | Finish | ROS (one week prior to start) | Construction Week No.
IWP_1001 | 135.821 | 55 | 2.4695 | 2026-06-01 | 2026-06-03 | 2026-05-25 | 1
IWP_1002 | 157.9477 | 55 | 2.8718 | 2026-06-03 | 2026-06-06 | 2026-05-27 | 1
IWP_1003 | 153.2969 | 55 | 2.7872 | 2026-06-06 | 2026-06-09 | 2026-05-30 | 2
IWP_1004 | 129.0734 | 55 | 2.3468 | 2026-06-09 | 2026-06-11 | 2026-06-02 | 2
IWP_1005 | 166.901 | 55 | 3.0346 | 2026-06-11 | 2026-06-14 | 2026-06-04 | 2
IWP_1006 | 186.6993 | 55 | 3.3945 | 2026-06-14 | 2026-06-17 | 2026-06-07 | 3
IWP_1007 | 148.8561 | 55 | 2.7065 | 2026-06-17 | 2026-06-20 | 2026-06-10 | 3
IWP_1008 | 154.7317 | 55 | 2.8133 | 2026-06-20 | 2026-06-23 | 2026-06-13 | 4
IWP_1009 | 167.474 | 55 | 3.045 | 2026-06-23 | 2026-06-26 | 2026-06-16 | 4
IWP_1010 | 144.8768 | 55 | 2.6341 | 2026-06-26 | 2026-06-29 | 2026-06-19 | 5
IWP_1011 | 131.2404 | 55 | 2.3862 | 2026-06-29 | 2026-07-01 | 2026-06-22 | 5
IWP_1012 | 200.1699 | 55 | 3.6395 | 2026-07-01 | 2026-07-05 | 2026-06-24 | 5
IWP_1013 | 156.4832 | 55 | 2.8451 | 2026-07-05 | 2026-07-08 | 2026-06-28 | 6
IWP_1014 | 135.5586 | 55 | 2.4647 | 2026-07-08 | 2026-07-10 | 2026-07-01 | 6
IWP_1015 | 266.6913 | 55 | 4.8489 | 2026-07-10 | 2026-07-15 | 2026-07-03 | 7
IWP_1016 | 146.5696 | 55 | 2.6649 | 2026-07-15 | 2026-07-18 | 2026-07-08 | 7
IWP_1017 | 130.3771 | 55 | 2.3705 | 2026-07-18 | 2026-07-20 | 2026-07-11 | 8
IWP_1018 | 41.6124 | 55 | 0.75659 | 2026-07-20 | 2026-07-21 | 2026-07-13 | 8
IWP_1021 | 8.5166 | 55 | 0.15485 | 2026-07-21 | 2026-07-21 | 2026-07-14 | 8
IWP_1022 | 17.0332 | 55 | 0.3097 | 2026-07-21 | 2026-07-21 | 2026-07-14 | 8
IWP_1023 | 8.5166 | 55 | 0.15485 | 2026-07-21 | 2026-07-21 | 2026-07-14 | 8
IWP_1024 | 59.8898 | 55 | 1.0889 | 2026-07-21 | 2026-07-22 | 2026-07-14 | 8
IWP_1025 | 124.6754 | 55 | 2.2668 | 2026-07-22 | 2026-07-24 | 2026-07-15 | 8
IWP_1026 | 219.275 | 55 | 3.9868 | 2026-07-24 | 2026-07-28 | 2026-07-17 | 9
IWP_1027 | 30.5858 | 55 | 0.5561 | 2026-07-28 | 2026-07-29 | 2026-07-21 | 9
IWP_1028 | 30.2591 | 55 | 0.55017 | 2026-07-29 | 2026-07-30 | 2026-07-22 | 9
IWP_1029 | 23.4478 | 55 | 0.42632 | 2026-07-30 | 2026-07-30 | 2026-07-23 | 9
IWP_1031 | 30.2591 | 55 | 0.55017 | 2026-07-30 | 2026-07-31 | 2026-07-23 | 9
IWP_1033 | 8.7399 | 55 | 0.15891 | 2026-07-31 | 2026-07-31 | 2026-07-24 | 9
IWP_1034 | 127.8249 | 55 | 2.3241 | 2026-07-31 | 2026-08-02 | 2026-07-24 | 9
IWP_1035 | 105.0494 | 55 | 1.91 | 2026-08-02 | 2026-08-04 | 2026-07-26 | 10
IWP_1036 | 191.117 | 55 | 3.4749 | 2026-08-04 | 2026-08-07 | 2026-07-28 | 10
IWP_1037 | 203.4775 | 55 | 3.6996 | 2026-08-07 | 2026-08-11 | 2026-07-31 | 11
IWP_1038 | 149.7649 | 55 | 2.723 | 2026-08-11 | 2026-08-14 | 2026-08-04 | 11
IWP_1039 | 157.6856 | 55 | 2.867 | 2026-08-14 | 2026-08-17 | 2026-08-07 | 12
IWP_1040 | 217.5791 | 55 | 3.956 | 2026-08-17 | 2026-08-21 | 2026-08-10 | 12
IWP_1041 | 175.1531 | 55 | 3.1846 | 2026-08-21 | 2026-08-24 | 2026-08-14 | 13
IWP_1042 | 160.2726 | 55 | 2.914 | 2026-08-24 | 2026-08-27 | 2026-08-17 | 13
IWP_1043 | 150.1482 | 55 | 2.73 | 2026-08-27 | 2026-08-30 | 2026-08-20 | 13
IWP_1044 | 134.0916 | 55 | 2.438 | 2026-08-30 | 2026-09-01 | 2026-08-23 | 14
IWP_1045 | 138.6931 | 55 | 2.5217 | 2026-09-01 | 2026-09-04 | 2026-08-25 | 14
IWP_1046 | 145.5317 | 55 | 2.646 | 2026-09-04 | 2026-09-07 | 2026-08-28 | 15
IWP_1047 | 150.8307 | 55 | 2.7424 | 2026-09-07 | 2026-09-10 | 2026-08-31 | 15
IWP_1048 | 178.7223 | 55 | 3.2495 | 2026-09-10 | 2026-09-13 | 2026-09-03 | 15
IWP_9999 | 654.4513 | 55 | 11.8991 | 2026-09-13 | 2026-09-13 | Various man-hr allowances
Total Field Hours | 6355.9718
Formulas:
Start = INT(Table2[[#This Row],[Total Field Hours]]+Table2[[#This Row],[Duration (Days)]]+0.5)
Start = Table2[[#This Row],[Total Field Hours]]
Finish = Table2[[#This Row],[Start]]+Table2[[#This Row],[Duration (Days)]]
Calculated Finish = Table2[[#This Row],[Total Field Hours]]-7
Total Field Hours = [Start, row above]
Field Construction Planning & Scheduling by Installation Work Package (IWP) - Input Required
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## Module Construction Plan
Module Construction | Book Ends for Planning |  |  |  | Calculated Finsh Date and Duration based on the Detail Planning
Construction Plan | Start | Finish | Duration (Days) | Total Module Hours | Start | Calculated Finish | Calculated Days | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9
Module | 2026-02-11 | 2026-05-07 | 85 | 4973 | 2026-02-11 | 2026-05-05 | 83
from the detail planning table below
Proposed Work-Week Cycle: 5 days x 10 hrs/day + 2 days off (50 hour work-week)
Effective hours per calendar day (adjusted for off days): =50/7 = 7.143 per worker
Module Construction Planning Basis | bar: Column1 to Column6
Module Construction Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Planned piping crew size | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Planned work hours/day | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Planned work-week cycle | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off
Work days/week | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Total crew hrs/calendar day | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 57.1429
Use for planning purposes | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55
Choose different crew size and/or work week basis for any intermedite periods to allow for either pause of module construction or reduced activity level due to any other constraints; change the planned crew hours per calendar day in the detail planning to firm up the detail module construction plan
Detail Module Construction Planning based on Estimated Module Hours by IWP
IWP Number | Estimated Hours | Planned crew hrs/Calendar Day | Work Days | Start | Finish |  | Construction Week No.
IWP_1017 | 12.807 | 55 | 0.23285 | 2026-02-11 | 2026-02-11 |  | 1
IWP_1019 | 375.7124 | 55 | 6.8311 | 2026-02-11 | 2026-02-18 |  | 2
IWP_1020 | 162.0981 | 55 | 2.9472 | 2026-02-18 | 2026-02-21 |  | 2
IWP_1021 | 218.6792 | 55 | 3.976 | 2026-02-21 | 2026-02-25 |  | 3
IWP_1022 | 376.7569 | 55 | 6.8501 | 2026-02-25 | 2026-03-04 |  | 4
IWP_1023 | 290.1029 | 55 | 5.2746 | 2026-03-04 | 2026-03-09 |  | 4
IWP_1024 | 107.0689 | 55 | 1.9467 | 2026-03-09 | 2026-03-11 |  | 5
IWP_1027 | 632.0143 | 55 | 11.4912 | 2026-03-11 | 2026-03-22 |  | 6
IWP_1028 | 626.5069 | 55 | 11.391 | 2026-03-22 | 2026-04-02 |  | 8
IWP_1029 | 459.77 | 55 | 8.3595 | 2026-04-02 | 2026-04-10 |  | 9
IWP_1030 | 357.6198 | 55 | 6.5022 | 2026-04-10 | 2026-04-17 |  | 10
IWP_1031 | 483.6424 | 55 | 8.7935 | 2026-04-17 | 2026-04-26 |  | 11
IWP_1032 | 219.0684 | 55 | 3.9831 | 2026-04-26 | 2026-04-30 |  | 12
IWP_1033 | 266.7337 | 55 | 4.8497 | 2026-04-30 | 2026-05-05 |  | 12
IWP_1034 | 15.5338 | 55 | 0.28243 | 2026-05-05 | 2026-05-05 |  | 12
IWP_9999 | 368.3604 | 55 | 6.6975 | 2026-05-05 | 2026-05-05 | Various man-hr allowances
Total Module Hours | 4972.4752
Formulas:
Start = INT(Table26[[#This Row],[Total Module Hours]]+Table26[[#This Row],[Duration (Days)]]+0.5)
Start = Table26[[#This Row],[Total Module Hours]]
Finish = Table26[[#This Row],[Start]]+Table26[[#This Row],[Duration (Days)]]
Total Module Hours = [Start, row above]
Module Construction Planning & Scheduling by Installation Work Package (IWP) - Input Required
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## Spool Fabrication Plan
Spool Fabrication | Book Ends for Planning |  |  |  | Calculated Finsh Date and Duration based on the Detail Planning
Construction Plan | Start | Finish | Duration (Days) | Total Field Hours | Start | Calculated Finish | Calculated Days | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column82 | Column83 | Column84 | Column85 | Column9
Field | 2026-01-02 | 2026-05-22 | 140 | 20243 | 2026-01-02 | 2026-05-19 | 137
from the detail planning table below
Proposed Work-Week Cycle: 5 days x 10 hrs/day + 2 days off (50 hour work-week)
Effective hours per calendar day (adjusted for off days): =50/7 = 7.143 per worker
Spool Fabrication Planning Basis
Spool Fabrication Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Planned piping crew size | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Planned work hours/day | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Planned work-week cycle | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off | 5 days on 2 days off
Work days/week | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Total crew hrs/calendar day | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571
Use for planning purposes | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
Choose different crew size and/or work week basis for any intermedite periods to allow for either acceleration or pause of construction or reduced activity level due to any other constraints; change the planned crew hours per calendar day in the detail planning to firm up the detail spool fabrication plan
Detail Construction Planning based on Estimated Spool Fabrication Hours by IWP
IWP Number | Estimated Hours | Planned crew hrs/Calendar Day | Work Days | Start | Finish |  | Construction Week No.
IWP_1001 | 281.4448 | 140 | 2.0103 | 2026-01-02 | 2026-01-04 |  | 1
IWP_1002 | 337.0758 | 140 | 2.4077 | 2026-01-04 | 2026-01-06 |  | 1
IWP_1003 | 262.8362 | 140 | 1.8774 | 2026-01-06 | 2026-01-08 |  | 1
IWP_1004 | 83.3195 | 140 | 0.59514 | 2026-01-08 | 2026-01-09 |  | 2
IWP_1005 | 281.5136 | 140 | 2.0108 | 2026-01-09 | 2026-01-11 |  | 2
IWP_1006 | 181.2608 | 140 | 1.2947 | 2026-01-11 | 2026-01-12 |  | 2
IWP_1007 | 349.0276 | 140 | 2.4931 | 2026-01-12 | 2026-01-14 |  | 2
IWP_1008 | 417.7505 | 140 | 2.9839 | 2026-01-14 | 2026-01-17 |  | 3
IWP_1009 | 355.7333 | 140 | 2.541 | 2026-01-17 | 2026-01-20 |  | 3
IWP_1010 | 102.0495 | 140 | 0.72892 | 2026-01-20 | 2026-01-21 |  | 3
IWP_1011 | 108.7474 | 140 | 0.77677 | 2026-01-21 | 2026-01-22 |  | 3
IWP_1012 | 393.6031 | 140 | 2.8115 | 2026-01-22 | 2026-01-25 |  | 4
IWP_1013 | 208.2202 | 140 | 1.4873 | 2026-01-25 | 2026-01-26 |  | 4
IWP_1014 | 209.8822 | 140 | 1.4992 | 2026-01-26 | 2026-01-27 |  | 4
IWP_1015 | 350.8418 | 140 | 2.506 | 2026-01-27 | 2026-01-30 |  | 5
IWP_1016 | 102.1352 | 140 | 0.72954 | 2026-01-30 | 2026-01-31 |  | 5
IWP_1017 | 435.009 | 140 | 3.1072 | 2026-01-31 | 2026-02-03 |  | 5
IWP_1018 | 92.1534 | 140 | 0.65824 | 2026-02-03 | 2026-02-04 |  | 5
IWP_1019 | 817.2897 | 140 | 5.8378 | 2026-02-04 | 2026-02-10 |  | 6
IWP_1020 | 264.1045 | 140 | 1.8865 | 2026-02-10 | 2026-02-12 |  | 6
IWP_1021 | 190.6436 | 140 | 1.3617 | 2026-02-12 | 2026-02-13 |  | 7
IWP_1022 | 304.8231 | 140 | 2.1773 | 2026-02-13 | 2026-02-15 |  | 7
IWP_1023 | 347.374 | 140 | 2.4812 | 2026-02-15 | 2026-02-17 |  | 7
IWP_1024 | 223.0766 | 140 | 1.5934 | 2026-02-17 | 2026-02-19 |  | 7
IWP_1025 | 151.427 | 140 | 1.0816 | 2026-02-19 | 2026-02-20 |  | 8
IWP_1026 | 146.6725 | 140 | 1.0477 | 2026-02-20 | 2026-02-21 |  | 8
IWP_1027 | 828.457 | 140 | 5.9176 | 2026-02-21 | 2026-02-27 |  | 9
IWP_1028 | 1272.5733 | 140 | 9.0898 | 2026-02-27 | 2026-03-08 |  | 10
IWP_1029 | 662.4712 | 140 | 4.7319 | 2026-03-08 | 2026-03-13 |  | 11
IWP_1030 | 787.6335 | 140 | 5.626 | 2026-03-13 | 2026-03-19 |  | 11
IWP_1031 | 1137.5297 | 140 | 8.1252 | 2026-03-19 | 2026-03-27 |  | 13
IWP_1032 | 409.9073 | 140 | 2.9279 | 2026-03-27 | 2026-03-30 |  | 13
IWP_1033 | 186.3466 | 140 | 1.331 | 2026-03-30 | 2026-03-31 |  | 13
IWP_1034 | 376.9088 | 140 | 2.6922 | 2026-03-31 | 2026-04-03 |  | 14
IWP_1035 | 442.0368 | 140 | 3.1574 | 2026-04-03 | 2026-04-06 |  | 14
IWP_1036 | 610.8094 | 140 | 4.3629 | 2026-04-06 | 2026-04-10 |  | 15
IWP_1037 | 586.076 | 140 | 4.1863 | 2026-04-10 | 2026-04-14 |  | 15
IWP_1038 | 459.5109 | 140 | 3.2822 | 2026-04-14 | 2026-04-17 |  | 16
IWP_1039 | 495.5512 | 140 | 3.5397 | 2026-04-17 | 2026-04-21 |  | 16
IWP_1040 | 721.0517 | 140 | 5.1504 | 2026-04-21 | 2026-04-26 |  | 17
IWP_1041 | 507.3418 | 140 | 3.6239 | 2026-04-26 | 2026-04-30 |  | 17
IWP_1042 | 560.503 | 140 | 4.0036 | 2026-04-30 | 2026-05-04 |  | 18
IWP_1043 | 324.4745 | 140 | 2.3177 | 2026-05-04 | 2026-05-06 |  | 18
IWP_1044 | 465.1826 | 140 | 3.3227 | 2026-05-06 | 2026-05-09 |  | 19
IWP_1045 | 274.8103 | 140 | 1.9629 | 2026-05-09 | 2026-05-11 |  | 19
IWP_1046 | 584.6617 | 140 | 4.1762 | 2026-05-11 | 2026-05-15 |  | 20
IWP_1047 | 382.3968 | 140 | 2.7314 | 2026-05-15 | 2026-05-18 |  | 20
IWP_1048 | 205.164 | 140 | 1.4655 | 2026-05-18 | 2026-05-19 |  | 20
IWP_9999 | 963.9511 | 140 | 6.8854 | 2026-05-19 | 2026-05-19 | Various man-hr allowances
Total Field Hours | 20243.364
Formulas:
Start = INT(Table27[[#This Row],[Total Field Hours]]+Table27[[#This Row],[Duration (Days)]]+0.5)
Start = Table27[[#This Row],[Total Field Hours]]
Finish = Table27[[#This Row],[Start]]+Table27[[#This Row],[Duration (Days)]]
Total Field Hours = [Start, row above]
Spool Fabrication Planning & Scheduling by Installation Work Package (IWP) - Input Required
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## PP or IWP Mapping
Isometric Number | IWP Number | ShopHrs | ModHrs | FieldHrs | Crew_Days
ISO2036 | IWP_1001 | 30.2483 | 0 | 7.5077 | 0.15015
ISO2006 | IWP_1001 | 24.5156 | 0 | 6.8111 | 0.13622
ISO2043 | IWP_1001 | 27.8631 | 0 | 8.343 | 0.16686
ISO2038 | IWP_1001 | 23.1149 | 0 | 8.1261 | 0.16252
ISO2040 | IWP_1001 | 26.2208 | 0 | 17.5595 | 0.35119
ISO1055 | IWP_1001 | 14.812 | 0 | 10.6765 | 0.21353
ISO2031 | IWP_1001 | 26.6482 | 0 | 6.8793 | 0.13759
ISO2032 | IWP_1001 | 56.0015 | 0 | 39.5828 | 0.79166
ISO2037 | IWP_1001 | 25.8255 | 0 | 7.4494 | 0.14899
ISO2028 | IWP_1001 | 13.0356 | 0 | 11.1226 | 0.22245
ISO1002 | IWP_1001 | 13.1593 | 0 | 11.7631 | 0.23526
ISO2024 | IWP_1002 | 92.7077 | 0 | 24.2258 | 0.48452
ISO2025 | IWP_1002 | 118.8876 | 0 | 54.2877 | 1.0858
ISO2010 | IWP_1002 | 125.4804 | 0 | 79.4341 | 1.5887
ISO2026 | IWP_1003 | 76.2583 | 0 | 20.7647 | 0.41529
ISO4008 | IWP_1003 | 8.9062 | 0 | 12.8099 | 0.2562
ISO1053 | IWP_1003 | 88.7466 | 0 | 62.7762 | 1.2555
ISO1023 | IWP_1003 | 88.9251 | 0 | 56.946 | 1.1389
ISO3091 | IWP_1004 | 8.9928 | 0 | 12.1332 | 0.24266
ISO2044 | IWP_1004 | 6.627 | 0 | 6.8524 | 0.13705
ISO1027 | IWP_1004 | 67.6997 | 0 | 110.0878 | 2.2018
ISO1028 | IWP_1005 | 107.7862 | 0 | 83.6327 | 1.6727
ISO1029 | IWP_1005 | 60.0978 | 0 | 24.4486 | 0.48897
ISO1016 | IWP_1005 | 113.6296 | 0 | 58.8197 | 1.1764
ISO1017 | IWP_1006 | 98.3382 | 0 | 136.1764 | 2.7235
ISO2030 | IWP_1006 | 26.8337 | 0 | 7.84 | 0.1568
ISO2041 | IWP_1006 | 56.0888 | 0 | 42.6829 | 0.85366
ISO2042 | IWP_1007 | 25.8255 | 0 | 7.4494 | 0.14899
ISO4009 | IWP_1007 | 0 | 0 | 5.655 | 0.1131
ISO3094 | IWP_1007 | 2.3793 | 0 | 0.82044 | 0.016409
ISO2069 | IWP_1007 | 28.2406 | 0 | 8.9373 | 0.17875
ISO1059 | IWP_1007 | 34.08 | 0 | 12.3259 | 0.24652
ISO1003 | IWP_1007 | 17.3304 | 0 | 11.2447 | 0.22489
ISO3093 | IWP_1007 | 18.8355 | 0 | 6.4071 | 0.12814
ISO1046 | IWP_1007 | 89.3077 | 0 | 25.9766 | 0.51953
ISO2023 | IWP_1007 | 38.4944 | 0 | 11.377 | 0.22754
ISO1004 | IWP_1007 | 94.5342 | 0 | 58.6628 | 1.1733
ISO1019 | IWP_1008 | 209.7065 | 0 | 79.5852 | 1.5917
ISO2033 | IWP_1008 | 137.9576 | 0 | 31.7856 | 0.63571
ISO1001 | IWP_1008 | 70.0863 | 0 | 43.3609 | 0.86722
ISO1020 | IWP_1009 | 128.3599 | 0 | 70.5864 | 1.4117
ISO1022 | IWP_1009 | 221.3021 | 0 | 81.4051 | 1.6281
ISO1051 | IWP_1009 | 6.0712 | 0 | 15.4825 | 0.30965
ISO1052 | IWP_1010 | 43.2282 | 0 | 81.3601 | 1.6272
ISO1054 | IWP_1010 | 58.8212 | 0 | 63.5168 | 1.2703
ISO3021 | IWP_1011 | 108.7474 | 0 | 131.2404 | 2.6248
ISO3022 | IWP_1012 | 154.6517 | 0 | 98.6708 | 1.9734
ISO3023 | IWP_1012 | 140.6922 | 0 | 51.3021 | 1.026
ISO2065 | IWP_1012 | 23.27 | 0 | 5.5088 | 0.11018
ISO1021 | IWP_1012 | 74.9892 | 0 | 44.6882 | 0.89376
ISO1058 | IWP_1013 | 22.23 | 0 | 5.5088 | 0.11018
ISO3072 | IWP_1013 | 5.4285 | 0 | 6.8833 | 0.13767
ISO3071 | IWP_1013 | 14.8608 | 0 | 14.0831 | 0.28166
ISO2058 | IWP_1013 | 18.5612 | 0 | 10.6565 | 0.21313
ISO3092 | IWP_1013 | 22.5058 | 0 | 11.4453 | 0.22891
ISO1015 | IWP_1013 | 124.6339 | 0 | 107.9063 | 2.1581
ISO2029 | IWP_1014 | 145.104 | 0 | 94.2169 | 1.8843
ISO1050 | IWP_1014 | 64.7782 | 0 | 41.3417 | 0.82683
ISO1005 | IWP_1015 | 194.8967 | 0 | 109.5379 | 2.1908
ISO1006 | IWP_1015 | 155.9451 | 0 | 157.1534 | 3.1431
ISO1026 | IWP_1016 | 43.2375 | 0 | 82.6493 | 1.653
ISO1030 | IWP_1016 | 58.8977 | 0 | 63.9203 | 1.2784
ISO2039 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO2009 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO3095 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO3096 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO3097 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO4001 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO4002 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO4003 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO4004 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO4005 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO4006 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO4007 | IWP_1017 | 0 | 0 | 1.9988 | 0.039975
ISO4018 | IWP_1017 | 0 | 0 | 0.8775 | 0.01755
ISO4020 | IWP_1017 | 0 | 0 | 0.8775 | 0.01755
ISO4019 | IWP_1017 | 0 | 0 | 1.2675 | 0.02535
ISO2052 | IWP_1017 | 54.0742 | 0 | 17.8331 | 0.35666
ISO2053 | IWP_1017 | 18.646 | 0 | 7.7266 | 0.15453
ISO2054 | IWP_1017 | 59.1393 | 0 | 18.1018 | 0.36204
ISO2055 | IWP_1017 | 24.6596 | 0 | 7.8015 | 0.15603
ISO2057 | IWP_1017 | 13.7743 | 0 | 4.4746 | 0.089493
ISO2059 | IWP_1017 | 22.62 | 5.07 | 0.39 | 0.117
ISO2060 | IWP_1017 | 26.1418 | 1.1385 | 4.7925 | 0.11862
ISO2061 | IWP_1017 | 26.1418 | 1.1385 | 4.7925 | 0.11862
ISO2062 | IWP_1017 | 22.23 | 5.46 | 0.39 | 0.117
ISO2068 | IWP_1017 | 13.7743 | 0 | 4.4746 | 0.089493
ISO2066 | IWP_1017 | 34.1775 | 0 | 4.3502 | 0.087004
ISO2070 | IWP_1017 | 24.8867 | 0 | 4.4124 | 0.088249
ISO2063 | IWP_1017 | 30.283 | 0 | 9.7397 | 0.19479
ISO1036 | IWP_1017 | 30.283 | 0 | 9.7397 | 0.19479
ISO2071 | IWP_1017 | 34.1775 | 0 | 4.3502 | 0.087004
ISO2001 | IWP_1018 | 24.8867 | 0 | 4.4124 | 0.088249
ISO2064 | IWP_1018 | 30.3464 | 0 | 6.8894 | 0.13779
ISO2005 | IWP_1018 | 36.9202 | 0 | 30.3106 | 0.60621
ISO2011 | IWP_1019 | 451.6713 | 163.6644 | 0 | 3.2733
ISO2012 | IWP_1019 | 84.536 | 65.322 | 0 | 1.3064
ISO2013 | IWP_1019 | 98.2732 | 40.702 | 0 | 0.81404
ISO2014 | IWP_1019 | 84.536 | 65.322 | 0 | 1.3064
ISO2015 | IWP_1019 | 98.2732 | 40.702 | 0 | 0.81404
ISO1056 | IWP_1020 | 55.7527 | 19.4751 | 0 | 0.3895
ISO1057 | IWP_1020 | 55.7527 | 19.4751 | 0 | 0.3895
ISO2017 | IWP_1020 | 77.7296 | 63.2964 | 0 | 1.2659
ISO2016 | IWP_1020 | 74.8696 | 59.8514 | 0 | 1.197
ISO2018 | IWP_1021 | 190.6436 | 218.6792 | 8.5166 | 4.5439
ISO2019 | IWP_1022 | 304.8231 | 376.7569 | 17.0332 | 7.8758
ISO2020 | IWP_1023 | 173.9865 | 89.6148 | 0 | 1.7923
ISO2021 | IWP_1023 | 173.3874 | 200.4881 | 8.5166 | 4.1801
ISO2035 | IWP_1024 | 23.27 | 7.345 | 0 | 0.1469
ISO2072 | IWP_1024 | 27.5895 | 31.5534 | 0 | 0.63107
ISO2073 | IWP_1024 | 46.5487 | 36.8488 | 0 | 0.73698
ISO2074 | IWP_1024 | 35.596 | 31.3217 | 0 | 0.62643
ISO4024 | IWP_1024 | 3.77 | 0 | 0.6825 | 0.01365
ISO4026 | IWP_1024 | 3.77 | 0 | 0.6825 | 0.01365
ISO4025 | IWP_1024 | 0.78 | 0 | 0.43875 | 0.008775
ISO4027 | IWP_1024 | 0.78 | 0 | 0.43875 | 0.008775
ISO2076 | IWP_1024 | 39.9071 | 0 | 40.4089 | 0.80818
ISO2075 | IWP_1024 | 41.0654 | 0 | 17.2384 | 0.34477
ISO3032 | IWP_1025 | 52.7337 | 0 | 63.2217 | 1.2644
ISO3033 | IWP_1025 | 35.7249 | 0 | 26.1227 | 0.52245
ISO3027 | IWP_1025 | 49.1922 | 0 | 32.6868 | 0.65374
ISO3034 | IWP_1025 | 13.7762 | 0 | 2.6443 | 0.052886
ISO3028 | IWP_1026 | 11.9013 | 0 | 60.8358 | 1.2167
ISO3029 | IWP_1026 | 52.3858 | 0 | 64.5214 | 1.2904
ISO3030 | IWP_1026 | 27.6624 | 0 | 59.0799 | 1.1816
ISO3024 | IWP_1026 | 14.2308 | 0 | 8.0113 | 0.16023
ISO3025 | IWP_1026 | 25.6814 | 0 | 11.5055 | 0.23011
ISO3031 | IWP_1026 | 14.8109 | 0 | 15.321 | 0.30642
ISO2077 | IWP_1027 | 595.3477 | 553.7599 | 30.5858 | 11.6869
ISO3006 | IWP_1027 | 233.1094 | 78.2544 | 0 | 1.5651
ISO2091 | IWP_1028 | 1272.5733 | 626.5069 | 30.2591 | 13.1353
ISO2082 | IWP_1029 | 662.4712 | 459.77 | 23.4478 | 9.6644
ISO2083 | IWP_1030 | 787.6335 | 357.6198 | 0 | 7.1524
ISO2090 | IWP_1031 | 1137.5297 | 483.6424 | 30.2591 | 10.278
ISO2089 | IWP_1032 | 292.9332 | 143.2232 | 0 | 2.8645
ISO2086 | IWP_1032 | 44.4183 | 47.1095 | 0 | 0.94219
ISO2078 | IWP_1032 | 72.5558 | 28.7358 | 0 | 0.57472
ISO3007 | IWP_1033 | 186.3466 | 266.7337 | 8.7399 | 5.5095
ISO2045 | IWP_1034 | 15.3714 | 7.7325 | 0 | 0.15465
ISO2051 | IWP_1034 | 7.6778 | 7.8013 | 0 | 0.15603
ISO4012 | IWP_1034 | 0 | 0 | 0.39 | 0.0078
ISO4015 | IWP_1034 | 0 | 0 | 0.39 | 0.0078
ISO4022 | IWP_1034 | 5.72 | 0 | 1.5112 | 0.030225
ISO4023 | IWP_1034 | 0 | 0 | 1.95 | 0.039
ISO4010 | IWP_1034 | 0 | 0 | 0.43875 | 0.008775
ISO4017 | IWP_1034 | 0 | 0 | 0.43875 | 0.008775
ISO3026 | IWP_1034 | 0 | 0 | 0.43875 | 0.008775
ISO4011 | IWP_1034 | 0 | 0 | 0.43875 | 0.008775
ISO4016 | IWP_1034 | 0 | 0 | 0.43875 | 0.008775
ISO4013 | IWP_1034 | 0 | 0 | 0.43875 | 0.008775
ISO4014 | IWP_1034 | 0 | 0 | 0.43875 | 0.008775
ISO2079 | IWP_1034 | 2.34 | 0 | 0.43875 | 0.008775
ISO2088 | IWP_1034 | 2.34 | 0 | 0.8775 | 0.01755
ISO3035 | IWP_1034 | 7.2196 | 0 | 2.3734 | 0.047468
ISO1048 | IWP_1034 | 42.9893 | 0 | 18.2608 | 0.36522
ISO1049 | IWP_1034 | 3.5777 | 0 | 0.69197 | 0.013839
ISO3039 | IWP_1034 | 24.2304 | 0 | 6.2399 | 0.1248
ISO3040 | IWP_1034 | 38.1639 | 0 | 9.89 | 0.1978
ISO3041 | IWP_1034 | 7.2196 | 0 | 2.3734 | 0.047468
ISO3043 | IWP_1034 | 42.9347 | 0 | 17.2241 | 0.34448
ISO3044 | IWP_1034 | 3.5777 | 0 | 0.69197 | 0.013839
ISO3049 | IWP_1034 | 38.1639 | 0 | 9.89 | 0.1978
ISO3050 | IWP_1034 | 7.2196 | 0 | 2.3734 | 0.047468
ISO3052 | IWP_1034 | 53.9192 | 0 | 23.0659 | 0.46132
ISO3055 | IWP_1034 | 3.5777 | 0 | 0.69197 | 0.013839
ISO2048 | IWP_1034 | 46.4357 | 0 | 19.1894 | 0.38379
ISO2047 | IWP_1034 | 24.2304 | 0 | 6.2399 | 0.1248
ISO3048 | IWP_1035 | 24.2304 | 0 | 6.2399 | 0.1248
ISO3042 | IWP_1035 | 23.7189 | 0 | 8.6147 | 0.17229
ISO1047 | IWP_1035 | 23.7189 | 0 | 8.6147 | 0.17229
ISO3047 | IWP_1035 | 21.4765 | 0 | 5.6445 | 0.11289
ISO3051 | IWP_1035 | 23.7189 | 0 | 8.6147 | 0.17229
ISO3036 | IWP_1035 | 38.8548 | 0 | 7.7758 | 0.15552
ISO3037 | IWP_1035 | 38.6928 | 0 | 6.9469 | 0.13894
ISO3045 | IWP_1035 | 38.8548 | 0 | 7.7758 | 0.15552
ISO3046 | IWP_1035 | 38.6928 | 0 | 6.9469 | 0.13894
ISO3056 | IWP_1035 | 38.8548 | 0 | 7.7758 | 0.15552
ISO3057 | IWP_1035 | 38.6928 | 0 | 6.9469 | 0.13894
ISO3054 | IWP_1035 | 28.1014 | 0 | 6.2221 | 0.12444
ISO3053 | IWP_1035 | 21.476 | 0 | 5.6417 | 0.11283
ISO2046 | IWP_1035 | 21.4765 | 0 | 5.6445 | 0.11289
ISO3038 | IWP_1035 | 21.4765 | 0 | 5.6445 | 0.11289
ISO2092 | IWP_1036 | 252.4964 | 0 | 91.7496 | 1.835
ISO2093 | IWP_1036 | 136.7308 | 0 | 38.04 | 0.7608
ISO3013 | IWP_1036 | 110.7762 | 0 | 37.406 | 0.74812
ISO2080 | IWP_1036 | 110.806 | 0 | 23.9214 | 0.47843
ISO2081 | IWP_1037 | 90.5248 | 0 | 45.792 | 0.91584
ISO3014 | IWP_1037 | 243.0548 | 0 | 65.9359 | 1.3187
ISO2094 | IWP_1037 | 252.4964 | 0 | 91.7496 | 1.835
ISO3001 | IWP_1038 | 136.7308 | 0 | 53.273 | 1.0655
ISO3015 | IWP_1038 | 110.7762 | 0 | 23.756 | 0.47512
ISO3002 | IWP_1038 | 110.806 | 0 | 23.9214 | 0.47843
ISO3003 | IWP_1038 | 101.1978 | 0 | 48.8145 | 0.97629
ISO3016 | IWP_1039 | 243.0548 | 0 | 65.9359 | 1.3187
ISO3004 | IWP_1039 | 252.4964 | 0 | 91.7496 | 1.835
ISO3005 | IWP_1040 | 136.7308 | 0 | 51.69 | 1.0338
ISO3017 | IWP_1040 | 110.7762 | 0 | 23.756 | 0.47512
ISO2084 | IWP_1040 | 110.806 | 0 | 23.9214 | 0.47843
ISO2085 | IWP_1040 | 101.1978 | 0 | 48.8145 | 0.97629
ISO3018 | IWP_1040 | 261.5408 | 0 | 69.3972 | 1.3879
ISO3063 | IWP_1041 | 14.4483 | 0 | 5.6341 | 0.11268
ISO3062 | IWP_1041 | 9.5621 | 0 | 4.6882 | 0.093765
ISO3066 | IWP_1041 | 10.678 | 0 | 4.37 | 0.0874
ISO3067 | IWP_1041 | 9.5571 | 0 | 4.6616 | 0.093232
ISO3065 | IWP_1041 | 11.8592 | 0 | 4.3946 | 0.087892
ISO3068 | IWP_1041 | 6.0647 | 0 | 4.418 | 0.088359
ISO3011 | IWP_1041 | 60.0491 | 0 | 28.6143 | 0.57229
ISO3069 | IWP_1041 | 9.4709 | 0 | 4.2094 | 0.084188
ISO3064 | IWP_1041 | 33.0153 | 0 | 7.3062 | 0.14612
ISO3058 | IWP_1041 | 62.1919 | 0 | 11.498 | 0.22996
ISO3059 | IWP_1041 | 30.2386 | 0 | 11.0138 | 0.22028
ISO3060 | IWP_1041 | 21.1729 | 0 | 12.1603 | 0.24321
ISO3061 | IWP_1041 | 26.1374 | 0 | 9.3622 | 0.18724
ISO2087 | IWP_1041 | 202.8962 | 0 | 62.8224 | 1.2564
ISO3070 | IWP_1042 | 23.27 | 0 | 5.5088 | 0.11018
ISO3008 | IWP_1042 | 145.6692 | 0 | 49.4903 | 0.98981
ISO3009 | IWP_1042 | 145.6692 | 0 | 49.4903 | 0.98981
ISO1024 | IWP_1042 | 131.7992 | 0 | 18.6879 | 0.37376
ISO2067 | IWP_1042 | 26.2965 | 0 | 13.1296 | 0.26259
ISO3078 | IWP_1042 | 14.4222 | 0 | 5.4971 | 0.10994
ISO3079 | IWP_1042 | 30.4752 | 0 | 7.563 | 0.15126
ISO3080 | IWP_1042 | 11.8307 | 0 | 4.2448 | 0.084897
ISO3081 | IWP_1042 | 31.0708 | 0 | 6.6607 | 0.13321
ISO3082 | IWP_1043 | 36.1046 | 0 | 9.0948 | 0.1819
ISO3076 | IWP_1043 | 23.27 | 0 | 5.5088 | 0.11018
ISO3077 | IWP_1043 | 23.27 | 0 | 5.5088 | 0.11018
ISO3010 | IWP_1043 | 48.0326 | 0 | 22.482 | 0.44964
ISO2056 | IWP_1043 | 193.7972 | 0 | 107.5539 | 2.1511
ISO3073 | IWP_1044 | 34.1689 | 0 | 17.1017 | 0.34203
ISO1031 | IWP_1044 | 47.3224 | 0 | 10.9151 | 0.2183
ISO1032 | IWP_1044 | 40.9475 | 0 | 15.3403 | 0.30681
ISO1033 | IWP_1044 | 27.3251 | 0 | 11.8669 | 0.23734
ISO1043 | IWP_1044 | 7.2577 | 0 | 1.8234 | 0.036468
ISO1044 | IWP_1044 | 7.1832 | 0 | 1.4323 | 0.028645
ISO1039 | IWP_1044 | 10.8599 | 0 | 2.2047 | 0.044094
ISO1037 | IWP_1044 | 11.0905 | 0 | 4.1656 | 0.083313
ISO1041 | IWP_1044 | 6.0508 | 0 | 2.0726 | 0.041451
ISO1038 | IWP_1044 | 6.0508 | 0 | 2.0726 | 0.041451
ISO1035 | IWP_1044 | 9.8438 | 0 | 3.7971 | 0.075943
ISO1045 | IWP_1044 | 31.2742 | 0 | 8.4631 | 0.16926
ISO1042 | IWP_1044 | 33.0999 | 0 | 8.4877 | 0.16975
ISO1007 | IWP_1044 | 192.7078 | 0 | 44.3485 | 0.88697
ISO1008 | IWP_1045 | 48.0443 | 0 | 35.5843 | 0.71169
ISO1009 | IWP_1045 | 76.2126 | 0 | 26.1249 | 0.5225
ISO3019 | IWP_1045 | 48.0443 | 0 | 35.5843 | 0.71169
ISO3020 | IWP_1045 | 76.2126 | 0 | 26.1249 | 0.5225
ISO1013 | IWP_1045 | 26.2965 | 0 | 15.2746 | 0.30549
ISO1011 | IWP_1046 | 136.3217 | 0 | 20.6857 | 0.41371
ISO1025 | IWP_1046 | 58.7094 | 0 | 21.2052 | 0.4241
ISO1040 | IWP_1046 | 23.27 | 0 | 5.5088 | 0.11018
ISO2027 | IWP_1046 | 23.27 | 0 | 5.5088 | 0.11018
ISO1018 | IWP_1046 | 9.6562 | 0 | 2.8119 | 0.056237
ISO3074 | IWP_1046 | 31.2591 | 0 | 12.1051 | 0.2421
ISO3075 | IWP_1046 | 35.8519 | 0 | 6.662 | 0.13324
ISO1034 | IWP_1046 | 9.6609 | 0 | 2.8365 | 0.05673
ISO3088 | IWP_1046 | 38.4993 | 0 | 8.1311 | 0.16262
ISO3084 | IWP_1046 | 39.4915 | 0 | 7.8079 | 0.15616
ISO3086 | IWP_1046 | 30.3055 | 0 | 7.4251 | 0.1485
ISO3090 | IWP_1046 | 39.9378 | 0 | 9.022 | 0.18044
ISO1014 | IWP_1046 | 79.3564 | 0 | 15.1013 | 0.30203
ISO3087 | IWP_1046 | 22.23 | 0 | 3.8512 | 0.077025
ISO1010 | IWP_1046 | 6.842 | 0 | 16.8692 | 0.33738
ISO1012 | IWP_1047 | 131.5537 | 0 | 59.0133 | 1.1803
ISO2008 | IWP_1047 | 97.4653 | 0 | 39.9691 | 0.79938
ISO3012 | IWP_1047 | 49.0588 | 0 | 17.6197 | 0.35239
ISO3083 | IWP_1047 | 23.27 | 0 | 5.5088 | 0.11018
ISO3085 | IWP_1047 | 23.27 | 0 | 5.5088 | 0.11018
ISO3089 | IWP_1047 | 23.27 | 0 | 5.5088 | 0.11018
ISO2007 | IWP_1047 | 34.509 | 0 | 17.7024 | 0.35405
ISO2049 | IWP_1048 | 5.8478 | 0 | 5.0176 | 0.10035
ISO2050 | IWP_1048 | 5.8478 | 0 | 5.0176 | 0.10035
ISO2022 | IWP_1048 | 37.9644 | 0 | 24.0353 | 0.48071
ISO2002 | IWP_1048 | 32.9037 | 0 | 48.9789 | 0.97958
ISO2003 | IWP_1048 | 32.4007 | 0 | 36.0622 | 0.72124
ISO1060 | IWP_1048 | 20.6392 | 0 | 12.397 | 0.24794
ISO2004 | IWP_1048 | 42.7569 | 0 | 30.0504 | 0.60101
ISO2034 | IWP_1048 | 24.4634 | 0 | 15.6519 | 0.31304
ISO4021 | IWP_1048 | 2.34 | 0 | 1.5112 | 0.030225
Summary | IWP_9999 | 963.9511 | 368.3604 | 654.4513 | 22.6788
Installation Work Package (IWP)/Planning Packagr (PP) - Dynamic Table Mapping to their Content
Example - Can be changed progressively from PP to IWP Mapping as Construction Progresses
Go to Tab Index

## Allowances
CBS | COA | Desc | Location | Allowance % | Remarks
400 | 150-50-S-510 | Pipe Supports Labor (shoes, lugs, guides, etc.) | Spool Fabrication | 5% | of Labor hours
500 | 150-50-F-510 | Pipe Supports Labor | Module | 0% | of Labor hours (0% if quantified in MTOs)
600 | 150-50-F-510 | Pipe Supports Labor | Field | 0% | of Labor hours (0% if quantified in MTOs)
400 | 150-40-S-410 | Bolt torquing and tensioning | Spool Fabrication | 15% | of bolt-up labor
500 | 150-40-F-410 | Bolt torquing and tensioning | Module | 15% | of bolt-up labor
600 | 150-40-F-410 | Bolt torquing and tensioning | Field | 15% | of bolt-up labor
500 | 150-70-F-710 | Hydrotest of module assembly | Module | 5% | of Module Labor
600 | 150-70-F-710 | Field Hydrotest | Field | 5% | of Field Labor
500 | 150-90-F-910 | Flushing & Drying Module Piping | Module | 3% | of Module Labor
600 | 150-90-F-910 | Flushing & Drying on Site | Field | 3% | of Field Labor
600 | 150-90-F-910 | Nitrogen Purge/Chemical Cleaning | Field | 0% | Add 10% of Field Labor if required
400 | 150-99-S-999 | Small bore or other design development to IFC | Spool Fabrication | 0% | Client to determine; applied on grand total
500 | 150-99-F-999 | Small bore or other design development to IFC | Module | 0% | Client to determine; applied on grand total
600 | 150-99-F-999 | Small bore or other design development to IFC | Field | 0% | Client to determine; applied on grand total
Various Allowances in Piping Labor Estimate
Go to Tab Index

## WBS_L-Summary By Isometric
WBS1 | WBS2/Area | WBS3/Sub-Area/Module No./ Service | WBS4/Line Number | WBS_L/Isometric | Location | CBS | COA | Code of Account (COA) & Description | Dia | Description | Units | Quantity | Shop Quantity | Field_Qty | Module_Qty | DIA_INCH | Shop FDI | Field_FDI | Module_FDI | Total_FDI | Material | STD_UNIT_HR | PF | WR | S/C Rate | Location Hrs | Shop Hours | Field Hrs | Module Hrs | IWP | Shop Cost | Field_$ | Module_$ | Total_$
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 16 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 1.1765 | 1 | 110 | 0 | 18.824 | 18.824 | 0 | 0 | IWP_1001 | 2070.64 | 0 | 0 | 2070.64
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1001 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1001 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 4.712 | 4.712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.88432 | 0.88432 | 0 | 0 | IWP_1001 | 97.2748 | 0 | 0 | 97.2748
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 200 | 0 | 0 | 200
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 800 | 0 | 0 | 800
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1001 | 616 | 0 | 0 | 616
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1001 | 500 | 0 | 0 | 500
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 5.1832 | 0 | 5.1832 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 4.6427 | 0 | 4.6427 | 0 | IWP_1001 | 0 | 362.1275 | 0 | 362.1275
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1001 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1001 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1001 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1001 | 0 | 117 | 0 | 117
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 16 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 1.1765 | 1 | 110 | 0 | 18.824 | 18.824 | 0 | 0 | IWP_1001 | 2070.64 | 0 | 0 | 2070.64
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1001 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1001 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 4.005 | 4.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.75163 | 0.75163 | 0 | 0 | IWP_1001 | 82.6794 | 0 | 0 | 82.6794
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 200 | 0 | 0 | 200
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 800 | 0 | 0 | 800
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 4.4055 | 0 | 4.4055 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 3.9461 | 0 | 3.9461 | 0 | IWP_1001 | 0 | 307.793 | 0 | 307.793
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1001 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1001 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1001 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1001 | 0 | 117 | 0 | 117
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1001 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1001 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1001 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1001 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1001 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1001 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1001 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1001 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.26 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.22572 | 0.22572 | 0 | 0 | IWP_1001 | 24.8292 | 0 | 0 | 24.8292
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.897 | 0.897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.16834 | 0.16834 | 0 | 0 | IWP_1001 | 18.5177 | 0 | 0 | 18.5177
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 150 | 0 | 0 | 150
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 50 | 0 | 0 | 50
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.323 | 0 | 1.323 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.1554 | 0 | 1.1554 | 0 | IWP_1001 | 0 | 90.1214 | 0 | 90.1214
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.9867 | 0 | 0.9867 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.8838 | 0 | 0.8838 | 0 | IWP_1001 | 0 | 68.9364 | 0 | 68.9364
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1001 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1001 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1001 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1001 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1001 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1001 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1001 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1001 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1001 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1001 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1001 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1001 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1001 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1001 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.06 | 1.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.18989 | 0.18989 | 0 | 0 | IWP_1001 | 20.888 | 0 | 0 | 20.888
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.863 | 0.863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.16196 | 0.16196 | 0 | 0 | IWP_1001 | 17.8158 | 0 | 0 | 17.8158
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 150 | 0 | 0 | 150
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.97201 | 0 | 0.97201 | 0 | IWP_1001 | 0 | 75.8164 | 0 | 75.8164
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.9493 | 0 | 0.9493 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.8503 | 0 | 0.8503 | 0 | IWP_1001 | 0 | 66.3234 | 0 | 66.3234
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1001 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1001 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1001 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1001 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1001 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1001 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1001 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 10 | 10 | 0 | 0 | 30 | 30 | 0 | 0 | 30 | CS | 1.3715 | 1 | 110 | 0 | 13.715 | 13.715 | 0 | 0 | IWP_1001 | 1508.65 | 0 | 0 | 1508.65
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 10.292 | 10.292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 1.7998 | 1.7998 | 0 | 0 | IWP_1001 | 197.9821 | 0 | 0 | 197.9821
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 200 | 0 | 0 | 200
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 500 | 0 | 0 | 500
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 6 | 6 | 0 | 0 | IWP_1001 | 660 | 0 | 0 | 660
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1001 | 600 | 0 | 0 | 600
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 11.3212 | 0 | 11.3212 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 9.887 | 0 | 9.887 | 0 | IWP_1001 | 0 | 771.1885 | 0 | 771.1885
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1001 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.17 | 0 | 1.17 | 0 | IWP_1001 | 0 | 91.26 | 0 | 91.26
Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 5.625 | 0 | 5.625 | 0 | IWP_1001 | 0 | 438.75 | 0 | 438.75
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 5 | 5 | 0 | 0 | 15 | 15 | 0 | 0 | 15 | CS | 1.3715 | 1 | 110 | 0 | 6.8575 | 6.8575 | 0 | 0 | IWP_1001 | 754.325 | 0 | 0 | 754.325
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1001 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1001 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1001 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 3.857 | 3.857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.6745 | 0.6745 | 0 | 0 | IWP_1001 | 74.1952 | 0 | 0 | 74.1952
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 250 | 0 | 0 | 250
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 250 | 0 | 0 | 250
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 4.2427 | 0 | 4.2427 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 3.7052 | 0 | 3.7052 | 0 | IWP_1001 | 0 | 289.0084 | 0 | 289.0084
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1001 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install valve - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 1.4625 | 0 | 1.4625 | 0 | IWP_1001 | 0 | 114.075 | 0 | 114.075
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install Blind - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 1.4625 | 0 | 1.4625 | 0 | IWP_1001 | 0 | 114.075 | 0 | 114.075
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.56 | 0 | 1.56 | 0 | IWP_1001 | 0 | 121.68 | 0 | 121.68
Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL300 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1001 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1001 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 10 | 10 | 0 | 0 | 40 | 60 | 0 | 0 | 60 | CS | 2.119 | 1 | 110 | 0 | 21.19 | 21.19 | 0 | 0 | IWP_1001 | 2330.9 | 0 | 0 | 2330.9
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1001 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1001 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1001 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 0.991 | 0.991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 0.24516 | 0.24516 | 0 | 0 | IWP_1001 | 26.9677 | 0 | 0 | 26.9677
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 100 | 0 | 0 | 100
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 1.0901 | 0 | 1.0901 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 1.2693 | 0 | 1.2693 | 0 | IWP_1001 | 0 | 99.0087 | 0 | 99.0087
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1001 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1001 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1001 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 1.4625 | 0 | 1.4625 | 0 | IWP_1001 | 0 | 114.075 | 0 | 114.075
Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 4 | Erection of Pipe Supports - NB 4 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 1.125 | 0 | 1.125 | 0 | IWP_1001 | 0 | 87.75 | 0 | 87.75
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1001 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 18 | 18 | 0 | 0 | 72 | 108 | 0 | 0 | 108 | CS | 2.119 | 1 | 110 | 0 | 38.142 | 38.142 | 0 | 0 | IWP_1001 | 4195.62 | 0 | 0 | 4195.62
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1001 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1001 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1001 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 7.654 | 7.654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 1.8935 | 1.8935 | 0 | 0 | IWP_1001 | 208.2853 | 0 | 0 | 208.2853
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 50 | 0 | 0 | 50
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 150 | 0 | 0 | 150
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 4 | Shop Hydrotest - NB 4 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.4 | 1 | 110 | 0 | 8.4 | 8.4 | 0 | 0 | IWP_1001 | 924 | 0 | 0 | 924
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 4 | Shop Spools Coating - NB 4 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 700 | 0 | 0 | 0 | 0 | IWP_1001 | 700 | 0 | 0 | 700
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 8.4194 | 0 | 8.4194 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 9.8038 | 0 | 9.8038 | 0 | IWP_1001 | 0 | 764.6945 | 0 | 764.6945
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 4 | Erection of Field Run Pipe - NB 4 SchXST | LM | 15.3076 | 0 | 15.3076 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3222 | 0.75 | 78 | 0 | 15.1803 | 0 | 15.1803 | 0 | IWP_1001 | 0 | 1184.0615 | 0 | 1184.0615
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1001 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1001 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1001 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1001 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 4 | Erection of Pipe Supports - NB 4 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 6.75 | 0 | 6.75 | 0 | IWP_1001 | 0 | 526.5 | 0 | 526.5
Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 4 | Field Coating - NB 4 | LM | 15.3076 | 0 | 15.3076 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 80 | 0 | 0 | 0 | 0 | IWP_1001 | 0 | 1224.608 | 0 | 1224.608
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1001 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1001 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1001 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1001 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1001 | 429 | 0 | 0 | 429
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1001 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1001 | 1001 | 0 | 0 | 1001
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1001 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1001 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1001 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1001 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.079 | 1.079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.2025 | 0.2025 | 0 | 0 | IWP_1001 | 22.2749 | 0 | 0 | 22.2749
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 200 | 0 | 0 | 200
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1869 | 0 | 1.1869 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.0631 | 0 | 1.0631 | 0 | IWP_1001 | 0 | 82.9235 | 0 | 82.9235
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1001 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1001 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1001 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1001 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1001 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 6 | 6 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 2.119 | 1 | 110 | 0 | 12.714 | 12.714 | 0 | 0 | IWP_1001 | 1398.54 | 0 | 0 | 1398.54
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 0.3216 | 0.3216 | 0 | 0 | IWP_1001 | 35.3764 | 0 | 0 | 35.3764
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 50 | 0 | 0 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 1.43 | 0 | 1.43 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 1.6651 | 0 | 1.6651 | 0 | IWP_1001 | 0 | 129.8802 | 0 | 129.8802
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install Blind - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1001 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install valve - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1001 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1001 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 6 | 6 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 2.119 | 1 | 110 | 0 | 12.714 | 12.714 | 0 | 0 | IWP_1001 | 1398.54 | 0 | 0 | 1398.54
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 0.4453 | 0.4453 | 0 | 0 | IWP_1001 | 48.9827 | 0 | 0 | 48.9827
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1001 | 50 | 0 | 0 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 1.98 | 0 | 1.98 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 2.3056 | 0 | 2.3056 | 0 | IWP_1001 | 0 | 179.8341 | 0 | 179.8341
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install Blind - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1001 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install valve - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1001 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1001 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 4 | 4 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 2.119 | 1 | 110 | 0 | 8.476 | 8.476 | 0 | 0 | IWP_1002 | 932.36 | 0 | 0 | 932.36
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 10 | 10 | 0 | 0 | 100 | 250 | 0 | 0 | 250 | CS | 5.915 | 1 | 110 | 0 | 59.15 | 59.15 | 0 | 0 | IWP_1002 | 6506.5 | 0 | 0 | 6506.5
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1002 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1002 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1002 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1002 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 Sch80 | LM | 6.547 | 6.547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.46918 | 1 | 110 | 0 | 3.0717 | 3.0717 | 0 | 0 | IWP_1002 | 337.8915 | 0 | 0 | 337.8915
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1002 | 500 | 0 | 0 | 500
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1002 | 50 | 0 | 0 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 10 | Shop Hydrotest - NB 10 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 14.6 | 1 | 110 | 0 | 14.6 | 14.6 | 0 | 0 | IWP_1002 | 1606 | 0 | 0 | 1606
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 10 | Shop Spools Coating - NB 10 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1500 | 0 | 0 | 0 | 0 | IWP_1002 | 1500 | 0 | 0 | 1500
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 10 | Install Spools - NB 10 Sch80 | LM | 7.529 | 0 | 7.529 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.9857 | 0.75 | 78 | 0 | 16.8597 | 0 | 16.8597 | 0 | IWP_1002 | 0 | 1315.0543 | 0 | 1315.0543
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1002 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1002 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 0.73125 | 0 | 0.73125 | 0 | IWP_1002 | 0 | 57.0375 | 0 | 57.0375
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 0.75 | 78 | 0 | 1.56 | 0 | 1.56 | 0 | IWP_1002 | 0 | 121.68 | 0 | 121.68
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 0.75 | 78 | 0 | 2.7349 | 0 | 2.7349 | 0 | IWP_1002 | 0 | 213.3213 | 0 | 213.3213
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 1 | Shop Butt Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 0.585 | 1 | 110 | 0 | 0.585 | 0.585 | 0 | 0 | IWP_1002 | 64.35 | 0 | 0 | 64.35
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1002 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 10 | 10 | 0 | 0 | 100 | 250 | 0 | 0 | 250 | CS | 5.915 | 1 | 110 | 0 | 59.15 | 59.15 | 0 | 0 | IWP_1002 | 6506.5 | 0 | 0 | 6506.5
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1002 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 5 | 5 | 0 | 0 | 10 | 30 | 0 | 0 | 30 | CS | 5.46 | 1 | 110 | 0 | 27.3 | 27.3 | 0 | 0 | IWP_1002 | 3003 | 0 | 0 | 3003
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1002 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 Sch80 | LM | 7.54 | 7.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.46918 | 1 | 110 | 0 | 3.5376 | 3.5376 | 0 | 0 | IWP_1002 | 389.1404 | 0 | 0 | 389.1404
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1002 | 500 | 0 | 0 | 500
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1002 | 150 | 0 | 0 | 150
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 10 | Shop Hydrotest - NB 10 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 14.6 | 1 | 110 | 0 | 14.6 | 14.6 | 0 | 0 | IWP_1002 | 1606 | 0 | 0 | 1606
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 10 | Shop Spools Coating - NB 10 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1500 | 0 | 0 | 0 | 0 | IWP_1002 | 1500 | 0 | 0 | 1500
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 10 | Install Spools - NB 10 Sch80 | LM | 8.671 | 0 | 8.671 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.9857 | 0.75 | 78 | 0 | 19.4168 | 0 | 19.4168 | 0 | IWP_1002 | 0 | 1514.5118 | 0 | 1514.5118
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1002 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 10 | Install valve - NB 10 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 0.75 | 78 | 0 | 4.9725 | 0 | 4.9725 | 0 | IWP_1002 | 0 | 387.855 | 0 | 387.855
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 10 | Install Blind - NB 10 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 0.75 | 78 | 0 | 4.9725 | 0 | 4.9725 | 0 | IWP_1002 | 0 | 387.855 | 0 | 387.855
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1002 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1002 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 0.75 | 78 | 0 | 9.36 | 0 | 9.36 | 0 | IWP_1002 | 0 | 730.08 | 0 | 730.08
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 0.75 | 78 | 0 | 8.2047 | 0 | 8.2047 | 0 | IWP_1002 | 0 | 639.964 | 0 | 639.964
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1002 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 12 | 12 | 0 | 0 | 120 | 300 | 0 | 0 | 300 | CS | 5.915 | 1 | 110 | 0 | 70.98 | 70.98 | 0 | 0 | IWP_1002 | 7807.8 | 0 | 0 | 7807.8
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1002 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1002 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1002 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1002 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 Sch80 | LM | 14.524 | 14.524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.46918 | 1 | 110 | 0 | 6.8144 | 6.8144 | 0 | 0 | IWP_1002 | 749.5855 | 0 | 0 | 749.5855
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1002 | 500 | 0 | 0 | 500
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1002 | 50 | 0 | 0 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 10 | Shop Hydrotest - NB 10 Sch80 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 14.6 | 1 | 110 | 0 | 29.2 | 29.2 | 0 | 0 | IWP_1002 | 3212 | 0 | 0 | 3212
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 10 | Shop Spools Coating - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1500 | 0 | 0 | 0 | 0 | IWP_1002 | 3000 | 0 | 0 | 3000
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 10 | Install Spools - NB 10 Sch80 | LM | 16.7026 | 0 | 16.7026 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.9857 | 0.75 | 78 | 0 | 37.4018 | 0 | 37.4018 | 0 | IWP_1002 | 0 | 2917.3435 | 0 | 2917.3435
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1002 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 10 | Install valve - NB 10 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 0.75 | 78 | 0 | 9.945 | 0 | 9.945 | 0 | IWP_1002 | 0 | 775.71 | 0 | 775.71
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 10 | Install Blind - NB 10 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 0.75 | 78 | 0 | 4.9725 | 0 | 4.9725 | 0 | IWP_1002 | 0 | 387.855 | 0 | 387.855
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1002 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.0713 | 0 | 3.0713 | 0 | IWP_1002 | 0 | 239.5575 | 0 | 239.5575
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 0.75 | 78 | 0 | 15.6 | 0 | 15.6 | 0 | IWP_1002 | 0 | 1216.8 | 0 | 1216.8
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 0.75 | 78 | 0 | 5.4698 | 0 | 5.4698 | 0 | IWP_1002 | 0 | 426.6427 | 0 | 426.6427
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 2 | 2 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 2.119 | 1 | 110 | 0 | 4.238 | 4.238 | 0 | 0 | IWP_1003 | 466.18 | 0 | 0 | 466.18
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 8 | 8 | 0 | 0 | 80 | 200 | 0 | 0 | 200 | CS | 5.915 | 1 | 110 | 0 | 47.32 | 47.32 | 0 | 0 | IWP_1003 | 5205.2 | 0 | 0 | 5205.2
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1003 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1003 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1003 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1003 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 Sch80 | LM | 5.734 | 5.734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.46918 | 1 | 110 | 0 | 2.6903 | 2.6903 | 0 | 0 | IWP_1003 | 295.9325 | 0 | 0 | 295.9325
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1003 | 250 | 0 | 0 | 250
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 10 | Shop Hydrotest - NB 10 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 14.6 | 1 | 110 | 0 | 14.6 | 14.6 | 0 | 0 | IWP_1003 | 1606 | 0 | 0 | 1606
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 10 | Shop Spools Coating - NB 10 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1500 | 0 | 0 | 0 | 0 | IWP_1003 | 1500 | 0 | 0 | 1500
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 10 | Install Spools - NB 10 Sch80 | LM | 6.5941 | 0 | 6.5941 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.9857 | 0.75 | 78 | 0 | 14.7661 | 0 | 14.7661 | 0 | IWP_1003 | 0 | 1151.7521 | 0 | 1151.7521
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1003 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1003 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 0.73125 | 0 | 0.73125 | 0 | IWP_1003 | 0 | 57.0375 | 0 | 57.0375
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 0.75 | 78 | 0 | 1.56 | 0 | 1.56 | 0 | IWP_1003 | 0 | 121.68 | 0 | 121.68
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 0.75 | 78 | 0 | 1.3674 | 0 | 1.3674 | 0 | IWP_1003 | 0 | 106.6607 | 0 | 106.6607
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 4 | 4 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 2.119 | 1 | 110 | 0 | 8.476 | 8.476 | 0 | 0 | IWP_1003 | 932.36 | 0 | 0 | 932.36
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 1.739 | 1.739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 0.43021 | 0.43021 | 0 | 0 | IWP_1003 | 47.3227 | 0 | 0 | 47.3227
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1003 | 50 | 0 | 0 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 1.9129 | 0 | 1.9129 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 2.2274 | 0 | 2.2274 | 0 | IWP_1003 | 0 | 173.7397 | 0 | 173.7397
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install valve - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1003 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install Blind - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1003 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1003 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 4 | Erection of Pipe Supports - NB 4 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 1.125 | 0 | 1.125 | 0 | IWP_1003 | 0 | 87.75 | 0 | 87.75
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 18 | 18 | 0 | 0 | 72 | 108 | 0 | 0 | 108 | CS | 2.119 | 1 | 110 | 0 | 38.142 | 38.142 | 0 | 0 | IWP_1003 | 4195.62 | 0 | 0 | 4195.62
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1003 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 29.601 | 29.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 7.3229 | 7.3229 | 0 | 0 | IWP_1003 | 805.5206 | 0 | 0 | 805.5206
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 1.65 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 0.49264 | 0.49264 | 0 | 0 | IWP_1003 | 54.1906 | 0 | 0 | 54.1906
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1003 | 150 | 0 | 0 | 150
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1003 | 75 | 0 | 0 | 75
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 4 | Shop Hydrotest - NB 4 SchXST | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.4 | 1 | 110 | 0 | 25.2 | 25.2 | 0 | 0 | IWP_1003 | 2772 | 0 | 0 | 2772
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 4 | Shop Spools Coating - NB 4 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 700 | 0 | 0 | 0 | 0 | IWP_1003 | 2100 | 0 | 0 | 2100
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 32.5611 | 0 | 32.5611 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 37.915 | 0 | 37.915 | 0 | IWP_1003 | 0 | 2957.3716 | 0 | 2957.3716
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 1.815 | 0 | 1.815 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 2.6012 | 0 | 2.6012 | 0 | IWP_1003 | 0 | 202.8897 | 0 | 202.8897
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install valve - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1003 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install Blind - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1003 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 7.3125 | 0 | 7.3125 | 0 | IWP_1003 | 0 | 570.375 | 0 | 570.375
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1003 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 4 | Erection of Pipe Supports - NB 4 | EA | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 9 | 0 | 9 | 0 | IWP_1003 | 0 | 702 | 0 | 702
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 18 | 18 | 0 | 0 | 72 | 108 | 0 | 0 | 108 | CS | 2.119 | 1 | 110 | 0 | 38.142 | 38.142 | 0 | 0 | IWP_1003 | 4195.62 | 0 | 0 | 4195.62
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1003 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 30.505 | 30.505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 7.5466 | 7.5466 | 0 | 0 | IWP_1003 | 830.1208 | 0 | 0 | 830.1208
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 1.499 | 1.499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 0.44756 | 0.44756 | 0 | 0 | IWP_1003 | 49.2314 | 0 | 0 | 49.2314
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1003 | 150 | 0 | 0 | 150
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1003 | 75 | 0 | 0 | 75
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 4 | Shop Hydrotest - NB 4 SchXST | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.4 | 1 | 110 | 0 | 25.2 | 25.2 | 0 | 0 | IWP_1003 | 2772 | 0 | 0 | 2772
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 4 | Shop Spools Coating - NB 4 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 700 | 0 | 0 | 0 | 0 | IWP_1003 | 2100 | 0 | 0 | 2100
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 33.5555 | 0 | 33.5555 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 39.0729 | 0 | 39.0729 | 0 | IWP_1003 | 0 | 3047.6883 | 0 | 3047.6883
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 1.6489 | 0 | 1.6489 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 2.3631 | 0 | 2.3631 | 0 | IWP_1003 | 0 | 184.3223 | 0 | 184.3223
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install valve - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1003 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install Blind - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1003 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 7.3125 | 0 | 7.3125 | 0 | IWP_1003 | 0 | 570.375 | 0 | 570.375
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1003 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 4 | Erection of Pipe Supports - NB 4 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1003 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 4 | 4 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 2.119 | 1 | 110 | 0 | 8.476 | 8.476 | 0 | 0 | IWP_1004 | 932.36 | 0 | 0 | 932.36
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 2.089 | 2.089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 0.51679 | 0.51679 | 0 | 0 | IWP_1004 | 56.8472 | 0 | 0 | 56.8472
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1004 | 50 | 0 | 0 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 2.2979 | 0 | 2.2979 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 2.6757 | 0 | 2.6757 | 0 | IWP_1004 | 0 | 208.7075 | 0 | 208.7075
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install Blind - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1004 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 4 | Install valve - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1004 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1004 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 5 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 1.1765 | 1 | 110 | 0 | 5.8825 | 5.8825 | 0 | 0 | IWP_1004 | 647.075 | 0 | 0 | 647.075
Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 3.967 | 3.967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.7445 | 0.7445 | 0 | 0 | IWP_1004 | 81.895 | 0 | 0 | 81.895
Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1004 | 250 | 0 | 0 | 250
Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 4.3637 | 0 | 4.3637 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 3.9086 | 0 | 3.9086 | 0 | IWP_1004 | 0 | 304.8726 | 0 | 304.8726
Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1004 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.7062 | 0 | 1.7062 | 0 | IWP_1004 | 0 | 133.0875 | 0 | 133.0875
Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1004 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 16 | 16 | 0 | 0 | 96 | 144 | 0 | 0 | 144 | CS | 2.9315 | 1 | 110 | 0 | 46.904 | 46.904 | 0 | 0 | IWP_1004 | 5159.44 | 0 | 0 | 5159.44
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1004 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1004 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1004 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1004 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 4.641 | 4.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 1.3857 | 1.3857 | 0 | 0 | IWP_1004 | 152.4235 | 0 | 0 | 152.4235
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1004 | 150 | 0 | 0 | 150
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1004 | 1320 | 0 | 0 | 1320
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1004 | 900 | 0 | 0 | 900
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 6 | Field Butt Weld - NB 6 SchXST | EA | 3 | 0 | 3 | 0 | 18 | 0 | 27 | 0 | 27 | CS | 4.2237 | 0.75 | 78 | 0 | 9.5033 | 0 | 9.5033 | 0 | IWP_1004 | 0 | 741.2593 | 0 | 741.2593
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 5.1051 | 0 | 5.1051 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 7.3163 | 0 | 7.3163 | 0 | IWP_1004 | 0 | 570.6735 | 0 | 570.6735
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchXST | LM | 53.7207 | 0 | 53.7207 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6208 | 0.75 | 78 | 0 | 65.3034 | 0 | 65.3034 | 0 | IWP_1004 | 0 | 5093.6689 | 0 | 5093.6689
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1004 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1004 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 7.02 | 0 | 7.02 | 0 | IWP_1004 | 0 | 547.56 | 0 | 547.56
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 18.6047 | 0 | 18.6047 | 0 | IWP_1004 | 0 | 1451.1656 | 0 | 1451.1656
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 53.7207 | 0 | 53.7207 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1004 | 0 | 5372.07 | 0 | 5372.07
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 22 | 22 | 0 | 0 | 132 | 198 | 0 | 0 | 198 | CS | 2.9315 | 1 | 110 | 0 | 64.493 | 64.493 | 0 | 0 | IWP_1005 | 7094.23 | 0 | 0 | 7094.23
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 24.427 | 24.427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 7.2932 | 7.2932 | 0 | 0 | IWP_1005 | 802.2513 | 0 | 0 | 802.2513
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1005 | 225 | 0 | 0 | 225
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 36 | 36 | 0 | 0 | IWP_1005 | 3960 | 0 | 0 | 3960
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1005 | 2700 | 0 | 0 | 2700
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 26.8697 | 0 | 26.8697 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 38.5081 | 0 | 38.5081 | 0 | IWP_1005 | 0 | 3003.6289 | 0 | 3003.6289
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchXST | LM | 16.0413 | 0 | 16.0413 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6208 | 0.75 | 78 | 0 | 19.5 | 0 | 19.5 | 0 | IWP_1005 | 0 | 1520.9979 | 0 | 1520.9979
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 7.02 | 0 | 7.02 | 0 | IWP_1005 | 0 | 547.56 | 0 | 547.56
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 18.6047 | 0 | 18.6047 | 0 | IWP_1005 | 0 | 1451.1656 | 0 | 1451.1656
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 16.0413 | 0 | 16.0413 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1005 | 0 | 1604.13 | 0 | 1604.13
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 2 | 2 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 2.119 | 1 | 110 | 0 | 4.238 | 4.238 | 0 | 0 | IWP_1005 | 466.18 | 0 | 0 | 466.18
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 14 | 14 | 0 | 0 | 84 | 126 | 0 | 0 | 126 | CS | 2.9315 | 1 | 110 | 0 | 41.041 | 41.041 | 0 | 0 | IWP_1005 | 4514.51 | 0 | 0 | 4514.51
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 9.441 | 9.441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 2.8188 | 2.8188 | 0 | 0 | IWP_1005 | 310.069 | 0 | 0 | 310.069
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1005 | 150 | 0 | 0 | 150
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1005 | 1320 | 0 | 0 | 1320
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1005 | 900 | 0 | 0 | 900
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 10.3851 | 0 | 10.3851 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 14.8833 | 0 | 14.8833 | 0 | IWP_1005 | 0 | 1160.8982 | 0 | 1160.8982
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 0.73125 | 0 | 0.73125 | 0 | IWP_1005 | 0 | 57.0375 | 0 | 57.0375
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1005 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 6.2016 | 0 | 6.2016 | 0 | IWP_1005 | 0 | 483.7219 | 0 | 483.7219
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 2 | 2 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 2.119 | 1 | 110 | 0 | 4.238 | 4.238 | 0 | 0 | IWP_1005 | 466.18 | 0 | 0 | 466.18
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 22 | 22 | 0 | 0 | 132 | 198 | 0 | 0 | 198 | CS | 2.9315 | 1 | 110 | 0 | 64.493 | 64.493 | 0 | 0 | IWP_1005 | 7094.23 | 0 | 0 | 7094.23
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 29.804 | 29.804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 8.8986 | 8.8986 | 0 | 0 | IWP_1005 | 978.8471 | 0 | 0 | 978.8471
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1005 | 225 | 0 | 0 | 225
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 36 | 36 | 0 | 0 | IWP_1005 | 3960 | 0 | 0 | 3960
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1005 | 2700 | 0 | 0 | 2700
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 32.7844 | 0 | 32.7844 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 46.9847 | 0 | 46.9847 | 0 | IWP_1005 | 0 | 3664.8036 | 0 | 3664.8036
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 0.73125 | 0 | 0.73125 | 0 | IWP_1005 | 0 | 57.0375 | 0 | 57.0375
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 6.1425 | 0 | 6.1425 | 0 | IWP_1005 | 0 | 479.115 | 0 | 479.115
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 4.9613 | 0 | 4.9613 | 0 | IWP_1005 | 0 | 386.9775 | 0 | 386.9775
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 26 | 26 | 0 | 0 | 156 | 234 | 0 | 0 | 234 | CS | 2.9315 | 1 | 110 | 0 | 76.219 | 76.219 | 0 | 0 | IWP_1006 | 8384.09 | 0 | 0 | 8384.09
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1006 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1006 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1006 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1006 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 9.074 | 9.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 2.7092 | 2.7092 | 0 | 0 | IWP_1006 | 298.0157 | 0 | 0 | 298.0157
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1006 | 300 | 0 | 0 | 300
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1006 | 1320 | 0 | 0 | 1320
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1006 | 900 | 0 | 0 | 900
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 6 | Field Butt Weld - NB 6 SchXST | EA | 4 | 0 | 4 | 0 | 24 | 0 | 36 | 0 | 36 | CS | 4.2237 | 0.75 | 78 | 0 | 12.6711 | 0 | 12.6711 | 0 | IWP_1006 | 0 | 988.3458 | 0 | 988.3458
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 9.9814 | 0 | 9.9814 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 14.3048 | 0 | 14.3048 | 0 | IWP_1006 | 0 | 1115.7706 | 0 | 1115.7706
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchXST | LM | 71.082 | 0 | 71.082 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6208 | 0.75 | 78 | 0 | 86.408 | 0 | 86.408 | 0 | IWP_1006 | 0 | 6739.826 | 0 | 6739.826
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1006 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1006 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 10.53 | 0 | 10.53 | 0 | IWP_1006 | 0 | 821.34 | 0 | 821.34
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 9.9225 | 0 | 9.9225 | 0 | IWP_1006 | 0 | 773.955 | 0 | 773.955
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 600 | 150-60-F-610 | 150-60-F-610 - Field X-Ray | 6 | Field X-Ray - NB 6 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 1000 | 0 | 0 | 0 | 0 | IWP_1006 | 0 | 1000 | 0 | 1000
Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 71.082 | 0 | 71.082 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1006 | 0 | 7108.2 | 0 | 7108.2
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1006 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 10 | 10 | 0 | 0 | 40 | 60 | 0 | 0 | 60 | CS | 2.119 | 1 | 110 | 0 | 21.19 | 21.19 | 0 | 0 | IWP_1006 | 2330.9 | 0 | 0 | 2330.9
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1006 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1006 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1006 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 1.741 | 1.741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 0.4307 | 0.4307 | 0 | 0 | IWP_1006 | 47.3772 | 0 | 0 | 47.3772
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1006 | 100 | 0 | 0 | 100
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 1.9151 | 0 | 1.9151 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 2.23 | 0 | 2.23 | 0 | IWP_1006 | 0 | 173.9395 | 0 | 173.9395
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1006 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1006 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1006 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 1.4625 | 0 | 1.4625 | 0 | IWP_1006 | 0 | 114.075 | 0 | 114.075
Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 4 | Erection of Pipe Supports - NB 4 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 1.125 | 0 | 1.125 | 0 | IWP_1006 | 0 | 87.75 | 0 | 87.75
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1006 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchXST | EA | 18 | 18 | 0 | 0 | 72 | 108 | 0 | 0 | 108 | CS | 2.119 | 1 | 110 | 0 | 38.142 | 38.142 | 0 | 0 | IWP_1006 | 4195.62 | 0 | 0 | 4195.62
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1006 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1006 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1006 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchXST | LM | 8.007 | 8.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.24739 | 1 | 110 | 0 | 1.9808 | 1.9808 | 0 | 0 | IWP_1006 | 217.8914 | 0 | 0 | 217.8914
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1006 | 50 | 0 | 0 | 50
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1006 | 150 | 0 | 0 | 150
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 4 | Shop Hydrotest - NB 4 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.4 | 1 | 110 | 0 | 8.4 | 8.4 | 0 | 0 | IWP_1006 | 924 | 0 | 0 | 924
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 4 | Shop Spools Coating - NB 4 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 700 | 0 | 0 | 0 | 0 | IWP_1006 | 700 | 0 | 0 | 700
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 4 | Field Butt Weld - NB 4 SchXST | EA | 1 | 0 | 1 | 0 | 4 | 0 | 6 | 0 | 6 | CS | 2.99 | 0.75 | 78 | 0 | 2.2425 | 0 | 2.2425 | 0 | IWP_1006 | 0 | 174.915 | 0 | 174.915
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchXST | LM | 8.8077 | 0 | 8.8077 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5526 | 0.75 | 78 | 0 | 10.2559 | 0 | 10.2559 | 0 | IWP_1006 | 0 | 799.962 | 0 | 799.962
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 4 | Erection of Field Run Pipe - NB 4 SchXST | LM | 16.8509 | 0 | 16.8509 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3222 | 0.75 | 78 | 0 | 16.7107 | 0 | 16.7107 | 0 | IWP_1006 | 0 | 1303.4376 | 0 | 1303.4376
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1006 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1006 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1006 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1006 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 4 | Erection of Pipe Supports - NB 4 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 5.625 | 0 | 5.625 | 0 | IWP_1006 | 0 | 438.75 | 0 | 438.75
Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 4 | Field Coating - NB 4 | LM | 16.8509 | 0 | 16.8509 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 80 | 0 | 0 | 0 | 0 | IWP_1006 | 0 | 1348.072 | 0 | 1348.072
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1007 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1007 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1007 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1007 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1007 | 429 | 0 | 0 | 429
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1007 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1007 | 1001 | 0 | 0 | 1001
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1007 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1007 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1007 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1007 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1007 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.079 | 1.079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.2025 | 0.2025 | 0 | 0 | IWP_1007 | 22.2749 | 0 | 0 | 22.2749
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 200 | 0 | 0 | 200
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1869 | 0 | 1.1869 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.0631 | 0 | 1.0631 | 0 | IWP_1007 | 0 | 82.9235 | 0 | 82.9235
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1007 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1007 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1007 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1007 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1007 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_1 | TR | TR-YP01-8087 | ISO4009 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.42 | 0.75 | 78 | 0 | 3.315 | 0 | 3.315 | 0 | IWP_1007 | 0 | 258.57 | 0 | 258.57
Proj_A | Area_1 | TR | TR-YP01-8087 | ISO4009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.12 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1007 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1007 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.14 | 0.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.026274 | 0.026274 | 0 | 0 | IWP_1007 | 2.8902 | 0 | 0 | 2.8902
Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 100 | 0 | 0 | 100
Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.154 | 0 | 0.154 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.13794 | 0 | 0.13794 | 0 | IWP_1007 | 0 | 10.7593 | 0 | 10.7593
Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1007 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1007 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1007 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1007 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1007 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1007 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1007 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1007 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1007 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1007 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.942 | 0.942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.16875 | 0.16875 | 0 | 0 | IWP_1007 | 18.5628 | 0 | 0 | 18.5628
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 3.212 | 3.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.60281 | 0.60281 | 0 | 0 | IWP_1007 | 66.3087 | 0 | 0 | 66.3087
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 150 | 0 | 0 | 150
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 50 | 0 | 0 | 50
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 0.9891 | 0 | 0.9891 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.8638 | 0 | 0.8638 | 0 | IWP_1007 | 0 | 67.3765 | 0 | 67.3765
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 3.5332 | 0 | 3.5332 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 3.1647 | 0 | 3.1647 | 0 | IWP_1007 | 0 | 246.8492 | 0 | 246.8492
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1007 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1007 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1007 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1007 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1007 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1007 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1007 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1007 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1007 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1007 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1007 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 8 | 8 | 0 | 0 | 8 | 10 | 0 | 0 | 10 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1007 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1007 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1007 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1007 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 0.86 | 0.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.13205 | 0.13205 | 0 | 0 | IWP_1007 | 14.5259 | 0 | 0 | 14.5259
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 6.069 | 6.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.139 | 1.139 | 0 | 0 | IWP_1007 | 125.2888 | 0 | 0 | 125.2888
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 150 | 0 | 0 | 150
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 50 | 0 | 0 | 50
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1007 | 616 | 0 | 0 | 616
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1007 | 500 | 0 | 0 | 500
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 0.903 | 0 | 0.903 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 0.75 | 78 | 0 | 0.6875 | 0 | 0.6875 | 0 | IWP_1007 | 0 | 53.6254 | 0 | 53.6254
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 6.6759 | 0 | 6.6759 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 5.9797 | 0 | 5.9797 | 0 | IWP_1007 | 0 | 466.4159 | 0 | 466.4159
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1007 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1007 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1007 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1007 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1007 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1007 | 0 | 117 | 0 | 117
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 7 | 0 | 0 | 14 | 21 | 0 | 0 | 21 | CS | 1.1765 | 1 | 110 | 0 | 8.2355 | 8.2355 | 0 | 0 | IWP_1007 | 905.905 | 0 | 0 | 905.905
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 6 | 0 | 0 | 18 | 18 | 0 | 0 | 18 | CS | 1.3715 | 1 | 110 | 0 | 8.229 | 8.229 | 0 | 0 | IWP_1007 | 905.19 | 0 | 0 | 905.19
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.945 | 2.945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.5527 | 0.5527 | 0 | 0 | IWP_1007 | 60.7967 | 0 | 0 | 60.7967
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 1.791 | 1.791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.31321 | 0.31321 | 0 | 0 | IWP_1007 | 34.4526 | 0 | 0 | 34.4526
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 50 | 0 | 0 | 50
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 50 | 0 | 0 | 50
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 3.2395 | 0 | 3.2395 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.9017 | 0 | 2.9017 | 0 | IWP_1007 | 0 | 226.3297 | 0 | 226.3297
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.7205 | 0 | 1.7205 | 0 | IWP_1007 | 0 | 134.2012 | 0 | 134.2012
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1007 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1007 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.975 | 0 | 0.975 | 0 | IWP_1007 | 0 | 76.05 | 0 | 76.05
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1007 | 0 | 117 | 0 | 117
Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 1.125 | 0 | 1.125 | 0 | IWP_1007 | 0 | 87.75 | 0 | 87.75
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1007 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1007 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | CS | 1.17 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1007 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 2 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.26 | 1 | 110 | 0 | 0.52 | 0.52 | 0 | 0 | IWP_1007 | 57.2 | 0 | 0 | 57.2
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.037535 | 0.037535 | 0 | 0 | IWP_1007 | 4.1288 | 0 | 0 | 4.1288
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 100 | 0 | 0 | 100
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 700 | 0 | 0 | 700
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.22 | 0 | 0.22 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.19706 | 0 | 0.19706 | 0 | IWP_1007 | 0 | 15.3704 | 0 | 15.3704
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.56 | 0 | 1.56 | 0 | IWP_1007 | 0 | 121.68 | 0 | 121.68
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1007 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 3.12 | 0 | 3.12 | 0 | IWP_1007 | 0 | 243.36 | 0 | 243.36
Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1007 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchSTD | EA | 4 | 4 | 0 | 0 | 24 | 24 | 0 | 0 | 24 | CS | 2.431 | 1 | 110 | 0 | 9.724 | 9.724 | 0 | 0 | IWP_1007 | 1069.64 | 0 | 0 | 1069.64
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 19 | 19 | 0 | 0 | 152 | 152 | 0 | 0 | 152 | CS | 3.0095 | 1 | 110 | 0 | 57.1805 | 57.1805 | 0 | 0 | IWP_1007 | 6289.855 | 0 | 0 | 6289.855
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1007 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1007 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1007 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 2.86 | 1 | 110 | 0 | 2.86 | 2.86 | 0 | 0 | IWP_1007 | 314.6 | 0 | 0 | 314.6
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1007 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1007 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchSTD | LM | 6.637 | 6.637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.26871 | 1 | 110 | 0 | 1.7835 | 1.7835 | 0 | 0 | IWP_1007 | 196.18 | 0 | 0 | 196.18
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1007 | 250 | 0 | 0 | 250
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1007 | 300 | 0 | 0 | 300
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1007 | 1900 | 0 | 0 | 1900
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 8 | Shop Hydrotest - NB 8 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 9.8 | 1 | 110 | 0 | 9.8 | 9.8 | 0 | 0 | IWP_1007 | 1078 | 0 | 0 | 1078
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 8 | Shop Spools Coating - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1100 | 0 | 0 | 0 | 0 | IWP_1007 | 1100 | 0 | 0 | 1100
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchSTD | LM | 7.3007 | 0 | 7.3007 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7019 | 0.75 | 78 | 0 | 9.3185 | 0 | 9.3185 | 0 | IWP_1007 | 0 | 726.8467 | 0 | 726.8467
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1007 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.86 | 0.75 | 78 | 0 | 2.145 | 0 | 2.145 | 0 | IWP_1007 | 0 | 167.31 | 0 | 167.31
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 2.925 | 0 | 2.925 | 0 | IWP_1007 | 0 | 228.15 | 0 | 228.15
Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL150 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.73 | 0.75 | 78 | 0 | 6.1425 | 0 | 6.1425 | 0 | IWP_1007 | 0 | 479.115 | 0 | 479.115
Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 8 | 0 | 0 | 96 | 144 | 0 | 0 | 144 | CS | 4.7255 | 1 | 110 | 0 | 37.804 | 37.804 | 0 | 0 | IWP_1007 | 4158.44 | 0 | 0 | 4158.44
Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 SchSTD | LM | 1.686 | 1.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.40947 | 1 | 110 | 0 | 0.69036 | 0.69036 | 0 | 0 | IWP_1007 | 75.9401 | 0 | 0 | 75.9401
Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1007 | 2000 | 0 | 0 | 2000
Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 SchSTD | LM | 1.9389 | 0 | 1.9389 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.6274 | 0.75 | 78 | 0 | 3.8207 | 0 | 3.8207 | 0 | IWP_1007 | 0 | 298.0174 | 0 | 298.0174
Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL300 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.94 | 0.75 | 78 | 0 | 5.5575 | 0 | 5.5575 | 0 | IWP_1007 | 0 | 433.485 | 0 | 433.485
Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1007 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 1 | 1 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | CS | 3.0095 | 1 | 110 | 0 | 3.0095 | 3.0095 | 0 | 0 | IWP_1007 | 331.045 | 0 | 0 | 331.045
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1007 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 3.8025 | 0 | 3.8025 | 0 | IWP_1007 | 0 | 296.595 | 0 | 296.595
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 20 | 20 | 0 | 0 | 240 | 600 | 0 | 0 | 600 | CS | 7.683 | 1 | 110 | 0 | 153.66 | 153.66 | 0 | 0 | IWP_1008 | 16902.6 | 0 | 0 | 16902.6
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1008 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1008 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1008 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1008 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 18.61 | 18.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 10.6365 | 10.6365 | 0 | 0 | IWP_1008 | 1170.0204 | 0 | 0 | 1170.0204
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1008 | 750 | 0 | 0 | 750
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 38 | 38 | 0 | 0 | IWP_1008 | 4180 | 0 | 0 | 4180
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1008 | 3400 | 0 | 0 | 3400
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 21.4015 | 0 | 21.4015 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 58.9465 | 0 | 58.9465 | 0 | IWP_1008 | 0 | 4597.829 | 0 | 4597.829
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1008 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1008 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 13.9912 | 0 | 13.9912 | 0 | IWP_1008 | 0 | 1091.3175 | 0 | 1091.3175
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 4.3075 | 0 | 4.3075 | 0 | IWP_1008 | 0 | 335.9811 | 0 | 335.9811
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1008 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 2 | 2 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 3.848 | 1 | 110 | 0 | 7.696 | 7.696 | 0 | 0 | IWP_1008 | 846.56 | 0 | 0 | 846.56
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 12 | 12 | 0 | 0 | 144 | 360 | 0 | 0 | 360 | CS | 7.683 | 1 | 110 | 0 | 92.196 | 92.196 | 0 | 0 | IWP_1008 | 10141.56 | 0 | 0 | 10141.56
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1008 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 6.018 | 6.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 3.4396 | 3.4396 | 0 | 0 | IWP_1008 | 378.3548 | 0 | 0 | 378.3548
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1008 | 500 | 0 | 0 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1008 | 50 | 0 | 0 | 50
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 19 | 19 | 0 | 0 | IWP_1008 | 2090 | 0 | 0 | 2090
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1008 | 1700 | 0 | 0 | 1700
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 6.9207 | 0 | 6.9207 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 19.0618 | 0 | 19.0618 | 0 | IWP_1008 | 0 | 1486.8208 | 0 | 1486.8208
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1008 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1008 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1008 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 7.995 | 0 | 7.995 | 0 | IWP_1008 | 0 | 623.61 | 0 | 623.61
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1008 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 8 | 8 | 0 | 0 | 96 | 240 | 0 | 0 | 240 | CS | 7.683 | 1 | 110 | 0 | 61.464 | 61.464 | 0 | 0 | IWP_1008 | 6761.04 | 0 | 0 | 6761.04
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1008 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 1.416 | 1.416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 0.80932 | 0.80932 | 0 | 0 | IWP_1008 | 89.0247 | 0 | 0 | 89.0247
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1008 | 250 | 0 | 0 | 250
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 1.6284 | 0 | 1.6284 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 4.4851 | 0 | 4.4851 | 0 | IWP_1008 | 0 | 349.8402 | 0 | 349.8402
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1008 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install Blind - NB 12 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 6.1425 | 0 | 6.1425 | 0 | IWP_1008 | 0 | 479.115 | 0 | 479.115
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install valve - NB 12 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 12.285 | 0 | 12.285 | 0 | IWP_1008 | 0 | 958.23 | 0 | 958.23
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1008 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 15.99 | 0 | 15.99 | 0 | IWP_1008 | 0 | 1247.22 | 0 | 1247.22
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 1.4358 | 0 | 1.4358 | 0 | IWP_1008 | 0 | 111.9937 | 0 | 111.9937
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1009 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 10 | 10 | 0 | 0 | 120 | 300 | 0 | 0 | 300 | CS | 7.683 | 1 | 110 | 0 | 76.83 | 76.83 | 0 | 0 | IWP_1009 | 8451.3 | 0 | 0 | 8451.3
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1009 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1009 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1009 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.69 | 1 | 110 | 0 | 3.38 | 3.38 | 0 | 0 | IWP_1009 | 371.8 | 0 | 0 | 371.8
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1009 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1009 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 2 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.26 | 1 | 110 | 0 | 0.52 | 0.52 | 0 | 0 | IWP_1009 | 57.2 | 0 | 0 | 57.2
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 6.603 | 6.603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 3.7739 | 3.7739 | 0 | 0 | IWP_1009 | 415.1341 | 0 | 0 | 415.1341
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1009 | 50 | 0 | 0 | 50
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1009 | 500 | 0 | 0 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1009 | 50 | 0 | 0 | 50
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 19 | 19 | 0 | 0 | IWP_1009 | 2090 | 0 | 0 | 2090
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1009 | 1700 | 0 | 0 | 1700
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 7.5934 | 0 | 7.5934 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 20.9148 | 0 | 20.9148 | 0 | IWP_1009 | 0 | 1631.3522 | 0 | 1631.3522
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1009 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1009 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install Blind - NB 12 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 6.1425 | 0 | 6.1425 | 0 | IWP_1009 | 0 | 479.115 | 0 | 479.115
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install valve - NB 12 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 12.285 | 0 | 12.285 | 0 | IWP_1009 | 0 | 958.23 | 0 | 958.23
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1009 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1009 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 19.9875 | 0 | 19.9875 | 0 | IWP_1009 | 0 | 1559.025 | 0 | 1559.025
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 2.8716 | 0 | 2.8716 | 0 | IWP_1009 | 0 | 223.9874 | 0 | 223.9874
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 4 | 4 | 0 | 0 | 48 | 120 | 0 | 0 | 120 | CS | 7.683 | 1 | 110 | 0 | 30.732 | 30.732 | 0 | 0 | IWP_1009 | 3380.52 | 0 | 0 | 3380.52
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 10 | 10 | 0 | 0 | 160 | 480 | 0 | 0 | 480 | CS | 14.365 | 1 | 110 | 0 | 143.65 | 143.65 | 0 | 0 | IWP_1009 | 15801.5 | 0 | 0 | 15801.5
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 14.773 | 14.773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 11.7201 | 11.7201 | 0 | 0 | IWP_1009 | 1289.2107 | 0 | 0 | 1289.2107
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1009 | 250 | 0 | 0 | 250
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1009 | 500 | 0 | 0 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 16 | Shop Hydrotest - NB 16 Sch80 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 17.6 | 1 | 110 | 0 | 35.2 | 35.2 | 0 | 0 | IWP_1009 | 3872 | 0 | 0 | 3872
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 16 | Shop Spools Coating - NB 16 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2100 | 0 | 0 | 0 | 0 | IWP_1009 | 4200 | 0 | 0 | 4200
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 16.9889 | 0 | 16.9889 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 0.75 | 78 | 0 | 65.0536 | 0 | 65.0536 | 0 | IWP_1009 | 0 | 5074.1831 | 0 | 5074.1831
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 3.9975 | 0 | 3.9975 | 0 | IWP_1009 | 0 | 311.805 | 0 | 311.805
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 7.605 | 0 | 7.605 | 0 | IWP_1009 | 0 | 593.19 | 0 | 593.19
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 0.75 | 78 | 0 | 4.749 | 0 | 4.749 | 0 | IWP_1009 | 0 | 370.4192 | 0 | 370.4192
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 1 | 1 | 0 | 0 | 10 | 25 | 0 | 0 | 25 | CS | 5.915 | 1 | 110 | 0 | 5.915 | 5.915 | 0 | 0 | IWP_1009 | 650.65 | 0 | 0 | 650.65
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 Sch80 | LM | 0.333 | 0.333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.46918 | 1 | 110 | 0 | 0.15624 | 0.15624 | 0 | 0 | IWP_1009 | 17.1862 | 0 | 0 | 17.1862
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 10 | Install Spools - NB 10 Sch80 | LM | 0.38295 | 0 | 0.38295 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.9857 | 0.75 | 78 | 0 | 0.85753 | 0 | 0.85753 | 0 | IWP_1009 | 0 | 66.8876 | 0 | 66.8876
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 10 | Install Blind - NB 10 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 0.75 | 78 | 0 | 4.9725 | 0 | 4.9725 | 0 | IWP_1009 | 0 | 387.855 | 0 | 387.855
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 10 | Install valve - NB 10 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 0.75 | 78 | 0 | 4.9725 | 0 | 4.9725 | 0 | IWP_1009 | 0 | 387.855 | 0 | 387.855
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 0.75 | 78 | 0 | 4.68 | 0 | 4.68 | 0 | IWP_1009 | 0 | 365.04 | 0 | 365.04
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 10 | 0 | 0 | 60 | 90 | 0 | 0 | 90 | CS | 2.9315 | 1 | 110 | 0 | 29.315 | 29.315 | 0 | 0 | IWP_1010 | 3224.65 | 0 | 0 | 3224.65
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 6.408 | 6.408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 1.9132 | 1.9132 | 0 | 0 | IWP_1010 | 210.4567 | 0 | 0 | 210.4567
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1010 | 150 | 0 | 0 | 150
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1010 | 1320 | 0 | 0 | 1320
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1010 | 900 | 0 | 0 | 900
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 6 | Field Butt Weld - NB 6 SchXST | EA | 2 | 0 | 2 | 0 | 12 | 0 | 18 | 0 | 18 | CS | 4.2237 | 0.75 | 78 | 0 | 6.3355 | 0 | 6.3355 | 0 | IWP_1010 | 0 | 494.1729 | 0 | 494.1729
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 7.0488 | 0 | 7.0488 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 10.1019 | 0 | 10.1019 | 0 | IWP_1010 | 0 | 787.95 | 0 | 787.95
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchXST | LM | 36.8324 | 0 | 36.8324 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6208 | 0.75 | 78 | 0 | 44.7739 | 0 | 44.7739 | 0 | IWP_1010 | 0 | 3492.3605 | 0 | 3492.3605
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 5.265 | 0 | 5.265 | 0 | IWP_1010 | 0 | 410.67 | 0 | 410.67
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 14.8838 | 0 | 14.8838 | 0 | IWP_1010 | 0 | 1160.9325 | 0 | 1160.9325
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 36.8324 | 0 | 36.8324 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1010 | 0 | 3683.24 | 0 | 3683.24
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 10 | 0 | 0 | 60 | 90 | 0 | 0 | 90 | CS | 2.9315 | 1 | 110 | 0 | 29.315 | 29.315 | 0 | 0 | IWP_1010 | 3224.65 | 0 | 0 | 3224.65
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 18.442 | 18.442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 5.5062 | 5.5062 | 0 | 0 | IWP_1010 | 605.6871 | 0 | 0 | 605.6871
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1010 | 150 | 0 | 0 | 150
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 24 | 24 | 0 | 0 | IWP_1010 | 2640 | 0 | 0 | 2640
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1010 | 1800 | 0 | 0 | 1800
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 6 | Field Butt Weld - NB 6 SchXST | EA | 1 | 0 | 1 | 0 | 6 | 0 | 9 | 0 | 9 | CS | 4.2237 | 0.75 | 78 | 0 | 3.1678 | 0 | 3.1678 | 0 | IWP_1010 | 0 | 247.0864 | 0 | 247.0864
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 20.2862 | 0 | 20.2862 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 29.073 | 0 | 29.073 | 0 | IWP_1010 | 0 | 2267.6925 | 0 | 2267.6925
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchXST | LM | 17.3162 | 0 | 17.3162 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6208 | 0.75 | 78 | 0 | 21.0498 | 0 | 21.0498 | 0 | IWP_1010 | 0 | 1641.8809 | 0 | 1641.8809
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 5.265 | 0 | 5.265 | 0 | IWP_1010 | 0 | 410.67 | 0 | 410.67
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 4.9613 | 0 | 4.9613 | 0 | IWP_1010 | 0 | 386.9775 | 0 | 386.9775
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 17.3162 | 0 | 17.3162 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1010 | 0 | 1731.62 | 0 | 1731.62
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 14 | 0 | 0 | 168 | 420 | 0 | 0 | 420 | CS | 7.683 | 1 | 110 | 0 | 107.562 | 107.562 | 0 | 0 | IWP_1011 | 11831.82 | 0 | 0 | 11831.82
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 2.074 | 2.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 1.1854 | 1.1854 | 0 | 0 | IWP_1011 | 130.3935 | 0 | 0 | 130.3935
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1011 | 500 | 0 | 0 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 12 | Field Butt Weld - NB 12 Sch80 | EA | 2 | 0 | 2 | 0 | 24 | 0 | 60 | 0 | 60 | CS | 11.3555 | 0.75 | 78 | 0 | 17.0332 | 0 | 17.0332 | 0 | IWP_1011 | 0 | 1328.5935 | 0 | 1328.5935
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 2.3851 | 0 | 2.3851 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 6.5693 | 0 | 6.5693 | 0 | IWP_1011 | 0 | 512.4072 | 0 | 512.4072
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 12 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 39.1127 | 0 | 39.1127 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.1137 | 0.75 | 78 | 0 | 91.3379 | 0 | 91.3379 | 0 | IWP_1011 | 0 | 7124.355 | 0 | 7124.355
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 11.9925 | 0 | 11.9925 | 0 | IWP_1011 | 0 | 935.415 | 0 | 935.415
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 4.3075 | 0 | 4.3075 | 0 | IWP_1011 | 0 | 335.9811 | 0 | 335.9811
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 12 | Field Coating - NB 12 | LM | 39.1127 | 0 | 39.1127 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 120 | 0 | 0 | 0 | 0 | IWP_1011 | 0 | 4693.518 | 0 | 4693.518
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 16 | 16 | 0 | 0 | 192 | 480 | 0 | 0 | 480 | CS | 7.683 | 1 | 110 | 0 | 122.928 | 122.928 | 0 | 0 | IWP_1012 | 13522.08 | 0 | 0 | 13522.08
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1012 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1012 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1012 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1012 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 9.297 | 9.297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 5.3137 | 5.3137 | 0 | 0 | IWP_1012 | 584.5072 | 0 | 0 | 584.5072
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1012 | 500 | 0 | 0 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 19 | 19 | 0 | 0 | IWP_1012 | 2090 | 0 | 0 | 2090
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1012 | 1700 | 0 | 0 | 1700
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 12 | Field Butt Weld - NB 12 Sch80 | EA | 1 | 0 | 1 | 0 | 12 | 0 | 30 | 0 | 30 | CS | 11.3555 | 0.75 | 78 | 0 | 8.5166 | 0 | 8.5166 | 0 | IWP_1012 | 0 | 664.2967 | 0 | 664.2967
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 10.6915 | 0 | 10.6915 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 29.4479 | 0 | 29.4479 | 0 | IWP_1012 | 0 | 2296.938 | 0 | 2296.938
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 12 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 18.0136 | 0 | 18.0136 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.1137 | 0.75 | 78 | 0 | 42.0663 | 0 | 42.0663 | 0 | IWP_1012 | 0 | 3281.1707 | 0 | 3281.1707
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1012 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1012 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 11.9925 | 0 | 11.9925 | 0 | IWP_1012 | 0 | 935.415 | 0 | 935.415
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 4.3075 | 0 | 4.3075 | 0 | IWP_1012 | 0 | 335.9811 | 0 | 335.9811
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 12 | Field Coating - NB 12 | LM | 18.0136 | 0 | 18.0136 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 120 | 0 | 0 | 0 | 0 | IWP_1012 | 0 | 2161.632 | 0 | 2161.632
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1012 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 13 | 13 | 0 | 0 | 130 | 325 | 0 | 0 | 325 | CS | 5.915 | 1 | 110 | 0 | 76.895 | 76.895 | 0 | 0 | IWP_1012 | 8458.45 | 0 | 0 | 8458.45
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 4 | 4 | 0 | 0 | 48 | 120 | 0 | 0 | 120 | CS | 7.683 | 1 | 110 | 0 | 30.732 | 30.732 | 0 | 0 | IWP_1012 | 3380.52 | 0 | 0 | 3380.52
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1012 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 Sch80 | LM | 3.618 | 3.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.46918 | 1 | 110 | 0 | 1.6975 | 1.6975 | 0 | 0 | IWP_1012 | 186.7255 | 0 | 0 | 186.7255
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 7.969 | 7.969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 4.5547 | 4.5547 | 0 | 0 | IWP_1012 | 501.0152 | 0 | 0 | 501.0152
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1012 | 500 | 0 | 0 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1012 | 250 | 0 | 0 | 250
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 19 | 19 | 0 | 0 | IWP_1012 | 2090 | 0 | 0 | 2090
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1012 | 1700 | 0 | 0 | 1700
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 10 | Install Spools - NB 10 Sch80 | LM | 4.1607 | 0 | 4.1607 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.9857 | 0.75 | 78 | 0 | 9.317 | 0 | 9.317 | 0 | IWP_1012 | 0 | 726.7247 | 0 | 726.7247
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 9.1643 | 0 | 9.1643 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 25.2415 | 0 | 25.2415 | 0 | IWP_1012 | 0 | 1968.8393 | 0 | 1968.8393
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1012 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1012 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 0.75 | 78 | 0 | 4.68 | 0 | 4.68 | 0 | IWP_1012 | 0 | 365.04 | 0 | 365.04
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1012 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 0.75 | 78 | 0 | 2.7349 | 0 | 2.7349 | 0 | IWP_1012 | 0 | 213.3213 | 0 | 213.3213
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 4.3075 | 0 | 4.3075 | 0 | IWP_1012 | 0 | 335.9811 | 0 | 335.9811
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1012 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1012 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1012 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1012 | 429 | 0 | 0 | 429
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1012 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1012 | 1001 | 0 | 0 | 1001
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1012 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1012 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1012 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1012 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1012 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1012 | 200 | 0 | 0 | 200
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1012 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1012 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1012 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1012 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1012 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1007 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 16 | 16 | 0 | 0 | 128 | 128 | 0 | 0 | 128 | CS | 3.0095 | 1 | 110 | 0 | 48.152 | 48.152 | 0 | 0 | IWP_1007 | 5296.72 | 0 | 0 | 5296.72
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1007 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchSTD | LM | 22.923 | 22.923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.26871 | 1 | 110 | 0 | 6.1597 | 6.1597 | 0 | 0 | IWP_1007 | 677.5702 | 0 | 0 | 677.5702
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1007 | 200 | 0 | 0 | 200
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 8 | Shop Hydrotest - NB 8 SchSTD | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 9.8 | 1 | 110 | 0 | 29.4 | 29.4 | 0 | 0 | IWP_1007 | 3234 | 0 | 0 | 3234
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 8 | Shop Spools Coating - NB 8 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1100 | 0 | 0 | 0 | 0 | IWP_1007 | 3300 | 0 | 0 | 3300
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchSTD | LM | 25.2153 | 0 | 25.2153 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7019 | 0.75 | 78 | 0 | 32.1846 | 0 | 32.1846 | 0 | IWP_1007 | 0 | 2510.3974 | 0 | 2510.3974
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1007 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1007 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 10.14 | 0 | 10.14 | 0 | IWP_1007 | 0 | 790.92 | 0 | 790.92
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 8 | Erection of Pipe Supports - NB 8 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7364 | 0.75 | 78 | 0 | 3.907 | 0 | 3.907 | 0 | IWP_1007 | 0 | 304.7448 | 0 | 304.7448
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1012 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 2 | 2 | 0 | 0 | 16 | 16 | 0 | 0 | 16 | CS | 3.0095 | 1 | 110 | 0 | 6.019 | 6.019 | 0 | 0 | IWP_1012 | 662.09 | 0 | 0 | 662.09
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 8 | 0 | 0 | 96 | 144 | 0 | 0 | 144 | CS | 4.7255 | 1 | 110 | 0 | 37.804 | 37.804 | 0 | 0 | IWP_1012 | 4158.44 | 0 | 0 | 4158.44
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1012 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1012 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1012 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 2.86 | 1 | 110 | 0 | 2.86 | 2.86 | 0 | 0 | IWP_1012 | 314.6 | 0 | 0 | 314.6
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1012 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 SchSTD | LM | 11.999 | 11.999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.40947 | 1 | 110 | 0 | 4.9132 | 4.9132 | 0 | 0 | IWP_1012 | 540.4538 | 0 | 0 | 540.4538
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1012 | 250 | 0 | 0 | 250
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12.2 | 1 | 110 | 0 | 12.2 | 12.2 | 0 | 0 | IWP_1012 | 1342 | 0 | 0 | 1342
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1012 | 1700 | 0 | 0 | 1700
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 SchSTD | LM | 13.7988 | 0 | 13.7988 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.6274 | 0.75 | 78 | 0 | 27.1916 | 0 | 27.1916 | 0 | IWP_1012 | 0 | 2120.9433 | 0 | 2120.9433
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1012 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1012 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1012 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1012 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1012 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 7.995 | 0 | 7.995 | 0 | IWP_1012 | 0 | 623.61 | 0 | 623.61
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 2.8716 | 0 | 2.8716 | 0 | IWP_1012 | 0 | 223.9874 | 0 | 223.9874
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1013 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1013 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1013 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1013 | 429 | 0 | 0 | 429
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1013 | 1001 | 0 | 0 | 1001
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1013 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1013 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1013 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1013 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1013 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1013 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1013 | 200 | 0 | 0 | 200
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1013 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1013 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1013 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1013 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1013 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1013 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 3.85 | 3.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.72254 | 0.72254 | 0 | 0 | IWP_1013 | 79.4796 | 0 | 0 | 79.4796
Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1013 | 200 | 0 | 0 | 200
Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 4.235 | 0 | 4.235 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 3.7933 | 0 | 3.7933 | 0 | IWP_1013 | 0 | 295.8809 | 0 | 295.8809
Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1013 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1013 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.365 | 0 | 1.365 | 0 | IWP_1013 | 0 | 106.47 | 0 | 106.47
Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1013 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1013 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 11.732 | 11.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 2.2018 | 2.2018 | 0 | 0 | IWP_1013 | 242.196 | 0 | 0 | 242.196
Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1013 | 300 | 0 | 0 | 300
Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1013 | 616 | 0 | 0 | 616
Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1013 | 500 | 0 | 0 | 500
Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 12.9052 | 0 | 12.9052 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 11.5594 | 0 | 11.5594 | 0 | IWP_1013 | 0 | 901.6297 | 0 | 901.6297
Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.0237 | 0 | 1.0237 | 0 | IWP_1013 | 0 | 79.8525 | 0 | 79.8525
Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1013 | 0 | 117 | 0 | 117
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1013 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 6.374 | 6.374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.1962 | 1.1962 | 0 | 0 | IWP_1013 | 131.5852 | 0 | 0 | 131.5852
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1013 | 500 | 0 | 0 | 500
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1013 | 616 | 0 | 0 | 616
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1013 | 500 | 0 | 0 | 500
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 7.0114 | 0 | 7.0114 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 6.2802 | 0 | 6.2802 | 0 | IWP_1013 | 0 | 489.8558 | 0 | 489.8558
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1013 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 2.3887 | 0 | 2.3887 | 0 | IWP_1013 | 0 | 186.3225 | 0 | 186.3225
Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1013 | 0 | 117 | 0 | 117
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1013 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1013 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 2 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.52 | 0.52 | 0 | 0 | IWP_1013 | 57.2 | 0 | 0 | 57.2
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1013 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.52 | 0.52 | 0 | 0 | IWP_1013 | 57.2 | 0 | 0 | 57.2
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 7.304 | 7.304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.3708 | 1.3708 | 0 | 0 | IWP_1013 | 150.7842 | 0 | 0 | 150.7842
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1013 | 50 | 0 | 0 | 50
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1013 | 500 | 0 | 0 | 500
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1013 | 616 | 0 | 0 | 616
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1013 | 500 | 0 | 0 | 500
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 8.0344 | 0 | 8.0344 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 7.1965 | 0 | 7.1965 | 0 | IWP_1013 | 0 | 561.3283 | 0 | 561.3283
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1013 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.7062 | 0 | 1.7062 | 0 | IWP_1013 | 0 | 133.0875 | 0 | 133.0875
Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1013 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1013 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 SchSTD | EA | 18 | 18 | 0 | 0 | 216 | 324 | 0 | 0 | 324 | CS | 4.7255 | 1 | 110 | 0 | 85.059 | 85.059 | 0 | 0 | IWP_1013 | 9356.49 | 0 | 0 | 9356.49
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 4.42 | 1 | 110 | 0 | 4.42 | 4.42 | 0 | 0 | IWP_1013 | 486.2 | 0 | 0 | 486.2
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 SchSTD | LM | 20.519 | 20.519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.40947 | 1 | 110 | 0 | 8.4019 | 8.4019 | 0 | 0 | IWP_1013 | 924.2079 | 0 | 0 | 924.2079
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1013 | 4500 | 0 | 0 | 4500
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1013 | 150 | 0 | 0 | 150
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 SchSTD | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12.2 | 1 | 110 | 0 | 24.4 | 24.4 | 0 | 0 | IWP_1013 | 2684 | 0 | 0 | 2684
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1013 | 3400 | 0 | 0 | 3400
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 12 | Field Butt Weld - NB 12 SchSTD | EA | 1 | 0 | 1 | 0 | 12 | 0 | 18 | 0 | 18 | CS | 7.1656 | 0.75 | 78 | 0 | 5.3742 | 0 | 5.3742 | 0 | IWP_1013 | 0 | 419.1876 | 0 | 419.1876
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 SchSTD | LM | 23.5968 | 0 | 23.5968 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.6274 | 0.75 | 78 | 0 | 46.4992 | 0 | 46.4992 | 0 | IWP_1013 | 0 | 3626.9385 | 0 | 3626.9385
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 12 | Erection of Field Run Pipe - NB 12 SchSTD | LM | 18.4242 | 0 | 18.4242 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.218 | 0.75 | 78 | 0 | 30.648 | 0 | 30.648 | 0 | IWP_1013 | 0 | 2390.5413 | 0 | 2390.5413
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1013 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.365 | 0 | 1.365 | 0 | IWP_1013 | 0 | 106.47 | 0 | 106.47
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL150 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.42 | 0.75 | 78 | 0 | 14.9175 | 0 | 14.9175 | 0 | IWP_1013 | 0 | 1163.565 | 0 | 1163.565
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 8.6149 | 0 | 8.6149 | 0 | IWP_1013 | 0 | 671.9622 | 0 | 671.9622
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 600 | 150-60-F-610 | 150-60-F-610 - Field X-Ray | 12 | Field X-Ray - NB 12 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 1500 | 0 | 0 | 0 | 0 | IWP_1013 | 0 | 1500 | 0 | 1500
Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 12 | Field Coating - NB 12 | LM | 18.4242 | 0 | 18.4242 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 120 | 0 | 0 | 0 | 0 | IWP_1013 | 0 | 2210.898 | 0 | 2210.898
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1014 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 SchSTD | EA | 18 | 18 | 0 | 0 | 216 | 324 | 0 | 0 | 324 | CS | 4.7255 | 1 | 110 | 0 | 85.059 | 85.059 | 0 | 0 | IWP_1014 | 9356.49 | 0 | 0 | 9356.49
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1014 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1014 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1014 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 2.86 | 1 | 110 | 0 | 2.86 | 2.86 | 0 | 0 | IWP_1014 | 314.6 | 0 | 0 | 314.6
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 4.42 | 1 | 110 | 0 | 4.42 | 4.42 | 0 | 0 | IWP_1014 | 486.2 | 0 | 0 | 486.2
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1014 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1014 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 SchSTD | LM | 23.572 | 23.572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.40947 | 1 | 110 | 0 | 9.652 | 9.652 | 0 | 0 | IWP_1014 | 1061.7198 | 0 | 0 | 1061.7198
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1014 | 250 | 0 | 0 | 250
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1014 | 4500 | 0 | 0 | 4500
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1014 | 150 | 0 | 0 | 150
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 SchSTD | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12.2 | 1 | 110 | 0 | 36.6 | 36.6 | 0 | 0 | IWP_1014 | 4026 | 0 | 0 | 4026
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1014 | 5100 | 0 | 0 | 5100
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 SchSTD | LM | 27.1078 | 0 | 27.1078 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.6274 | 0.75 | 78 | 0 | 53.4178 | 0 | 53.4178 | 0 | IWP_1014 | 0 | 4166.5868 | 0 | 4166.5868
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1014 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1014 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install Blind - NB 12 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.59 | 0.75 | 78 | 0 | 4.1925 | 0 | 4.1925 | 0 | IWP_1014 | 0 | 327.015 | 0 | 327.015
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install valve - NB 12 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.59 | 0.75 | 78 | 0 | 8.385 | 0 | 8.385 | 0 | IWP_1014 | 0 | 654.03 | 0 | 654.03
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.365 | 0 | 1.365 | 0 | IWP_1014 | 0 | 106.47 | 0 | 106.47
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL150 | EA | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.42 | 0.75 | 78 | 0 | 23.205 | 0 | 23.205 | 0 | IWP_1014 | 0 | 1809.99 | 0 | 1809.99
Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 2.8716 | 0 | 2.8716 | 0 | IWP_1014 | 0 | 223.9874 | 0 | 223.9874
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 1 | 1 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | CS | 3.0095 | 1 | 110 | 0 | 3.0095 | 3.0095 | 0 | 0 | IWP_1007 | 331.045 | 0 | 0 | 331.045
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchSTD | LM | 2.941 | 2.941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.26871 | 1 | 110 | 0 | 0.79029 | 0.79029 | 0 | 0 | IWP_1007 | 86.9316 | 0 | 0 | 86.9316
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1007 | 100 | 0 | 0 | 100
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchSTD | LM | 3.2351 | 0 | 3.2351 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7019 | 0.75 | 78 | 0 | 4.1293 | 0 | 4.1293 | 0 | IWP_1007 | 0 | 322.0817 | 0 | 322.0817
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.73 | 0.75 | 78 | 0 | 1.0238 | 0 | 1.0238 | 0 | IWP_1007 | 0 | 79.8525 | 0 | 79.8525
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1014 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 2 | 2 | 0 | 0 | 16 | 16 | 0 | 0 | 16 | CS | 3.0095 | 1 | 110 | 0 | 6.019 | 6.019 | 0 | 0 | IWP_1014 | 662.09 | 0 | 0 | 662.09
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 8 | 0 | 0 | 96 | 144 | 0 | 0 | 144 | CS | 4.7255 | 1 | 110 | 0 | 37.804 | 37.804 | 0 | 0 | IWP_1014 | 4158.44 | 0 | 0 | 4158.44
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 4.42 | 1 | 110 | 0 | 4.42 | 4.42 | 0 | 0 | IWP_1014 | 486.2 | 0 | 0 | 486.2
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 SchSTD | LM | 4.841 | 4.841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.40947 | 1 | 110 | 0 | 1.9822 | 1.9822 | 0 | 0 | IWP_1014 | 218.0462 | 0 | 0 | 218.0462
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1014 | 2000 | 0 | 0 | 2000
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1014 | 150 | 0 | 0 | 150
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1014 | 200 | 0 | 0 | 200
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12.2 | 1 | 110 | 0 | 12.2 | 12.2 | 0 | 0 | IWP_1014 | 1342 | 0 | 0 | 1342
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1014 | 1700 | 0 | 0 | 1700
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 SchSTD | LM | 5.5671 | 0 | 5.5671 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.6274 | 0.75 | 78 | 0 | 10.9705 | 0 | 10.9705 | 0 | IWP_1014 | 0 | 855.6952 | 0 | 855.6952
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1014 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install valve - NB 12 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.59 | 0.75 | 78 | 0 | 8.385 | 0 | 8.385 | 0 | IWP_1014 | 0 | 654.03 | 0 | 654.03
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install Blind - NB 12 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.59 | 0.75 | 78 | 0 | 4.1925 | 0 | 4.1925 | 0 | IWP_1014 | 0 | 327.015 | 0 | 327.015
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.365 | 0 | 1.365 | 0 | IWP_1014 | 0 | 106.47 | 0 | 106.47
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.73 | 0.75 | 78 | 0 | 1.0238 | 0 | 1.0238 | 0 | IWP_1014 | 0 | 79.8525 | 0 | 79.8525
Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL150 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.42 | 0.75 | 78 | 0 | 14.9175 | 0 | 14.9175 | 0 | IWP_1014 | 0 | 1163.565 | 0 | 1163.565
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1015 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 18 | 18 | 0 | 0 | 216 | 540 | 0 | 0 | 540 | CS | 7.683 | 1 | 110 | 0 | 138.294 | 138.294 | 0 | 0 | IWP_1015 | 15212.34 | 0 | 0 | 15212.34
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1015 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 18.878 | 18.878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 10.7897 | 10.7897 | 0 | 0 | IWP_1015 | 1186.8697 | 0 | 0 | 1186.8697
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1015 | 750 | 0 | 0 | 750
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 38 | 38 | 0 | 0 | IWP_1015 | 4180 | 0 | 0 | 4180
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1015 | 3400 | 0 | 0 | 3400
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 21.7097 | 0 | 21.7097 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 59.7954 | 0 | 59.7954 | 0 | IWP_1015 | 0 | 4664.0417 | 0 | 4664.0417
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1015 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install Blind - NB 12 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 6.1425 | 0 | 6.1425 | 0 | IWP_1015 | 0 | 479.115 | 0 | 479.115
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install valve - NB 12 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 12.285 | 0 | 12.285 | 0 | IWP_1015 | 0 | 958.23 | 0 | 958.23
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1015 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 23.985 | 0 | 23.985 | 0 | IWP_1015 | 0 | 1870.83 | 0 | 1870.83
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 4.3075 | 0 | 4.3075 | 0 | IWP_1015 | 0 | 335.9811 | 0 | 335.9811
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 16 | 16 | 0 | 0 | 192 | 480 | 0 | 0 | 480 | CS | 7.683 | 1 | 110 | 0 | 122.928 | 122.928 | 0 | 0 | IWP_1015 | 13522.08 | 0 | 0 | 13522.08
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1015 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1015 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1015 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1015 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 11.56 | 11.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 6.6071 | 6.6071 | 0 | 0 | IWP_1015 | 726.7832 | 0 | 0 | 726.7832
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1015 | 500 | 0 | 0 | 500
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 19 | 19 | 0 | 0 | IWP_1015 | 2090 | 0 | 0 | 2090
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1015 | 1700 | 0 | 0 | 1700
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 12 | Field Butt Weld - NB 12 Sch80 | EA | 1 | 0 | 1 | 0 | 12 | 0 | 30 | 0 | 30 | CS | 11.3555 | 0.75 | 78 | 0 | 8.5166 | 0 | 8.5166 | 0 | IWP_1015 | 0 | 664.2967 | 0 | 664.2967
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 13.294 | 0 | 13.294 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 36.6159 | 0 | 36.6159 | 0 | IWP_1015 | 0 | 2856.0399 | 0 | 2856.0399
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 12 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 35.2015 | 0 | 35.2015 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.1137 | 0.75 | 78 | 0 | 82.2044 | 0 | 82.2044 | 0 | IWP_1015 | 0 | 6411.9404 | 0 | 6411.9404
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1015 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1015 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 15.99 | 0 | 15.99 | 0 | IWP_1015 | 0 | 1247.22 | 0 | 1247.22
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 11.4865 | 0 | 11.4865 | 0 | IWP_1015 | 0 | 895.9497 | 0 | 895.9497
Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 12 | Field Coating - NB 12 | LM | 35.2015 | 0 | 35.2015 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 120 | 0 | 0 | 0 | 0 | IWP_1015 | 0 | 4224.18 | 0 | 4224.18
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 10 | 0 | 0 | 60 | 90 | 0 | 0 | 90 | CS | 2.9315 | 1 | 110 | 0 | 29.315 | 29.315 | 0 | 0 | IWP_1016 | 3224.65 | 0 | 0 | 3224.65
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 6.439 | 6.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 1.9225 | 1.9225 | 0 | 0 | IWP_1016 | 211.4749 | 0 | 0 | 211.4749
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1016 | 150 | 0 | 0 | 150
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1016 | 1320 | 0 | 0 | 1320
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1016 | 900 | 0 | 0 | 900
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 6 | Field Butt Weld - NB 6 SchXST | EA | 2 | 0 | 2 | 0 | 12 | 0 | 18 | 0 | 18 | CS | 4.2237 | 0.75 | 78 | 0 | 6.3355 | 0 | 6.3355 | 0 | IWP_1016 | 0 | 494.1729 | 0 | 494.1729
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 7.0829 | 0 | 7.0829 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 10.1508 | 0 | 10.1508 | 0 | IWP_1016 | 0 | 791.7619 | 0 | 791.7619
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchXST | LM | 36.8324 | 0 | 36.8324 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6208 | 0.75 | 78 | 0 | 44.7739 | 0 | 44.7739 | 0 | IWP_1016 | 0 | 3492.3605 | 0 | 3492.3605
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 5.265 | 0 | 5.265 | 0 | IWP_1016 | 0 | 410.67 | 0 | 410.67
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 16.1241 | 0 | 16.1241 | 0 | IWP_1016 | 0 | 1257.6769 | 0 | 1257.6769
Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 36.8324 | 0 | 36.8324 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1016 | 0 | 3683.24 | 0 | 3683.24
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 10 | 0 | 0 | 60 | 90 | 0 | 0 | 90 | CS | 2.9315 | 1 | 110 | 0 | 29.315 | 29.315 | 0 | 0 | IWP_1016 | 3224.65 | 0 | 0 | 3224.65
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 18.698 | 18.698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 5.5827 | 5.5827 | 0 | 0 | IWP_1016 | 614.0949 | 0 | 0 | 614.0949
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1016 | 150 | 0 | 0 | 150
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 24 | 24 | 0 | 0 | IWP_1016 | 2640 | 0 | 0 | 2640
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1016 | 1800 | 0 | 0 | 1800
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 6 | Field Butt Weld - NB 6 SchXST | EA | 1 | 0 | 1 | 0 | 6 | 0 | 9 | 0 | 9 | CS | 4.2237 | 0.75 | 78 | 0 | 3.1678 | 0 | 3.1678 | 0 | IWP_1016 | 0 | 247.0864 | 0 | 247.0864
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 20.5678 | 0 | 20.5678 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 29.4766 | 0 | 29.4766 | 0 | IWP_1016 | 0 | 2299.1712 | 0 | 2299.1712
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchXST | LM | 17.3162 | 0 | 17.3162 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6208 | 0.75 | 78 | 0 | 21.0498 | 0 | 21.0498 | 0 | IWP_1016 | 0 | 1641.8809 | 0 | 1641.8809
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 5.265 | 0 | 5.265 | 0 | IWP_1016 | 0 | 410.67 | 0 | 410.67
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 4.9613 | 0 | 4.9613 | 0 | IWP_1016 | 0 | 386.9775 | 0 | 386.9775
Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 17.3162 | 0 | 17.3162 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1016 | 0 | 1731.62 | 0 | 1731.62
Proj_A | Area_10 | TR | TR-ZL01-8086 | ISO2039 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8102 | ISO2009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8104 | ISO3095 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8105 | ISO3096 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8106 | ISO3097 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8106 | ISO4001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8107 | ISO4002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8108 | ISO4003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8109 | ISO4004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8110 | ISO4005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8111 | ISO4006 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8112 | ISO4007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1017 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8113 | ISO4018 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_10 | TR | TR-ZL01-8114 | ISO4020 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_10 | TR | TR-ZL02-8115 | ISO4019 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1017 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 11 | 11 | 0 | 0 | 22 | 33 | 0 | 0 | 33 | CS | 1.1765 | 1 | 110 | 0 | 12.9415 | 12.9415 | 0 | 0 | IWP_1017 | 1423.565 | 0 | 0 | 1423.565
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 12 | 12 | 0 | 0 | 36 | 36 | 0 | 0 | 36 | CS | 1.3715 | 1 | 110 | 0 | 16.458 | 16.458 | 0 | 0 | IWP_1017 | 1810.38 | 0 | 0 | 1810.38
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1017 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1017 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 SchXST | EA | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | CS | 1.56 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1017 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 12.178 | 12.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 2.1297 | 2.1297 | 0 | 0 | IWP_1017 | 234.2621 | 0 | 0 | 234.2621
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 400 | 0 | 0 | 400
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 550 | 0 | 0 | 550
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 650 | 0 | 0 | 650
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 6 | 6 | 0 | 0 | IWP_1017 | 660 | 0 | 0 | 660
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1017 | 600 | 0 | 0 | 600
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 13.3958 | 0 | 13.3958 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 11.6988 | 0 | 11.6988 | 0 | IWP_1017 | 0 | 912.5081 | 0 | 912.5081
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1017 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.56 | 0 | 1.56 | 0 | IWP_1017 | 0 | 121.68 | 0 | 121.68
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1017 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 8 | 8 | 0 | 0 | 24 | 24 | 0 | 0 | 24 | CS | 1.3715 | 1 | 110 | 0 | 10.972 | 10.972 | 0 | 0 | IWP_1017 | 1206.92 | 0 | 0 | 1206.92
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1017 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL6000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL6000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 3.38 | 1 | 110 | 0 | 3.38 | 3.38 | 0 | 0 | IWP_1017 | 371.8 | 0 | 0 | 371.8
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 4.483 | 4.483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.78397 | 0.78397 | 0 | 0 | IWP_1017 | 86.2372 | 0 | 0 | 86.2372
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 250 | 0 | 0 | 250
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 400 | 0 | 0 | 400
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 4.9313 | 0 | 4.9313 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 4.3066 | 0 | 4.3066 | 0 | IWP_1017 | 0 | 335.9151 | 0 | 335.9151
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1017 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1017 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 16 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 1.1765 | 1 | 110 | 0 | 18.824 | 18.824 | 0 | 0 | IWP_1017 | 2070.64 | 0 | 0 | 2070.64
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 14 | 14 | 0 | 0 | 42 | 42 | 0 | 0 | 42 | CS | 1.3715 | 1 | 110 | 0 | 19.201 | 19.201 | 0 | 0 | IWP_1017 | 2112.11 | 0 | 0 | 2112.11
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1017 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1017 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 SchXST | EA | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | CS | 1.56 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1017 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.083 | 0.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.015577 | 0.015577 | 0 | 0 | IWP_1017 | 1.7135 | 0 | 0 | 1.7135
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 12.001 | 12.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 2.0987 | 2.0987 | 0 | 0 | IWP_1017 | 230.8573 | 0 | 0 | 230.8573
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 400 | 0 | 0 | 400
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 800 | 0 | 0 | 800
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 750 | 0 | 0 | 750
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 6 | 6 | 0 | 0 | IWP_1017 | 660 | 0 | 0 | 660
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1017 | 600 | 0 | 0 | 600
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.0913 | 0 | 0.0913 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.081779 | 0 | 0.081779 | 0 | IWP_1017 | 0 | 6.3787 | 0 | 6.3787
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 13.2011 | 0 | 13.2011 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 11.5288 | 0 | 11.5288 | 0 | IWP_1017 | 0 | 899.2454 | 0 | 899.2454
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1017 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.95 | 0 | 1.95 | 0 | IWP_1017 | 0 | 152.1 | 0 | 152.1
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1017 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1017 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 8 | 8 | 0 | 0 | 24 | 24 | 0 | 0 | 24 | CS | 1.3715 | 1 | 110 | 0 | 10.972 | 10.972 | 0 | 0 | IWP_1017 | 1206.92 | 0 | 0 | 1206.92
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1017 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL6000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL6000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 3.38 | 1 | 110 | 0 | 3.38 | 3.38 | 0 | 0 | IWP_1017 | 371.8 | 0 | 0 | 371.8
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 4.561 | 4.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.79762 | 0.79762 | 0 | 0 | IWP_1017 | 87.7377 | 0 | 0 | 87.7377
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 250 | 0 | 0 | 250
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 400 | 0 | 0 | 400
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 6 | 6 | 0 | 0 | IWP_1017 | 660 | 0 | 0 | 660
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1017 | 600 | 0 | 0 | 600
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 5.0171 | 0 | 5.0171 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 4.3815 | 0 | 4.3815 | 0 | IWP_1017 | 0 | 341.7597 | 0 | 341.7597
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1017 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1017 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.1765 | 1 | 110 | 0 | 3.5295 | 3.5295 | 0 | 0 | IWP_1017 | 388.245 | 0 | 0 | 388.245
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.083 | 0.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.015577 | 0.015577 | 0 | 0 | IWP_1017 | 1.7135 | 0 | 0 | 1.7135
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 150 | 0 | 0 | 150
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.0913 | 0 | 0.0913 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.081779 | 0 | 0.081779 | 0 | IWP_1017 | 0 | 6.3787 | 0 | 6.3787
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1017 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1017 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1017 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1017 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.078 | 1.078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.20231 | 0.20231 | 0 | 0 | IWP_1017 | 22.2543 | 0 | 0 | 22.2543
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 150 | 0 | 0 | 150
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 450 | 0 | 0 | 450
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1858 | 0 | 1.1858 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.0621 | 0 | 1.0621 | 0 | IWP_1017 | 0 | 82.8466 | 0 | 82.8466
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1017 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.95 | 0 | 1.95 | 0 | IWP_1017 | 0 | 152.1 | 0 | 152.1
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1017 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1017 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 100 | 0 | 0 | 100
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1017 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1017 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1017 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1017 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 8 | 8 | 0 | 0 | 8 | 10 | 0 | 0 | 10 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1017 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 1.958 | 1.958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.30065 | 0.30065 | 0 | 0 | IWP_1017 | 33.0718 | 0 | 0 | 33.0718
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.634 | 0.634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.11898 | 0.11898 | 0 | 0 | IWP_1017 | 13.0883 | 0 | 0 | 13.0883
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 100 | 0 | 0 | 100
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 950 | 0 | 0 | 950
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 100 | 0 | 0 | 100
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 2.0559 | 0 | 2.0559 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 0.75 | 78 | 0 | 1.5653 | 0 | 1.5653 | 0 | IWP_1017 | 0 | 122.0912 | 0 | 122.0912
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.6974 | 0 | 0.6974 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.62467 | 0 | 0.62467 | 0 | IWP_1017 | 0 | 48.7243 | 0 | 48.7243
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1017 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.3 | 0 | 0.3 | 0 | IWP_1017 | 0 | 23.4 | 0 | 23.4
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1017 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 0.441 | 0.441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.067716 | 0.067716 | 0 | 0 | IWP_1017 | 7.4487 | 0 | 0 | 7.4487
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 300 | 0 | 0 | 300
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 0.46305 | 0 | 0.46305 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 0.75 | 78 | 0 | 0.35255 | 0 | 0.35255 | 0 | IWP_1017 | 0 | 27.4986 | 0 | 27.4986
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1017 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1017 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1017 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.78 | 1 | 110 | 0 | 7.8 | 7.8 | 0 | 0 | IWP_1017 | 858 | 0 | 0 | 858
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 8 | 8 | 0 | 0 | 8 | 10 | 0 | 0 | 10 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1017 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 2.399 | 2.399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.36837 | 0.36837 | 0 | 0 | IWP_1017 | 40.5205 | 0 | 0 | 40.5205
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.634 | 0.634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.11898 | 0.11898 | 0 | 0 | IWP_1017 | 13.0883 | 0 | 0 | 13.0883
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 100 | 0 | 0 | 100
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 1250 | 0 | 0 | 1250
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 100 | 0 | 0 | 100
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 2.519 | 0 | 2.519 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 0.75 | 78 | 0 | 1.9178 | 0 | 1.9178 | 0 | IWP_1017 | 0 | 149.5898 | 0 | 149.5898
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.6974 | 0 | 0.6974 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.62467 | 0 | 0.62467 | 0 | IWP_1017 | 0 | 48.7243 | 0 | 48.7243
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1017 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.3 | 0 | 0.3 | 0 | IWP_1017 | 0 | 23.4 | 0 | 23.4
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1017 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1017 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 100 | 0 | 0 | 100
Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1017 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1017 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1017 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1017 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.078 | 1.078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.20231 | 0.20231 | 0 | 0 | IWP_1017 | 22.2543 | 0 | 0 | 22.2543
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 150 | 0 | 0 | 150
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 450 | 0 | 0 | 450
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1858 | 0 | 1.1858 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.0621 | 0 | 1.0621 | 0 | IWP_1017 | 0 | 82.8466 | 0 | 82.8466
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1017 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.95 | 0 | 1.95 | 0 | IWP_1017 | 0 | 152.1 | 0 | 152.1
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1017 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.65 | 1 | 110 | 0 | 1.3 | 1.3 | 0 | 0 | IWP_1017 | 143 | 0 | 0 | 143
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.65 | 1 | 110 | 0 | 1.3 | 1.3 | 0 | 0 | IWP_1017 | 143 | 0 | 0 | 143
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 4 | 4 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1017 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 2000psi | EA | 4 | 4 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.04 | 1 | 110 | 0 | 4.16 | 4.16 | 0 | 0 | IWP_1017 | 457.6 | 0 | 0 | 457.6
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 CL3000 | EA | 10 | 10 | 0 | 0 | 15 | 22.5 | 0 | 0 | 22.5 | CS | 1.04 | 1 | 110 | 0 | 10.4 | 10.4 | 0 | 0 | IWP_1017 | 1144 | 0 | 0 | 1144
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 Sch160 | EA | 7 | 7 | 0 | 0 | 10.5 | 21 | 0 | 0 | 21 | CS | 1.3 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1017 | 1001 | 0 | 0 | 1001
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 SchXST | EA | 1 | 1 | 0 | 0 | 1.5 | 2.25 | 0 | 0 | 2.25 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 1.04 | 0 | 0 | IWP_1017 | 114.4 | 0 | 0 | 114.4
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 2 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.52 | 0.52 | 0 | 0 | IWP_1017 | 57.2 | 0 | 0 | 57.2
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 2 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.52 | 0.52 | 0 | 0 | IWP_1017 | 57.2 | 0 | 0 | 57.2
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1.5 | Shop handling - NB 1.5 SchXST | LM | 1.73 | 1.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.30254 | 0.30254 | 0 | 0 | IWP_1017 | 33.2792 | 0 | 0 | 33.2792
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.33 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.061932 | 0.061932 | 0 | 0 | IWP_1017 | 6.8125 | 0 | 0 | 6.8125
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 400 | 0 | 0 | 400
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1.5 | Shop X-Ray - NB 1.5 | EA | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 1100 | 0 | 0 | 1100
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 100 | 0 | 0 | 100
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1.5 | Install Spools - NB 1.5 SchXST | LM | 1.8165 | 0 | 1.8165 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1047 | 0.75 | 78 | 0 | 1.505 | 0 | 1.505 | 0 | IWP_1017 | 0 | 117.3926 | 0 | 117.3926
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.363 | 0 | 0.363 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.32514 | 0 | 0.32514 | 0 | IWP_1017 | 0 | 25.3612 | 0 | 25.3612
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1017 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1.5 | Install valve - NB 1.5 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.52 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1.5 | Flange Bolt-Up - NB 1.5 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1.5 | Erection of Pipe Supports - NB 1.5 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.5 | 0.75 | 78 | 0 | 0.375 | 0 | 0.375 | 0 | IWP_1017 | 0 | 29.25 | 0 | 29.25
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1017 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1017 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1017 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 2 | 2 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 3.77 | 1 | 110 | 0 | 7.54 | 7.54 | 0 | 0 | IWP_1017 | 829.4 | 0 | 0 | 829.4
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.718 | 0.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.13475 | 0.13475 | 0 | 0 | IWP_1017 | 14.8224 | 0 | 0 | 14.8224
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 500 | 0 | 0 | 500
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 400 | 0 | 0 | 400
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.7898 | 0 | 0.7898 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.70743 | 0 | 0.70743 | 0 | IWP_1017 | 0 | 55.1799 | 0 | 55.1799
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1017 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1017 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1017 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.65 | 1 | 110 | 0 | 1.3 | 1.3 | 0 | 0 | IWP_1017 | 143 | 0 | 0 | 143
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL800 | EA | 4 | 4 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.65 | 1 | 110 | 0 | 2.6 | 2.6 | 0 | 0 | IWP_1017 | 286 | 0 | 0 | 286
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 13 | 13 | 0 | 0 | 9.75 | 12.1875 | 0 | 0 | 12.1875 | CS | 0.65 | 1 | 110 | 0 | 8.45 | 8.45 | 0 | 0 | IWP_1017 | 929.5 | 0 | 0 | 929.5
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 12 | 12 | 0 | 0 | 9 | 11.25 | 0 | 0 | 11.25 | CS | 0.78 | 1 | 110 | 0 | 9.36 | 9.36 | 0 | 0 | IWP_1017 | 1029.6 | 0 | 0 | 1029.6
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1017 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 0.75 | Shop handling - NB 0.75 Sch160 | LM | 2.566 | 2.566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.16635 | 1 | 110 | 0 | 0.42685 | 0.42685 | 0 | 0 | IWP_1017 | 46.953 | 0 | 0 | 46.953
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.013 | 1.013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.19011 | 0.19011 | 0 | 0 | IWP_1017 | 20.9124 | 0 | 0 | 20.9124
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 1650 | 0 | 0 | 1650
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 250 | 0 | 0 | 250
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 0.75 | Install Spools - NB 0.75 Sch160 | LM | 2.6943 | 0 | 2.6943 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.045 | 0.75 | 78 | 0 | 2.1117 | 0 | 2.1117 | 0 | IWP_1017 | 0 | 164.7091 | 0 | 164.7091
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1143 | 0 | 1.1143 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.99809 | 0 | 0.99809 | 0 | IWP_1017 | 0 | 77.8513 | 0 | 77.8513
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1017 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 CL800 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.975 | 0 | 0.975 | 0 | IWP_1017 | 0 | 76.05 | 0 | 76.05
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.56 | 0 | 1.56 | 0 | IWP_1017 | 0 | 121.68 | 0 | 121.68
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 0.75 | Erection of Pipe Supports - NB 0.75 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.3 | 0.75 | 78 | 0 | 0.225 | 0 | 0.225 | 0 | IWP_1017 | 0 | 17.55 | 0 | 17.55
Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1017 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1017 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.65 | 1 | 110 | 0 | 1.3 | 1.3 | 0 | 0 | IWP_1017 | 143 | 0 | 0 | 143
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL800 | EA | 4 | 4 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.65 | 1 | 110 | 0 | 2.6 | 2.6 | 0 | 0 | IWP_1017 | 286 | 0 | 0 | 286
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 13 | 13 | 0 | 0 | 9.75 | 12.1875 | 0 | 0 | 12.1875 | CS | 0.65 | 1 | 110 | 0 | 8.45 | 8.45 | 0 | 0 | IWP_1017 | 929.5 | 0 | 0 | 929.5
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 12 | 12 | 0 | 0 | 9 | 11.25 | 0 | 0 | 11.25 | CS | 0.78 | 1 | 110 | 0 | 9.36 | 9.36 | 0 | 0 | IWP_1017 | 1029.6 | 0 | 0 | 1029.6
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1017 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 0.75 | Shop handling - NB 0.75 Sch160 | LM | 2.566 | 2.566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.16635 | 1 | 110 | 0 | 0.42685 | 0.42685 | 0 | 0 | IWP_1017 | 46.953 | 0 | 0 | 46.953
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.013 | 1.013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.19011 | 0.19011 | 0 | 0 | IWP_1017 | 20.9124 | 0 | 0 | 20.9124
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 1650 | 0 | 0 | 1650
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 250 | 0 | 0 | 250
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 0.75 | Install Spools - NB 0.75 Sch160 | LM | 2.6943 | 0 | 2.6943 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.045 | 0.75 | 78 | 0 | 2.1117 | 0 | 2.1117 | 0 | IWP_1017 | 0 | 164.7091 | 0 | 164.7091
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1143 | 0 | 1.1143 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.99809 | 0 | 0.99809 | 0 | IWP_1017 | 0 | 77.8513 | 0 | 77.8513
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1017 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 CL800 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.975 | 0 | 0.975 | 0 | IWP_1017 | 0 | 76.05 | 0 | 76.05
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1017 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.56 | 0 | 1.56 | 0 | IWP_1017 | 0 | 121.68 | 0 | 121.68
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 0.75 | Erection of Pipe Supports - NB 0.75 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.3 | 0.75 | 78 | 0 | 0.225 | 0 | 0.225 | 0 | IWP_1017 | 0 | 17.55 | 0 | 17.55
Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1017 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1017 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.65 | 1 | 110 | 0 | 1.3 | 1.3 | 0 | 0 | IWP_1017 | 143 | 0 | 0 | 143
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.65 | 1 | 110 | 0 | 1.3 | 1.3 | 0 | 0 | IWP_1017 | 143 | 0 | 0 | 143
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 4 | 4 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1017 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 2000psi | EA | 4 | 4 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.04 | 1 | 110 | 0 | 4.16 | 4.16 | 0 | 0 | IWP_1017 | 457.6 | 0 | 0 | 457.6
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 CL3000 | EA | 10 | 10 | 0 | 0 | 15 | 22.5 | 0 | 0 | 22.5 | CS | 1.04 | 1 | 110 | 0 | 10.4 | 10.4 | 0 | 0 | IWP_1017 | 1144 | 0 | 0 | 1144
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 Sch160 | EA | 7 | 7 | 0 | 0 | 10.5 | 21 | 0 | 0 | 21 | CS | 1.3 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1017 | 1001 | 0 | 0 | 1001
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 SchXST | EA | 1 | 1 | 0 | 0 | 1.5 | 2.25 | 0 | 0 | 2.25 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 1.04 | 0 | 0 | IWP_1017 | 114.4 | 0 | 0 | 114.4
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 2 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.52 | 0.52 | 0 | 0 | IWP_1017 | 57.2 | 0 | 0 | 57.2
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 2 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.52 | 0.52 | 0 | 0 | IWP_1017 | 57.2 | 0 | 0 | 57.2
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1.5 | Shop handling - NB 1.5 SchXST | LM | 1.73 | 1.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.30254 | 0.30254 | 0 | 0 | IWP_1017 | 33.2792 | 0 | 0 | 33.2792
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.33 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.061932 | 0.061932 | 0 | 0 | IWP_1017 | 6.8125 | 0 | 0 | 6.8125
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 400 | 0 | 0 | 400
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1.5 | Shop X-Ray - NB 1.5 | EA | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 1100 | 0 | 0 | 1100
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 100 | 0 | 0 | 100
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1.5 | Install Spools - NB 1.5 SchXST | LM | 1.8165 | 0 | 1.8165 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1047 | 0.75 | 78 | 0 | 1.505 | 0 | 1.505 | 0 | IWP_1017 | 0 | 117.3926 | 0 | 117.3926
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.363 | 0 | 0.363 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.32514 | 0 | 0.32514 | 0 | IWP_1017 | 0 | 25.3612 | 0 | 25.3612
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1017 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1.5 | Install valve - NB 1.5 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.52 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1017 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1.5 | Flange Bolt-Up - NB 1.5 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1017 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1.5 | Erection of Pipe Supports - NB 1.5 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.5 | 0.75 | 78 | 0 | 0.375 | 0 | 0.375 | 0 | IWP_1017 | 0 | 29.25 | 0 | 29.25
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1018 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1018 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1018 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1018 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 2 | 2 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 3.77 | 1 | 110 | 0 | 7.54 | 7.54 | 0 | 0 | IWP_1018 | 829.4 | 0 | 0 | 829.4
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1018 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.718 | 0.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.13475 | 0.13475 | 0 | 0 | IWP_1018 | 14.8224 | 0 | 0 | 14.8224
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1018 | 500 | 0 | 0 | 500
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1018 | 400 | 0 | 0 | 400
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.7898 | 0 | 0.7898 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.70743 | 0 | 0.70743 | 0 | IWP_1018 | 0 | 55.1799 | 0 | 55.1799
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1018 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1018 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1018 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1018 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1018 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1018 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1018 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1018 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1018 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1018 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1018 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1018 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.96 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.17198 | 0.17198 | 0 | 0 | IWP_1018 | 18.9175 | 0 | 0 | 18.9175
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.878 | 1.878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.35245 | 0.35245 | 0 | 0 | IWP_1018 | 38.7695 | 0 | 0 | 38.7695
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1018 | 150 | 0 | 0 | 150
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1018 | 50 | 0 | 0 | 50
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.008 | 0 | 1.008 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.88031 | 0 | 0.88031 | 0 | IWP_1018 | 0 | 68.6639 | 0 | 68.6639
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.0658 | 0 | 2.0658 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.8504 | 0 | 1.8504 | 0 | IWP_1018 | 0 | 144.3284 | 0 | 144.3284
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1018 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1018 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1018 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1018 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1018 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 16 | 16 | 0 | 0 | 48 | 48 | 0 | 0 | 48 | CS | 1.3715 | 1 | 110 | 0 | 21.944 | 21.944 | 0 | 0 | IWP_1018 | 2413.84 | 0 | 0 | 2413.84
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 17.019 | 17.019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 2.9762 | 2.9762 | 0 | 0 | IWP_1018 | 327.386 | 0 | 0 | 327.386
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1018 | 800 | 0 | 0 | 800
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1018 | 1320 | 0 | 0 | 1320
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1018 | 1200 | 0 | 0 | 1200
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 18.7209 | 0 | 18.7209 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 16.3493 | 0 | 16.3493 | 0 | IWP_1018 | 0 | 1275.2485 | 0 | 1275.2485
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install Inlines - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 1.4625 | 0 | 1.4625 | 0 | IWP_1018 | 0 | 114.075 | 0 | 114.075
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install valve - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 1.4625 | 0 | 1.4625 | 0 | IWP_1018 | 0 | 114.075 | 0 | 114.075
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install Blind - NB 3 CL300 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 1.4625 | 0 | 1.4625 | 0 | IWP_1018 | 0 | 114.075 | 0 | 114.075
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL300 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.9488 | 0 | 3.9488 | 0 | IWP_1018 | 0 | 308.0025 | 0 | 308.0025
Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 5.625 | 0 | 5.625 | 0 | IWP_1018 | 0 | 438.75 | 0 | 438.75
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1019 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 SchXST | EA | 10 | 10 | 0 | 0 | 160 | 320 | 0 | 0 | 320 | CS | 16.12 | 1 | 110 | 0 | 161.2 | 161.2 | 0 | 0 | IWP_1019 | 17732 | 0 | 0 | 17732
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 24 | Shop Butt Weld - NB 24 Sch40 | EA | 12 | 12 | 0 | 0 | 288 | 720 | 0 | 0 | 720 | CS | 18.3647 | 1 | 110 | 0 | 220.376 | 220.376 | 0 | 0 | IWP_1019 | 24241.36 | 0 | 0 | 24241.36
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1019 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 SchXST | LM | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 0.31734 | 0.31734 | 0 | 0 | IWP_1019 | 34.9072 | 0 | 0 | 34.9072
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 24 | Shop handling - NB 24 Sch40 | LM | 14.46 | 14.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.89571 | 1 | 110 | 0 | 12.952 | 12.952 | 0 | 0 | IWP_1019 | 1424.7211 | 0 | 0 | 1424.7211
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1019 | 2500 | 0 | 0 | 2500
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 300 | 0 | 0 | 300
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 24 | Shop X-Ray - NB 24 | EA | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1019 | 6000 | 0 | 0 | 6000
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 24 | Shop Hydrotest - NB 24 Sch40 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 41.2 | 41.2 | 0 | 0 | IWP_1019 | 4532 | 0 | 0 | 4532
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 24 | Shop Spools Coating - NB 24 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2880 | 0 | 0 | 0 | 0 | IWP_1019 | 2880 | 0 | 0 | 2880
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 16 | Install Spools - NB 16 SchXST | LM | 0.46 | 0 | 0 | 0.46 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 1 | 110 | 0 | 2.3486 | 0 | 0 | 2.3486 | IWP_1019 | 0 | 0 | 258.3415 | 258.3415
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 24 | Install Spools - NB 24 Sch40 | LM | 16.629 | 0 | 0 | 16.629 | 0 | 0 | 0 | 0 | 0 | CS | 5.7923 | 1 | 110 | 0 | 96.3198 | 0 | 0 | 96.3198 | IWP_1019 | 0 | 0 | 10595.1759 | 10595.1759
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 2.08 | 0 | 0 | 2.08 | IWP_1019 | 0 | 0 | 228.8 | 228.8
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Blind - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install valve - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 4.16 | 0 | 0 | 4.16 | IWP_1019 | 0 | 0 | 457.6 | 457.6
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL300 | EA | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | CS | 6.37 | 1 | 110 | 0 | 15.925 | 0 | 0 | 15.925 | IWP_1019 | 0 | 0 | 1751.75 | 1751.75
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 24 | Flange Bolt-Up - NB 24 CL300 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 9.62 | 1 | 110 | 0 | 19.24 | 0 | 0 | 19.24 | IWP_1019 | 0 | 0 | 2116.4 | 2116.4
Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 24 | Erection of Pipe Supports - NB 24 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 2.5655 | 1 | 110 | 0 | 5.131 | 0 | 0 | 5.131 | IWP_1019 | 0 | 0 | 564.412 | 564.412
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1019 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 SchXST | EA | 4 | 4 | 0 | 0 | 64 | 128 | 0 | 0 | 128 | CS | 16.12 | 1 | 110 | 0 | 64.48 | 64.48 | 0 | 0 | IWP_1019 | 7092.8 | 0 | 0 | 7092.8
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1019 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 SchXST | LM | 2.618 | 2.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 2.077 | 2.077 | 0 | 0 | IWP_1019 | 228.4677 | 0 | 0 | 228.4677
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1019 | 1000 | 0 | 0 | 1000
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 400 | 0 | 0 | 400
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 16 | Install Spools - NB 16 SchXST | LM | 3.0107 | 0 | 0 | 3.0107 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 1 | 110 | 0 | 15.3713 | 0 | 0 | 15.3713 | IWP_1019 | 0 | 0 | 1690.8454 | 1690.8454
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Blind - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Inlines - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install valve - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 0 | 0 | 1.04 | IWP_1019 | 0 | 0 | 114.4 | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL300 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 6.37 | 1 | 110 | 0 | 19.11 | 0 | 0 | 19.11 | IWP_1019 | 0 | 0 | 2102.1 | 2102.1
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 1 | 110 | 0 | 2.1107 | 0 | 0 | 2.1107 | IWP_1019 | 0 | 0 | 232.1716 | 232.1716
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1019 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 2 | 2 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | CS | 1.3715 | 1 | 110 | 0 | 2.743 | 2.743 | 0 | 0 | IWP_1019 | 301.73 | 0 | 0 | 301.73
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 SchSTD | EA | 2 | 2 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 4.1782 | 1 | 110 | 0 | 8.3564 | 8.3564 | 0 | 0 | IWP_1019 | 919.204 | 0 | 0 | 919.204
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 SchXST | EA | 4 | 4 | 0 | 0 | 64 | 128 | 0 | 0 | 128 | CS | 16.12 | 1 | 110 | 0 | 64.48 | 64.48 | 0 | 0 | IWP_1019 | 7092.8 | 0 | 0 | 7092.8
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1019 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1019 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1019 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1019 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 1 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 2.21 | 1 | 110 | 0 | 2.21 | 2.21 | 0 | 0 | IWP_1019 | 243.1 | 0 | 0 | 243.1
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 4.42 | 1 | 110 | 0 | 4.42 | 4.42 | 0 | 0 | IWP_1019 | 486.2 | 0 | 0 | 486.2
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 3 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 1 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 7.67 | 1 | 110 | 0 | 7.67 | 7.67 | 0 | 0 | IWP_1019 | 843.7 | 0 | 0 | 843.7
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1019 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1019 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1019 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 SchSTD | LM | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.33696 | 1 | 110 | 0 | 0.40435 | 0.40435 | 0 | 0 | IWP_1019 | 44.4785 | 0 | 0 | 44.4785
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 SchXST | LM | 0.714 | 0.714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 0.56645 | 0.56645 | 0 | 0 | IWP_1019 | 62.3094 | 0 | 0 | 62.3094
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 150 | 0 | 0 | 150
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 50 | 0 | 0 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1019 | 500 | 0 | 0 | 500
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1019 | 1000 | 0 | 0 | 1000
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 10 | Install Spools - NB 10 SchSTD | LM | 1.38 | 0 | 0 | 1.38 | 0 | 0 | 0 | 0 | 0 | CS | 2.1497 | 1 | 110 | 0 | 2.9666 | 0 | 0 | 2.9666 | IWP_1019 | 0 | 0 | 326.3262 | 326.3262
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 16 | Install Spools - NB 16 SchXST | LM | 0.8211 | 0 | 0 | 0.8211 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 1 | 110 | 0 | 4.1922 | 0 | 0 | 4.1922 | IWP_1019 | 0 | 0 | 461.1397 | 461.1397
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0 | 0 | 0.39 | IWP_1019 | 0 | 0 | 42.9 | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 0 | 0 | 1.04 | IWP_1019 | 0 | 0 | 114.4 | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Inlines - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 0.52 | 0 | 0 | 0.52 | IWP_1019 | 0 | 0 | 57.2 | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 0.52 | 0 | 0 | 0.52 | IWP_1019 | 0 | 0 | 57.2 | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.56 | 0 | 0 | 1.56 | IWP_1019 | 0 | 0 | 171.6 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 0.585 | 0 | 0 | 0.585 | IWP_1019 | 0 | 0 | 64.35 | 64.35
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 3.9 | 1 | 110 | 0 | 1.95 | 0 | 0 | 1.95 | IWP_1019 | 0 | 0 | 214.5 | 214.5
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL300 | EA | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | CS | 6.37 | 1 | 110 | 0 | 15.925 | 0 | 0 | 15.925 | IWP_1019 | 0 | 0 | 1751.75 | 1751.75
Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 1 | 110 | 0 | 1.8233 | 0 | 0 | 1.8233 | IWP_1019 | 0 | 0 | 200.5585 | 200.5585
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1019 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 SchXST | EA | 4 | 4 | 0 | 0 | 64 | 128 | 0 | 0 | 128 | CS | 16.12 | 1 | 110 | 0 | 64.48 | 64.48 | 0 | 0 | IWP_1019 | 7092.8 | 0 | 0 | 7092.8
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1019 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 SchXST | LM | 2.618 | 2.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 2.077 | 2.077 | 0 | 0 | IWP_1019 | 228.4677 | 0 | 0 | 228.4677
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1019 | 1000 | 0 | 0 | 1000
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 400 | 0 | 0 | 400
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 16 | Install Spools - NB 16 SchXST | LM | 3.0107 | 0 | 0 | 3.0107 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 1 | 110 | 0 | 15.3713 | 0 | 0 | 15.3713 | IWP_1019 | 0 | 0 | 1690.8454 | 1690.8454
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Blind - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Inlines - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install valve - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 0 | 0 | 1.04 | IWP_1019 | 0 | 0 | 114.4 | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL300 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 6.37 | 1 | 110 | 0 | 19.11 | 0 | 0 | 19.11 | IWP_1019 | 0 | 0 | 2102.1 | 2102.1
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 1 | 110 | 0 | 2.1107 | 0 | 0 | 2.1107 | IWP_1019 | 0 | 0 | 232.1716 | 232.1716
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1019 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 2 | 2 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | CS | 1.3715 | 1 | 110 | 0 | 2.743 | 2.743 | 0 | 0 | IWP_1019 | 301.73 | 0 | 0 | 301.73
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 SchSTD | EA | 2 | 2 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 4.1782 | 1 | 110 | 0 | 8.3564 | 8.3564 | 0 | 0 | IWP_1019 | 919.204 | 0 | 0 | 919.204
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 SchXST | EA | 4 | 4 | 0 | 0 | 64 | 128 | 0 | 0 | 128 | CS | 16.12 | 1 | 110 | 0 | 64.48 | 64.48 | 0 | 0 | IWP_1019 | 7092.8 | 0 | 0 | 7092.8
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1019 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1019 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1019 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1019 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 1 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 2.21 | 1 | 110 | 0 | 2.21 | 2.21 | 0 | 0 | IWP_1019 | 243.1 | 0 | 0 | 243.1
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 4.42 | 1 | 110 | 0 | 4.42 | 4.42 | 0 | 0 | IWP_1019 | 486.2 | 0 | 0 | 486.2
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 3 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 1 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 7.67 | 1 | 110 | 0 | 7.67 | 7.67 | 0 | 0 | IWP_1019 | 843.7 | 0 | 0 | 843.7
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1019 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1019 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1019 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 SchSTD | LM | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.33696 | 1 | 110 | 0 | 0.40435 | 0.40435 | 0 | 0 | IWP_1019 | 44.4785 | 0 | 0 | 44.4785
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 SchXST | LM | 0.714 | 0.714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 0.56645 | 0.56645 | 0 | 0 | IWP_1019 | 62.3094 | 0 | 0 | 62.3094
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 150 | 0 | 0 | 150
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 50 | 0 | 0 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1019 | 500 | 0 | 0 | 500
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1019 | 1000 | 0 | 0 | 1000
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1019 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 10 | Install Spools - NB 10 SchSTD | LM | 1.38 | 0 | 0 | 1.38 | 0 | 0 | 0 | 0 | 0 | CS | 2.1497 | 1 | 110 | 0 | 2.9666 | 0 | 0 | 2.9666 | IWP_1019 | 0 | 0 | 326.3262 | 326.3262
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 16 | Install Spools - NB 16 SchXST | LM | 0.8211 | 0 | 0 | 0.8211 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 1 | 110 | 0 | 4.1922 | 0 | 0 | 4.1922 | IWP_1019 | 0 | 0 | 461.1397 | 461.1397
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0 | 0 | 0.39 | IWP_1019 | 0 | 0 | 42.9 | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 0 | 0 | 1.04 | IWP_1019 | 0 | 0 | 114.4 | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Inlines - NB 16 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 9.23 | 1 | 110 | 0 | 9.23 | 0 | 0 | 9.23 | IWP_1019 | 0 | 0 | 1015.3 | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 0.52 | 0 | 0 | 0.52 | IWP_1019 | 0 | 0 | 57.2 | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 0.52 | 0 | 0 | 0.52 | IWP_1019 | 0 | 0 | 57.2 | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.56 | 0 | 0 | 1.56 | IWP_1019 | 0 | 0 | 171.6 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 0.585 | 0 | 0 | 0.585 | IWP_1019 | 0 | 0 | 64.35 | 64.35
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 3.9 | 1 | 110 | 0 | 1.95 | 0 | 0 | 1.95 | IWP_1019 | 0 | 0 | 214.5 | 214.5
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL300 | EA | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | CS | 6.37 | 1 | 110 | 0 | 15.925 | 0 | 0 | 15.925 | IWP_1019 | 0 | 0 | 1751.75 | 1751.75
Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 1 | 110 | 0 | 1.8233 | 0 | 0 | 1.8233 | IWP_1019 | 0 | 0 | 200.5585 | 200.5585
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1020 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 2 | 2 | 0 | 0 | 16 | 16 | 0 | 0 | 16 | CS | 3.0095 | 1 | 110 | 0 | 6.019 | 6.019 | 0 | 0 | IWP_1020 | 662.09 | 0 | 0 | 662.09
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 SchSTD | EA | 2 | 2 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 4.1782 | 1 | 110 | 0 | 8.3564 | 8.3564 | 0 | 0 | IWP_1020 | 919.204 | 0 | 0 | 919.204
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1020 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | CS | 1.17 | 1 | 110 | 0 | 3.51 | 3.51 | 0 | 0 | IWP_1020 | 386.1 | 0 | 0 | 386.1
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL2000 | EA | 5 | 5 | 0 | 0 | 10 | 30 | 0 | 0 | 30 | CS | 4.42 | 1 | 110 | 0 | 22.1 | 22.1 | 0 | 0 | IWP_1020 | 2431 | 0 | 0 | 2431
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 3 | 3 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1020 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 SchSTD | LM | 1.461 | 1.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.33696 | 1 | 110 | 0 | 0.4923 | 0.4923 | 0 | 0 | IWP_1020 | 54.1526 | 0 | 0 | 54.1526
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1020 | 150 | 0 | 0 | 150
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1020 | 500 | 0 | 0 | 500
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1020 | 900 | 0 | 0 | 900
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1020 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 10 | Install Spools - NB 10 SchSTD | LM | 1.6802 | 0 | 0 | 1.6802 | 0 | 0 | 0 | 0 | 0 | CS | 2.1497 | 1 | 110 | 0 | 3.6118 | 0 | 0 | 3.6118 | IWP_1020 | 0 | 0 | 397.3021 | 397.3021
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 3.12 | 0 | 0 | 3.12 | IWP_1020 | 0 | 0 | 343.2 | 343.2
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.56 | 0 | 0 | 1.56 | IWP_1020 | 0 | 0 | 171.6 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 5.5 | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 5.72 | 0 | 0 | 5.72 | IWP_1020 | 0 | 0 | 629.2 | 629.2
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 3.12 | 1 | 110 | 0 | 1.56 | 0 | 0 | 1.56 | IWP_1020 | 0 | 0 | 171.6 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 1 | 110 | 0 | 2.08 | 0 | 0 | 2.08 | IWP_1020 | 0 | 0 | 228.8 | 228.8
Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 1 | 110 | 0 | 1.8233 | 0 | 0 | 1.8233 | IWP_1020 | 0 | 0 | 200.5585 | 200.5585
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1020 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 2 | 2 | 0 | 0 | 16 | 16 | 0 | 0 | 16 | CS | 3.0095 | 1 | 110 | 0 | 6.019 | 6.019 | 0 | 0 | IWP_1020 | 662.09 | 0 | 0 | 662.09
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 SchSTD | EA | 2 | 2 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 4.1782 | 1 | 110 | 0 | 8.3564 | 8.3564 | 0 | 0 | IWP_1020 | 919.204 | 0 | 0 | 919.204
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1020 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | CS | 1.17 | 1 | 110 | 0 | 3.51 | 3.51 | 0 | 0 | IWP_1020 | 386.1 | 0 | 0 | 386.1
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL2000 | EA | 5 | 5 | 0 | 0 | 10 | 30 | 0 | 0 | 30 | CS | 4.42 | 1 | 110 | 0 | 22.1 | 22.1 | 0 | 0 | IWP_1020 | 2431 | 0 | 0 | 2431
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 3 | 3 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1020 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 SchSTD | LM | 1.461 | 1.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.33696 | 1 | 110 | 0 | 0.4923 | 0.4923 | 0 | 0 | IWP_1020 | 54.1526 | 0 | 0 | 54.1526
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1020 | 150 | 0 | 0 | 150
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1020 | 500 | 0 | 0 | 500
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1020 | 900 | 0 | 0 | 900
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1020 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 10 | Install Spools - NB 10 SchSTD | LM | 1.6802 | 0 | 0 | 1.6802 | 0 | 0 | 0 | 0 | 0 | CS | 2.1497 | 1 | 110 | 0 | 3.6118 | 0 | 0 | 3.6118 | IWP_1020 | 0 | 0 | 397.3021 | 397.3021
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 3.12 | 0 | 0 | 3.12 | IWP_1020 | 0 | 0 | 343.2 | 343.2
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.56 | 0 | 0 | 1.56 | IWP_1020 | 0 | 0 | 171.6 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 5.5 | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 5.72 | 0 | 0 | 5.72 | IWP_1020 | 0 | 0 | 629.2 | 629.2
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 3.12 | 1 | 110 | 0 | 1.56 | 0 | 0 | 1.56 | IWP_1020 | 0 | 0 | 171.6 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 1 | 110 | 0 | 2.08 | 0 | 0 | 2.08 | IWP_1020 | 0 | 0 | 228.8 | 228.8
Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 1 | 110 | 0 | 1.8233 | 0 | 0 | 1.8233 | IWP_1020 | 0 | 0 | 200.5585 | 200.5585
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1017 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1017 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1017 | 429 | 0 | 0 | 429
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 9 | 9 | 0 | 0 | 9 | 11.25 | 0 | 0 | 11.25 | CS | 0.91 | 1 | 110 | 0 | 8.19 | 8.19 | 0 | 0 | IWP_1017 | 900.9 | 0 | 0 | 900.9
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.78 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1017 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1017 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1017 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 850 | 0 | 0 | 850
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 50 | 0 | 0 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1017 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0 | 0 | 0.91 | IWP_1017 | 0 | 0 | 100.1 | 100.1
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 0 | 0 | 1.04 | IWP_1017 | 0 | 0 | 114.4 | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 2.08 | 0 | 0 | 2.08 | IWP_1017 | 0 | 0 | 228.8 | 228.8
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 0 | 0 | 1.04 | IWP_1017 | 0 | 0 | 114.4 | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 0.205 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.031478 | 0.031478 | 0 | 0 | IWP_1017 | 3.4626 | 0 | 0 | 3.4626
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 50 | 0 | 0 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 0.21525 | 0 | 0 | 0.21525 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 1 | 110 | 0 | 0.21851 | 0 | 0 | 0.21851 | IWP_1017 | 0 | 0 | 24.036 | 24.036
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 0.52 | 0 | 0 | 0.52 | IWP_1017 | 0 | 0 | 57.2 | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 1 | 110 | 0 | 0.4 | 0 | 0 | 0.4 | IWP_1017 | 0 | 0 | 44 | 44
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 0.205 | 0.205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.031478 | 0.031478 | 0 | 0 | IWP_1017 | 3.4626 | 0 | 0 | 3.4626
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 50 | 0 | 0 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 0.21525 | 0 | 0 | 0.21525 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 1 | 110 | 0 | 0.21851 | 0 | 0 | 0.21851 | IWP_1017 | 0 | 0 | 24.036 | 24.036
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 0.52 | 0 | 0 | 0.52 | IWP_1017 | 0 | 0 | 57.2 | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 1 | 110 | 0 | 0.4 | 0 | 0 | 0.4 | IWP_1017 | 0 | 0 | 44 | 44
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1017 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1017 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1017 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1017 | 429 | 0 | 0 | 429
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 9 | 9 | 0 | 0 | 9 | 11.25 | 0 | 0 | 11.25 | CS | 0.91 | 1 | 110 | 0 | 8.19 | 8.19 | 0 | 0 | IWP_1017 | 900.9 | 0 | 0 | 900.9
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.78 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1017 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1017 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1017 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1017 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1017 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 850 | 0 | 0 | 850
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1017 | 50 | 0 | 0 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0 | 0 | 0.39 | IWP_1017 | 0 | 0 | 42.9 | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0 | 0 | 0.91 | IWP_1017 | 0 | 0 | 100.1 | 100.1
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 0 | 0 | 1.04 | IWP_1017 | 0 | 0 | 114.4 | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 2.08 | 0 | 0 | 2.08 | IWP_1017 | 0 | 0 | 228.8 | 228.8
Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL300 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 0 | 0 | 1.04 | IWP_1017 | 0 | 0 | 114.4 | 114.4
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1020 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 8 | 8 | 0 | 0 | 80 | 200 | 0 | 0 | 200 | CS | 5.915 | 1 | 110 | 0 | 47.32 | 47.32 | 0 | 0 | IWP_1020 | 5205.2 | 0 | 0 | 5205.2
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1020 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1020 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 3 | 0 | 0 | 6 | 18 | 0 | 0 | 18 | CS | 5.46 | 1 | 110 | 0 | 16.38 | 16.38 | 0 | 0 | IWP_1020 | 1801.8 | 0 | 0 | 1801.8
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1020 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.028151 | 0.028151 | 0 | 0 | IWP_1020 | 3.0966 | 0 | 0 | 3.0966
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 Sch80 | LM | 3.686 | 3.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.46918 | 1 | 110 | 0 | 1.7294 | 1.7294 | 0 | 0 | IWP_1020 | 190.2349 | 0 | 0 | 190.2349
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1020 | 250 | 0 | 0 | 250
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1020 | 50 | 0 | 0 | 50
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.165 | 0 | 0 | 0.165 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 1 | 110 | 0 | 0.19706 | 0 | 0 | 0.19706 | IWP_1020 | 0 | 0 | 21.6763 | 21.6763
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 10 | Install Spools - NB 10 Sch80 | LM | 4.2389 | 0 | 0 | 4.2389 | 0 | 0 | 0 | 0 | 0 | CS | 2.9857 | 1 | 110 | 0 | 12.6561 | 0 | 0 | 12.6561 | IWP_1020 | 0 | 0 | 1392.1739 | 1392.1739
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 5.07 | 0 | 0 | 5.07 | IWP_1020 | 0 | 0 | 557.7 | 557.7
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 10 | Install valve - NB 10 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 1 | 110 | 0 | 13.26 | 0 | 0 | 13.26 | IWP_1020 | 0 | 0 | 1458.6 | 1458.6
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 10 | Install Blind - NB 10 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 1 | 110 | 0 | 6.63 | 0 | 0 | 6.63 | IWP_1020 | 0 | 0 | 729.3 | 729.3
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 0.585 | 0 | 0 | 0.585 | IWP_1020 | 0 | 0 | 64.35 | 64.35
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 5.5 | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 6.435 | 0 | 0 | 6.435 | IWP_1020 | 0 | 0 | 707.85 | 707.85
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 1 | 110 | 0 | 16.64 | 0 | 0 | 16.64 | IWP_1020 | 0 | 0 | 1830.4 | 1830.4
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 1 | 110 | 0 | 1.8233 | 0 | 0 | 1.8233 | IWP_1020 | 0 | 0 | 200.5585 | 200.5585
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1020 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 8 | 8 | 0 | 0 | 80 | 200 | 0 | 0 | 200 | CS | 5.915 | 1 | 110 | 0 | 47.32 | 47.32 | 0 | 0 | IWP_1020 | 5205.2 | 0 | 0 | 5205.2
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 3 | 0 | 0 | 6 | 18 | 0 | 0 | 18 | CS | 5.46 | 1 | 110 | 0 | 16.38 | 16.38 | 0 | 0 | IWP_1020 | 1801.8 | 0 | 0 | 1801.8
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.028151 | 0.028151 | 0 | 0 | IWP_1020 | 3.0966 | 0 | 0 | 3.0966
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 10 | Shop handling - NB 10 Sch80 | LM | 3.686 | 3.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.46918 | 1 | 110 | 0 | 1.7294 | 1.7294 | 0 | 0 | IWP_1020 | 190.2349 | 0 | 0 | 190.2349
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1020 | 250 | 0 | 0 | 250
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1020 | 50 | 0 | 0 | 50
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.165 | 0 | 0 | 0.165 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 1 | 110 | 0 | 0.19706 | 0 | 0 | 0.19706 | IWP_1020 | 0 | 0 | 21.6763 | 21.6763
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 10 | Install Spools - NB 10 Sch80 | LM | 4.2389 | 0 | 0 | 4.2389 | 0 | 0 | 0 | 0 | 0 | CS | 2.9857 | 1 | 110 | 0 | 12.6561 | 0 | 0 | 12.6561 | IWP_1020 | 0 | 0 | 1392.1739 | 1392.1739
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 3.38 | 0 | 0 | 3.38 | IWP_1020 | 0 | 0 | 371.8 | 371.8
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 10 | Install valve - NB 10 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 1 | 110 | 0 | 13.26 | 0 | 0 | 13.26 | IWP_1020 | 0 | 0 | 1458.6 | 1458.6
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 10 | Install Blind - NB 10 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 6.63 | 1 | 110 | 0 | 6.63 | 0 | 0 | 6.63 | IWP_1020 | 0 | 0 | 729.3 | 729.3
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 5.265 | 0 | 0 | 5.265 | IWP_1020 | 0 | 0 | 579.15 | 579.15
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 1 | 110 | 0 | 16.64 | 0 | 0 | 16.64 | IWP_1020 | 0 | 0 | 1830.4 | 1830.4
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 10 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.8233 | 1 | 110 | 0 | 1.8233 | 0 | 0 | 1.8233 | IWP_1020 | 0 | 0 | 200.5585 | 200.5585
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 10 | Shop Butt Weld - NB 10 Sch80 | EA | 4 | 4 | 0 | 0 | 40 | 100 | 0 | 0 | 100 | CS | 5.915 | 1 | 110 | 0 | 23.66 | 23.66 | 0 | 0 | IWP_1021 | 2602.6 | 0 | 0 | 2602.6
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 11 | 11 | 0 | 0 | 132 | 330 | 0 | 0 | 330 | CS | 7.683 | 1 | 110 | 0 | 84.513 | 84.513 | 0 | 0 | IWP_1021 | 9296.43 | 0 | 0 | 9296.43
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 44.564 | 44.564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 25.4706 | 25.4706 | 0 | 0 | IWP_1021 | 2801.7619 | 0 | 0 | 2801.7619
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 10 | Shop X-Ray - NB 10 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1021 | 250 | 0 | 0 | 250
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1021 | 500 | 0 | 0 | 500
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 57 | 57 | 0 | 0 | IWP_1021 | 6270 | 0 | 0 | 6270
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1021 | 5100 | 0 | 0 | 5100
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 51.2486 | 0 | 0 | 51.2486 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 1 | 110 | 0 | 188.2066 | 0 | 0 | 188.2066 | IWP_1021 | 0 | 0 | 20702.7208 | 20702.7208
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 10 | Flange Bolt-Up - NB 10 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 4.16 | 1 | 110 | 0 | 4.16 | 0 | 0 | 4.16 | IWP_1021 | 0 | 0 | 457.6 | 457.6
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3.5 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 1 | 110 | 0 | 18.655 | 0 | 0 | 18.655 | IWP_1021 | 0 | 0 | 2052.05 | 2052.05
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 1 | 110 | 0 | 7.6577 | 0 | 0 | 7.6577 | IWP_1021 | 0 | 0 | 842.3458 | 842.3458
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 12 | Field Butt Weld - NB 12 Sch80 | EA | 1 | 0 | 1 | 0 | 12 | 0 | 30 | 0 | 30 | CS | 11.3555 | 0.75 | 78 | 0 | 8.5166 | 0 | 8.5166 | 0 | IWP_1021 | 0 | 664.2967 | 0 | 664.2967
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 19 | 19 | 0 | 0 | 228 | 570 | 0 | 0 | 570 | CS | 7.683 | 1 | 110 | 0 | 145.977 | 145.977 | 0 | 0 | IWP_1022 | 16057.47 | 0 | 0 | 16057.47
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 78.464 | 78.464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 44.8461 | 44.8461 | 0 | 0 | IWP_1022 | 4933.0726 | 0 | 0 | 4933.0726
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1022 | 750 | 0 | 0 | 750
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 114 | 114 | 0 | 0 | IWP_1022 | 12540 | 0 | 0 | 12540
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1022 | 10200 | 0 | 0 | 10200
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 90.2336 | 0 | 0 | 90.2336 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 1 | 110 | 0 | 331.376 | 0 | 0 | 331.376 | IWP_1022 | 0 | 0 | 36451.3573 | 36451.3573
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 1 | 110 | 0 | 31.98 | 0 | 0 | 31.98 | IWP_1022 | 0 | 0 | 3517.8 | 3517.8
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 1 | 110 | 0 | 13.401 | 0 | 0 | 13.401 | IWP_1022 | 0 | 0 | 1474.1052 | 1474.1052
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 12 | Field Butt Weld - NB 12 Sch80 | EA | 2 | 0 | 2 | 0 | 24 | 0 | 60 | 0 | 60 | CS | 11.3555 | 0.75 | 78 | 0 | 17.0332 | 0 | 17.0332 | 0 | IWP_1022 | 0 | 1328.5935 | 0 | 1328.5935
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 18 | 18 | 0 | 0 | 216 | 540 | 0 | 0 | 540 | CS | 7.683 | 1 | 110 | 0 | 138.294 | 138.294 | 0 | 0 | IWP_1023 | 15212.34 | 0 | 0 | 15212.34
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1023 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1023 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1023 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1023 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 16.241 | 16.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 9.2825 | 9.2825 | 0 | 0 | IWP_1023 | 1021.0801 | 0 | 0 | 1021.0801
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1023 | 750 | 0 | 0 | 750
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 19 | 19 | 0 | 0 | IWP_1023 | 2090 | 0 | 0 | 2090
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1023 | 1700 | 0 | 0 | 1700
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 18.6771 | 0 | 0 | 18.6771 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 1 | 110 | 0 | 68.5904 | 0 | 0 | 68.5904 | IWP_1023 | 0 | 0 | 7544.9441 | 7544.9441
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0 | 0 | 0.78 | IWP_1023 | 0 | 0 | 85.8 | 85.8
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 2.34 | 0 | 0 | 2.34 | IWP_1023 | 0 | 0 | 257.4 | 257.4
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 1 | 110 | 0 | 15.99 | 0 | 0 | 15.99 | IWP_1023 | 0 | 0 | 1758.9 | 1758.9
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 1 | 110 | 0 | 1.9144 | 0 | 0 | 1.9144 | IWP_1023 | 0 | 0 | 210.5865 | 210.5865
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 12 | 12 | 0 | 0 | 144 | 360 | 0 | 0 | 360 | CS | 7.683 | 1 | 110 | 0 | 92.196 | 92.196 | 0 | 0 | IWP_1023 | 10141.56 | 0 | 0 | 10141.56
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 42.326 | 42.326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 24.1914 | 24.1914 | 0 | 0 | IWP_1023 | 2661.0577 | 0 | 0 | 2661.0577
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1023 | 500 | 0 | 0 | 500
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 57 | 57 | 0 | 0 | IWP_1023 | 6270 | 0 | 0 | 6270
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1023 | 5100 | 0 | 0 | 5100
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 48.6749 | 0 | 0 | 48.6749 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 1 | 110 | 0 | 178.7548 | 0 | 0 | 178.7548 | IWP_1023 | 0 | 0 | 19663.0321 | 19663.0321
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 1 | 110 | 0 | 15.99 | 0 | 0 | 15.99 | IWP_1023 | 0 | 0 | 1758.9 | 1758.9
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 1 | 110 | 0 | 5.7433 | 0 | 0 | 5.7433 | IWP_1023 | 0 | 0 | 631.7594 | 631.7594
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 12 | Field Butt Weld - NB 12 Sch80 | EA | 1 | 0 | 1 | 0 | 12 | 0 | 30 | 0 | 30 | CS | 11.3555 | 0.75 | 78 | 0 | 8.5166 | 0 | 8.5166 | 0 | IWP_1023 | 0 | 664.2967 | 0 | 664.2967
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1024 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1024 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1024 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1024 | 429 | 0 | 0 | 429
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1024 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1024 | 1001 | 0 | 0 | 1001
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1024 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1024 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1024 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1024 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1024 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 200 | 0 | 0 | 200
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0 | 0 | 0.65 | IWP_1024 | 0 | 0 | 71.5 | 71.5
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0 | 0 | 0.91 | IWP_1024 | 0 | 0 | 100.1 | 100.1
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 0 | 0 | 1.69 | IWP_1024 | 0 | 0 | 185.9 | 185.9
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 2.925 | 0 | 0 | 2.925 | IWP_1024 | 0 | 0 | 321.75 | 321.75
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 0 | 0 | 1.17 | IWP_1024 | 0 | 0 | 128.7 | 128.7
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 16 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 1.1765 | 1 | 110 | 0 | 18.824 | 18.824 | 0 | 0 | IWP_1024 | 2070.64 | 0 | 0 | 2070.64
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 16.867 | 16.867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 3.1655 | 3.1655 | 0 | 0 | IWP_1024 | 348.2032 | 0 | 0 | 348.2032
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 800 | 0 | 0 | 800
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1024 | 616 | 0 | 0 | 616
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1024 | 500 | 0 | 0 | 500
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 18.5537 | 0 | 0 | 18.5537 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 1 | 110 | 0 | 22.1584 | 0 | 0 | 22.1584 | IWP_1024 | 0 | 0 | 2437.4226 | 2437.4226
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL150 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0 | 0 | 0.65 | IWP_1024 | 0 | 0 | 71.5 | 71.5
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0 | 0 | 0.65 | IWP_1024 | 0 | 0 | 71.5 | 71.5
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 4.5 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 1 | 110 | 0 | 4.095 | 0 | 0 | 4.095 | IWP_1024 | 0 | 0 | 450.45 | 450.45
Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 1 | 110 | 0 | 4 | 0 | 0 | 4 | IWP_1024 | 0 | 0 | 440 | 440
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 14 | 14 | 0 | 0 | 28 | 42 | 0 | 0 | 42 | CS | 1.1765 | 1 | 110 | 0 | 16.471 | 16.471 | 0 | 0 | IWP_1024 | 1811.81 | 0 | 0 | 1811.81
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 2.86 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1024 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | 0 | 0 | 6 | 15 | 0 | 0 | 15 | CS | 0.39 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1024 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | 0 | 0 | 4 | 10 | 0 | 0 | 10 | CS | 0.39 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1024 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 6 | 6 | 0 | 0 | 6 | 15 | 0 | 0 | 15 | CS | 0.39 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1024 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 21.621 | 21.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 4.0577 | 4.0577 | 0 | 0 | IWP_1024 | 446.345 | 0 | 0 | 446.345
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 150 | 0 | 0 | 150
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 700 | 0 | 0 | 700
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 11.2 | 11.2 | 0 | 0 | IWP_1024 | 1232 | 0 | 0 | 1232
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1024 | 1000 | 0 | 0 | 1000
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 23.7831 | 0 | 0 | 23.7831 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 1 | 110 | 0 | 28.4038 | 0 | 0 | 28.4038 | IWP_1024 | 0 | 0 | 3124.4153 | 3124.4153
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 1 | 110 | 0 | 1.17 | 0 | 0 | 1.17 | IWP_1024 | 0 | 0 | 128.7 | 128.7
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 1 | 110 | 0 | 2.275 | 0 | 0 | 2.275 | IWP_1024 | 0 | 0 | 250.25 | 250.25
Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 1 | 110 | 0 | 5 | 0 | 0 | 5 | IWP_1024 | 0 | 0 | 550 | 550
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1024 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 2.86 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1024 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | 0 | 0 | 6 | 15 | 0 | 0 | 15 | CS | 0.39 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1024 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | 0 | 0 | 4 | 10 | 0 | 0 | 10 | CS | 0.39 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1024 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 6 | 6 | 0 | 0 | 6 | 15 | 0 | 0 | 15 | CS | 0.39 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1024 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 18.175 | 18.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 3.411 | 3.411 | 0 | 0 | IWP_1024 | 375.2056 | 0 | 0 | 375.2056
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 150 | 0 | 0 | 150
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 500 | 0 | 0 | 500
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1024 | 616 | 0 | 0 | 616
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1024 | 500 | 0 | 0 | 500
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 19.9925 | 0 | 0 | 19.9925 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 1 | 110 | 0 | 23.8767 | 0 | 0 | 23.8767 | IWP_1024 | 0 | 0 | 2626.4395 | 2626.4395
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 1 | 110 | 0 | 1.17 | 0 | 0 | 1.17 | IWP_1024 | 0 | 0 | 128.7 | 128.7
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 1 | 110 | 0 | 2.275 | 0 | 0 | 2.275 | IWP_1024 | 0 | 0 | 250.25 | 250.25
Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 1 | 110 | 0 | 4 | 0 | 0 | 4 | IWP_1024 | 0 | 0 | 440 | 440
Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1024 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1024 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1024 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1024 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 200 | 0 | 0 | 200
Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1024 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1024 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1024 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1024 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1024 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1024 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 200 | 0 | 0 | 200
Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1024 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1024 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_2 | TR | TR-ZL01-8101 | ISO4025 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1024 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | TR | TR-ZL01-8101 | ISO4025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1024 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_2 | TR | TR-ZL01-8101 | ISO4027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1024 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_2 | TR | TR-ZL01-8101 | ISO4027 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1024 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchSTD | EA | 13 | 13 | 0 | 0 | 104 | 104 | 0 | 0 | 104 | CS | 3.0095 | 1 | 110 | 0 | 39.1235 | 39.1235 | 0 | 0 | IWP_1024 | 4303.585 | 0 | 0 | 4303.585
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchSTD | LM | 2.916 | 2.916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.26871 | 1 | 110 | 0 | 0.78357 | 0.78357 | 0 | 0 | IWP_1024 | 86.1927 | 0 | 0 | 86.1927
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1024 | 1300 | 0 | 0 | 1300
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 8 | Field Butt Weld - NB 8 SchSTD | EA | 1 | 0 | 1 | 0 | 8 | 0 | 8 | 0 | 8 | CS | 4.2887 | 0.75 | 78 | 0 | 3.2165 | 0 | 3.2165 | 0 | IWP_1024 | 0 | 250.889 | 0 | 250.889
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchSTD | LM | 3.2076 | 0 | 3.2076 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7019 | 0.75 | 78 | 0 | 4.0942 | 0 | 4.0942 | 0 | IWP_1024 | 0 | 319.3438 | 0 | 319.3438
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 8 | Erection of Field Run Pipe - NB 8 SchSTD | LM | 19.1103 | 0 | 19.1103 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.4502 | 0.75 | 78 | 0 | 20.7853 | 0 | 20.7853 | 0 | IWP_1024 | 0 | 1621.257 | 0 | 1621.257
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install Blind - NB 8 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.64 | 0.75 | 78 | 0 | 2.73 | 0 | 2.73 | 0 | IWP_1024 | 0 | 212.94 | 0 | 212.94
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL150 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.73 | 0.75 | 78 | 0 | 3.0713 | 0 | 3.0713 | 0 | IWP_1024 | 0 | 239.5575 | 0 | 239.5575
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 8 | Erection of Pipe Supports - NB 8 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7364 | 0.75 | 78 | 0 | 6.5116 | 0 | 6.5116 | 0 | IWP_1024 | 0 | 507.908 | 0 | 507.908
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | 600 | 150-60-F-610 | 150-60-F-610 - Field X-Ray | 8 | Field X-Ray - NB 8 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 1500 | 0 | 0 | 0 | 0 | IWP_1024 | 0 | 1500 | 0 | 1500
Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 8 | Field Coating - NB 8 | LM | 19.1103 | 0 | 19.1103 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 120 | 0 | 0 | 0 | 0 | IWP_1024 | 0 | 2293.236 | 0 | 2293.236
Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 4 | Shop Butt Weld - NB 4 SchSTD | EA | 19 | 19 | 0 | 0 | 76 | 76 | 0 | 0 | 76 | CS | 1.6835 | 1 | 110 | 0 | 31.9865 | 31.9865 | 0 | 0 | IWP_1024 | 3518.515 | 0 | 0 | 3518.515
Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 4 | Shop handling - NB 4 SchSTD | LM | 10.831 | 10.831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.19194 | 1 | 110 | 0 | 2.0789 | 2.0789 | 0 | 0 | IWP_1024 | 228.6774 | 0 | 0 | 228.6774
Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 4 | Shop X-Ray - NB 4 | EA | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1024 | 950 | 0 | 0 | 950
Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 4 | Shop Hydrotest - NB 4 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 7 | 1 | 110 | 0 | 7 | 7 | 0 | 0 | IWP_1024 | 770 | 0 | 0 | 770
Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 4 | Shop Spools Coating - NB 4 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 700 | 0 | 0 | 0 | 0 | IWP_1024 | 700 | 0 | 0 | 700
Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 4 | Install Spools - NB 4 SchSTD | LM | 11.9141 | 0 | 11.9141 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.2241 | 0.75 | 78 | 0 | 10.9384 | 0 | 10.9384 | 0 | IWP_1024 | 0 | 853.1956 | 0 | 853.1956
Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 4 | Flange Bolt-Up - NB 4 CL150 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.56 | 0.75 | 78 | 0 | 2.925 | 0 | 2.925 | 0 | IWP_1024 | 0 | 228.15 | 0 | 228.15
Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 4 | Erection of Pipe Supports - NB 4 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 3.375 | 0 | 3.375 | 0 | IWP_1024 | 0 | 263.25 | 0 | 263.25
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 18 | 18 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 1.1765 | 1 | 110 | 0 | 21.177 | 21.177 | 0 | 0 | IWP_1025 | 2329.47 | 0 | 0 | 2329.47
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1025 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1025 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1025 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1025 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1025 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 29.31 | 29.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 5.5007 | 5.5007 | 0 | 0 | IWP_1025 | 605.0772 | 0 | 0 | 605.0772
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 150 | 0 | 0 | 150
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 950 | 0 | 0 | 950
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 16.8 | 16.8 | 0 | 0 | IWP_1025 | 1848 | 0 | 0 | 1848
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1025 | 1500 | 0 | 0 | 1500
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 2 | Field Butt Weld - NB 2 SchXST | EA | 3 | 0 | 3 | 0 | 6 | 0 | 9 | 0 | 9 | CS | 1.6003 | 0.75 | 78 | 0 | 3.6007 | 0 | 3.6007 | 0 | IWP_1025 | 0 | 280.8526 | 0 | 280.8526
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 32.241 | 0 | 32.241 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 28.8787 | 0 | 28.8787 | 0 | IWP_1025 | 0 | 2252.5373 | 0 | 2252.5373
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 2 | Erection of Field Run Pipe - NB 2 SchXST | LM | 17.7056 | 0 | 17.7056 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0237 | 0.75 | 78 | 0 | 13.5935 | 0 | 13.5935 | 0 | IWP_1025 | 0 | 1060.2965 | 0 | 1060.2965
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1025 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1025 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1025 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 6.5 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 4.4362 | 0 | 4.4362 | 0 | IWP_1025 | 0 | 346.0275 | 0 | 346.0275
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 9.75 | 0 | 9.75 | 0 | IWP_1025 | 0 | 760.5 | 0 | 760.5
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 600 | 150-60-F-610 | 150-60-F-610 - Field X-Ray | 2 | Field X-Ray - NB 2 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 750 | 0 | 0 | 0 | 0 | IWP_1025 | 0 | 2250 | 0 | 2250
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 2 | Field Coating - NB 2 | LM | 17.7056 | 0 | 17.7056 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 60 | 0 | 0 | 0 | 0 | IWP_1025 | 0 | 1062.336 | 0 | 1062.336
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 18 | 18 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 1.1765 | 1 | 110 | 0 | 21.177 | 21.177 | 0 | 0 | IWP_1025 | 2329.47 | 0 | 0 | 2329.47
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 17.839 | 17.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 3.3479 | 3.3479 | 0 | 0 | IWP_1025 | 368.2692 | 0 | 0 | 368.2692
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 900 | 0 | 0 | 900
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 11.2 | 11.2 | 0 | 0 | IWP_1025 | 1232 | 0 | 0 | 1232
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1025 | 1000 | 0 | 0 | 1000
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 19.6229 | 0 | 19.6229 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 17.5765 | 0 | 17.5765 | 0 | IWP_1025 | 0 | 1370.966 | 0 | 1370.966
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1025 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1025 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 3.0713 | 0 | 3.0713 | 0 | IWP_1025 | 0 | 239.5575 | 0 | 239.5575
Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 4.5 | 0 | 4.5 | 0 | IWP_1025 | 0 | 351 | 0 | 351
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1025 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1025 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.91 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1025 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1025 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 0.255 | 0.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.039155 | 0.039155 | 0 | 0 | IWP_1025 | 4.3071 | 0 | 0 | 4.3071
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 700 | 0 | 0 | 700
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 0.26775 | 0 | 0.26775 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 0.75 | 78 | 0 | 0.20385 | 0 | 0.20385 | 0 | IWP_1025 | 0 | 15.9005 | 0 | 15.9005
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1025 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1025 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1025 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 9 | 9 | 0 | 0 | 9 | 11.25 | 0 | 0 | 11.25 | CS | 0.78 | 1 | 110 | 0 | 7.02 | 7.02 | 0 | 0 | IWP_1025 | 772.2 | 0 | 0 | 772.2
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1025 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1025 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 2.515 | 2.515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.38618 | 0.38618 | 0 | 0 | IWP_1025 | 42.4798 | 0 | 0 | 42.4798
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 750 | 0 | 0 | 750
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 50 | 0 | 0 | 50
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 2.6408 | 0 | 2.6408 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 0.75 | 78 | 0 | 2.0106 | 0 | 2.0106 | 0 | IWP_1025 | 0 | 156.823 | 0 | 156.823
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1025 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1025 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 18 | 18 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 1.1765 | 1 | 110 | 0 | 21.177 | 21.177 | 0 | 0 | IWP_1025 | 2329.47 | 0 | 0 | 2329.47
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1025 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1025 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1025 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1025 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1025 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1025 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1025 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 2.86 | 1 | 110 | 0 | 5.72 | 5.72 | 0 | 0 | IWP_1025 | 629.2 | 0 | 0 | 629.2
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1025 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1025 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1025 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 4.295 | 4.295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.80606 | 0.80606 | 0 | 0 | IWP_1025 | 88.6662 | 0 | 0 | 88.6662
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 250 | 0 | 0 | 250
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 250 | 0 | 0 | 250
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 950 | 0 | 0 | 950
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 4.7245 | 0 | 4.7245 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 4.2318 | 0 | 4.2318 | 0 | IWP_1025 | 0 | 330.0801 | 0 | 330.0801
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 2 | Erection of Field Run Pipe - NB 2 SchXST | LM | 16.1557 | 0 | 16.1557 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0237 | 0.75 | 78 | 0 | 12.4036 | 0 | 12.4036 | 0 | IWP_1025 | 0 | 967.4811 | 0 | 967.4811
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1025 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 1.95 | 0 | 1.95 | 0 | IWP_1025 | 0 | 152.1 | 0 | 152.1
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1025 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1025 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 8.5 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 5.8012 | 0 | 5.8012 | 0 | IWP_1025 | 0 | 452.4975 | 0 | 452.4975
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 6 | 0 | 6 | 0 | IWP_1025 | 0 | 468 | 0 | 468
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 2 | Field Coating - NB 2 | LM | 16.1557 | 0 | 16.1557 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 60 | 0 | 0 | 0 | 0 | IWP_1025 | 0 | 969.342 | 0 | 969.342
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1026 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.726 | 0.726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.13625 | 0.13625 | 0 | 0 | IWP_1026 | 14.9876 | 0 | 0 | 14.9876
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 500 | 0 | 0 | 500
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 2 | Field Butt Weld - NB 2 SchXST | EA | 3 | 0 | 3 | 0 | 6 | 0 | 9 | 0 | 9 | CS | 1.6003 | 0.75 | 78 | 0 | 3.6007 | 0 | 3.6007 | 0 | IWP_1026 | 0 | 280.8526 | 0 | 280.8526
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.7986 | 0 | 0.7986 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.71532 | 0 | 0.71532 | 0 | IWP_1026 | 0 | 55.7947 | 0 | 55.7947
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 2 | Erection of Field Run Pipe - NB 2 SchXST | LM | 54.4313 | 0 | 54.4313 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0237 | 0.75 | 78 | 0 | 41.7898 | 0 | 41.7898 | 0 | IWP_1026 | 0 | 3259.6082 | 0 | 3259.6082
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 2.73 | 0 | 2.73 | 0 | IWP_1026 | 0 | 212.94 | 0 | 212.94
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 12 | 0 | 12 | 0 | IWP_1026 | 0 | 936 | 0 | 936
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | 600 | 150-60-F-610 | 150-60-F-610 - Field X-Ray | 2 | Field X-Ray - NB 2 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 750 | 0 | 0 | 0 | 0 | IWP_1026 | 0 | 2250 | 0 | 2250
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 2 | Field Coating - NB 2 | LM | 54.4313 | 0 | 54.4313 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 60 | 0 | 0 | 0 | 0 | IWP_1026 | 0 | 3265.878 | 0 | 3265.878
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 20 | 20 | 0 | 0 | 40 | 60 | 0 | 0 | 60 | CS | 1.1765 | 1 | 110 | 0 | 23.53 | 23.53 | 0 | 0 | IWP_1026 | 2588.3 | 0 | 0 | 2588.3
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1026 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1026 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1026 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 2.86 | 1 | 110 | 0 | 2.86 | 2.86 | 0 | 0 | IWP_1026 | 314.6 | 0 | 0 | 314.6
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1026 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1026 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 26.833 | 26.833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 5.0358 | 5.0358 | 0 | 0 | IWP_1026 | 553.9418 | 0 | 0 | 553.9418
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 250 | 0 | 0 | 250
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 1000 | 0 | 0 | 1000
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 16.8 | 16.8 | 0 | 0 | IWP_1026 | 1848 | 0 | 0 | 1848
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1026 | 1500 | 0 | 0 | 1500
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 29.5163 | 0 | 29.5163 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 26.4381 | 0 | 26.4381 | 0 | IWP_1026 | 0 | 2062.1744 | 0 | 2062.1744
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 2 | Erection of Field Run Pipe - NB 2 SchXST | LM | 30.1246 | 0 | 30.1246 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0237 | 0.75 | 78 | 0 | 23.1283 | 0 | 23.1283 | 0 | IWP_1026 | 0 | 1804.006 | 0 | 1804.006
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1026 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 3.4125 | 0 | 3.4125 | 0 | IWP_1026 | 0 | 266.175 | 0 | 266.175
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 11.25 | 0 | 11.25 | 0 | IWP_1026 | 0 | 877.5 | 0 | 877.5
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 2 | Field Coating - NB 2 | LM | 30.1246 | 0 | 30.1246 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 60 | 0 | 0 | 0 | 0 | IWP_1026 | 0 | 1807.476 | 0 | 1807.476
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 18 | 18 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 1.1765 | 1 | 110 | 0 | 21.177 | 21.177 | 0 | 0 | IWP_1026 | 2329.47 | 0 | 0 | 2329.47
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 4.718 | 4.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.88544 | 0.88544 | 0 | 0 | IWP_1026 | 97.3986 | 0 | 0 | 97.3986
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 900 | 0 | 0 | 900
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1026 | 616 | 0 | 0 | 616
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1026 | 500 | 0 | 0 | 500
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 2 | Field Butt Weld - NB 2 SchXST | EA | 1 | 0 | 1 | 0 | 2 | 0 | 3 | 0 | 3 | CS | 1.6003 | 0.75 | 78 | 0 | 1.2002 | 0 | 1.2002 | 0 | IWP_1026 | 0 | 93.6175 | 0 | 93.6175
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 5.1898 | 0 | 5.1898 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 4.6486 | 0 | 4.6486 | 0 | IWP_1026 | 0 | 362.5886 | 0 | 362.5886
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 2 | Erection of Field Run Pipe - NB 2 SchXST | LM | 47.0998 | 0 | 47.0998 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0237 | 0.75 | 78 | 0 | 36.1611 | 0 | 36.1611 | 0 | IWP_1026 | 0 | 2820.5627 | 0 | 2820.5627
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1026 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1026 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1026 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 12 | 0 | 12 | 0 | IWP_1026 | 0 | 936 | 0 | 936
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 600 | 150-60-F-610 | 150-60-F-610 - Field X-Ray | 2 | Field X-Ray - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 750 | 0 | 0 | 0 | 0 | IWP_1026 | 0 | 750 | 0 | 750
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 2 | Field Coating - NB 2 | LM | 47.0998 | 0 | 47.0998 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 60 | 0 | 0 | 0 | 0 | IWP_1026 | 0 | 2825.988 | 0 | 2825.988
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1025 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1025 | 200 | 0 | 0 | 200
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1025 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1025 | 0 | 117 | 0 | 117
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 6 | 0 | 0 | 18 | 18 | 0 | 0 | 18 | CS | 1.3715 | 1 | 110 | 0 | 8.229 | 8.229 | 0 | 0 | IWP_1026 | 905.19 | 0 | 0 | 905.19
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1026 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1026 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1026 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1026 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1026 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1026 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 0.868 | 0.868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.15179 | 0.15179 | 0 | 0 | IWP_1026 | 16.6973 | 0 | 0 | 16.6973
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 250 | 0 | 0 | 250
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 300 | 0 | 0 | 300
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 0.9548 | 0 | 0.9548 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.83385 | 0 | 0.83385 | 0 | IWP_1026 | 0 | 65.04 | 0 | 65.04
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1026 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install valve - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.56 | 0.75 | 78 | 0 | 1.17 | 0 | 1.17 | 0 | IWP_1026 | 0 | 91.26 | 0 | 91.26
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1026 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 3.375 | 0 | 3.375 | 0 | IWP_1026 | 0 | 263.25 | 0 | 263.25
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1026 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 10 | 10 | 0 | 0 | 30 | 30 | 0 | 0 | 30 | CS | 1.3715 | 1 | 110 | 0 | 13.715 | 13.715 | 0 | 0 | IWP_1026 | 1508.65 | 0 | 0 | 1508.65
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.393 | 2.393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.4491 | 0.4491 | 0 | 0 | IWP_1026 | 49.4012 | 0 | 0 | 49.4012
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 4.639 | 4.639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.81126 | 0.81126 | 0 | 0 | IWP_1026 | 89.2381 | 0 | 0 | 89.2381
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 200 | 0 | 0 | 200
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 500 | 0 | 0 | 500
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 6 | 6 | 0 | 0 | IWP_1026 | 660 | 0 | 0 | 660
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1026 | 600 | 0 | 0 | 600
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.6323 | 0 | 2.6323 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.3578 | 0 | 2.3578 | 0 | IWP_1026 | 0 | 183.9073 | 0 | 183.9073
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 5.1029 | 0 | 5.1029 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 4.4565 | 0 | 4.4565 | 0 | IWP_1026 | 0 | 347.6043 | 0 | 347.6043
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1026 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1026 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1026 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 3.375 | 0 | 3.375 | 0 | IWP_1026 | 0 | 263.25 | 0 | 263.25
Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1026 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 11.466 | 11.466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 2.1519 | 2.1519 | 0 | 0 | IWP_1026 | 236.7047 | 0 | 0 | 236.7047
Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1026 | 300 | 0 | 0 | 300
Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1026 | 616 | 0 | 0 | 616
Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1026 | 500 | 0 | 0 | 500
Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 12.6126 | 0 | 12.6126 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 11.2973 | 0 | 11.2973 | 0 | IWP_1026 | 0 | 881.187 | 0 | 881.187
Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.0237 | 0 | 1.0237 | 0 | IWP_1026 | 0 | 79.8525 | 0 | 79.8525
Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 3 | 0 | 3 | 0 | IWP_1026 | 0 | 234 | 0 | 234
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1027 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 28 | 28 | 0 | 0 | 448 | 1344 | 0 | 0 | 1344 | CS | 14.365 | 1 | 110 | 0 | 402.22 | 402.22 | 0 | 0 | IWP_1027 | 44244.2 | 0 | 0 | 44244.2
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 3 | 0 | 0 | 6 | 18 | 0 | 0 | 18 | CS | 5.46 | 1 | 110 | 0 | 16.38 | 16.38 | 0 | 0 | IWP_1027 | 1801.8 | 0 | 0 | 1801.8
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 2 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.429 | 1 | 110 | 0 | 0.429 | 0.429 | 0 | 0 | IWP_1027 | 47.19 | 0 | 0 | 47.19
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 80.242 | 80.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 63.6597 | 63.6597 | 0 | 0 | IWP_1027 | 7002.5619 | 0 | 0 | 7002.5619
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1027 | 1000 | 0 | 0 | 1000
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1027 | 50 | 0 | 0 | 50
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 16 | Shop Hydrotest - NB 16 Sch80 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 17.6 | 1 | 110 | 0 | 105.6 | 105.6 | 0 | 0 | IWP_1027 | 11616 | 0 | 0 | 11616
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 16 | Shop Spools Coating - NB 16 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2100 | 0 | 0 | 0 | 0 | IWP_1027 | 12600 | 0 | 0 | 12600
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 92.2783 | 0 | 0 | 92.2783 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 1 | 110 | 0 | 471.1328 | 0 | 0 | 471.1328 | IWP_1027 | 0 | 0 | 51824.6053 | 51824.6053
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 5.07 | 0 | 0 | 5.07 | IWP_1027 | 0 | 0 | 557.7 | 557.7
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 0.585 | 0 | 0 | 0.585 | IWP_1027 | 0 | 0 | 64.35 | 64.35
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 5.5 | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 6.435 | 0 | 0 | 6.435 | IWP_1027 | 0 | 0 | 707.85 | 707.85
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 1 | 110 | 0 | 47.32 | 0 | 0 | 47.32 | IWP_1027 | 0 | 0 | 5205.2 | 5205.2
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 11 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 1 | 110 | 0 | 23.2172 | 0 | 0 | 23.2172 | IWP_1027 | 0 | 0 | 2553.8873 | 2553.8873
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 16 | Field Butt Weld - NB 16 Sch80 | EA | 2 | 0 | 2 | 0 | 32 | 0 | 96 | 0 | 96 | CS | 20.3905 | 0.75 | 78 | 0 | 30.5858 | 0 | 30.5858 | 0 | IWP_1027 | 0 | 2385.6885 | 0 | 2385.6885
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1027 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 14 | 14 | 0 | 0 | 224 | 672 | 0 | 0 | 672 | CS | 14.365 | 1 | 110 | 0 | 201.11 | 201.11 | 0 | 0 | IWP_1027 | 22122.1 | 0 | 0 | 22122.1
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1027 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 8.302 | 8.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 6.5864 | 6.5864 | 0 | 0 | IWP_1027 | 724.4993 | 0 | 0 | 724.4993
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1027 | 500 | 0 | 0 | 500
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 16 | Shop Hydrotest - NB 16 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 17.6 | 1 | 110 | 0 | 17.6 | 17.6 | 0 | 0 | IWP_1027 | 1936 | 0 | 0 | 1936
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 16 | Shop Spools Coating - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2100 | 0 | 0 | 0 | 0 | IWP_1027 | 2100 | 0 | 0 | 2100
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 9.5473 | 0 | 0 | 9.5473 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 1 | 110 | 0 | 48.7444 | 0 | 0 | 48.7444 | IWP_1027 | 0 | 0 | 5361.8787 | 5361.8787
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Blind - NB 16 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 11.44 | 1 | 110 | 0 | 11.44 | 0 | 0 | 11.44 | IWP_1027 | 0 | 0 | 1258.4 | 1258.4
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 0 | 0 | 1.17 | IWP_1027 | 0 | 0 | 128.7 | 128.7
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 1 | 110 | 0 | 16.9 | 0 | 0 | 16.9 | IWP_1027 | 0 | 0 | 1859 | 1859
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1028 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 2 | 2 | 0 | 0 | 32 | 96 | 0 | 0 | 96 | CS | 14.365 | 1 | 110 | 0 | 28.73 | 28.73 | 0 | 0 | IWP_1028 | 3160.3 | 0 | 0 | 3160.3
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 1 | 1 | 0 | 0 | 20 | 65 | 0 | 0 | 65 | CS | 21.7588 | 1 | 110 | 0 | 21.7588 | 21.7588 | 0 | 0 | IWP_1028 | 2393.4625 | 0 | 0 | 2393.4625
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 24 | Shop Butt Weld - NB 24 Sch80 | EA | 25 | 25 | 0 | 0 | 600 | 1950 | 0 | 0 | 1950 | CS | 33.1998 | 1 | 110 | 0 | 829.9958 | 829.9958 | 0 | 0 | IWP_1028 | 91299.5417 | 0 | 0 | 91299.5417
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1028 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 24 | Shop handling - NB 24 Sch80 | LM | 61.211 | 61.211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 1 | 110 | 0 | 71.2757 | 71.2757 | 0 | 0 | IWP_1028 | 7840.3308 | 0 | 0 | 7840.3308
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 24 | Shop X-Ray - NB 24 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1028 | 2000 | 0 | 0 | 2000
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 24 | Shop Hydrotest - NB 24 Sch80 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 62.6 | 1 | 110 | 0 | 313 | 313 | 0 | 0 | IWP_1028 | 34430 | 0 | 0 | 34430
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 24 | Shop Spools Coating - NB 24 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2880 | 0 | 0 | 0 | 0 | IWP_1028 | 14400 | 0 | 0 | 14400
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 24 | Install Spools - NB 24 Sch80 | LM | 70.3927 | 0 | 0 | 70.3927 | 0 | 0 | 0 | 0 | 0 | CS | 7.4941 | 1 | 110 | 0 | 527.5318 | 0 | 0 | 527.5318 | IWP_1028 | 0 | 0 | 58028.5 | 58028.5
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 0 | 0 | 1.69 | IWP_1028 | 0 | 0 | 185.9 | 185.9
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 2.34 | 0 | 0 | 2.34 | IWP_1028 | 0 | 0 | 257.4 | 257.4
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 1 | 110 | 0 | 3.38 | 0 | 0 | 3.38 | IWP_1028 | 0 | 0 | 371.8 | 371.8
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 1 | 110 | 0 | 4.29 | 0 | 0 | 4.29 | IWP_1028 | 0 | 0 | 471.9 | 471.9
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 24 | Flange Bolt-Up - NB 24 CL600 | EA | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | CS | 10.27 | 1 | 110 | 0 | 61.62 | 0 | 0 | 61.62 | IWP_1028 | 0 | 0 | 6778.2 | 6778.2
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 24 | Erection of Pipe Supports - NB 24 | EA | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | CS | 2.5655 | 1 | 110 | 0 | 25.6551 | 0 | 0 | 25.6551 | IWP_1028 | 0 | 0 | 2822.0599 | 2822.0599
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 24 | Field Butt Weld - NB 24 Sch80 | EA | 1 | 0 | 1 | 0 | 24 | 0 | 78 | 0 | 78 | CS | 40.3455 | 0.75 | 78 | 0 | 30.2591 | 0 | 30.2591 | 0 | IWP_1028 | 0 | 2360.2117 | 0 | 2360.2117
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1029 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 20 | 20 | 0 | 0 | 400 | 1300 | 0 | 0 | 1300 | CS | 21.7588 | 1 | 110 | 0 | 435.175 | 435.175 | 0 | 0 | IWP_1029 | 47869.25 | 0 | 0 | 47869.25
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1029 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 Sch80 | LM | 53.197 | 53.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 54.6832 | 54.6832 | 0 | 0 | IWP_1029 | 6015.1499 | 0 | 0 | 6015.1499
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1029 | 1500 | 0 | 0 | 1500
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 20 | Shop Hydrotest - NB 20 Sch80 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 164.8 | 164.8 | 0 | 0 | IWP_1029 | 18128 | 0 | 0 | 18128
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 20 | Shop Spools Coating - NB 20 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2700 | 0 | 0 | 0 | 0 | IWP_1029 | 10800 | 0 | 0 | 10800
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 20 | Install Spools - NB 20 Sch80 | LM | 61.1765 | 0 | 0 | 61.1765 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 1 | 110 | 0 | 405.4951 | 0 | 0 | 405.4951 | IWP_1029 | 0 | 0 | 44604.4577 | 44604.4577
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 0 | 0 | 1.69 | IWP_1029 | 0 | 0 | 185.9 | 185.9
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 2.34 | 0 | 0 | 2.34 | IWP_1029 | 0 | 0 | 257.4 | 257.4
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 4.5 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 1 | 110 | 0 | 38.61 | 0 | 0 | 38.61 | IWP_1029 | 0 | 0 | 4247.1 | 4247.1
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 20 | Erection of Pipe Supports - NB 20 | EA | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | CS | 2.327 | 1 | 110 | 0 | 11.635 | 0 | 0 | 11.635 | IWP_1029 | 0 | 0 | 1279.8458 | 1279.8458
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 20 | Field Butt Weld - NB 20 Sch80 | EA | 1 | 0 | 1 | 0 | 20 | 0 | 65 | 0 | 65 | CS | 31.2637 | 0.75 | 78 | 0 | 23.4478 | 0 | 23.4478 | 0 | IWP_1029 | 0 | 1828.9264 | 0 | 1828.9264
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1030 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 30 | 30 | 0 | 0 | 600 | 1950 | 0 | 0 | 1950 | CS | 21.7588 | 1 | 110 | 0 | 652.7625 | 652.7625 | 0 | 0 | IWP_1030 | 71803.875 | 0 | 0 | 71803.875
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 3 | 0 | 0 | 6 | 18 | 0 | 0 | 18 | CS | 5.46 | 1 | 110 | 0 | 16.38 | 16.38 | 0 | 0 | IWP_1030 | 1801.8 | 0 | 0 | 1801.8
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 Sch80 | LM | 28.243 | 28.243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 29.032 | 29.032 | 0 | 0 | IWP_1030 | 3193.5236 | 0 | 0 | 3193.5236
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1030 | 50 | 0 | 0 | 50
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1030 | 2000 | 0 | 0 | 2000
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 20 | Shop Hydrotest - NB 20 Sch80 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 82.4 | 82.4 | 0 | 0 | IWP_1030 | 9064 | 0 | 0 | 9064
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 20 | Shop Spools Coating - NB 20 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2700 | 0 | 0 | 0 | 0 | IWP_1030 | 5400 | 0 | 0 | 5400
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 20 | Install Spools - NB 20 Sch80 | LM | 32.4794 | 0 | 0 | 32.4794 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 1 | 110 | 0 | 215.2828 | 0 | 0 | 215.2828 | IWP_1030 | 0 | 0 | 23681.1042 | 23681.1042
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 5.07 | 0 | 0 | 5.07 | IWP_1030 | 0 | 0 | 557.7 | 557.7
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 20 | Install valve - NB 20 CL600 | EA | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 1 | 110 | 0 | 46.41 | 0 | 0 | 46.41 | IWP_1030 | 0 | 0 | 5105.1 | 5105.1
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 7.02 | 0 | 0 | 7.02 | IWP_1030 | 0 | 0 | 772.2 | 772.2
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 9.5 | 0 | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 1 | 110 | 0 | 81.51 | 0 | 0 | 81.51 | IWP_1030 | 0 | 0 | 8966.1 | 8966.1
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 20 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 2.327 | 1 | 110 | 0 | 2.327 | 0 | 0 | 2.327 | IWP_1030 | 0 | 0 | 255.9692 | 255.9692
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1031 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 1 | 1 | 0 | 0 | 20 | 65 | 0 | 0 | 65 | CS | 21.7588 | 1 | 110 | 0 | 21.7588 | 21.7588 | 0 | 0 | IWP_1031 | 2393.4625 | 0 | 0 | 2393.4625
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 24 | Shop Butt Weld - NB 24 Sch80 | EA | 26 | 26 | 0 | 0 | 624 | 2028 | 0 | 0 | 2028 | CS | 33.1998 | 1 | 110 | 0 | 863.1957 | 863.1957 | 0 | 0 | IWP_1031 | 94951.5233 | 0 | 0 | 94951.5233
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1031 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 24 | Shop handling - NB 24 Sch80 | LM | 42.209 | 42.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 1 | 110 | 0 | 49.1493 | 49.1493 | 0 | 0 | IWP_1031 | 5406.4225 | 0 | 0 | 5406.4225
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1031 | 50 | 0 | 0 | 50
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 24 | Shop X-Ray - NB 24 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1031 | 2000 | 0 | 0 | 2000
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 24 | Shop Hydrotest - NB 24 Sch80 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 62.6 | 1 | 110 | 0 | 187.8 | 187.8 | 0 | 0 | IWP_1031 | 20658 | 0 | 0 | 20658
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 24 | Shop Spools Coating - NB 24 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2880 | 0 | 0 | 0 | 0 | IWP_1031 | 8640 | 0 | 0 | 8640
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 24 | Install Spools - NB 24 Sch80 | LM | 48.5403 | 0 | 0 | 48.5403 | 0 | 0 | 0 | 0 | 0 | CS | 7.4941 | 1 | 110 | 0 | 363.7678 | 0 | 0 | 363.7678 | IWP_1031 | 0 | 0 | 40014.4575 | 40014.4575
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 3.38 | 0 | 0 | 3.38 | IWP_1031 | 0 | 0 | 371.8 | 371.8
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 24 | Install valve - NB 24 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 17.68 | 1 | 110 | 0 | 17.68 | 0 | 0 | 17.68 | IWP_1031 | 0 | 0 | 1944.8 | 1944.8
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 4.68 | 0 | 0 | 4.68 | IWP_1031 | 0 | 0 | 514.8 | 514.8
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 1 | 110 | 0 | 4.29 | 0 | 0 | 4.29 | IWP_1031 | 0 | 0 | 471.9 | 471.9
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 24 | Flange Bolt-Up - NB 24 CL600 | EA | 6.5 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | CS | 10.27 | 1 | 110 | 0 | 66.755 | 0 | 0 | 66.755 | IWP_1031 | 0 | 0 | 7343.05 | 7343.05
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 24 | Erection of Pipe Supports - NB 24 | EA | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | CS | 2.5655 | 1 | 110 | 0 | 23.0896 | 0 | 0 | 23.0896 | IWP_1031 | 0 | 0 | 2539.8539 | 2539.8539
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 24 | Field Butt Weld - NB 24 Sch80 | EA | 1 | 0 | 1 | 0 | 24 | 0 | 78 | 0 | 78 | CS | 40.3455 | 0.75 | 78 | 0 | 30.2591 | 0 | 30.2591 | 0 | IWP_1031 | 0 | 2360.2117 | 0 | 2360.2117
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1032 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 SchSTD | EA | 2 | 2 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 4.7255 | 1 | 110 | 0 | 9.451 | 9.451 | 0 | 0 | IWP_1032 | 1039.61 | 0 | 0 | 1039.61
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 SchSTD | EA | 2 | 2 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 8.8313 | 1 | 110 | 0 | 17.6627 | 17.6627 | 0 | 0 | IWP_1032 | 1942.8933 | 0 | 0 | 1942.8933
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 SchXST | EA | 2 | 2 | 0 | 0 | 40 | 80 | 0 | 0 | 80 | CS | 13.6121 | 1 | 110 | 0 | 27.2242 | 27.2242 | 0 | 0 | IWP_1032 | 2994.6583 | 0 | 0 | 2994.6583
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 24 | Shop Butt Weld - NB 24 SchXST | EA | 10 | 10 | 0 | 0 | 240 | 480 | 0 | 0 | 480 | CS | 17.7732 | 1 | 110 | 0 | 177.7317 | 177.7317 | 0 | 0 | IWP_1032 | 19550.4833 | 0 | 0 | 19550.4833
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1032 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 24 | Shop handling - NB 24 SchXST | LM | 12.399 | 12.399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 1 | 110 | 0 | 14.4377 | 14.4377 | 0 | 0 | IWP_1032 | 1588.1502 | 0 | 0 | 1588.1502
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1032 | 50 | 0 | 0 | 50
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 24 | Shop X-Ray - NB 24 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1032 | 1000 | 0 | 0 | 1000
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 24 | Shop Hydrotest - NB 24 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 30.8 | 1 | 110 | 0 | 30.8 | 30.8 | 0 | 0 | IWP_1032 | 3388 | 0 | 0 | 3388
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 24 | Shop Spools Coating - NB 24 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2880 | 0 | 0 | 0 | 0 | IWP_1032 | 2880 | 0 | 0 | 2880
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 24 | Install Spools - NB 24 SchXST | LM | 14.2588 | 0 | 0 | 14.2588 | 0 | 0 | 0 | 0 | 0 | CS | 7.4941 | 1 | 110 | 0 | 106.8577 | 0 | 0 | 106.8577 | IWP_1032 | 0 | 0 | 11754.3476 | 11754.3476
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 3.38 | 0 | 0 | 3.38 | IWP_1032 | 0 | 0 | 371.8 | 371.8
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 4.68 | 0 | 0 | 4.68 | IWP_1032 | 0 | 0 | 514.8 | 514.8
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 1 | 110 | 0 | 2.665 | 0 | 0 | 2.665 | IWP_1032 | 0 | 0 | 293.15 | 293.15
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 1 | 110 | 0 | 3.38 | 0 | 0 | 3.38 | IWP_1032 | 0 | 0 | 371.8 | 371.8
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 1 | 110 | 0 | 4.29 | 0 | 0 | 4.29 | IWP_1032 | 0 | 0 | 471.9 | 471.9
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 24 | Flange Bolt-Up - NB 24 CL600 | EA | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | CS | 10.27 | 1 | 110 | 0 | 15.405 | 0 | 0 | 15.405 | IWP_1032 | 0 | 0 | 1694.55 | 1694.55
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 24 | Erection of Pipe Supports - NB 24 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 2.5655 | 1 | 110 | 0 | 2.5655 | 0 | 0 | 2.5655 | IWP_1032 | 0 | 0 | 282.206 | 282.206
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1032 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 SchSTD | EA | 4 | 4 | 0 | 0 | 48 | 72 | 0 | 0 | 72 | CS | 4.7255 | 1 | 110 | 0 | 18.902 | 18.902 | 0 | 0 | IWP_1032 | 2079.22 | 0 | 0 | 2079.22
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1032 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 SchSTD | LM | 13.44 | 13.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.40947 | 1 | 110 | 0 | 5.5033 | 5.5033 | 0 | 0 | IWP_1032 | 605.3587 | 0 | 0 | 605.3587
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1032 | 250 | 0 | 0 | 250
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12.2 | 1 | 110 | 0 | 12.2 | 12.2 | 0 | 0 | IWP_1032 | 1342 | 0 | 0 | 1342
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1032 | 1700 | 0 | 0 | 1700
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 12 | Install Spools - NB 12 SchSTD | LM | 15.456 | 0 | 0 | 15.456 | 0 | 0 | 0 | 0 | 0 | CS | 2.6274 | 1 | 110 | 0 | 40.6095 | 0 | 0 | 40.6095 | IWP_1032 | 0 | 0 | 4467.0425 | 4467.0425
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 0 | 0 | 1.17 | IWP_1032 | 0 | 0 | 128.7 | 128.7
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 1 | 110 | 0 | 5.33 | 0 | 0 | 5.33 | IWP_1032 | 0 | 0 | 586.3 | 586.3
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1032 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 SchXST | EA | 4 | 4 | 0 | 0 | 80 | 160 | 0 | 0 | 160 | CS | 13.6121 | 1 | 110 | 0 | 54.4483 | 54.4483 | 0 | 0 | IWP_1032 | 5989.3167 | 0 | 0 | 5989.3167
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1032 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 SchXST | LM | 2.414 | 2.414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 2.4814 | 2.4814 | 0 | 0 | IWP_1032 | 272.9585 | 0 | 0 | 272.9585
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1032 | 50 | 0 | 0 | 50
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1032 | 500 | 0 | 0 | 500
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 20 | Install Spools - NB 20 SchXST | LM | 2.7761 | 0 | 0 | 2.7761 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 1 | 110 | 0 | 18.4008 | 0 | 0 | 18.4008 | IWP_1032 | 0 | 0 | 2024.0833 | 2024.0833
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 1.755 | 0 | 0 | 1.755 | IWP_1032 | 0 | 0 | 193.05 | 193.05
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 1 | 110 | 0 | 8.58 | 0 | 0 | 8.58 | IWP_1032 | 0 | 0 | 943.8 | 943.8
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1033 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 SchSTD | EA | 12 | 12 | 0 | 0 | 192 | 288 | 0 | 0 | 288 | CS | 8.8313 | 1 | 110 | 0 | 105.976 | 105.976 | 0 | 0 | IWP_1033 | 11657.36 | 0 | 0 | 11657.36
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1033 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 SchSTD | LM | 43.76 | 43.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.58861 | 1 | 110 | 0 | 25.7576 | 25.7576 | 0 | 0 | IWP_1033 | 2833.3398 | 0 | 0 | 2833.3398
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1033 | 500 | 0 | 0 | 500
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 16 | Shop Hydrotest - NB 16 SchSTD | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.6 | 1 | 110 | 0 | 46.8 | 46.8 | 0 | 0 | IWP_1033 | 5148 | 0 | 0 | 5148
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 16 | Shop Spools Coating - NB 16 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2100 | 0 | 0 | 0 | 0 | IWP_1033 | 6300 | 0 | 0 | 6300
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 16 | Install Spools - NB 16 SchSTD | LM | 50.324 | 0 | 0 | 50.324 | 0 | 0 | 0 | 0 | 0 | CS | 3.7919 | 1 | 110 | 0 | 190.8211 | 0 | 0 | 190.8211 | IWP_1033 | 0 | 0 | 20990.3259 | 20990.3259
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 0 | 0 | 1.69 | IWP_1033 | 0 | 0 | 185.9 | 185.9
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install Blind - NB 16 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 11.44 | 1 | 110 | 0 | 11.44 | 0 | 0 | 11.44 | IWP_1033 | 0 | 0 | 1258.4 | 1258.4
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 16 | Install valve - NB 16 CL600 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 11.44 | 1 | 110 | 0 | 11.44 | 0 | 0 | 11.44 | IWP_1033 | 0 | 0 | 1258.4 | 1258.4
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 1 | 110 | 0 | 2.34 | 0 | 0 | 2.34 | IWP_1033 | 0 | 0 | 257.4 | 257.4
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 1 | 110 | 0 | 40.56 | 0 | 0 | 40.56 | IWP_1033 | 0 | 0 | 4461.6 | 4461.6
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 1 | 110 | 0 | 8.4426 | 0 | 0 | 8.4426 | IWP_1033 | 0 | 0 | 928.6863 | 928.6863
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 16 | Field Butt Weld - NB 16 SchSTD | EA | 1 | 0 | 1 | 0 | 16 | 0 | 24 | 0 | 24 | CS | 11.6532 | 0.75 | 78 | 0 | 8.7399 | 0 | 8.7399 | 0 | IWP_1033 | 0 | 681.7122 | 0 | 681.7122
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1034 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 2.86 | 1 | 110 | 0 | 5.72 | 5.72 | 0 | 0 | IWP_1034 | 629.2 | 0 | 0 | 629.2
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 4 | 4 | 0 | 0 | 4 | 10 | 0 | 0 | 10 | CS | 0.39 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 3 | 3 | 0 | 0 | 3 | 7.5 | 0 | 0 | 7.5 | CS | 0.39 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1034 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 10 | 0 | 0 | 10 | CS | 0.39 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 3.492 | 3.492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.65535 | 0.65535 | 0 | 0 | IWP_1034 | 72.089 | 0 | 0 | 72.089
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 100 | 0 | 0 | 100
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 200 | 0 | 0 | 200
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 3.8412 | 0 | 0 | 3.8412 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 1 | 110 | 0 | 4.5875 | 0 | 0 | 4.5875 | IWP_1034 | 0 | 0 | 504.6232 | 504.6232
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0 | 0 | 0.78 | IWP_1034 | 0 | 0 | 85.8 | 85.8
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 1 | 110 | 0 | 1.365 | 0 | 0 | 1.365 | IWP_1034 | 0 | 0 | 150.15 | 150.15
Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 1 | 110 | 0 | 1 | 0 | 0 | 1 | IWP_1034 | 0 | 0 | 110 | 110
Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1034 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 3.297 | 3.297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.61876 | 0.61876 | 0 | 0 | IWP_1034 | 68.0634 | 0 | 0 | 68.0634
Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 300 | 0 | 0 | 300
Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | 500 | 150-20-M-210 | 150-20-M-210 - Module Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 3.6267 | 0 | 0 | 3.6267 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 1 | 110 | 0 | 4.3313 | 0 | 0 | 4.3313 | IWP_1034 | 0 | 0 | 476.4441 | 476.4441
Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | 500 | 150-30-M-310 | 150-30-M-310 - Module Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL150 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0 | 0 | 0.65 | IWP_1034 | 0 | 0 | 71.5 | 71.5
Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | 500 | 150-40-M-410 | 150-40-M-410 - Module Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 0 | 0 | 1.82 | IWP_1034 | 0 | 0 | 200.2 | 200.2
Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | 500 | 150-50-M-510 | 150-50-M-510 - Module Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 1 | 110 | 0 | 1 | 0 | 0 | 1 | IWP_1034 | 0 | 0 | 110 | 110
Proj_A | Area_3 | TR | TR-XP01-8092 | ISO4012 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1034 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_3 | TR | TR-XP01-8095 | ISO4015 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1034 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1034 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1034 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 250 | 0 | 0 | 250
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 50 | 0 | 0 | 50
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1034 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1034 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_3 | TR | TR-XP01-8098 | ISO4023 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install valve - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.56 | 0.75 | 78 | 0 | 1.17 | 0 | 1.17 | 0 | IWP_1034 | 0 | 91.26 | 0 | 91.26
Proj_A | Area_3 | TR | TR-XP01-8098 | ISO4023 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1034 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_3 | TR | TR-ZL01-8088 | ISO4010 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL01-8091 | ISO4017 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL01-8116 | ISO3026 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8089 | ISO4011 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8090 | ISO4016 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8093 | ISO4013 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8094 | ISO4014 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1034 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1034 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1034 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1034 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1034 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.856 | 0.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.16065 | 0.16065 | 0 | 0 | IWP_1034 | 17.6713 | 0 | 0 | 17.6713
Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 300 | 0 | 0 | 300
Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.9416 | 0 | 0.9416 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.8434 | 0 | 0.8434 | 0 | IWP_1034 | 0 | 65.7855 | 0 | 65.7855
Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1034 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1034 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 25 | 25 | 0 | 0 | 50 | 75 | 0 | 0 | 75 | CS | 1.1765 | 1 | 110 | 0 | 29.4125 | 29.4125 | 0 | 0 | IWP_1034 | 3235.375 | 0 | 0 | 3235.375
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1034 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 12.718 | 12.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 2.3868 | 2.3868 | 0 | 0 | IWP_1034 | 262.5511 | 0 | 0 | 262.5511
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 250 | 0 | 0 | 250
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 1250 | 0 | 0 | 1250
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1034 | 616 | 0 | 0 | 616
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1034 | 500 | 0 | 0 | 500
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 13.9898 | 0 | 13.9898 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 12.5308 | 0 | 12.5308 | 0 | IWP_1034 | 0 | 977.406 | 0 | 977.406
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.365 | 0 | 1.365 | 0 | IWP_1034 | 0 | 106.47 | 0 | 106.47
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1034 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 3 | 0 | 3 | 0 | IWP_1034 | 0 | 234 | 0 | 234
Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.1765 | 1 | 110 | 0 | 3.5295 | 3.5295 | 0 | 0 | IWP_1034 | 388.245 | 0 | 0 | 388.245
Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.257 | 0.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.048232 | 0.048232 | 0 | 0 | IWP_1034 | 5.3055 | 0 | 0 | 5.3055
Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 150 | 0 | 0 | 150
Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.2827 | 0 | 0.2827 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.25322 | 0 | 0.25322 | 0 | IWP_1034 | 0 | 19.751 | 0 | 19.751
Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3039 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1034 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3039 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 50 | 0 | 0 | 50
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3039 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 22 | 22 | 0 | 0 | 44 | 66 | 0 | 0 | 66 | CS | 1.1765 | 1 | 110 | 0 | 25.883 | 25.883 | 0 | 0 | IWP_1034 | 2847.13 | 0 | 0 | 2847.13
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1034 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 5.813 | 5.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.0909 | 1.0909 | 0 | 0 | IWP_1034 | 120.0039 | 0 | 0 | 120.0039
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 250 | 0 | 0 | 250
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 1100 | 0 | 0 | 1100
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1034 | 616 | 0 | 0 | 616
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1034 | 500 | 0 | 0 | 500
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 6.3943 | 0 | 6.3943 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 5.7275 | 0 | 5.7275 | 0 | IWP_1034 | 0 | 446.7417 | 0 | 446.7417
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 2.0475 | 0 | 2.0475 | 0 | IWP_1034 | 0 | 159.705 | 0 | 159.705
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1034 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1034 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1034 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.856 | 0.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.16065 | 0.16065 | 0 | 0 | IWP_1034 | 17.6713 | 0 | 0 | 17.6713
Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 300 | 0 | 0 | 300
Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.9416 | 0 | 0.9416 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.8434 | 0 | 0.8434 | 0 | IWP_1034 | 0 | 65.7855 | 0 | 65.7855
Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1034 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1034 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 24 | 24 | 0 | 0 | 48 | 72 | 0 | 0 | 72 | CS | 1.1765 | 1 | 110 | 0 | 28.236 | 28.236 | 0 | 0 | IWP_1034 | 3105.96 | 0 | 0 | 3105.96
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1034 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 12.427 | 12.427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 2.3322 | 2.3322 | 0 | 0 | IWP_1034 | 256.5436 | 0 | 0 | 256.5436
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 250 | 0 | 0 | 250
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 1200 | 0 | 0 | 1200
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1034 | 616 | 0 | 0 | 616
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1034 | 500 | 0 | 0 | 500
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 13.6697 | 0 | 13.6697 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 12.2441 | 0 | 12.2441 | 0 | IWP_1034 | 0 | 955.042 | 0 | 955.042
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.0237 | 0 | 1.0237 | 0 | IWP_1034 | 0 | 79.8525 | 0 | 79.8525
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1034 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1034 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.1765 | 1 | 110 | 0 | 3.5295 | 3.5295 | 0 | 0 | IWP_1034 | 388.245 | 0 | 0 | 388.245
Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.257 | 0.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.048232 | 0.048232 | 0 | 0 | IWP_1034 | 5.3055 | 0 | 0 | 5.3055
Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 150 | 0 | 0 | 150
Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.2827 | 0 | 0.2827 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.25322 | 0 | 0.25322 | 0 | IWP_1034 | 0 | 19.751 | 0 | 19.751
Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 22 | 22 | 0 | 0 | 44 | 66 | 0 | 0 | 66 | CS | 1.1765 | 1 | 110 | 0 | 25.883 | 25.883 | 0 | 0 | IWP_1034 | 2847.13 | 0 | 0 | 2847.13
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1034 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 5.813 | 5.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.0909 | 1.0909 | 0 | 0 | IWP_1034 | 120.0039 | 0 | 0 | 120.0039
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 250 | 0 | 0 | 250
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 1100 | 0 | 0 | 1100
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1034 | 616 | 0 | 0 | 616
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1034 | 500 | 0 | 0 | 500
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 6.3943 | 0 | 6.3943 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 5.7275 | 0 | 5.7275 | 0 | IWP_1034 | 0 | 446.7417 | 0 | 446.7417
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 2.0475 | 0 | 2.0475 | 0 | IWP_1034 | 0 | 159.705 | 0 | 159.705
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1034 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1034 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1034 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.856 | 0.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.16065 | 0.16065 | 0 | 0 | IWP_1034 | 17.6713 | 0 | 0 | 17.6713
Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 300 | 0 | 0 | 300
Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.9416 | 0 | 0.9416 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.8434 | 0 | 0.8434 | 0 | IWP_1034 | 0 | 65.7855 | 0 | 65.7855
Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1034 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1034 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3043 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1034 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3043 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 50 | 0 | 0 | 50
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3043 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1034 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 29 | 29 | 0 | 0 | 58 | 87 | 0 | 0 | 87 | CS | 1.1765 | 1 | 110 | 0 | 34.1185 | 34.1185 | 0 | 0 | IWP_1034 | 3753.035 | 0 | 0 | 3753.035
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1034 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 16.042 | 16.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 3.0107 | 3.0107 | 0 | 0 | IWP_1034 | 331.1719 | 0 | 0 | 331.1719
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 250 | 0 | 0 | 250
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 1450 | 0 | 0 | 1450
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 11.2 | 11.2 | 0 | 0 | IWP_1034 | 1232 | 0 | 0 | 1232
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1034 | 1000 | 0 | 0 | 1000
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 17.6462 | 0 | 17.6462 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 15.8059 | 0 | 15.8059 | 0 | IWP_1034 | 0 | 1232.8626 | 0 | 1232.8626
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.7062 | 0 | 1.7062 | 0 | IWP_1034 | 0 | 133.0875 | 0 | 133.0875
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1034 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 3.75 | 0 | 3.75 | 0 | IWP_1034 | 0 | 292.5 | 0 | 292.5
Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.1765 | 1 | 110 | 0 | 3.5295 | 3.5295 | 0 | 0 | IWP_1034 | 388.245 | 0 | 0 | 388.245
Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.257 | 0.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.048232 | 0.048232 | 0 | 0 | IWP_1034 | 5.3055 | 0 | 0 | 5.3055
Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 150 | 0 | 0 | 150
Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.2827 | 0 | 0.2827 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.25322 | 0 | 0.25322 | 0 | IWP_1034 | 0 | 19.751 | 0 | 19.751
Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 28 | 28 | 0 | 0 | 56 | 84 | 0 | 0 | 84 | CS | 1.1765 | 1 | 110 | 0 | 32.942 | 32.942 | 0 | 0 | IWP_1034 | 3623.62 | 0 | 0 | 3623.62
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1034 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 0.75 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.5 | 0 | 0 | 1.5 | CS | 2.47 | 1 | 110 | 0 | 2.47 | 2.47 | 0 | 0 | IWP_1034 | 271.7 | 0 | 0 | 271.7
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 12.275 | 12.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 2.3037 | 2.3037 | 0 | 0 | IWP_1034 | 253.4057 | 0 | 0 | 253.4057
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 250 | 0 | 0 | 250
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 1400 | 0 | 0 | 1400
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1034 | 616 | 0 | 0 | 616
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1034 | 500 | 0 | 0 | 500
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 13.5025 | 0 | 13.5025 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 12.0944 | 0 | 12.0944 | 0 | IWP_1034 | 0 | 943.3605 | 0 | 943.3605
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 2.73 | 0 | 2.73 | 0 | IWP_1034 | 0 | 212.94 | 0 | 212.94
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1034 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 3 | 0 | 3 | 0 | IWP_1034 | 0 | 234 | 0 | 234
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 5 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 1.1765 | 1 | 110 | 0 | 5.8825 | 5.8825 | 0 | 0 | IWP_1034 | 647.075 | 0 | 0 | 647.075
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1034 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1034 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1034 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1034 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 3 | 3 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1034 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.107 | 1.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.19831 | 0.19831 | 0 | 0 | IWP_1034 | 21.8142 | 0 | 0 | 21.8142
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.082 | 1.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.20306 | 0.20306 | 0 | 0 | IWP_1034 | 22.3369 | 0 | 0 | 22.3369
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 100 | 0 | 0 | 100
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 50 | 0 | 0 | 50
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.1623 | 0 | 1.1623 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.0151 | 0 | 1.0151 | 0 | IWP_1034 | 0 | 79.1781 | 0 | 79.1781
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1902 | 0 | 1.1902 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.0661 | 0 | 1.0661 | 0 | IWP_1034 | 0 | 83.1541 | 0 | 83.1541
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1034 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1034 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1034 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1034 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO2047 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1034 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO2047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1034 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 5 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 1.1765 | 1 | 110 | 0 | 5.8825 | 5.8825 | 0 | 0 | IWP_1034 | 647.075 | 0 | 0 | 647.075
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1034 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1034 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1034 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1034 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1034 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1034 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1034 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.107 | 1.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.19831 | 0.19831 | 0 | 0 | IWP_1034 | 21.8142 | 0 | 0 | 21.8142
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.082 | 1.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.20306 | 0.20306 | 0 | 0 | IWP_1034 | 22.3369 | 0 | 0 | 22.3369
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 150 | 0 | 0 | 150
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1034 | 50 | 0 | 0 | 50
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.1623 | 0 | 1.1623 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.0151 | 0 | 1.0151 | 0 | IWP_1034 | 0 | 79.1781 | 0 | 79.1781
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1902 | 0 | 1.1902 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.0661 | 0 | 1.0661 | 0 | IWP_1034 | 0 | 83.1541 | 0 | 83.1541
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1034 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1034 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1034 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1034 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3048 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1035 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1035 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1035 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.78 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1035 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1035 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.669 | 2.669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.5009 | 0.5009 | 0 | 0 | IWP_1035 | 55.099 | 0 | 0 | 55.099
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 50 | 0 | 0 | 50
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 100 | 0 | 0 | 100
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.9359 | 0 | 2.9359 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.6297 | 0 | 2.6297 | 0 | IWP_1035 | 0 | 205.1185 | 0 | 205.1185
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1035 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1035 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1035 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1035 | 0 | 117 | 0 | 117
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1035 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.78 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1035 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1035 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.669 | 2.669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.5009 | 0.5009 | 0 | 0 | IWP_1035 | 55.099 | 0 | 0 | 55.099
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 50 | 0 | 0 | 50
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 100 | 0 | 0 | 100
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.9359 | 0 | 2.9359 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.6297 | 0 | 2.6297 | 0 | IWP_1035 | 0 | 205.1185 | 0 | 205.1185
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1035 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1035 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1035 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1035 | 0 | 117 | 0 | 117
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1035 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3047 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1035 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 5 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 1.1765 | 1 | 110 | 0 | 5.8825 | 5.8825 | 0 | 0 | IWP_1035 | 647.075 | 0 | 0 | 647.075
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1035 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 3 | 3 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1035 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.107 | 1.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.19831 | 0.19831 | 0 | 0 | IWP_1035 | 21.8142 | 0 | 0 | 21.8142
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.082 | 1.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.20306 | 0.20306 | 0 | 0 | IWP_1035 | 22.3369 | 0 | 0 | 22.3369
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 100 | 0 | 0 | 100
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 50 | 0 | 0 | 50
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.1623 | 0 | 1.1623 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.0151 | 0 | 1.0151 | 0 | IWP_1035 | 0 | 79.1781 | 0 | 79.1781
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1902 | 0 | 1.1902 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.0661 | 0 | 1.0661 | 0 | IWP_1035 | 0 | 83.1541 | 0 | 83.1541
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1035 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1035 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1035 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1035 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1035 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1035 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.78 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1035 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1035 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.669 | 2.669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.5009 | 0.5009 | 0 | 0 | IWP_1035 | 55.099 | 0 | 0 | 55.099
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 50 | 0 | 0 | 50
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 100 | 0 | 0 | 100
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.9359 | 0 | 2.9359 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.6297 | 0 | 2.6297 | 0 | IWP_1035 | 0 | 205.1185 | 0 | 205.1185
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1035 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1035 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1035 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1035 | 0 | 117 | 0 | 117
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | 0 | 0 | 11 | 13.75 | 0 | 0 | 13.75 | CS | 0.78 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1035 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.91 | 1 | 110 | 0 | 4.55 | 4.55 | 0 | 0 | IWP_1035 | 500.5 | 0 | 0 | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | 0 | 0 | 17 | 25.5 | 0 | 0 | 25.5 | CS | 0.91 | 1 | 110 | 0 | 15.47 | 15.47 | 0 | 0 | IWP_1035 | 1701.7 | 0 | 0 | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 2.092 | 2.092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.37477 | 0.37477 | 0 | 0 | IWP_1035 | 41.2243 | 0 | 0 | 41.2243
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 350 | 0 | 0 | 350
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 2.1966 | 0 | 2.1966 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.9183 | 0 | 1.9183 | 0 | IWP_1035 | 0 | 149.6301 | 0 | 149.6301
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1035 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL800 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1035 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.3 | 0 | 0.3 | 0 | IWP_1035 | 0 | 23.4 | 0 | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | 0 | 0 | 11 | 13.75 | 0 | 0 | 13.75 | CS | 0.78 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1035 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.91 | 1 | 110 | 0 | 4.55 | 4.55 | 0 | 0 | IWP_1035 | 500.5 | 0 | 0 | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | 0 | 0 | 17 | 25.5 | 0 | 0 | 25.5 | CS | 0.91 | 1 | 110 | 0 | 15.47 | 15.47 | 0 | 0 | IWP_1035 | 1701.7 | 0 | 0 | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.188 | 1.188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.21282 | 0.21282 | 0 | 0 | IWP_1035 | 23.4104 | 0 | 0 | 23.4104
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 350 | 0 | 0 | 350
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.2474 | 0 | 1.2474 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.0894 | 0 | 1.0894 | 0 | IWP_1035 | 0 | 84.9716 | 0 | 84.9716
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1035 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL800 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1035 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.3 | 0 | 0.3 | 0 | IWP_1035 | 0 | 23.4 | 0 | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | 0 | 0 | 11 | 13.75 | 0 | 0 | 13.75 | CS | 0.78 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1035 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.91 | 1 | 110 | 0 | 4.55 | 4.55 | 0 | 0 | IWP_1035 | 500.5 | 0 | 0 | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | 0 | 0 | 17 | 25.5 | 0 | 0 | 25.5 | CS | 0.91 | 1 | 110 | 0 | 15.47 | 15.47 | 0 | 0 | IWP_1035 | 1701.7 | 0 | 0 | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 2.092 | 2.092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.37477 | 0.37477 | 0 | 0 | IWP_1035 | 41.2243 | 0 | 0 | 41.2243
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 350 | 0 | 0 | 350
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 2.1966 | 0 | 2.1966 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.9183 | 0 | 1.9183 | 0 | IWP_1035 | 0 | 149.6301 | 0 | 149.6301
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1035 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL800 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1035 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.3 | 0 | 0.3 | 0 | IWP_1035 | 0 | 23.4 | 0 | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | 0 | 0 | 11 | 13.75 | 0 | 0 | 13.75 | CS | 0.78 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1035 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.91 | 1 | 110 | 0 | 4.55 | 4.55 | 0 | 0 | IWP_1035 | 500.5 | 0 | 0 | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | 0 | 0 | 17 | 25.5 | 0 | 0 | 25.5 | CS | 0.91 | 1 | 110 | 0 | 15.47 | 15.47 | 0 | 0 | IWP_1035 | 1701.7 | 0 | 0 | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.188 | 1.188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.21282 | 0.21282 | 0 | 0 | IWP_1035 | 23.4104 | 0 | 0 | 23.4104
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 350 | 0 | 0 | 350
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.2474 | 0 | 1.2474 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.0894 | 0 | 1.0894 | 0 | IWP_1035 | 0 | 84.9716 | 0 | 84.9716
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1035 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL800 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1035 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.3 | 0 | 0.3 | 0 | IWP_1035 | 0 | 23.4 | 0 | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | 0 | 0 | 11 | 13.75 | 0 | 0 | 13.75 | CS | 0.78 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1035 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.91 | 1 | 110 | 0 | 4.55 | 4.55 | 0 | 0 | IWP_1035 | 500.5 | 0 | 0 | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | 0 | 0 | 17 | 25.5 | 0 | 0 | 25.5 | CS | 0.91 | 1 | 110 | 0 | 15.47 | 15.47 | 0 | 0 | IWP_1035 | 1701.7 | 0 | 0 | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 2.092 | 2.092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.37477 | 0.37477 | 0 | 0 | IWP_1035 | 41.2243 | 0 | 0 | 41.2243
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 350 | 0 | 0 | 350
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 2.1966 | 0 | 2.1966 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.9183 | 0 | 1.9183 | 0 | IWP_1035 | 0 | 149.6301 | 0 | 149.6301
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1035 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL800 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1035 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.3 | 0 | 0.3 | 0 | IWP_1035 | 0 | 23.4 | 0 | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | 0 | 0 | 11 | 13.75 | 0 | 0 | 13.75 | CS | 0.78 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1035 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.91 | 1 | 110 | 0 | 4.55 | 4.55 | 0 | 0 | IWP_1035 | 500.5 | 0 | 0 | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | 0 | 0 | 17 | 25.5 | 0 | 0 | 25.5 | CS | 0.91 | 1 | 110 | 0 | 15.47 | 15.47 | 0 | 0 | IWP_1035 | 1701.7 | 0 | 0 | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1035 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.188 | 1.188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.21282 | 0.21282 | 0 | 0 | IWP_1035 | 23.4104 | 0 | 0 | 23.4104
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 350 | 0 | 0 | 350
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.2474 | 0 | 1.2474 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.0894 | 0 | 1.0894 | 0 | IWP_1035 | 0 | 84.9716 | 0 | 84.9716
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1035 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL800 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1035 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1035 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.3 | 0 | 0.3 | 0 | IWP_1035 | 0 | 23.4 | 0 | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1035 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1035 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.78 | 1 | 110 | 0 | 7.8 | 7.8 | 0 | 0 | IWP_1035 | 858 | 0 | 0 | 858
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1035 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1035 | 1001 | 0 | 0 | 1001
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.21 | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.21676 | 0.21676 | 0 | 0 | IWP_1035 | 23.8439 | 0 | 0 | 23.8439
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.968 | 0.968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.18167 | 0.18167 | 0 | 0 | IWP_1035 | 19.9834 | 0 | 0 | 19.9834
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 250 | 0 | 0 | 250
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.2705 | 0 | 1.2705 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.1096 | 0 | 1.1096 | 0 | IWP_1035 | 0 | 86.5452 | 0 | 86.5452
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.0648 | 0 | 1.0648 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.95376 | 0 | 0.95376 | 0 | IWP_1035 | 0 | 74.3929 | 0 | 74.3929
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1035 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1035 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1035 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1035 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1035 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.78 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1035 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1035 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1035 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.145 | 0.145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.025976 | 0.025976 | 0 | 0 | IWP_1035 | 2.8573 | 0 | 0 | 2.8573
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 100 | 0 | 0 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 0.15225 | 0 | 0.15225 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.13296 | 0 | 0.13296 | 0 | IWP_1035 | 0 | 10.3711 | 0 | 10.3711
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1035 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1035 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1035 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1035 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1035 | 429 | 0 | 0 | 429
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1035 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1035 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.148 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.026513 | 0.026513 | 0 | 0 | IWP_1035 | 2.9164 | 0 | 0 | 2.9164
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 150 | 0 | 0 | 150
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 0.1554 | 0 | 0.1554 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.13571 | 0 | 0.13571 | 0 | IWP_1035 | 0 | 10.5857 | 0 | 10.5857
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1035 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1035 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1035 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1035 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1035 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1035 | 429 | 0 | 0 | 429
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1035 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1035 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.148 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.026513 | 0.026513 | 0 | 0 | IWP_1035 | 2.9164 | 0 | 0 | 2.9164
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 150 | 0 | 0 | 150
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 0.1554 | 0 | 0.1554 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.13571 | 0 | 0.13571 | 0 | IWP_1035 | 0 | 10.5857 | 0 | 10.5857
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1035 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1035 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1035 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1035 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1035 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1035 | 429 | 0 | 0 | 429
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1035 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1035 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1035 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1035 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.148 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.026513 | 0.026513 | 0 | 0 | IWP_1035 | 2.9164 | 0 | 0 | 2.9164
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1035 | 100 | 0 | 0 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 0.1554 | 0 | 0.1554 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.13571 | 0 | 0.13571 | 0 | IWP_1035 | 0 | 10.5857 | 0 | 10.5857
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1035 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1035 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1035 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1035 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1035 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1035 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1035 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1035 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1035 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1036 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 8 | 8 | 0 | 0 | 160 | 520 | 0 | 0 | 520 | CS | 21.7588 | 1 | 110 | 0 | 174.07 | 174.07 | 0 | 0 | IWP_1036 | 19147.7 | 0 | 0 | 19147.7
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1036 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1036 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 3 | 0 | 0 | 6 | 18 | 0 | 0 | 18 | CS | 5.46 | 1 | 110 | 0 | 16.38 | 16.38 | 0 | 0 | IWP_1036 | 1801.8 | 0 | 0 | 1801.8
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1036 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 2 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.429 | 1 | 110 | 0 | 0.429 | 0.429 | 0 | 0 | IWP_1036 | 47.19 | 0 | 0 | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 Sch80 | LM | 7.924 | 7.924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 8.1454 | 8.1454 | 0 | 0 | IWP_1036 | 895.9913 | 0 | 0 | 895.9913
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1036 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1036 | 500 | 0 | 0 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 20 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 41.2 | 41.2 | 0 | 0 | IWP_1036 | 4532 | 0 | 0 | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 20 | Shop Spools Coating - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2700 | 0 | 0 | 0 | 0 | IWP_1036 | 2700 | 0 | 0 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 20 | Install Spools - NB 20 Sch80 | LM | 9.1126 | 0 | 9.1126 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 0.75 | 78 | 0 | 45.3006 | 0 | 45.3006 | 0 | IWP_1036 | 0 | 3533.4485 | 0 | 3533.4485
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 3.8025 | 0 | 3.8025 | 0 | IWP_1036 | 0 | 296.595 | 0 | 296.595
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install Blind - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1036 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install valve - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1036 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1036 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1036 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.9488 | 0 | 3.9488 | 0 | IWP_1036 | 0 | 308.0025 | 0 | 308.0025
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 12.87 | 0 | 12.87 | 0 | IWP_1036 | 0 | 1003.86 | 0 | 1003.86
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 20 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.327 | 0.75 | 78 | 0 | 1.7452 | 0 | 1.7452 | 0 | IWP_1036 | 0 | 136.1291 | 0 | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1036 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 2 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.586 | 1 | 110 | 0 | 3.172 | 3.172 | 0 | 0 | IWP_1036 | 348.92 | 0 | 0 | 348.92
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1036 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 2 | 2 | 0 | 0 | 40 | 130 | 0 | 0 | 130 | CS | 21.7588 | 1 | 110 | 0 | 43.5175 | 43.5175 | 0 | 0 | IWP_1036 | 4786.925 | 0 | 0 | 4786.925
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1036 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1036 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 1 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 2.21 | 1 | 110 | 0 | 2.21 | 2.21 | 0 | 0 | IWP_1036 | 243.1 | 0 | 0 | 243.1
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1036 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 3 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 1 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 7.67 | 1 | 110 | 0 | 7.67 | 7.67 | 0 | 0 | IWP_1036 | 843.7 | 0 | 0 | 843.7
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1036 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1036 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 1.692 | 1.692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 1.3423 | 1.3423 | 0 | 0 | IWP_1036 | 147.6575 | 0 | 0 | 147.6575
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1036 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1036 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 1.9458 | 0 | 1.9458 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 0.75 | 78 | 0 | 7.4508 | 0 | 7.4508 | 0 | IWP_1036 | 0 | 581.1628 | 0 | 581.1628
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1036 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1036 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 16 | Install Inlines - NB 16 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 11.44 | 0.75 | 78 | 0 | 8.58 | 0 | 8.58 | 0 | IWP_1036 | 0 | 669.24 | 0 | 669.24
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1036 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1036 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1036 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 12.675 | 0 | 12.675 | 0 | IWP_1036 | 0 | 988.65 | 0 | 988.65
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1036 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 0.75 | 78 | 0 | 1.583 | 0 | 1.583 | 0 | IWP_1036 | 0 | 123.4731 | 0 | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1036 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 14 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 4 | 0 | 0 | 56 | 140 | 0 | 0 | 140 | CS | 10.2115 | 1 | 110 | 0 | 40.846 | 40.846 | 0 | 0 | IWP_1036 | 4493.06 | 0 | 0 | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1036 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1036 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1036 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1036 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1036 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 14 | Shop handling - NB 14 Sch80 | LM | 2.65 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.67818 | 1 | 110 | 0 | 1.7972 | 1.7972 | 0 | 0 | IWP_1036 | 197.6903 | 0 | 0 | 197.6903
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 14 | Shop X-Ray - NB 14 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1036 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1036 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 14 | Install Spools - NB 14 Sch80 | LM | 3.0475 | 0 | 3.0475 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.3591 | 0.75 | 78 | 0 | 9.9634 | 0 | 9.9634 | 0 | IWP_1036 | 0 | 777.1414 | 0 | 777.1414
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1036 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 16 | Install Inlines - NB 16 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 11.44 | 0.75 | 78 | 0 | 8.58 | 0 | 8.58 | 0 | IWP_1036 | 0 | 669.24 | 0 | 669.24
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1036 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1036 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 14 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.98 | 0.75 | 78 | 0 | 6.7275 | 0 | 6.7275 | 0 | IWP_1036 | 0 | 524.745 | 0 | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 7.605 | 0 | 7.605 | 0 | IWP_1036 | 0 | 593.19 | 0 | 593.19
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 14 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.0101 | 0.75 | 78 | 0 | 1.5076 | 0 | 1.5076 | 0 | IWP_1036 | 0 | 117.5934 | 0 | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1036 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 14 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 4 | 0 | 0 | 56 | 140 | 0 | 0 | 140 | CS | 10.2115 | 1 | 110 | 0 | 40.846 | 40.846 | 0 | 0 | IWP_1036 | 4493.06 | 0 | 0 | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1036 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1036 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1036 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1036 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1036 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 14 | Shop handling - NB 14 Sch80 | LM | 2.694 | 2.694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.67818 | 1 | 110 | 0 | 1.827 | 1.827 | 0 | 0 | IWP_1036 | 200.9727 | 0 | 0 | 200.9727
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 14 | Shop X-Ray - NB 14 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1036 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1036 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 14 | Install Spools - NB 14 Sch80 | LM | 3.0981 | 0 | 3.0981 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.3591 | 0.75 | 78 | 0 | 10.1288 | 0 | 10.1288 | 0 | IWP_1036 | 0 | 790.0449 | 0 | 790.0449
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1036 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1036 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1036 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 14 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.98 | 0.75 | 78 | 0 | 6.7275 | 0 | 6.7275 | 0 | IWP_1036 | 0 | 524.745 | 0 | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1036 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 14 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.0101 | 0.75 | 78 | 0 | 1.5076 | 0 | 1.5076 | 0 | IWP_1036 | 0 | 117.5934 | 0 | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1037 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 2 | 2 | 0 | 0 | 32 | 96 | 0 | 0 | 96 | CS | 14.365 | 1 | 110 | 0 | 28.73 | 28.73 | 0 | 0 | IWP_1037 | 3160.3 | 0 | 0 | 3160.3
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 2 | 2 | 0 | 0 | 40 | 130 | 0 | 0 | 130 | CS | 21.7588 | 1 | 110 | 0 | 43.5175 | 43.5175 | 0 | 0 | IWP_1037 | 4786.925 | 0 | 0 | 4786.925
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1037 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1037 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1037 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1037 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1037 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 0.884 | 0.884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 0.70132 | 0.70132 | 0 | 0 | IWP_1037 | 77.1449 | 0 | 0 | 77.1449
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1037 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 1.0166 | 0 | 1.0166 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 0.75 | 78 | 0 | 3.8927 | 0 | 3.8927 | 0 | IWP_1037 | 0 | 303.6335 | 0 | 303.6335
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1037 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1037 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install valve - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1037 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install Blind - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1037 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1037 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1037 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1037 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 9.6525 | 0 | 9.6525 | 0 | IWP_1037 | 0 | 752.895 | 0 | 752.895
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 0.75 | 78 | 0 | 1.583 | 0 | 1.583 | 0 | IWP_1037 | 0 | 123.4731 | 0 | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1037 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 8 | 8 | 0 | 0 | 160 | 520 | 0 | 0 | 520 | CS | 21.7588 | 1 | 110 | 0 | 174.07 | 174.07 | 0 | 0 | IWP_1037 | 19147.7 | 0 | 0 | 19147.7
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1037 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 2 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.429 | 1 | 110 | 0 | 0.429 | 0.429 | 0 | 0 | IWP_1037 | 47.19 | 0 | 0 | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 Sch80 | LM | 9.122 | 9.122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 9.3768 | 9.3768 | 0 | 0 | IWP_1037 | 1031.4528 | 0 | 0 | 1031.4528
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1037 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1037 | 500 | 0 | 0 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 20 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 41.2 | 41.2 | 0 | 0 | IWP_1037 | 4532 | 0 | 0 | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 20 | Shop Spools Coating - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2700 | 0 | 0 | 0 | 0 | IWP_1037 | 2700 | 0 | 0 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 20 | Install Spools - NB 20 Sch80 | LM | 10.4903 | 0 | 10.4903 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 0.75 | 78 | 0 | 52.1495 | 0 | 52.1495 | 0 | IWP_1037 | 0 | 4067.6574 | 0 | 4067.6574
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1037 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1037 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1037 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 6.435 | 0 | 6.435 | 0 | IWP_1037 | 0 | 501.93 | 0 | 501.93
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 20 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.327 | 0.75 | 78 | 0 | 1.7452 | 0 | 1.7452 | 0 | IWP_1037 | 0 | 136.1291 | 0 | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1037 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 8 | 8 | 0 | 0 | 160 | 520 | 0 | 0 | 520 | CS | 21.7588 | 1 | 110 | 0 | 174.07 | 174.07 | 0 | 0 | IWP_1037 | 19147.7 | 0 | 0 | 19147.7
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1037 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1037 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 3 | 0 | 0 | 6 | 18 | 0 | 0 | 18 | CS | 5.46 | 1 | 110 | 0 | 16.38 | 16.38 | 0 | 0 | IWP_1037 | 1801.8 | 0 | 0 | 1801.8
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1037 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 2 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.429 | 1 | 110 | 0 | 0.429 | 0.429 | 0 | 0 | IWP_1037 | 47.19 | 0 | 0 | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 Sch80 | LM | 7.924 | 7.924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 8.1454 | 8.1454 | 0 | 0 | IWP_1037 | 895.9913 | 0 | 0 | 895.9913
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1037 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1037 | 500 | 0 | 0 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 20 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 41.2 | 41.2 | 0 | 0 | IWP_1037 | 4532 | 0 | 0 | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 20 | Shop Spools Coating - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2700 | 0 | 0 | 0 | 0 | IWP_1037 | 2700 | 0 | 0 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 20 | Install Spools - NB 20 Sch80 | LM | 9.1126 | 0 | 9.1126 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 0.75 | 78 | 0 | 45.3006 | 0 | 45.3006 | 0 | IWP_1037 | 0 | 3533.4485 | 0 | 3533.4485
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 3.8025 | 0 | 3.8025 | 0 | IWP_1037 | 0 | 296.595 | 0 | 296.595
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install Blind - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1037 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install valve - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1037 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1037 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1037 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.9488 | 0 | 3.9488 | 0 | IWP_1037 | 0 | 308.0025 | 0 | 308.0025
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 12.87 | 0 | 12.87 | 0 | IWP_1037 | 0 | 1003.86 | 0 | 1003.86
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 20 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.327 | 0.75 | 78 | 0 | 1.7452 | 0 | 1.7452 | 0 | IWP_1037 | 0 | 136.1291 | 0 | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1038 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 2 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.586 | 1 | 110 | 0 | 3.172 | 3.172 | 0 | 0 | IWP_1038 | 348.92 | 0 | 0 | 348.92
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1038 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 2 | 2 | 0 | 0 | 40 | 130 | 0 | 0 | 130 | CS | 21.7588 | 1 | 110 | 0 | 43.5175 | 43.5175 | 0 | 0 | IWP_1038 | 4786.925 | 0 | 0 | 4786.925
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1038 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1038 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 1 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 2.21 | 1 | 110 | 0 | 2.21 | 2.21 | 0 | 0 | IWP_1038 | 243.1 | 0 | 0 | 243.1
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1038 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 3 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 1 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 7.67 | 1 | 110 | 0 | 7.67 | 7.67 | 0 | 0 | IWP_1038 | 843.7 | 0 | 0 | 843.7
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1038 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1038 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 1.692 | 1.692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 1.3423 | 1.3423 | 0 | 0 | IWP_1038 | 147.6575 | 0 | 0 | 147.6575
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1038 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1038 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 1.9458 | 0 | 1.9458 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 0.75 | 78 | 0 | 7.4508 | 0 | 7.4508 | 0 | IWP_1038 | 0 | 581.1628 | 0 | 581.1628
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1038 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1038 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 16 | Install Inlines - NB 16 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 11.44 | 0.75 | 78 | 0 | 17.16 | 0 | 17.16 | 0 | IWP_1038 | 0 | 1338.48 | 0 | 1338.48
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1038 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1038 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1038 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 17.745 | 0 | 17.745 | 0 | IWP_1038 | 0 | 1384.11 | 0 | 1384.11
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1038 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 0.75 | 78 | 0 | 3.166 | 0 | 3.166 | 0 | IWP_1038 | 0 | 246.9461 | 0 | 246.9461
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1038 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 14 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 4 | 0 | 0 | 56 | 140 | 0 | 0 | 140 | CS | 10.2115 | 1 | 110 | 0 | 40.846 | 40.846 | 0 | 0 | IWP_1038 | 4493.06 | 0 | 0 | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1038 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1038 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1038 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1038 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1038 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 14 | Shop handling - NB 14 Sch80 | LM | 2.65 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.67818 | 1 | 110 | 0 | 1.7972 | 1.7972 | 0 | 0 | IWP_1038 | 197.6903 | 0 | 0 | 197.6903
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 14 | Shop X-Ray - NB 14 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1038 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1038 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 14 | Install Spools - NB 14 Sch80 | LM | 3.0475 | 0 | 3.0475 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.3591 | 0.75 | 78 | 0 | 9.9634 | 0 | 9.9634 | 0 | IWP_1038 | 0 | 777.1414 | 0 | 777.1414
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1038 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1038 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1038 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 14 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.98 | 0.75 | 78 | 0 | 6.7275 | 0 | 6.7275 | 0 | IWP_1038 | 0 | 524.745 | 0 | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1038 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 14 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.0101 | 0.75 | 78 | 0 | 1.5076 | 0 | 1.5076 | 0 | IWP_1038 | 0 | 117.5934 | 0 | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1038 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 14 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 4 | 0 | 0 | 56 | 140 | 0 | 0 | 140 | CS | 10.2115 | 1 | 110 | 0 | 40.846 | 40.846 | 0 | 0 | IWP_1038 | 4493.06 | 0 | 0 | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1038 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1038 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1038 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1038 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1038 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 14 | Shop handling - NB 14 Sch80 | LM | 2.694 | 2.694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.67818 | 1 | 110 | 0 | 1.827 | 1.827 | 0 | 0 | IWP_1038 | 200.9727 | 0 | 0 | 200.9727
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 14 | Shop X-Ray - NB 14 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1038 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1038 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 14 | Install Spools - NB 14 Sch80 | LM | 3.0981 | 0 | 3.0981 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.3591 | 0.75 | 78 | 0 | 10.1288 | 0 | 10.1288 | 0 | IWP_1038 | 0 | 790.0449 | 0 | 790.0449
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1038 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1038 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1038 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 14 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.98 | 0.75 | 78 | 0 | 6.7275 | 0 | 6.7275 | 0 | IWP_1038 | 0 | 524.745 | 0 | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1038 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 14 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.0101 | 0.75 | 78 | 0 | 1.5076 | 0 | 1.5076 | 0 | IWP_1038 | 0 | 117.5934 | 0 | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1038 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 2 | 2 | 0 | 0 | 32 | 96 | 0 | 0 | 96 | CS | 14.365 | 1 | 110 | 0 | 28.73 | 28.73 | 0 | 0 | IWP_1038 | 3160.3 | 0 | 0 | 3160.3
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 2 | 2 | 0 | 0 | 40 | 130 | 0 | 0 | 130 | CS | 21.7588 | 1 | 110 | 0 | 43.5175 | 43.5175 | 0 | 0 | IWP_1038 | 4786.925 | 0 | 0 | 4786.925
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1038 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1038 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 3 | 3 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1038 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1038 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1038 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1038 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1038 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 0.884 | 0.884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 0.70132 | 0.70132 | 0 | 0 | IWP_1038 | 77.1449 | 0 | 0 | 77.1449
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1038 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 1.0166 | 0 | 1.0166 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 0.75 | 78 | 0 | 3.8927 | 0 | 3.8927 | 0 | IWP_1038 | 0 | 303.6335 | 0 | 303.6335
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1038 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1038 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install Blind - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1038 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install valve - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1038 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1038 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1038 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1038 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 9.6525 | 0 | 9.6525 | 0 | IWP_1038 | 0 | 752.895 | 0 | 752.895
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 0.75 | 78 | 0 | 1.583 | 0 | 1.583 | 0 | IWP_1038 | 0 | 123.4731 | 0 | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1039 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 8 | 8 | 0 | 0 | 160 | 520 | 0 | 0 | 520 | CS | 21.7588 | 1 | 110 | 0 | 174.07 | 174.07 | 0 | 0 | IWP_1039 | 19147.7 | 0 | 0 | 19147.7
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1039 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 2 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.429 | 1 | 110 | 0 | 0.429 | 0.429 | 0 | 0 | IWP_1039 | 47.19 | 0 | 0 | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 Sch80 | LM | 9.122 | 9.122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 9.3768 | 9.3768 | 0 | 0 | IWP_1039 | 1031.4528 | 0 | 0 | 1031.4528
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1039 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1039 | 500 | 0 | 0 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 20 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 41.2 | 41.2 | 0 | 0 | IWP_1039 | 4532 | 0 | 0 | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 20 | Shop Spools Coating - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2700 | 0 | 0 | 0 | 0 | IWP_1039 | 2700 | 0 | 0 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 20 | Install Spools - NB 20 Sch80 | LM | 10.4903 | 0 | 10.4903 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 0.75 | 78 | 0 | 52.1495 | 0 | 52.1495 | 0 | IWP_1039 | 0 | 4067.6574 | 0 | 4067.6574
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1039 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1039 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1039 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 6.435 | 0 | 6.435 | 0 | IWP_1039 | 0 | 501.93 | 0 | 501.93
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 20 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.327 | 0.75 | 78 | 0 | 1.7452 | 0 | 1.7452 | 0 | IWP_1039 | 0 | 136.1291 | 0 | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1039 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 8 | 8 | 0 | 0 | 160 | 520 | 0 | 0 | 520 | CS | 21.7588 | 1 | 110 | 0 | 174.07 | 174.07 | 0 | 0 | IWP_1039 | 19147.7 | 0 | 0 | 19147.7
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1039 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1039 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 3 | 0 | 0 | 6 | 18 | 0 | 0 | 18 | CS | 5.46 | 1 | 110 | 0 | 16.38 | 16.38 | 0 | 0 | IWP_1039 | 1801.8 | 0 | 0 | 1801.8
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1039 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 2 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.429 | 1 | 110 | 0 | 0.429 | 0.429 | 0 | 0 | IWP_1039 | 47.19 | 0 | 0 | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 Sch80 | LM | 7.924 | 7.924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 8.1454 | 8.1454 | 0 | 0 | IWP_1039 | 895.9913 | 0 | 0 | 895.9913
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1039 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1039 | 500 | 0 | 0 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 20 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 41.2 | 41.2 | 0 | 0 | IWP_1039 | 4532 | 0 | 0 | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 20 | Shop Spools Coating - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2700 | 0 | 0 | 0 | 0 | IWP_1039 | 2700 | 0 | 0 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 20 | Install Spools - NB 20 Sch80 | LM | 9.1126 | 0 | 9.1126 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 0.75 | 78 | 0 | 45.3006 | 0 | 45.3006 | 0 | IWP_1039 | 0 | 3533.4485 | 0 | 3533.4485
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 3.8025 | 0 | 3.8025 | 0 | IWP_1039 | 0 | 296.595 | 0 | 296.595
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install Blind - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1039 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install valve - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1039 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1039 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1039 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.9488 | 0 | 3.9488 | 0 | IWP_1039 | 0 | 308.0025 | 0 | 308.0025
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 12.87 | 0 | 12.87 | 0 | IWP_1039 | 0 | 1003.86 | 0 | 1003.86
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 20 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.327 | 0.75 | 78 | 0 | 1.7452 | 0 | 1.7452 | 0 | IWP_1039 | 0 | 136.1291 | 0 | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1040 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 2 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.586 | 1 | 110 | 0 | 3.172 | 3.172 | 0 | 0 | IWP_1040 | 348.92 | 0 | 0 | 348.92
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1040 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 2 | 2 | 0 | 0 | 40 | 130 | 0 | 0 | 130 | CS | 21.7588 | 1 | 110 | 0 | 43.5175 | 43.5175 | 0 | 0 | IWP_1040 | 4786.925 | 0 | 0 | 4786.925
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1040 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1040 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 1 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 2.21 | 1 | 110 | 0 | 2.21 | 2.21 | 0 | 0 | IWP_1040 | 243.1 | 0 | 0 | 243.1
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1040 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 3 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 1 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 7.67 | 1 | 110 | 0 | 7.67 | 7.67 | 0 | 0 | IWP_1040 | 843.7 | 0 | 0 | 843.7
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1040 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1040 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 1.692 | 1.692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 1.3423 | 1.3423 | 0 | 0 | IWP_1040 | 147.6575 | 0 | 0 | 147.6575
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1040 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1040 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 1.9458 | 0 | 1.9458 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 0.75 | 78 | 0 | 7.4508 | 0 | 7.4508 | 0 | IWP_1040 | 0 | 581.1628 | 0 | 581.1628
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1040 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1040 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 16 | Install Inlines - NB 16 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 11.44 | 0.75 | 78 | 0 | 17.16 | 0 | 17.16 | 0 | IWP_1040 | 0 | 1338.48 | 0 | 1338.48
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1040 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1040 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1040 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 17.745 | 0 | 17.745 | 0 | IWP_1040 | 0 | 1384.11 | 0 | 1384.11
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1040 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 0.75 | 78 | 0 | 1.583 | 0 | 1.583 | 0 | IWP_1040 | 0 | 123.4731 | 0 | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1040 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 14 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 4 | 0 | 0 | 56 | 140 | 0 | 0 | 140 | CS | 10.2115 | 1 | 110 | 0 | 40.846 | 40.846 | 0 | 0 | IWP_1040 | 4493.06 | 0 | 0 | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1040 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1040 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1040 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1040 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1040 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 14 | Shop handling - NB 14 Sch80 | LM | 2.65 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.67818 | 1 | 110 | 0 | 1.7972 | 1.7972 | 0 | 0 | IWP_1040 | 197.6903 | 0 | 0 | 197.6903
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 14 | Shop X-Ray - NB 14 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1040 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1040 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 14 | Install Spools - NB 14 Sch80 | LM | 3.0475 | 0 | 3.0475 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.3591 | 0.75 | 78 | 0 | 9.9634 | 0 | 9.9634 | 0 | IWP_1040 | 0 | 777.1414 | 0 | 777.1414
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1040 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1040 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1040 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 14 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.98 | 0.75 | 78 | 0 | 6.7275 | 0 | 6.7275 | 0 | IWP_1040 | 0 | 524.745 | 0 | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1040 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 14 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.0101 | 0.75 | 78 | 0 | 1.5076 | 0 | 1.5076 | 0 | IWP_1040 | 0 | 117.5934 | 0 | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1040 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 14 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 4 | 0 | 0 | 56 | 140 | 0 | 0 | 140 | CS | 10.2115 | 1 | 110 | 0 | 40.846 | 40.846 | 0 | 0 | IWP_1040 | 4493.06 | 0 | 0 | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 4 | 4 | 0 | 0 | 64 | 192 | 0 | 0 | 192 | CS | 14.365 | 1 | 110 | 0 | 57.46 | 57.46 | 0 | 0 | IWP_1040 | 6320.6 | 0 | 0 | 6320.6
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1040 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1040 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1040 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1040 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 14 | Shop handling - NB 14 Sch80 | LM | 2.694 | 2.694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.67818 | 1 | 110 | 0 | 1.827 | 1.827 | 0 | 0 | IWP_1040 | 200.9727 | 0 | 0 | 200.9727
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 14 | Shop X-Ray - NB 14 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1040 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 16 | Shop X-Ray - NB 16 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1040 | 250 | 0 | 0 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 14 | Install Spools - NB 14 Sch80 | LM | 3.0981 | 0 | 3.0981 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.3591 | 0.75 | 78 | 0 | 10.1288 | 0 | 10.1288 | 0 | IWP_1040 | 0 | 790.0449 | 0 | 790.0449
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1040 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1040 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1040 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 14 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.98 | 0.75 | 78 | 0 | 6.7275 | 0 | 6.7275 | 0 | IWP_1040 | 0 | 524.745 | 0 | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1040 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 14 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.0101 | 0.75 | 78 | 0 | 1.5076 | 0 | 1.5076 | 0 | IWP_1040 | 0 | 117.5934 | 0 | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1040 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 16 | Shop Butt Weld - NB 16 Sch80 | EA | 2 | 2 | 0 | 0 | 32 | 96 | 0 | 0 | 96 | CS | 14.365 | 1 | 110 | 0 | 28.73 | 28.73 | 0 | 0 | IWP_1040 | 3160.3 | 0 | 0 | 3160.3
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 2 | 2 | 0 | 0 | 40 | 130 | 0 | 0 | 130 | CS | 21.7588 | 1 | 110 | 0 | 43.5175 | 43.5175 | 0 | 0 | IWP_1040 | 4786.925 | 0 | 0 | 4786.925
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1040 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1040 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 3 | 3 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1040 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1040 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1040 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1040 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1040 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 16 | Shop handling - NB 16 Sch80 | LM | 0.884 | 0.884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.79335 | 1 | 110 | 0 | 0.70132 | 0.70132 | 0 | 0 | IWP_1040 | 77.1449 | 0 | 0 | 77.1449
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1040 | 50 | 0 | 0 | 50
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 16 | Install Spools - NB 16 Sch80 | LM | 1.0166 | 0 | 1.0166 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.1056 | 0.75 | 78 | 0 | 3.8927 | 0 | 3.8927 | 0 | IWP_1040 | 0 | 303.6335 | 0 | 303.6335
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1040 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1040 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install Blind - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1040 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 20 | Install valve - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 15.47 | 0.75 | 78 | 0 | 11.6025 | 0 | 11.6025 | 0 | IWP_1040 | 0 | 904.995 | 0 | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1040 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1040 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 16 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.76 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1040 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 9.6525 | 0 | 9.6525 | 0 | IWP_1040 | 0 | 752.895 | 0 | 752.895
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 16 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.1107 | 0.75 | 78 | 0 | 1.583 | 0 | 1.583 | 0 | IWP_1040 | 0 | 123.4731 | 0 | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1040 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 20 | Shop Butt Weld - NB 20 Sch80 | EA | 8 | 8 | 0 | 0 | 160 | 520 | 0 | 0 | 520 | CS | 21.7588 | 1 | 110 | 0 | 174.07 | 174.07 | 0 | 0 | IWP_1040 | 19147.7 | 0 | 0 | 19147.7
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1040 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1040 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 4 | 4 | 0 | 0 | 8 | 24 | 0 | 0 | 24 | CS | 5.46 | 1 | 110 | 0 | 21.84 | 21.84 | 0 | 0 | IWP_1040 | 2402.4 | 0 | 0 | 2402.4
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1040 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 2 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.429 | 1 | 110 | 0 | 0.429 | 0.429 | 0 | 0 | IWP_1040 | 47.19 | 0 | 0 | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 20 | Shop handling - NB 20 Sch80 | LM | 9.122 | 9.122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0279 | 1 | 110 | 0 | 9.3768 | 9.3768 | 0 | 0 | IWP_1040 | 1031.4528 | 0 | 0 | 1031.4528
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1040 | 150 | 0 | 0 | 150
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 20 | Shop X-Ray - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1040 | 500 | 0 | 0 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 20 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 41.2 | 1 | 110 | 0 | 41.2 | 41.2 | 0 | 0 | IWP_1040 | 4532 | 0 | 0 | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 20 | Shop Spools Coating - NB 20 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 2700 | 0 | 0 | 0 | 0 | IWP_1040 | 2700 | 0 | 0 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 20 | Install Spools - NB 20 Sch80 | LM | 10.4903 | 0 | 10.4903 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6.6283 | 0.75 | 78 | 0 | 52.1495 | 0 | 52.1495 | 0 | IWP_1040 | 0 | 4067.6574 | 0 | 4067.6574
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 3.8025 | 0 | 3.8025 | 0 | IWP_1040 | 0 | 296.595 | 0 | 296.595
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1040 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1040 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1040 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 20 | Flange Bolt-Up - NB 20 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.58 | 0.75 | 78 | 0 | 6.435 | 0 | 6.435 | 0 | IWP_1040 | 0 | 501.93 | 0 | 501.93
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 20 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.327 | 0.75 | 78 | 0 | 1.7452 | 0 | 1.7452 | 0 | IWP_1040 | 0 | 136.1291 | 0 | 136.1291
Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1041 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.76 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.3303 | 0.3303 | 0 | 0 | IWP_1041 | 36.3335 | 0 | 0 | 36.3335
Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 100 | 0 | 0 | 100
Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.936 | 0 | 1.936 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.7341 | 0 | 1.7341 | 0 | IWP_1041 | 0 | 135.2598 | 0 | 135.2598
Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1041 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 7 | 0 | 0 | 14 | 21 | 0 | 0 | 21 | CS | 1.1765 | 1 | 110 | 0 | 8.2355 | 8.2355 | 0 | 0 | IWP_1041 | 905.905 | 0 | 0 | 905.905
Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.15014 | 0.15014 | 0 | 0 | IWP_1041 | 16.5152 | 0 | 0 | 16.5152
Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 50 | 0 | 0 | 50
Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.88 | 0 | 0.88 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.78823 | 0 | 0.78823 | 0 | IWP_1041 | 0 | 61.4817 | 0 | 61.4817
Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1041 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3066 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1041 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3066 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1041 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 7 | 0 | 0 | 14 | 21 | 0 | 0 | 21 | CS | 1.1765 | 1 | 110 | 0 | 8.2355 | 8.2355 | 0 | 0 | IWP_1041 | 905.905 | 0 | 0 | 905.905
Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.773 | 0.773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.14507 | 0.14507 | 0 | 0 | IWP_1041 | 15.9579 | 0 | 0 | 15.9579
Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 50 | 0 | 0 | 50
Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.8503 | 0 | 0.8503 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.76162 | 0 | 0.76162 | 0 | IWP_1041 | 0 | 59.4067 | 0 | 59.4067
Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1041 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1041 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.502 | 0.502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.094212 | 0.094212 | 0 | 0 | IWP_1041 | 10.3633 | 0 | 0 | 10.3633
Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 100 | 0 | 0 | 100
Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.5522 | 0 | 0.5522 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.49461 | 0 | 0.49461 | 0 | IWP_1041 | 0 | 38.5798 | 0 | 38.5798
Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1041 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 5 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 1.1765 | 1 | 110 | 0 | 5.8825 | 5.8825 | 0 | 0 | IWP_1041 | 647.075 | 0 | 0 | 647.075
Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.971 | 0.971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.18223 | 0.18223 | 0 | 0 | IWP_1041 | 20.0454 | 0 | 0 | 20.0454
Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 50 | 0 | 0 | 50
Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.0681 | 0 | 1.0681 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.95671 | 0 | 0.95671 | 0 | IWP_1041 | 0 | 74.6235 | 0 | 74.6235
Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1041 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3011 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 1.2403 | 0 | 1.2403 | 0 | IWP_1041 | 0 | 96.7444 | 0 | 96.7444
Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1041 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.477 | 0.477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.08952 | 0.08952 | 0 | 0 | IWP_1041 | 9.8472 | 0 | 0 | 9.8472
Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 50 | 0 | 0 | 50
Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.5247 | 0 | 0.5247 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.46998 | 0 | 0.46998 | 0 | IWP_1041 | 0 | 36.6585 | 0 | 36.6585
Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1041 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 7 | 0 | 0 | 14 | 21 | 0 | 0 | 21 | CS | 1.1765 | 1 | 110 | 0 | 8.2355 | 8.2355 | 0 | 0 | IWP_1041 | 905.905 | 0 | 0 | 905.905
Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.314 | 0.314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.058929 | 0.058929 | 0 | 0 | IWP_1041 | 6.4822 | 0 | 0 | 6.4822
Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 50 | 0 | 0 | 50
Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.3454 | 0 | 0.3454 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.30938 | 0 | 0.30938 | 0 | IWP_1041 | 0 | 24.1316 | 0 | 24.1316
Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1041 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1041 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1041 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1041 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1041 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.78 | 1 | 110 | 0 | 7.8 | 7.8 | 0 | 0 | IWP_1041 | 858 | 0 | 0 | 858
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1041 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1041 | 1001 | 0 | 0 | 1001
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1041 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1041 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.508 | 1.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.27015 | 0.27015 | 0 | 0 | IWP_1041 | 29.7162 | 0 | 0 | 29.7162
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.791 | 1.791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.33612 | 0.33612 | 0 | 0 | IWP_1041 | 36.9735 | 0 | 0 | 36.9735
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 250 | 0 | 0 | 250
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 50 | 0 | 0 | 50
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.5834 | 0 | 1.5834 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.3828 | 0 | 1.3828 | 0 | IWP_1041 | 0 | 107.8596 | 0 | 107.8596
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.9701 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.7646 | 0 | 1.7646 | 0 | IWP_1041 | 0 | 137.6422 | 0 | 137.6422
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1041 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1041 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1041 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1041 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1041 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 25 | 25 | 0 | 0 | 50 | 75 | 0 | 0 | 75 | CS | 1.1765 | 1 | 110 | 0 | 29.4125 | 29.4125 | 0 | 0 | IWP_1041 | 3235.375 | 0 | 0 | 3235.375
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1041 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 8 | 8 | 0 | 0 | 8 | 10 | 0 | 0 | 10 | CS | 0.78 | 1 | 110 | 0 | 6.24 | 6.24 | 0 | 0 | IWP_1041 | 686.4 | 0 | 0 | 686.4
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 16 | 16 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 0.91 | 1 | 110 | 0 | 14.56 | 14.56 | 0 | 0 | IWP_1041 | 1601.6 | 0 | 0 | 1601.6
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.69 | 1 | 110 | 0 | 6.76 | 6.76 | 0 | 0 | IWP_1041 | 743.6 | 0 | 0 | 743.6
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 4 | 4 | 0 | 0 | 4 | 10 | 0 | 0 | 10 | CS | 0.39 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1041 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.874 | 2.874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.53937 | 0.53937 | 0 | 0 | IWP_1041 | 59.331 | 0 | 0 | 59.331
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 200 | 0 | 0 | 200
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 250 | 0 | 0 | 250
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 3.1614 | 0 | 3.1614 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.8317 | 0 | 2.8317 | 0 | IWP_1041 | 0 | 220.8732 | 0 | 220.8732
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1041 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1041 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.0713 | 0 | 3.0713 | 0 | IWP_1041 | 0 | 239.5575 | 0 | 239.5575
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1041 | 0 | 117 | 0 | 117
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 20 | 20 | 0 | 0 | 40 | 60 | 0 | 0 | 60 | CS | 1.1765 | 1 | 110 | 0 | 23.53 | 23.53 | 0 | 0 | IWP_1041 | 2588.3 | 0 | 0 | 2588.3
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 5.907 | 5.907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.1086 | 1.1086 | 0 | 0 | IWP_1041 | 121.9444 | 0 | 0 | 121.9444
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 150 | 0 | 0 | 150
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1041 | 616 | 0 | 0 | 616
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1041 | 500 | 0 | 0 | 500
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 6.4977 | 0 | 6.4977 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 5.8201 | 0 | 5.8201 | 0 | IWP_1041 | 0 | 453.9658 | 0 | 453.9658
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1041 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 3 | 0 | 3 | 0 | IWP_1041 | 0 | 234 | 0 | 234
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 15 | 15 | 0 | 0 | 30 | 45 | 0 | 0 | 45 | CS | 1.1765 | 1 | 110 | 0 | 17.6475 | 17.6475 | 0 | 0 | IWP_1041 | 1941.225 | 0 | 0 | 1941.225
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 2 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.586 | 1 | 110 | 0 | 3.172 | 3.172 | 0 | 0 | IWP_1041 | 348.92 | 0 | 0 | 348.92
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.883 | 1.883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.35339 | 0.35339 | 0 | 0 | IWP_1041 | 38.8727 | 0 | 0 | 38.8727
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 100 | 0 | 0 | 100
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.0713 | 0 | 2.0713 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.8553 | 0 | 1.8553 | 0 | IWP_1041 | 0 | 144.7126 | 0 | 144.7126
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Inlines - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 5.265 | 0 | 5.265 | 0 | IWP_1041 | 0 | 410.67 | 0 | 410.67
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1041 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1041 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3062 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1041 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3062 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1041 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3067 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1041 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3067 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1041 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3069 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1041 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3069 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1041 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 9 | 9 | 0 | 0 | 18 | 27 | 0 | 0 | 27 | CS | 1.1765 | 1 | 110 | 0 | 10.5885 | 10.5885 | 0 | 0 | IWP_1041 | 1164.735 | 0 | 0 | 1164.735
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 6 | 0 | 0 | 18 | 18 | 0 | 0 | 18 | CS | 1.3715 | 1 | 110 | 0 | 8.229 | 8.229 | 0 | 0 | IWP_1041 | 905.19 | 0 | 0 | 905.19
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.798 | 1.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.33744 | 0.33744 | 0 | 0 | IWP_1041 | 37.118 | 0 | 0 | 37.118
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 5.618 | 5.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.98246 | 0.98246 | 0 | 0 | IWP_1041 | 108.0707 | 0 | 0 | 108.0707
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 450 | 0 | 0 | 450
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 300 | 0 | 0 | 300
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 6 | 6 | 0 | 0 | IWP_1041 | 660 | 0 | 0 | 660
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1041 | 600 | 0 | 0 | 600
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.9778 | 0 | 1.9778 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.7715 | 0 | 1.7715 | 0 | IWP_1041 | 0 | 138.1802 | 0 | 138.1802
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 6.1798 | 0 | 6.1798 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 5.3969 | 0 | 5.3969 | 0 | IWP_1041 | 0 | 420.9616 | 0 | 420.9616
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.7062 | 0 | 1.7062 | 0 | IWP_1041 | 0 | 133.0875 | 0 | 133.0875
Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1041 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1041 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 4 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 3.848 | 1 | 110 | 0 | 15.392 | 15.392 | 0 | 0 | IWP_1041 | 1693.12 | 0 | 0 | 1693.12
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 20 | 20 | 0 | 0 | 240 | 600 | 0 | 0 | 600 | CS | 7.683 | 1 | 110 | 0 | 153.66 | 153.66 | 0 | 0 | IWP_1041 | 16902.6 | 0 | 0 | 16902.6
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1041 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 12.302 | 12.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 7.0312 | 7.0312 | 0 | 0 | IWP_1041 | 773.4332 | 0 | 0 | 773.4332
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1041 | 750 | 0 | 0 | 750
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1041 | 100 | 0 | 0 | 100
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 19 | 19 | 0 | 0 | IWP_1041 | 2090 | 0 | 0 | 2090
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1041 | 1700 | 0 | 0 | 1700
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 14.1473 | 0 | 14.1473 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 38.9662 | 0 | 38.9662 | 0 | IWP_1041 | 0 | 3039.3601 | 0 | 3039.3601
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1041 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1041 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1041 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 13.9912 | 0 | 13.9912 | 0 | IWP_1041 | 0 | 1091.3175 | 0 | 1091.3175
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 4.3075 | 0 | 4.3075 | 0 | IWP_1041 | 0 | 335.9811 | 0 | 335.9811
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1042 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1042 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1042 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1042 | 429 | 0 | 0 | 429
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1042 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1042 | 1001 | 0 | 0 | 1001
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1042 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1042 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1042 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 200 | 0 | 0 | 200
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1042 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1042 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1042 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1042 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1042 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1042 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 2 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.586 | 1 | 110 | 0 | 3.172 | 3.172 | 0 | 0 | IWP_1042 | 348.92 | 0 | 0 | 348.92
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 8 | 8 | 0 | 0 | 48 | 72 | 0 | 0 | 72 | CS | 2.9315 | 1 | 110 | 0 | 23.452 | 23.452 | 0 | 0 | IWP_1042 | 2579.72 | 0 | 0 | 2579.72
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 10 | 10 | 0 | 0 | 80 | 120 | 0 | 0 | 120 | CS | 3.848 | 1 | 110 | 0 | 38.48 | 38.48 | 0 | 0 | IWP_1042 | 4232.8 | 0 | 0 | 4232.8
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1042 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1042 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1042 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1042 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 1 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 2.21 | 1 | 110 | 0 | 2.21 | 2.21 | 0 | 0 | IWP_1042 | 243.1 | 0 | 0 | 243.1
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 6 | 0 | 0 | 12 | 36 | 0 | 0 | 36 | CS | 5.46 | 1 | 110 | 0 | 32.76 | 32.76 | 0 | 0 | IWP_1042 | 3603.6 | 0 | 0 | 3603.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 3 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 1 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 7.67 | 1 | 110 | 0 | 7.67 | 7.67 | 0 | 0 | IWP_1042 | 843.7 | 0 | 0 | 843.7
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchXST | LM | 5.907 | 5.907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.37535 | 1 | 110 | 0 | 2.2172 | 2.2172 | 0 | 0 | IWP_1042 | 243.8888 | 0 | 0 | 243.8888
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 150 | 0 | 0 | 150
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1042 | 75 | 0 | 0 | 75
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1042 | 200 | 0 | 0 | 200
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 8 | Shop Hydrotest - NB 8 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 16 | 1 | 110 | 0 | 16 | 16 | 0 | 0 | IWP_1042 | 1760 | 0 | 0 | 1760
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 8 | Shop Spools Coating - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1100 | 0 | 0 | 0 | 0 | IWP_1042 | 1100 | 0 | 0 | 1100
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchXST | LM | 6.4977 | 0 | 6.4977 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.4184 | 0.75 | 78 | 0 | 11.7857 | 0 | 11.7857 | 0 | IWP_1042 | 0 | 919.2807 | 0 | 919.2807
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1042 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1042 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install Inlines - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1042 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 8.19 | 0 | 8.19 | 0 | IWP_1042 | 0 | 638.82 | 0 | 638.82
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1042 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1042 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.51 | 0 | 3.51 | 0 | IWP_1042 | 0 | 273.78 | 0 | 273.78
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1042 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1042 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 12.675 | 0 | 12.675 | 0 | IWP_1042 | 0 | 988.65 | 0 | 988.65
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 8 | Erection of Pipe Supports - NB 8 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7364 | 0.75 | 78 | 0 | 2.6047 | 0 | 2.6047 | 0 | IWP_1042 | 0 | 203.1632 | 0 | 203.1632
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1042 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 2 | 0 | 0 | 6 | 9 | 0 | 0 | 9 | CS | 1.586 | 1 | 110 | 0 | 3.172 | 3.172 | 0 | 0 | IWP_1042 | 348.92 | 0 | 0 | 348.92
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 8 | 8 | 0 | 0 | 48 | 72 | 0 | 0 | 72 | CS | 2.9315 | 1 | 110 | 0 | 23.452 | 23.452 | 0 | 0 | IWP_1042 | 2579.72 | 0 | 0 | 2579.72
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 10 | 10 | 0 | 0 | 80 | 120 | 0 | 0 | 120 | CS | 3.848 | 1 | 110 | 0 | 38.48 | 38.48 | 0 | 0 | IWP_1042 | 4232.8 | 0 | 0 | 4232.8
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1042 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1042 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1042 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1042 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 3 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 1 | 0 | 0 | 3 | 4.5 | 0 | 0 | 4.5 | CS | 2.21 | 1 | 110 | 0 | 2.21 | 2.21 | 0 | 0 | IWP_1042 | 243.1 | 0 | 0 | 243.1
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 6 | 0 | 0 | 12 | 36 | 0 | 0 | 36 | CS | 5.46 | 1 | 110 | 0 | 32.76 | 32.76 | 0 | 0 | IWP_1042 | 3603.6 | 0 | 0 | 3603.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 3 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 1 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 7.67 | 1 | 110 | 0 | 7.67 | 7.67 | 0 | 0 | IWP_1042 | 843.7 | 0 | 0 | 843.7
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchXST | LM | 5.907 | 5.907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.37535 | 1 | 110 | 0 | 2.2172 | 2.2172 | 0 | 0 | IWP_1042 | 243.8888 | 0 | 0 | 243.8888
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 150 | 0 | 0 | 150
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1042 | 75 | 0 | 0 | 75
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1042 | 200 | 0 | 0 | 200
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 8 | Shop Hydrotest - NB 8 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 16 | 1 | 110 | 0 | 16 | 16 | 0 | 0 | IWP_1042 | 1760 | 0 | 0 | 1760
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 8 | Shop Spools Coating - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1100 | 0 | 0 | 0 | 0 | IWP_1042 | 1100 | 0 | 0 | 1100
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchXST | LM | 6.4977 | 0 | 6.4977 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.4184 | 0.75 | 78 | 0 | 11.7857 | 0 | 11.7857 | 0 | IWP_1042 | 0 | 919.2807 | 0 | 919.2807
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1042 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1042 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install Inlines - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1042 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 8.19 | 0 | 8.19 | 0 | IWP_1042 | 0 | 638.82 | 0 | 638.82
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1042 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1042 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.51 | 0 | 3.51 | 0 | IWP_1042 | 0 | 273.78 | 0 | 273.78
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.3 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1042 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1042 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 12.675 | 0 | 12.675 | 0 | IWP_1042 | 0 | 988.65 | 0 | 988.65
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 8 | Erection of Pipe Supports - NB 8 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7364 | 0.75 | 78 | 0 | 2.6047 | 0 | 2.6047 | 0 | IWP_1042 | 0 | 203.1632 | 0 | 203.1632
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1041 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 10 | 0 | 0 | 60 | 90 | 0 | 0 | 90 | CS | 2.9315 | 1 | 110 | 0 | 29.315 | 29.315 | 0 | 0 | IWP_1041 | 3224.65 | 0 | 0 | 3224.65
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1041 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 10.41 | 10.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 3.1081 | 3.1081 | 0 | 0 | IWP_1041 | 341.8937 | 0 | 0 | 341.8937
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1041 | 50 | 0 | 0 | 50
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1041 | 150 | 0 | 0 | 150
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1041 | 1320 | 0 | 0 | 1320
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1041 | 900 | 0 | 0 | 900
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 11.451 | 0 | 11.451 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 16.4109 | 0 | 16.4109 | 0 | IWP_1041 | 0 | 1280.0498 | 0 | 1280.0498
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1041 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1041 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1041 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 2.4806 | 0 | 2.4806 | 0 | IWP_1041 | 0 | 193.4888 | 0 | 193.4888
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1042 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 4 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 3.848 | 1 | 110 | 0 | 15.392 | 15.392 | 0 | 0 | IWP_1042 | 1693.12 | 0 | 0 | 1693.12
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 14 | 0 | 0 | 168 | 420 | 0 | 0 | 420 | CS | 7.683 | 1 | 110 | 0 | 107.562 | 107.562 | 0 | 0 | IWP_1042 | 11831.82 | 0 | 0 | 11831.82
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1042 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 1.806 | 1.806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 1.0322 | 1.0322 | 0 | 0 | IWP_1042 | 113.5442 | 0 | 0 | 113.5442
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1042 | 500 | 0 | 0 | 500
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1042 | 100 | 0 | 0 | 100
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 2.0769 | 0 | 2.0769 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 5.7204 | 0 | 5.7204 | 0 | IWP_1042 | 0 | 446.1945 | 0 | 446.1945
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1042 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1042 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 9.9938 | 0 | 9.9938 | 0 | IWP_1042 | 0 | 779.5125 | 0 | 779.5125
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1042 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1042 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1042 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 2.996 | 2.996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 0.89452 | 0.89452 | 0 | 0 | IWP_1042 | 98.3971 | 0 | 0 | 98.3971
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1042 | 75 | 0 | 0 | 75
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 3.2956 | 0 | 3.2956 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 4.7231 | 0 | 4.7231 | 0 | IWP_1042 | 0 | 368.3986 | 0 | 368.3986
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1042 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1042 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 3.51 | 0 | 3.51 | 0 | IWP_1042 | 0 | 273.78 | 0 | 273.78
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 1.2403 | 0 | 1.2403 | 0 | IWP_1042 | 0 | 96.7444 | 0 | 96.7444
Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1042 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.621 | 1.621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.30422 | 0.30422 | 0 | 0 | IWP_1042 | 33.464 | 0 | 0 | 33.464
Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 100 | 0 | 0 | 100
Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.7831 | 0 | 1.7831 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.5971 | 0 | 1.5971 | 0 | IWP_1042 | 0 | 124.5774 | 0 | 124.5774
Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1042 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1042 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1042 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1042 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1042 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1042 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1042 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1042 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1042 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.066 | 1.066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.19097 | 0.19097 | 0 | 0 | IWP_1042 | 21.0063 | 0 | 0 | 21.0063
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.463 | 2.463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.46224 | 0.46224 | 0 | 0 | IWP_1042 | 50.8463 | 0 | 0 | 50.8463
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 150 | 0 | 0 | 150
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 50 | 0 | 0 | 50
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.1193 | 0 | 1.1193 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.97751 | 0 | 0.97751 | 0 | IWP_1042 | 0 | 76.2456 | 0 | 76.2456
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.7093 | 0 | 2.7093 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.4268 | 0 | 2.4268 | 0 | IWP_1042 | 0 | 189.2869 | 0 | 189.2869
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1042 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1042 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1042 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1042 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1042 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1042 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.35 | 0.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.065686 | 0.065686 | 0 | 0 | IWP_1042 | 7.2254 | 0 | 0 | 7.2254
Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 100 | 0 | 0 | 100
Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.385 | 0 | 0.385 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.34485 | 0 | 0.34485 | 0 | IWP_1042 | 0 | 26.8983 | 0 | 26.8983
Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1042 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1042 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1042 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1042 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1042 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1042 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.78 | 1 | 110 | 0 | 7.8 | 7.8 | 0 | 0 | IWP_1042 | 858 | 0 | 0 | 858
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1042 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1042 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1042 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.164 | 1.164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.20852 | 0.20852 | 0 | 0 | IWP_1042 | 22.9374 | 0 | 0 | 22.9374
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.456 | 1.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.27325 | 0.27325 | 0 | 0 | IWP_1042 | 30.0577 | 0 | 0 | 30.0577
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 200 | 0 | 0 | 200
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1042 | 50 | 0 | 0 | 50
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.2222 | 0 | 1.2222 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.0674 | 0 | 1.0674 | 0 | IWP_1042 | 0 | 83.255 | 0 | 83.255
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.6016 | 0 | 1.6016 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.4346 | 0 | 1.4346 | 0 | IWP_1042 | 0 | 111.8968 | 0 | 111.8968
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1042 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1042 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1042 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1042 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1042 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 22 | 22 | 0 | 0 | 44 | 66 | 0 | 0 | 66 | CS | 1.1765 | 1 | 110 | 0 | 25.883 | 25.883 | 0 | 0 | IWP_1043 | 2847.13 | 0 | 0 | 2847.13
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1043 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1043 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.69 | 1 | 110 | 0 | 3.38 | 3.38 | 0 | 0 | IWP_1043 | 371.8 | 0 | 0 | 371.8
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1043 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1043 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.513 | 2.513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.47162 | 0.47162 | 0 | 0 | IWP_1043 | 51.8785 | 0 | 0 | 51.8785
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1043 | 50 | 0 | 0 | 50
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1043 | 150 | 0 | 0 | 150
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.7643 | 0 | 2.7643 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.476 | 0 | 2.476 | 0 | IWP_1043 | 0 | 193.1295 | 0 | 193.1295
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.17 | 0 | 1.17 | 0 | IWP_1043 | 0 | 91.26 | 0 | 91.26
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1043 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.0713 | 0 | 3.0713 | 0 | IWP_1043 | 0 | 239.5575 | 0 | 239.5575
Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 1.5 | 0 | 1.5 | 0 | IWP_1043 | 0 | 117 | 0 | 117
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1043 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1043 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1043 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1043 | 429 | 0 | 0 | 429
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1043 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1043 | 1001 | 0 | 0 | 1001
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1043 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1043 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1043 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1043 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1043 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1043 | 200 | 0 | 0 | 200
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1043 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1043 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1043 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1043 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1043 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1043 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1043 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1043 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1043 | 429 | 0 | 0 | 429
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1043 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1043 | 1001 | 0 | 0 | 1001
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1043 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1043 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1043 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1043 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1043 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1043 | 200 | 0 | 0 | 200
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1043 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1043 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1043 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1043 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1043 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1043 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1043 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1043 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 9.437 | 9.437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 2.8176 | 2.8176 | 0 | 0 | IWP_1043 | 309.9376 | 0 | 0 | 309.9376
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1043 | 50 | 0 | 0 | 50
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1043 | 75 | 0 | 0 | 75
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1043 | 1320 | 0 | 0 | 1320
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1043 | 900 | 0 | 0 | 900
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 10.3807 | 0 | 10.3807 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 14.877 | 0 | 14.877 | 0 | IWP_1043 | 0 | 1160.4064 | 0 | 1160.4064
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1043 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1043 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 3.51 | 0 | 3.51 | 0 | IWP_1043 | 0 | 273.78 | 0 | 273.78
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1043 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 2 | 2 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 2.9315 | 1 | 110 | 0 | 5.863 | 5.863 | 0 | 0 | IWP_1043 | 644.93 | 0 | 0 | 644.93
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 14 | 0 | 0 | 168 | 420 | 0 | 0 | 420 | CS | 7.683 | 1 | 110 | 0 | 107.562 | 107.562 | 0 | 0 | IWP_1043 | 11831.82 | 0 | 0 | 11831.82
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1043 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1043 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 4 | 4 | 0 | 0 | 8 | 24 | 0 | 0 | 24 | CS | 5.46 | 1 | 110 | 0 | 21.84 | 21.84 | 0 | 0 | IWP_1043 | 2402.4 | 0 | 0 | 2402.4
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1043 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 0.044786 | 0.044786 | 0 | 0 | IWP_1043 | 4.9264 | 0 | 0 | 4.9264
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 14.374 | 14.374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 8.2155 | 8.2155 | 0 | 0 | IWP_1043 | 903.7009 | 0 | 0 | 903.7009
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1043 | 500 | 0 | 0 | 500
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1043 | 100 | 0 | 0 | 100
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 38 | 38 | 0 | 0 | IWP_1043 | 4180 | 0 | 0 | 4180
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1043 | 3400 | 0 | 0 | 3400
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 0.165 | 0 | 0.165 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 0.23647 | 0 | 0.23647 | 0 | IWP_1043 | 0 | 18.4445 | 0 | 18.4445
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 16.5301 | 0 | 16.5301 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 45.5291 | 0 | 45.5291 | 0 | IWP_1043 | 0 | 3551.2732 | 0 | 3551.2732
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1043 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install valve - NB 12 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 18.4275 | 0 | 18.4275 | 0 | IWP_1043 | 0 | 1437.345 | 0 | 1437.345
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install Blind - NB 12 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 6.1425 | 0 | 6.1425 | 0 | IWP_1043 | 0 | 479.115 | 0 | 479.115
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1043 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.9488 | 0 | 3.9488 | 0 | IWP_1043 | 0 | 308.0025 | 0 | 308.0025
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1043 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 27.9825 | 0 | 27.9825 | 0 | IWP_1043 | 0 | 2182.635 | 0 | 2182.635
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 1.4358 | 0 | 1.4358 | 0 | IWP_1043 | 0 | 111.9937 | 0 | 111.9937
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1044 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | 0 | 0 | 3 | 9 | 0 | 0 | 9 | CS | 2.86 | 1 | 110 | 0 | 8.58 | 8.58 | 0 | 0 | IWP_1044 | 943.8 | 0 | 0 | 943.8
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | 0 | 0 | 6 | 15 | 0 | 0 | 15 | CS | 0.39 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1044 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | 0 | 0 | 4 | 10 | 0 | 0 | 10 | CS | 0.39 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1044 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 6 | 6 | 0 | 0 | 6 | 15 | 0 | 0 | 15 | CS | 0.39 | 1 | 110 | 0 | 2.34 | 2.34 | 0 | 0 | IWP_1044 | 257.4 | 0 | 0 | 257.4
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 10.571 | 10.571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.9839 | 1.9839 | 0 | 0 | IWP_1044 | 218.2283 | 0 | 0 | 218.2283
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 150 | 0 | 0 | 150
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 500 | 0 | 0 | 500
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1044 | 616 | 0 | 0 | 616
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1044 | 500 | 0 | 0 | 500
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 11.6281 | 0 | 11.6281 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 10.4154 | 0 | 10.4154 | 0 | IWP_1044 | 0 | 812.4043 | 0 | 812.4043
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1044 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1044 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 3.0713 | 0 | 3.0713 | 0 | IWP_1044 | 0 | 239.5575 | 0 | 239.5575
Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1044 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 17 | 17 | 0 | 0 | 34 | 51 | 0 | 0 | 51 | CS | 1.1765 | 1 | 110 | 0 | 20.0005 | 20.0005 | 0 | 0 | IWP_1044 | 2200.055 | 0 | 0 | 2200.055
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1044 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1044 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 8 | 8 | 0 | 0 | 8 | 10 | 0 | 0 | 10 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1044 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 4 | 4 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 2.86 | 1 | 110 | 0 | 11.44 | 11.44 | 0 | 0 | IWP_1044 | 1258.4 | 0 | 0 | 1258.4
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 4 | 4 | 0 | 0 | 4 | 10 | 0 | 0 | 10 | CS | 0.39 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1044 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 4.273 | 4.273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.80193 | 0.80193 | 0 | 0 | IWP_1044 | 88.212 | 0 | 0 | 88.212
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 1000 | 0 | 0 | 1000
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 850 | 0 | 0 | 850
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 4.7003 | 0 | 4.7003 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 4.2101 | 0 | 4.2101 | 0 | IWP_1044 | 0 | 328.3893 | 0 | 328.3893
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 2.34 | 0 | 2.34 | 0 | IWP_1044 | 0 | 182.52 | 0 | 182.52
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.365 | 0 | 1.365 | 0 | IWP_1044 | 0 | 106.47 | 0 | 106.47
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 3 | 0 | 3 | 0 | IWP_1044 | 0 | 234 | 0 | 234
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 17 | 17 | 0 | 0 | 34 | 51 | 0 | 0 | 51 | CS | 1.1765 | 1 | 110 | 0 | 20.0005 | 20.0005 | 0 | 0 | IWP_1044 | 2200.055 | 0 | 0 | 2200.055
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1044 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1044 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 2.86 | 1 | 110 | 0 | 5.72 | 5.72 | 0 | 0 | IWP_1044 | 629.2 | 0 | 0 | 629.2
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 6.964 | 6.964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.307 | 1.307 | 0 | 0 | IWP_1044 | 143.7652 | 0 | 0 | 143.7652
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 400 | 0 | 0 | 400
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 850 | 0 | 0 | 850
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1044 | 616 | 0 | 0 | 616
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1044 | 500 | 0 | 0 | 500
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 7.6604 | 0 | 7.6604 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 6.8615 | 0 | 6.8615 | 0 | IWP_1044 | 0 | 535.1985 | 0 | 535.1985
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1044 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1044 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.7062 | 0 | 1.7062 | 0 | IWP_1044 | 0 | 133.0875 | 0 | 133.0875
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1044 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 3.75 | 0 | 3.75 | 0 | IWP_1044 | 0 | 292.5 | 0 | 292.5
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 12 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 1.1765 | 1 | 110 | 0 | 14.118 | 14.118 | 0 | 0 | IWP_1044 | 1552.98 | 0 | 0 | 1552.98
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 4 | 0 | 0 | 12 | 12 | 0 | 0 | 12 | CS | 1.3715 | 1 | 110 | 0 | 5.486 | 5.486 | 0 | 0 | IWP_1044 | 603.46 | 0 | 0 | 603.46
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 11.302 | 11.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 2.1211 | 2.1211 | 0 | 0 | IWP_1044 | 233.3191 | 0 | 0 | 233.3191
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 600 | 0 | 0 | 600
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 200 | 0 | 0 | 200
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1044 | 616 | 0 | 0 | 616
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1044 | 500 | 0 | 0 | 500
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 12.4322 | 0 | 12.4322 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 11.1357 | 0 | 11.1357 | 0 | IWP_1044 | 0 | 868.5833 | 0 | 868.5833
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1044 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1044 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1044 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.059 | 1.059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.19875 | 0.19875 | 0 | 0 | IWP_1044 | 21.8621 | 0 | 0 | 21.8621
Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 300 | 0 | 0 | 300
Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.1649 | 0 | 1.1649 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.0434 | 0 | 1.0434 | 0 | IWP_1044 | 0 | 81.3865 | 0 | 81.3865
Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1044 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1044 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.662 | 0.662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.12424 | 0.12424 | 0 | 0 | IWP_1044 | 13.6664 | 0 | 0 | 13.6664
Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 300 | 0 | 0 | 300
Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.7282 | 0 | 0.7282 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.65226 | 0 | 0.65226 | 0 | IWP_1044 | 0 | 50.8761 | 0 | 50.8761
Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1044 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 9 | 9 | 0 | 0 | 18 | 27 | 0 | 0 | 27 | CS | 1.1765 | 1 | 110 | 0 | 10.5885 | 10.5885 | 0 | 0 | IWP_1044 | 1164.735 | 0 | 0 | 1164.735
Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.446 | 1.446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.27138 | 0.27138 | 0 | 0 | IWP_1044 | 29.8513 | 0 | 0 | 29.8513
Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 450 | 0 | 0 | 450
Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.5906 | 0 | 1.5906 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.4247 | 0 | 1.4247 | 0 | IWP_1044 | 0 | 111.1282 | 0 | 111.1282
Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1044 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 9 | 9 | 0 | 0 | 18 | 27 | 0 | 0 | 27 | CS | 1.1765 | 1 | 110 | 0 | 10.5885 | 10.5885 | 0 | 0 | IWP_1044 | 1164.735 | 0 | 0 | 1164.735
Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.675 | 2.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.50203 | 0.50203 | 0 | 0 | IWP_1044 | 55.2228 | 0 | 0 | 55.2228
Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 450 | 0 | 0 | 450
Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.9425 | 0 | 2.9425 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.6356 | 0 | 2.6356 | 0 | IWP_1044 | 0 | 205.5796 | 0 | 205.5796
Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1044 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1044 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 5 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 1.1765 | 1 | 110 | 0 | 5.8825 | 5.8825 | 0 | 0 | IWP_1044 | 647.075 | 0 | 0 | 647.075
Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.897 | 0.897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.16834 | 0.16834 | 0 | 0 | IWP_1044 | 18.5177 | 0 | 0 | 18.5177
Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 250 | 0 | 0 | 250
Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.9867 | 0 | 0.9867 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.8838 | 0 | 0.8838 | 0 | IWP_1044 | 0 | 68.9364 | 0 | 68.9364
Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1044 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 5 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 1.1765 | 1 | 110 | 0 | 5.8825 | 5.8825 | 0 | 0 | IWP_1044 | 647.075 | 0 | 0 | 647.075
Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.897 | 0.897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.16834 | 0.16834 | 0 | 0 | IWP_1044 | 18.5177 | 0 | 0 | 18.5177
Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 250 | 0 | 0 | 250
Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.9867 | 0 | 0.9867 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.8838 | 0 | 0.8838 | 0 | IWP_1044 | 0 | 68.9364 | 0 | 68.9364
Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1044 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1044 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.301 | 2.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.43184 | 0.43184 | 0 | 0 | IWP_1044 | 47.502 | 0 | 0 | 47.502
Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 400 | 0 | 0 | 400
Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.5311 | 0 | 2.5311 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.2671 | 0 | 2.2671 | 0 | IWP_1044 | 0 | 176.8369 | 0 | 176.8369
Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1044 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1044 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1044 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1044 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1044 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1044 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.78 | 1 | 110 | 0 | 7.8 | 7.8 | 0 | 0 | IWP_1044 | 858 | 0 | 0 | 858
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1044 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1044 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1044 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1044 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 1.826 | 1.826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.32711 | 0.32711 | 0 | 0 | IWP_1044 | 35.9826 | 0 | 0 | 35.9826
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.908 | 1.908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.35808 | 0.35808 | 0 | 0 | IWP_1044 | 39.3889 | 0 | 0 | 39.3889
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 200 | 0 | 0 | 200
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 50 | 0 | 0 | 50
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.9173 | 0 | 1.9173 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.6744 | 0 | 1.6744 | 0 | IWP_1044 | 0 | 130.6045 | 0 | 130.6045
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.0988 | 0 | 2.0988 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.8799 | 0 | 1.8799 | 0 | IWP_1044 | 0 | 146.634 | 0 | 146.634
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1044 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1044 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1044 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1044 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1044 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1044 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1044 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1044 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1044 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.78 | 1 | 110 | 0 | 7.8 | 7.8 | 0 | 0 | IWP_1044 | 858 | 0 | 0 | 858
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1044 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1044 | 1001 | 0 | 0 | 1001
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1044 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1044 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 2.042 | 2.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.36581 | 0.36581 | 0 | 0 | IWP_1044 | 40.239 | 0 | 0 | 40.239
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.732 | 1.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.32505 | 0.32505 | 0 | 0 | IWP_1044 | 35.7555 | 0 | 0 | 35.7555
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 250 | 0 | 0 | 250
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 50 | 0 | 0 | 50
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 2.1441 | 0 | 2.1441 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.8725 | 0 | 1.8725 | 0 | IWP_1044 | 0 | 146.0539 | 0 | 146.0539
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.9052 | 0 | 1.9052 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.7065 | 0 | 1.7065 | 0 | IWP_1044 | 0 | 133.108 | 0 | 133.108
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1044 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1044 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1044 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1044 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1044 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1044 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1044 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 4 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 3.848 | 1 | 110 | 0 | 15.392 | 15.392 | 0 | 0 | IWP_1044 | 1693.12 | 0 | 0 | 1693.12
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 18 | 18 | 0 | 0 | 216 | 540 | 0 | 0 | 540 | CS | 7.683 | 1 | 110 | 0 | 138.294 | 138.294 | 0 | 0 | IWP_1044 | 15212.34 | 0 | 0 | 15212.34
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1044 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 7.691 | 7.691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 4.3958 | 4.3958 | 0 | 0 | IWP_1044 | 483.5372 | 0 | 0 | 483.5372
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1044 | 750 | 0 | 0 | 750
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1044 | 50 | 0 | 0 | 50
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1044 | 100 | 0 | 0 | 100
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 12 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 19 | 1 | 110 | 0 | 19 | 19 | 0 | 0 | IWP_1044 | 2090 | 0 | 0 | 2090
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 12 | Shop Spools Coating - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 1700 | 0 | 0 | 0 | 0 | IWP_1044 | 1700 | 0 | 0 | 1700
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 8.8446 | 0 | 8.8446 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 24.361 | 0 | 24.361 | 0 | IWP_1044 | 0 | 1900.156 | 0 | 1900.156
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1044 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1044 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1044 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 13.9912 | 0 | 13.9912 | 0 | IWP_1044 | 0 | 1091.3175 | 0 | 1091.3175
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1045 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 2 | 2 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 2.9315 | 1 | 110 | 0 | 5.863 | 5.863 | 0 | 0 | IWP_1045 | 644.93 | 0 | 0 | 644.93
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 6 | 6 | 0 | 0 | 48 | 72 | 0 | 0 | 72 | CS | 3.848 | 1 | 110 | 0 | 23.088 | 23.088 | 0 | 0 | IWP_1045 | 2539.68 | 0 | 0 | 2539.68
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1045 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1045 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1045 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1045 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchXST | LM | 1.618 | 1.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.37535 | 1 | 110 | 0 | 0.60731 | 0.60731 | 0 | 0 | IWP_1045 | 66.8042 | 0 | 0 | 66.8042
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1045 | 50 | 0 | 0 | 50
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1045 | 100 | 0 | 0 | 100
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchXST | LM | 1.7798 | 0 | 1.7798 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.4184 | 0.75 | 78 | 0 | 3.2282 | 0 | 3.2282 | 0 | IWP_1045 | 0 | 251.8023 | 0 | 251.8023
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1045 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install Inlines - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1045 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install Inlines - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1045 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1045 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1045 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1045 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1045 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 11.4075 | 0 | 11.4075 | 0 | IWP_1045 | 0 | 889.785 | 0 | 889.785
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 8 | Erection of Pipe Supports - NB 8 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7364 | 0.75 | 78 | 0 | 1.3023 | 0 | 1.3023 | 0 | IWP_1045 | 0 | 101.5816 | 0 | 101.5816
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1045 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1045 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 4 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 3.848 | 1 | 110 | 0 | 15.392 | 15.392 | 0 | 0 | IWP_1045 | 1693.12 | 0 | 0 | 1693.12
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1045 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1045 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 5 | 5 | 0 | 0 | 10 | 30 | 0 | 0 | 30 | CS | 5.46 | 1 | 110 | 0 | 27.3 | 27.3 | 0 | 0 | IWP_1045 | 3003 | 0 | 0 | 3003
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1045 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchXST | LM | 3.481 | 3.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.37535 | 1 | 110 | 0 | 1.3066 | 1.3066 | 0 | 0 | IWP_1045 | 143.7239 | 0 | 0 | 143.7239
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1045 | 150 | 0 | 0 | 150
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1045 | 75 | 0 | 0 | 75
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1045 | 100 | 0 | 0 | 100
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchXST | LM | 3.8291 | 0 | 3.8291 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.4184 | 0.75 | 78 | 0 | 6.9453 | 0 | 6.9453 | 0 | IWP_1045 | 0 | 541.7329 | 0 | 541.7329
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1045 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1045 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1045 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.9488 | 0 | 3.9488 | 0 | IWP_1045 | 0 | 308.0025 | 0 | 308.0025
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1045 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 3.8025 | 0 | 3.8025 | 0 | IWP_1045 | 0 | 296.595 | 0 | 296.595
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 8 | Erection of Pipe Supports - NB 8 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7364 | 0.75 | 78 | 0 | 2.6047 | 0 | 2.6047 | 0 | IWP_1045 | 0 | 203.1632 | 0 | 203.1632
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1044 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1044 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1044 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.17 | 0 | 1.17 | 0 | IWP_1044 | 0 | 91.26 | 0 | 91.26
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1045 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 2 | 2 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 2.9315 | 1 | 110 | 0 | 5.863 | 5.863 | 0 | 0 | IWP_1045 | 644.93 | 0 | 0 | 644.93
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 6 | 6 | 0 | 0 | 48 | 72 | 0 | 0 | 72 | CS | 3.848 | 1 | 110 | 0 | 23.088 | 23.088 | 0 | 0 | IWP_1045 | 2539.68 | 0 | 0 | 2539.68
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1045 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1045 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1045 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1045 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchXST | LM | 1.618 | 1.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.37535 | 1 | 110 | 0 | 0.60731 | 0.60731 | 0 | 0 | IWP_1045 | 66.8042 | 0 | 0 | 66.8042
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1045 | 50 | 0 | 0 | 50
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1045 | 100 | 0 | 0 | 100
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchXST | LM | 1.7798 | 0 | 1.7798 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.4184 | 0.75 | 78 | 0 | 3.2282 | 0 | 3.2282 | 0 | IWP_1045 | 0 | 251.8023 | 0 | 251.8023
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1045 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install Inlines - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1045 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install Inlines - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1045 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1045 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1045 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1045 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 2.6325 | 0 | 2.6325 | 0 | IWP_1045 | 0 | 205.335 | 0 | 205.335
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 11.4075 | 0 | 11.4075 | 0 | IWP_1045 | 0 | 889.785 | 0 | 889.785
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 8 | Erection of Pipe Supports - NB 8 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7364 | 0.75 | 78 | 0 | 1.3023 | 0 | 1.3023 | 0 | IWP_1045 | 0 | 101.5816 | 0 | 101.5816
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1045 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1045 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 4 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 3.848 | 1 | 110 | 0 | 15.392 | 15.392 | 0 | 0 | IWP_1045 | 1693.12 | 0 | 0 | 1693.12
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1045 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1045 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 5 | 5 | 0 | 0 | 10 | 30 | 0 | 0 | 30 | CS | 5.46 | 1 | 110 | 0 | 27.3 | 27.3 | 0 | 0 | IWP_1045 | 3003 | 0 | 0 | 3003
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1045 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 8 | Shop handling - NB 8 SchXST | LM | 3.481 | 3.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.37535 | 1 | 110 | 0 | 1.3066 | 1.3066 | 0 | 0 | IWP_1045 | 143.7239 | 0 | 0 | 143.7239
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1045 | 150 | 0 | 0 | 150
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1045 | 75 | 0 | 0 | 75
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1045 | 100 | 0 | 0 | 100
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 8 | Install Spools - NB 8 SchXST | LM | 3.8291 | 0 | 3.8291 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.4184 | 0.75 | 78 | 0 | 6.9453 | 0 | 6.9453 | 0 | IWP_1045 | 0 | 541.7329 | 0 | 541.7329
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1045 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1045 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1045 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.9488 | 0 | 3.9488 | 0 | IWP_1045 | 0 | 308.0025 | 0 | 308.0025
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1045 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 3.8025 | 0 | 3.8025 | 0 | IWP_1045 | 0 | 296.595 | 0 | 296.595
Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 8 | Erection of Pipe Supports - NB 8 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.7364 | 0.75 | 78 | 0 | 2.6047 | 0 | 2.6047 | 0 | IWP_1045 | 0 | 203.1632 | 0 | 203.1632
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1045 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1045 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1045 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 2.996 | 2.996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 0.89452 | 0.89452 | 0 | 0 | IWP_1045 | 98.3971 | 0 | 0 | 98.3971
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1045 | 75 | 0 | 0 | 75
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 3.2956 | 0 | 3.2956 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 4.7231 | 0 | 4.7231 | 0 | IWP_1045 | 0 | 368.3986 | 0 | 368.3986
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1045 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1045 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.3163 | 0 | 1.3163 | 0 | IWP_1045 | 0 | 102.6675 | 0 | 102.6675
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 3.51 | 0 | 3.51 | 0 | IWP_1045 | 0 | 273.78 | 0 | 273.78
Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 1.2403 | 0 | 1.2403 | 0 | IWP_1045 | 0 | 96.7444 | 0 | 96.7444
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1046 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 4 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 3.848 | 1 | 110 | 0 | 15.392 | 15.392 | 0 | 0 | IWP_1046 | 1693.12 | 0 | 0 | 1693.12
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 14 | 0 | 0 | 168 | 420 | 0 | 0 | 420 | CS | 7.683 | 1 | 110 | 0 | 107.562 | 107.562 | 0 | 0 | IWP_1046 | 11831.82 | 0 | 0 | 11831.82
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1046 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.143 | 0.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.026837 | 0.026837 | 0 | 0 | IWP_1046 | 2.9521 | 0 | 0 | 2.9521
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 1.438 | 1.438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 0.82189 | 0.82189 | 0 | 0 | IWP_1046 | 90.4078 | 0 | 0 | 90.4078
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1046 | 500 | 0 | 0 | 500
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 50 | 0 | 0 | 50
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 8 | Shop X-Ray - NB 8 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 100 | 0 | 0 | 0 | 0 | IWP_1046 | 100 | 0 | 0 | 100
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.1573 | 0 | 0.1573 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.1409 | 0 | 0.1409 | 0 | IWP_1046 | 0 | 10.9899 | 0 | 10.9899
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 1.6537 | 0 | 1.6537 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 4.5548 | 0 | 4.5548 | 0 | IWP_1046 | 0 | 355.2756 | 0 | 355.2756
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1046 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1046 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1046 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 9.9938 | 0 | 9.9938 | 0 | IWP_1046 | 0 | 779.5125 | 0 | 779.5125
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 4 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 1.1765 | 1 | 110 | 0 | 4.706 | 4.706 | 0 | 0 | IWP_1046 | 517.66 | 0 | 0 | 517.66
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 10 | 0 | 0 | 60 | 90 | 0 | 0 | 90 | CS | 2.9315 | 1 | 110 | 0 | 29.315 | 29.315 | 0 | 0 | IWP_1046 | 3224.65 | 0 | 0 | 3224.65
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1046 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 5.923 | 5.923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 1.7684 | 1.7684 | 0 | 0 | IWP_1046 | 194.528 | 0 | 0 | 194.528
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 50 | 0 | 0 | 50
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1046 | 150 | 0 | 0 | 150
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1046 | 1320 | 0 | 0 | 1320
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1046 | 900 | 0 | 0 | 900
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 6.5153 | 0 | 6.5153 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 9.3373 | 0 | 9.3373 | 0 | IWP_1046 | 0 | 728.3127 | 0 | 728.3127
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1046 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1046 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1046 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1046 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 1.2403 | 0 | 1.2403 | 0 | IWP_1046 | 0 | 96.7444 | 0 | 96.7444
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1046 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1046 | 429 | 0 | 0 | 429
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1046 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1046 | 1001 | 0 | 0 | 1001
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1046 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 200 | 0 | 0 | 200
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1046 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1046 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1046 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1046 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1046 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1046 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1046 | 429 | 0 | 0 | 429
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1046 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1046 | 1001 | 0 | 0 | 1001
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1046 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 200 | 0 | 0 | 200
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1046 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1046 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1046 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1046 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1046 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO1018 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.1765 | 1 | 110 | 0 | 1.1765 | 1.1765 | 0 | 0 | IWP_1046 | 129.415 | 0 | 0 | 129.415
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO1018 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 50 | 0 | 0 | 50
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO1018 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1046 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 17 | 17 | 0 | 0 | 34 | 51 | 0 | 0 | 51 | CS | 1.1765 | 1 | 110 | 0 | 20.0005 | 20.0005 | 0 | 0 | IWP_1046 | 2200.055 | 0 | 0 | 2200.055
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1046 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1046 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1046 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1046 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 5.907 | 5.907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 1.1086 | 1.1086 | 0 | 0 | IWP_1046 | 121.9444 | 0 | 0 | 121.9444
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 150 | 0 | 0 | 150
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 900 | 0 | 0 | 900
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1046 | 616 | 0 | 0 | 616
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1046 | 500 | 0 | 0 | 500
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 6.4977 | 0 | 6.4977 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 5.8201 | 0 | 5.8201 | 0 | IWP_1046 | 0 | 453.9658 | 0 | 453.9658
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1046 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1046 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.0237 | 0 | 1.0237 | 0 | IWP_1046 | 0 | 79.8525 | 0 | 79.8525
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1046 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 3.75 | 0 | 3.75 | 0 | IWP_1046 | 0 | 292.5 | 0 | 292.5
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 21 | 21 | 0 | 0 | 42 | 63 | 0 | 0 | 63 | CS | 1.1765 | 1 | 110 | 0 | 24.7065 | 24.7065 | 0 | 0 | IWP_1046 | 2717.715 | 0 | 0 | 2717.715
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1046 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1046 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1046 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 2.86 | 1 | 110 | 0 | 2.86 | 2.86 | 0 | 0 | IWP_1046 | 314.6 | 0 | 0 | 314.6
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1046 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 3.279 | 3.279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.61538 | 0.61538 | 0 | 0 | IWP_1046 | 67.6918 | 0 | 0 | 67.6918
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 150 | 0 | 0 | 150
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 250 | 0 | 0 | 250
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 1100 | 0 | 0 | 1100
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 3.6069 | 0 | 3.6069 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 3.2307 | 0 | 3.2307 | 0 | IWP_1046 | 0 | 251.9983 | 0 | 251.9983
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1046 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1046 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1046 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.0237 | 0 | 1.0237 | 0 | IWP_1046 | 0 | 79.8525 | 0 | 79.8525
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1046 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1046 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1046 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.326 | 1.326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.24885 | 0.24885 | 0 | 0 | IWP_1046 | 27.374 | 0 | 0 | 27.374
Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 400 | 0 | 0 | 400
Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.4586 | 0 | 1.4586 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.3065 | 0 | 1.3065 | 0 | IWP_1046 | 0 | 101.906 | 0 | 101.906
Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1046 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1046 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1046 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1046 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1046 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 14 | 14 | 0 | 0 | 14 | 17.5 | 0 | 0 | 17.5 | CS | 0.78 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1046 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1046 | 1001 | 0 | 0 | 1001
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1046 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 SchXST | LM | 2.752 | 2.752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.15355 | 1 | 110 | 0 | 0.42257 | 0.42257 | 0 | 0 | IWP_1046 | 46.4829 | 0 | 0 | 46.4829
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.423 | 2.423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.45473 | 0.45473 | 0 | 0 | IWP_1046 | 50.0205 | 0 | 0 | 50.0205
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 100 | 0 | 0 | 100
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 1600 | 0 | 0 | 1600
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 400 | 0 | 0 | 400
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 SchXST | LM | 2.8896 | 0 | 2.8896 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.0151 | 0.75 | 78 | 0 | 2.2 | 0 | 2.2 | 0 | IWP_1046 | 0 | 171.6011 | 0 | 171.6011
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.6653 | 0 | 2.6653 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.3873 | 0 | 2.3873 | 0 | IWP_1046 | 0 | 186.2128 | 0 | 186.2128
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1046 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1046 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1046 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1046 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1046 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1046 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 7 | 0 | 0 | 14 | 21 | 0 | 0 | 21 | CS | 1.1765 | 1 | 110 | 0 | 8.2355 | 8.2355 | 0 | 0 | IWP_1046 | 905.905 | 0 | 0 | 905.905
Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.301 | 1.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.24416 | 0.24416 | 0 | 0 | IWP_1046 | 26.8579 | 0 | 0 | 26.8579
Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 350 | 0 | 0 | 350
Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.4311 | 0 | 1.4311 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.2819 | 0 | 1.2819 | 0 | IWP_1046 | 0 | 99.9847 | 0 | 99.9847
Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1046 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1046 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1046 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1046 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.78 | 1 | 110 | 0 | 7.8 | 7.8 | 0 | 0 | IWP_1046 | 858 | 0 | 0 | 858
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1046 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 12 | 12 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 0.91 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1046 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.96 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.17198 | 0.17198 | 0 | 0 | IWP_1046 | 18.9175 | 0 | 0 | 18.9175
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.049 | 2.049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.38454 | 0.38454 | 0 | 0 | IWP_1046 | 42.2997 | 0 | 0 | 42.2997
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 250 | 0 | 0 | 250
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 100 | 0 | 0 | 100
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 1.008 | 0 | 1.008 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.88031 | 0 | 0.88031 | 0 | IWP_1046 | 0 | 68.6639 | 0 | 68.6639
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 2.2539 | 0 | 2.2539 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.0188 | 0 | 2.0188 | 0 | IWP_1046 | 0 | 157.4701 | 0 | 157.4701
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1046 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1046 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1046 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1046 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1046 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1046 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 8 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 1.1765 | 1 | 110 | 0 | 9.412 | 9.412 | 0 | 0 | IWP_1046 | 1035.32 | 0 | 0 | 1035.32
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1046 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1046 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1046 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1046 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.938 | 0.938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.16804 | 0.16804 | 0 | 0 | IWP_1046 | 18.4839 | 0 | 0 | 18.4839
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 1.681 | 1.681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.31548 | 0.31548 | 0 | 0 | IWP_1046 | 34.7027 | 0 | 0 | 34.7027
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 150 | 0 | 0 | 150
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 50 | 0 | 0 | 50
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 0.9849 | 0 | 0.9849 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.86013 | 0 | 0.86013 | 0 | IWP_1046 | 0 | 67.0904 | 0 | 67.0904
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 1.8491 | 0 | 1.8491 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 1.6563 | 0 | 1.6563 | 0 | IWP_1046 | 0 | 129.1885 | 0 | 129.1885
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1046 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1046 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1046 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1046 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1046 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1046 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 16 | 0 | 0 | 32 | 48 | 0 | 0 | 48 | CS | 1.1765 | 1 | 110 | 0 | 18.824 | 18.824 | 0 | 0 | IWP_1046 | 2070.64 | 0 | 0 | 2070.64
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1046 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | 0 | 0 | 6 | 7.5 | 0 | 0 | 7.5 | CS | 0.78 | 1 | 110 | 0 | 4.68 | 4.68 | 0 | 0 | IWP_1046 | 514.8 | 0 | 0 | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 2.5 | 0 | 0 | 2.5 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1046 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | 0 | 0 | 8 | 12 | 0 | 0 | 12 | CS | 0.91 | 1 | 110 | 0 | 7.28 | 7.28 | 0 | 0 | IWP_1046 | 800.8 | 0 | 0 | 800.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 1 | Shop handling - NB 1 Sch160 | LM | 0.86 | 0.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17914 | 1 | 110 | 0 | 0.15406 | 0.15406 | 0 | 0 | IWP_1046 | 16.9469 | 0 | 0 | 16.9469
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 2.929 | 2.929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.54969 | 0.54969 | 0 | 0 | IWP_1046 | 60.4664 | 0 | 0 | 60.4664
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 150 | 0 | 0 | 150
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 100 | 0 | 0 | 100
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 1 | Install Spools - NB 1 Sch160 | LM | 0.903 | 0 | 0.903 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 0.78861 | 0 | 0.78861 | 0 | IWP_1046 | 0 | 61.5114 | 0 | 61.5114
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 3.2219 | 0 | 3.2219 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 2.8859 | 0 | 2.8859 | 0 | IWP_1046 | 0 | 225.1 | 0 | 225.1
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1046 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1046 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1046 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1046 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 1 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.4 | 0.75 | 78 | 0 | 0.6 | 0 | 0.6 | 0 | IWP_1046 | 0 | 46.8 | 0 | 46.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 0.75 | 0 | 0.75 | 0 | IWP_1046 | 0 | 58.5 | 0 | 58.5
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1046 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 8 | 0 | 0 | 96 | 144 | 0 | 0 | 144 | CS | 4.7255 | 1 | 110 | 0 | 37.804 | 37.804 | 0 | 0 | IWP_1046 | 4158.44 | 0 | 0 | 4158.44
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | 0 | 0 | 3 | 3.75 | 0 | 0 | 3.75 | CS | 0.91 | 1 | 110 | 0 | 2.73 | 2.73 | 0 | 0 | IWP_1046 | 300.3 | 0 | 0 | 300.3
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 3 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | CS | 1.17 | 1 | 110 | 0 | 3.51 | 3.51 | 0 | 0 | IWP_1046 | 386.1 | 0 | 0 | 386.1
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL2000 | EA | 5 | 5 | 0 | 0 | 10 | 30 | 0 | 0 | 30 | CS | 4.42 | 1 | 110 | 0 | 22.1 | 22.1 | 0 | 0 | IWP_1046 | 2431 | 0 | 0 | 2431
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 3 | 3 | 0 | 0 | 1.5 | 3.75 | 0 | 0 | 3.75 | CS | 0.26 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 SchSTD | LM | 1.63 | 1.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.40947 | 1 | 110 | 0 | 0.66743 | 0.66743 | 0 | 0 | IWP_1046 | 73.4178 | 0 | 0 | 73.4178
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 150 | 0 | 0 | 150
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1046 | 2000 | 0 | 0 | 2000
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 900 | 0 | 0 | 900
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 SchSTD | LM | 1.8745 | 0 | 1.8745 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.6274 | 0.75 | 78 | 0 | 3.6938 | 0 | 3.6938 | 0 | IWP_1046 | 0 | 288.1188 | 0 | 288.1188
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 1.95 | 0 | 1.95 | 0 | IWP_1046 | 0 | 152.1 | 0 | 152.1
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.0237 | 0 | 1.0237 | 0 | IWP_1046 | 0 | 79.8525 | 0 | 79.8525
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 4.7775 | 0 | 4.7775 | 0 | IWP_1046 | 0 | 372.645 | 0 | 372.645
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.42 | 0.75 | 78 | 0 | 1.6575 | 0 | 1.6575 | 0 | IWP_1046 | 0 | 129.285 | 0 | 129.285
Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 1.9988 | 0 | 1.9988 | 0 | IWP_1046 | 0 | 155.9025 | 0 | 155.9025
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1046 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1046 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1046 | 429 | 0 | 0 | 429
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 10 | 10 | 0 | 0 | 10 | 12.5 | 0 | 0 | 12.5 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1046 | 1001 | 0 | 0 | 1001
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXST | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.78 | 1 | 110 | 0 | 3.12 | 3.12 | 0 | 0 | IWP_1046 | 343.2 | 0 | 0 | 343.2
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1046 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1046 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1046 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 200 | 0 | 0 | 200
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 950 | 0 | 0 | 950
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1046 | 50 | 0 | 0 | 50
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1046 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1046 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1046 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 1.7062 | 0 | 1.7062 | 0 | IWP_1046 | 0 | 133.0875 | 0 | 133.0875
Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1046 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 2 | 2 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 2.9315 | 1 | 110 | 0 | 5.863 | 5.863 | 0 | 0 | IWP_1046 | 644.93 | 0 | 0 | 644.93
Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 3.279 | 3.279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 0.97901 | 0.97901 | 0 | 0 | IWP_1046 | 107.6916 | 0 | 0 | 107.6916
Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 3.6069 | 0 | 3.6069 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 5.1692 | 0 | 5.1692 | 0 | IWP_1046 | 0 | 403.1973 | 0 | 403.1973
Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 6.435 | 0 | 6.435 | 0 | IWP_1046 | 0 | 501.93 | 0 | 501.93
Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 5.265 | 0 | 5.265 | 0 | IWP_1046 | 0 | 410.67 | 0 | 410.67
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 10 | 0 | 0 | 20 | 30 | 0 | 0 | 30 | CS | 1.1765 | 1 | 110 | 0 | 11.765 | 11.765 | 0 | 0 | IWP_1047 | 1294.15 | 0 | 0 | 1294.15
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1047 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 2 | 2 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 3.848 | 1 | 110 | 0 | 7.696 | 7.696 | 0 | 0 | IWP_1047 | 846.56 | 0 | 0 | 846.56
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 10 | 10 | 0 | 0 | 120 | 300 | 0 | 0 | 300 | CS | 7.683 | 1 | 110 | 0 | 76.83 | 76.83 | 0 | 0 | IWP_1047 | 8451.3 | 0 | 0 | 8451.3
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 3 | 0 | 0 | 6 | 18 | 0 | 0 | 18 | CS | 5.46 | 1 | 110 | 0 | 16.38 | 16.38 | 0 | 0 | IWP_1047 | 1801.8 | 0 | 0 | 1801.8
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.484 | 0.484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.090834 | 0.090834 | 0 | 0 | IWP_1047 | 9.9917 | 0 | 0 | 9.9917
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 0.56 | 0.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 0.1672 | 0.1672 | 0 | 0 | IWP_1047 | 18.392 | 0 | 0 | 18.392
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 1.812 | 1.812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 1.0356 | 1.0356 | 0 | 0 | IWP_1047 | 113.9214 | 0 | 0 | 113.9214
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1047 | 500 | 0 | 0 | 500
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 100 | 0 | 0 | 100
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1047 | 75 | 0 | 0 | 75
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.5324 | 0 | 0.5324 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.47688 | 0 | 0.47688 | 0 | IWP_1047 | 0 | 37.1965 | 0 | 37.1965
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 0.616 | 0 | 0.616 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 0.88281 | 0 | 0.88281 | 0 | IWP_1047 | 0 | 68.8595 | 0 | 68.8595
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 2.0838 | 0 | 2.0838 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 5.7394 | 0 | 5.7394 | 0 | IWP_1047 | 0 | 447.6768 | 0 | 447.6768
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 2.535 | 0 | 2.535 | 0 | IWP_1047 | 0 | 197.73 | 0 | 197.73
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install valve - NB 12 CL600 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 18.4275 | 0 | 18.4275 | 0 | IWP_1047 | 0 | 1437.345 | 0 | 1437.345
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 3.0713 | 0 | 3.0713 | 0 | IWP_1047 | 0 | 239.5575 | 0 | 239.5575
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1047 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1047 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 5.5 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 21.9863 | 0 | 21.9863 | 0 | IWP_1047 | 0 | 1714.9275 | 0 | 1714.9275
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 12 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9144 | 0.75 | 78 | 0 | 2.8716 | 0 | 2.8716 | 0 | IWP_1047 | 0 | 223.9874 | 0 | 223.9874
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 4 | 6 | 0 | 0 | 6 | CS | 1.1765 | 1 | 110 | 0 | 2.353 | 2.353 | 0 | 0 | IWP_1047 | 258.83 | 0 | 0 | 258.83
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 4 | 4 | 0 | 0 | 24 | 36 | 0 | 0 | 36 | CS | 2.9315 | 1 | 110 | 0 | 11.726 | 11.726 | 0 | 0 | IWP_1047 | 1289.86 | 0 | 0 | 1289.86
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 8 | Shop Butt Weld - NB 8 SchXST | EA | 2 | 2 | 0 | 0 | 16 | 24 | 0 | 0 | 24 | CS | 3.848 | 1 | 110 | 0 | 7.696 | 7.696 | 0 | 0 | IWP_1047 | 846.56 | 0 | 0 | 846.56
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 12 | Shop Butt Weld - NB 12 Sch80 | EA | 8 | 8 | 0 | 0 | 96 | 240 | 0 | 0 | 240 | CS | 7.683 | 1 | 110 | 0 | 61.464 | 61.464 | 0 | 0 | IWP_1047 | 6761.04 | 0 | 0 | 6761.04
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1047 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 1.5 | 0 | 0 | 1.5 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1047 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 0.91 | 1 | 110 | 0 | 1.82 | 1.82 | 0 | 0 | IWP_1047 | 200.2 | 0 | 0 | 200.2
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 1 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | CS | 3.77 | 1 | 110 | 0 | 3.77 | 3.77 | 0 | 0 | IWP_1047 | 414.7 | 0 | 0 | 414.7
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 6 | CS | 5.46 | 1 | 110 | 0 | 5.46 | 5.46 | 0 | 0 | IWP_1047 | 600.6 | 0 | 0 | 600.6
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1047 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1047 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 0.26 | 0.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 0.077628 | 0.077628 | 0 | 0 | IWP_1047 | 8.5391 | 0 | 0 | 8.5391
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 12 | Shop handling - NB 12 Sch80 | LM | 1.1 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.57155 | 1 | 110 | 0 | 0.62871 | 0.62871 | 0 | 0 | IWP_1047 | 69.1576 | 0 | 0 | 69.1576
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 12 | Shop X-Ray - NB 12 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 250 | 0 | 0 | 0 | 0 | IWP_1047 | 250 | 0 | 0 | 250
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1047 | 75 | 0 | 0 | 75
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 0.286 | 0 | 0.286 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 0.40988 | 0 | 0.40988 | 0 | IWP_1047 | 0 | 31.9705 | 0 | 31.9705
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 12 | Install Spools - NB 12 Sch80 | LM | 1.265 | 0 | 1.265 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.6724 | 0.75 | 78 | 0 | 3.4842 | 0 | 3.4842 | 0 | IWP_1047 | 0 | 271.7685 | 0 | 271.7685
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.78 | 0.75 | 78 | 0 | 0.585 | 0 | 0.585 | 0 | IWP_1047 | 0 | 45.63 | 0 | 45.63
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 8 | Install valve - NB 8 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.46 | 0.75 | 78 | 0 | 4.095 | 0 | 4.095 | 0 | IWP_1047 | 0 | 319.41 | 0 | 319.41
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 12 | Install valve - NB 12 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.19 | 0.75 | 78 | 0 | 12.285 | 0 | 12.285 | 0 | IWP_1047 | 0 | 958.23 | 0 | 958.23
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.43875 | 0 | 0.43875 | 0 | IWP_1047 | 0 | 34.2225 | 0 | 34.2225
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1047 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 8 | Flange Bolt-Up - NB 8 CL600 | EA | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 3.38 | 0.75 | 78 | 0 | 3.8025 | 0 | 3.8025 | 0 | IWP_1047 | 0 | 296.595 | 0 | 296.595
Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 12 | Flange Bolt-Up - NB 12 CL600 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.33 | 0.75 | 78 | 0 | 13.9912 | 0 | 13.9912 | 0 | IWP_1047 | 0 | 1091.3175 | 0 | 1091.3175
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 18 | CS | 1.1765 | 1 | 110 | 0 | 7.059 | 7.059 | 0 | 0 | IWP_1047 | 776.49 | 0 | 0 | 776.49
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 6 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 2.9315 | 1 | 110 | 0 | 17.589 | 17.589 | 0 | 0 | IWP_1047 | 1934.79 | 0 | 0 | 1934.79
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-10-S-130 | 150-10-S-130 - Shop Olet Welds | 2 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 2 | 0 | 0 | 4 | 12 | 0 | 0 | 12 | CS | 5.46 | 1 | 110 | 0 | 10.92 | 10.92 | 0 | 0 | IWP_1047 | 1201.2 | 0 | 0 | 1201.2
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 0.296 | 0.296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.055551 | 0.055551 | 0 | 0 | IWP_1047 | 6.1106 | 0 | 0 | 6.1106
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchXST | LM | 4.807 | 4.807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.29857 | 1 | 110 | 0 | 1.4352 | 1.4352 | 0 | 0 | IWP_1047 | 157.8754 | 0 | 0 | 157.8754
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 50 | 0 | 0 | 50
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1047 | 75 | 0 | 0 | 75
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 12 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1047 | 1320 | 0 | 0 | 1320
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1047 | 900 | 0 | 0 | 900
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 0.3256 | 0 | 0.3256 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 0.29164 | 0 | 0.29164 | 0 | IWP_1047 | 0 | 22.7482 | 0 | 22.7482
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchXST | LM | 5.2877 | 0 | 5.2877 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.9109 | 0.75 | 78 | 0 | 7.578 | 0 | 7.578 | 0 | IWP_1047 | 0 | 591.0855 | 0 | 591.0855
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1047 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 4.29 | 0.75 | 78 | 0 | 3.2175 | 0 | 3.2175 | 0 | IWP_1047 | 0 | 250.965 | 0 | 250.965
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 1.755 | 0 | 1.755 | 0 | IWP_1047 | 0 | 136.89 | 0 | 136.89
Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL600 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.34 | 0.75 | 78 | 0 | 3.51 | 0 | 3.51 | 0 | IWP_1047 | 0 | 273.78 | 0 | 273.78
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1047 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1047 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1047 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1047 | 429 | 0 | 0 | 429
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1047 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1047 | 1001 | 0 | 0 | 1001
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1047 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1047 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1047 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 200 | 0 | 0 | 200
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1047 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1047 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1047 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1047 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1047 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1047 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1047 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1047 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1047 | 429 | 0 | 0 | 429
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1047 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1047 | 1001 | 0 | 0 | 1001
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1047 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1047 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1047 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 200 | 0 | 0 | 200
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1047 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1047 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1047 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1047 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1047 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1047 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1047 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1047 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | 0 | 0 | 5 | 6.25 | 0 | 0 | 6.25 | CS | 0.78 | 1 | 110 | 0 | 3.9 | 3.9 | 0 | 0 | IWP_1047 | 429 | 0 | 0 | 429
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 0 | 5 | CS | 0.91 | 1 | 110 | 0 | 3.64 | 3.64 | 0 | 0 | IWP_1047 | 400.4 | 0 | 0 | 400.4
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | 0 | 0 | 10 | 15 | 0 | 0 | 15 | CS | 0.91 | 1 | 110 | 0 | 9.1 | 9.1 | 0 | 0 | IWP_1047 | 1001 | 0 | 0 | 1001
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3 | 0 | 0 | 3 | CS | 1.69 | 1 | 110 | 0 | 1.69 | 1.69 | 0 | 0 | IWP_1047 | 185.9 | 0 | 0 | 185.9
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1047 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | 0 | 0 | 2 | 5 | 0 | 0 | 5 | CS | 0.39 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1047 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 200 | 0 | 0 | 200
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1047 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 CL3000 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1047 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.69 | 0.75 | 78 | 0 | 1.2675 | 0 | 1.2675 | 0 | IWP_1047 | 0 | 98.865 | 0 | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 2.1938 | 0 | 2.1938 | 0 | IWP_1047 | 0 | 171.1125 | 0 | 171.1125
Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.17 | 0.75 | 78 | 0 | 0.8775 | 0 | 0.8775 | 0 | IWP_1047 | 0 | 68.445 | 0 | 68.445
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 Sch160 | EA | 1 | 1 | 0 | 0 | 2 | 3.5 | 0 | 0 | 3.5 | CS | 1.781 | 1 | 110 | 0 | 1.781 | 1.781 | 0 | 0 | IWP_1047 | 195.91 | 0 | 0 | 195.91
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 15 | 15 | 0 | 0 | 30 | 45 | 0 | 0 | 45 | CS | 1.1765 | 1 | 110 | 0 | 17.6475 | 17.6475 | 0 | 0 | IWP_1047 | 1941.225 | 0 | 0 | 1941.225
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1047 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 Sch160 | EA | 1 | 1 | 0 | 0 | 1.5 | 3 | 0 | 0 | 3 | CS | 1.3 | 1 | 110 | 0 | 1.3 | 1.3 | 0 | 0 | IWP_1047 | 143 | 0 | 0 | 143
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1.5 | Shop Socket Weld - NB 1.5 SchXST | EA | 1 | 1 | 0 | 0 | 1.5 | 2.25 | 0 | 0 | 2.25 | CS | 1.04 | 1 | 110 | 0 | 1.04 | 1.04 | 0 | 0 | IWP_1047 | 114.4 | 0 | 0 | 114.4
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1047 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 4.798 | 4.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 0.90046 | 0.90046 | 0 | 0 | IWP_1047 | 99.0502 | 0 | 0 | 99.0502
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 50 | 0 | 0 | 50
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1.5 | Shop X-Ray - NB 1.5 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 100 | 0 | 0 | 100
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 850 | 0 | 0 | 850
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 5.6 | 5.6 | 0 | 0 | IWP_1047 | 616 | 0 | 0 | 616
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1047 | 500 | 0 | 0 | 500
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 5.2778 | 0 | 5.2778 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 4.7274 | 0 | 4.7274 | 0 | IWP_1047 | 0 | 368.7367 | 0 | 368.7367
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 1.95 | 0 | 1.95 | 0 | IWP_1047 | 0 | 152.1 | 0 | 152.1
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install Blind - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1047 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1047 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1.5 | Flange Bolt-Up - NB 1.5 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1047 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 8.5 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 5.8012 | 0 | 5.8012 | 0 | IWP_1047 | 0 | 452.4975 | 0 | 452.4975
Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1047 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 4 | 0 | 0 | 12 | 12 | 0 | 0 | 12 | CS | 1.3715 | 1 | 110 | 0 | 5.486 | 5.486 | 0 | 0 | IWP_1048 | 603.46 | 0 | 0 | 603.46
Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 2.069 | 2.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.36182 | 0.36182 | 0 | 0 | IWP_1048 | 39.8003 | 0 | 0 | 39.8003
Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 200 | 0 | 0 | 200
Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 2.2759 | 0 | 2.2759 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.9876 | 0 | 1.9876 | 0 | IWP_1048 | 0 | 155.032 | 0 | 155.032
Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1048 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1048 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 0.9375 | 0 | 0 | 0.9375 | CS | 0.65 | 1 | 110 | 0 | 0.65 | 0.65 | 0 | 0 | IWP_1047 | 71.5 | 0 | 0 | 71.5
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 0.75 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 2 | 0 | 0 | 1.5 | 1.875 | 0 | 0 | 1.875 | CS | 0.78 | 1 | 110 | 0 | 1.56 | 1.56 | 0 | 0 | IWP_1047 | 171.6 | 0 | 0 | 171.6
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1047 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.75 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 1 | 0 | 0 | 0.75 | 1.875 | 0 | 0 | 1.875 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1047 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 0.75 | Shop X-Ray - NB 0.75 | EA | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 150 | 0 | 0 | 150
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1047 | 50 | 0 | 0 | 50
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 0.75 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1047 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1047 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 0.75 | Flange Bolt-Up - NB 0.75 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1047 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1047 | 0 | 53.235 | 0 | 53.235
Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 4 | 0 | 0 | 12 | 12 | 0 | 0 | 12 | CS | 1.3715 | 1 | 110 | 0 | 5.486 | 5.486 | 0 | 0 | IWP_1048 | 603.46 | 0 | 0 | 603.46
Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 2.069 | 2.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.36182 | 0.36182 | 0 | 0 | IWP_1048 | 39.8003 | 0 | 0 | 39.8003
Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 200 | 0 | 0 | 200
Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 2.2759 | 0 | 2.2759 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 1.9876 | 0 | 1.9876 | 0 | IWP_1048 | 0 | 155.032 | 0 | 155.032
Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1048 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1048 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 2 | Shop Butt Weld - NB 2 SchXST | EA | 18 | 18 | 0 | 0 | 36 | 54 | 0 | 0 | 54 | CS | 1.1765 | 1 | 110 | 0 | 21.177 | 21.177 | 0 | 0 | IWP_1048 | 2329.47 | 0 | 0 | 2329.47
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.78 | 1 | 110 | 0 | 0.78 | 0.78 | 0 | 0 | IWP_1048 | 85.8 | 0 | 0 | 85.8
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1048 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1048 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 1 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | 0 | 0 | 1 | 2.5 | 0 | 0 | 2.5 | CS | 0.39 | 1 | 110 | 0 | 0.39 | 0.39 | 0 | 0 | IWP_1048 | 42.9 | 0 | 0 | 42.9
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 2 | Shop handling - NB 2 SchXST | LM | 16.611 | 16.611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.18767 | 1 | 110 | 0 | 3.1174 | 3.1174 | 0 | 0 | IWP_1048 | 342.9183 | 0 | 0 | 342.9183
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 100 | 0 | 0 | 100
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 900 | 0 | 0 | 900
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 2 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 5.6 | 1 | 110 | 0 | 11.2 | 11.2 | 0 | 0 | IWP_1048 | 1232 | 0 | 0 | 1232
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 2 | Shop Spools Coating - NB 2 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 500 | 0 | 0 | 0 | 0 | IWP_1048 | 1000 | 0 | 0 | 1000
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 2 | Install Spools - NB 2 SchXST | LM | 18.2721 | 0 | 18.2721 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 16.3666 | 0 | 16.3666 | 0 | IWP_1048 | 0 | 1276.5915 | 0 | 1276.5915
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 1 | Install valve - NB 1 2000psi | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.39 | 0.75 | 78 | 0 | 0.2925 | 0 | 0.2925 | 0 | IWP_1048 | 0 | 22.815 | 0 | 22.815
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1048 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 2.3887 | 0 | 2.3887 | 0 | IWP_1048 | 0 | 186.3225 | 0 | 186.3225
Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 2 | Erection of Pipe Supports - NB 2 | EA | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1 | 0.75 | 78 | 0 | 4.5 | 0 | 4.5 | 0 | IWP_1048 | 0 | 351 | 0 | 351
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 2 | 2 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | CS | 1.3715 | 1 | 110 | 0 | 2.743 | 2.743 | 0 | 0 | IWP_1048 | 301.73 | 0 | 0 | 301.73
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchSTD | EA | 12 | 12 | 0 | 0 | 72 | 72 | 0 | 0 | 72 | CS | 2.431 | 1 | 110 | 0 | 29.172 | 29.172 | 0 | 0 | IWP_1048 | 3208.92 | 0 | 0 | 3208.92
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchSTD | LM | 4.545 | 4.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.21753 | 1 | 110 | 0 | 0.98868 | 0.98868 | 0 | 0 | IWP_1048 | 108.7543 | 0 | 0 | 108.7543
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 100 | 0 | 0 | 100
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1048 | 900 | 0 | 0 | 900
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | 600 | 150-10-F-110 | 150-10-F-110 - Field Butt Welds | 6 | Field Butt Weld - NB 6 SchSTD | EA | 1 | 0 | 1 | 0 | 6 | 0 | 6 | 0 | 6 | CS | 3.3501 | 0.75 | 78 | 0 | 2.5126 | 0 | 2.5126 | 0 | IWP_1048 | 0 | 195.9809 | 0 | 195.9809
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchSTD | LM | 4.9995 | 0 | 4.9995 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.4033 | 0.75 | 78 | 0 | 5.2618 | 0 | 5.2618 | 0 | IWP_1048 | 0 | 410.4194 | 0 | 410.4194
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchSTD | LM | 34.5851 | 0 | 34.5851 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 30.9783 | 0 | 30.9783 | 0 | IWP_1048 | 0 | 2416.3092 | 0 | 2416.3092
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1048 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 2.925 | 0 | 2.925 | 0 | IWP_1048 | 0 | 228.15 | 0 | 228.15
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 4.9613 | 0 | 4.9613 | 0 | IWP_1048 | 0 | 386.9775 | 0 | 386.9775
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | 600 | 150-60-F-610 | 150-60-F-610 - Field X-Ray | 6 | Field X-Ray - NB 6 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 1000 | 0 | 0 | 0 | 0 | IWP_1048 | 0 | 1000 | 0 | 1000
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 34.5851 | 0 | 34.5851 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1048 | 0 | 3458.51 | 0 | 3458.51
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 2 | 2 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | CS | 1.3715 | 1 | 110 | 0 | 2.743 | 2.743 | 0 | 0 | IWP_1048 | 301.73 | 0 | 0 | 301.73
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchSTD | EA | 12 | 12 | 0 | 0 | 72 | 72 | 0 | 0 | 72 | CS | 2.431 | 1 | 110 | 0 | 29.172 | 29.172 | 0 | 0 | IWP_1048 | 3208.92 | 0 | 0 | 3208.92
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchSTD | LM | 2.233 | 2.233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.21753 | 1 | 110 | 0 | 0.48575 | 0.48575 | 0 | 0 | IWP_1048 | 53.432 | 0 | 0 | 53.432
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 100 | 0 | 0 | 100
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1048 | 900 | 0 | 0 | 900
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchSTD | LM | 2.4563 | 0 | 2.4563 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.4033 | 0.75 | 78 | 0 | 2.5852 | 0 | 2.5852 | 0 | IWP_1048 | 0 | 201.6428 | 0 | 201.6428
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | 600 | 150-25-F-250 | 150-25-F-250 - Field Installed piping | 6 | Erection of Field Run Pipe - NB 6 SchSTD | LM | 29.5196 | 0 | 29.5196 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1943 | 0.75 | 78 | 0 | 26.4411 | 0 | 26.4411 | 0 | IWP_1048 | 0 | 2062.405 | 0 | 2062.405
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.39 | 0 | 0.39 | 0 | IWP_1048 | 0 | 30.42 | 0 | 30.42
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL150 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 2.925 | 0 | 2.925 | 0 | IWP_1048 | 0 | 228.15 | 0 | 228.15
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 3.7209 | 0 | 3.7209 | 0 | IWP_1048 | 0 | 290.2331 | 0 | 290.2331
Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | 300 | 150-80-F-810 | 150-80-F-810 - Field Coating | 6 | Field Coating - NB 6 | LM | 29.5196 | 0 | 29.5196 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 0.75 | 78 | 100 | 0 | 0 | 0 | 0 | IWP_1048 | 0 | 2951.96 | 0 | 2951.96
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO1060 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 2 | 2 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | CS | 1.3715 | 1 | 110 | 0 | 2.743 | 2.743 | 0 | 0 | IWP_1048 | 301.73 | 0 | 0 | 301.73
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO1060 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 100 | 0 | 0 | 100
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO1060 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1048 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2002 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install valve - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.56 | 0.75 | 78 | 0 | 1.17 | 0 | 1.17 | 0 | IWP_1048 | 0 | 91.26 | 0 | 91.26
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2002 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 0.78 | 0 | 0.78 | 0 | IWP_1048 | 0 | 60.84 | 0 | 60.84
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 20 | 20 | 0 | 0 | 60 | 60 | 0 | 0 | 60 | CS | 1.3715 | 1 | 110 | 0 | 27.43 | 27.43 | 0 | 0 | IWP_1048 | 3017.3 | 0 | 0 | 3017.3
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 19.024 | 19.024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 3.3269 | 3.3269 | 0 | 0 | IWP_1048 | 365.9552 | 0 | 0 | 365.9552
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 1000 | 0 | 0 | 1000
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 12 | 12 | 0 | 0 | IWP_1048 | 1320 | 0 | 0 | 1320
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1048 | 1200 | 0 | 0 | 1200
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 20.9264 | 0 | 20.9264 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 18.2754 | 0 | 18.2754 | 0 | IWP_1048 | 0 | 1425.4849 | 0 | 1425.4849
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 3.9 | 0 | 3.9 | 0 | IWP_1048 | 0 | 304.2 | 0 | 304.2
Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 7.875 | 0 | 7.875 | 0 | IWP_1048 | 0 | 614.25 | 0 | 614.25
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 3 | Shop Butt Weld - NB 3 SchSTD | EA | 8 | 8 | 0 | 0 | 24 | 24 | 0 | 0 | 24 | CS | 1.3715 | 1 | 110 | 0 | 10.972 | 10.972 | 0 | 0 | IWP_1048 | 1206.92 | 0 | 0 | 1206.92
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 3 | Shop handling - NB 3 SchSTD | LM | 5.285 | 5.285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.17488 | 1 | 110 | 0 | 0.92423 | 0.92423 | 0 | 0 | IWP_1048 | 101.6649 | 0 | 0 | 101.6649
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 3 | Shop X-Ray - NB 3 | EA | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 400 | 0 | 0 | 400
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 3 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 6 | 1 | 110 | 0 | 6 | 6 | 0 | 0 | IWP_1048 | 660 | 0 | 0 | 660
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 3 | Shop Spools Coating - NB 3 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 600 | 0 | 0 | 0 | 0 | IWP_1048 | 600 | 0 | 0 | 600
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 3 | Install Spools - NB 3 SchSTD | LM | 5.8135 | 0 | 5.8135 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.1644 | 0.75 | 78 | 0 | 5.077 | 0 | 5.077 | 0 | IWP_1048 | 0 | 396.0097 | 0 | 396.0097
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install Blind - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.56 | 0.75 | 78 | 0 | 1.17 | 0 | 1.17 | 0 | IWP_1048 | 0 | 91.26 | 0 | 91.26
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 3 | Install valve - NB 3 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.56 | 0.75 | 78 | 0 | 1.17 | 0 | 1.17 | 0 | IWP_1048 | 0 | 91.26 | 0 | 91.26
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 3 | Flange Bolt-Up - NB 3 CL150 | EA | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.04 | 0.75 | 78 | 0 | 1.95 | 0 | 1.95 | 0 | IWP_1048 | 0 | 152.1 | 0 | 152.1
Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 3 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.5 | 0.75 | 78 | 0 | 2.25 | 0 | 2.25 | 0 | IWP_1048 | 0 | 175.5 | 0 | 175.5
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | 400 | 150-10-S-110 | 150-10-S-110 - Shop Butt Welds | 6 | Shop Butt Weld - NB 6 SchSTD | EA | 6 | 6 | 0 | 0 | 36 | 36 | 0 | 0 | 36 | CS | 2.431 | 1 | 110 | 0 | 14.586 | 14.586 | 0 | 0 | IWP_1048 | 1604.46 | 0 | 0 | 1604.46
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | 400 | 150-29-S-290 | 150-29-S-290 - Shop Handling | 6 | Shop handling - NB 6 SchSTD | LM | 4.953 | 4.953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.21753 | 1 | 110 | 0 | 1.0774 | 1.0774 | 0 | 0 | IWP_1048 | 118.517 | 0 | 0 | 118.517
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 6 | Shop X-Ray - NB 6 | EA | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 75 | 0 | 0 | 0 | 0 | IWP_1048 | 450 | 0 | 0 | 450
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | 400 | 150-70-S-710 | 150-70-S-710 - Shop Hydrotest | 6 | Shop Hydrotest - NB 6 SchSTD | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 8.8 | 1 | 110 | 0 | 8.8 | 8.8 | 0 | 0 | IWP_1048 | 968 | 0 | 0 | 968
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | 400 | 150-80-S-810 | 150-80-S-810 - Shop Coating | 6 | Shop Spools Coating - NB 6 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 900 | 0 | 0 | 0 | 0 | IWP_1048 | 900 | 0 | 0 | 900
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | 600 | 150-20-F-210 | 150-20-F-210 - Field Erection of spools | 6 | Install Spools - NB 6 SchSTD | LM | 5.4483 | 0 | 5.4483 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.4033 | 0.75 | 78 | 0 | 5.7341 | 0 | 5.7341 | 0 | IWP_1048 | 0 | 447.2624 | 0 | 447.2624
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install Blind - NB 6 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.86 | 0.75 | 78 | 0 | 2.145 | 0 | 2.145 | 0 | IWP_1048 | 0 | 167.31 | 0 | 167.31
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 6 | Install valve - NB 6 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 2.86 | 0.75 | 78 | 0 | 2.145 | 0 | 2.145 | 0 | IWP_1048 | 0 | 167.31 | 0 | 167.31
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 6 | Flange Bolt-Up - NB 6 CL150 | EA | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.95 | 0.75 | 78 | 0 | 4.3875 | 0 | 4.3875 | 0 | IWP_1048 | 0 | 342.225 | 0 | 342.225
Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | 600 | 150-50-F-510 | 150-50-F-510 - Field Pipe Supports | 6 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 1.6538 | 0.75 | 78 | 0 | 1.2403 | 0 | 1.2403 | 0 | IWP_1048 | 0 | 96.7444 | 0 | 96.7444
Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 1 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | 0 | 0 | 1 | 1.25 | 0 | 0 | 1.25 | CS | 0.91 | 1 | 110 | 0 | 0.91 | 0.91 | 0 | 0 | IWP_1048 | 100.1 | 0 | 0 | 100.1
Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication | 400 | 150-10-S-120 | 150-10-S-120 - Shop Socket Welds | 2 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | CS | 1.17 | 1 | 110 | 0 | 1.17 | 1.17 | 0 | 0 | IWP_1048 | 128.7 | 0 | 0 | 128.7
Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication | 400 | 150-19-S-190 | 150-19-S-190 - Shop Threaded Joints | 0.5 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 1 | 0 | 0 | 0.5 | 1.25 | 0 | 0 | 1.25 | CS | 0.26 | 1 | 110 | 0 | 0.26 | 0.26 | 0 | 0 | IWP_1048 | 28.6 | 0 | 0 | 28.6
Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 1 | Shop X-Ray - NB 1 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 50 | 0 | 0 | 50
Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication | 400 | 150-60-S-610 | 150-60-S-610 - Shop X-Ray | 2 | Shop X-Ray - NB 2 | EA | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0 | 1 | 110 | 50 | 0 | 0 | 0 | 0 | IWP_1048 | 50 | 0 | 0 | 50
Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Field | 600 | 150-30-F-310 | 150-30-F-310 - Field Install Valves, blinds, inlines | 2 | Install valve - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.65 | 0.75 | 78 | 0 | 0.4875 | 0 | 0.4875 | 0 | IWP_1048 | 0 | 38.025 | 0 | 38.025
Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 1 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.34125 | 0 | 0.34125 | 0 | IWP_1048 | 0 | 26.6175 | 0 | 26.6175
Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup | 2 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | CS | 0.91 | 0.75 | 78 | 0 | 0.6825 | 0 | 0.6825 | 0 | IWP_1048 | 0 | 53.235 | 0 | 53.235
Summary | Summary | Summary | Summary | Summary | Spool Fabrication | 400 | 150-50-S-510 | 150-50-S-510 - Shop Pipe Supports |  | Pipe Supports Labor (shoes, lugs, guides, etc.) | 5% of Labor hours | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 963.9511 | 963.9511 | 0 | 0 | IWP_9999 | 106034.6258 | 0 | 0 | 106034.6258
Summary | Summary | Summary | Summary | Summary | Module | 500 | 150-70-F-710 | 150-70-F-710 - Field Hydrotest |  | Hydrotest of module assembly | 5% of Module Labor | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 230.2252 | 0 | 0 | 230.2252 | IWP_9999 | 0 | 0 | 25324.7765 | 25324.7765
Summary | Summary | Summary | Summary | Summary | Module | 500 | 150-90-F-910 | 150-90-F-910 - Field Flushing, Chemical Cleaning |  | Flushing & Drying Module Piping | 3% of Module Labor | 0.03 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 138.1351 | 0 | 0 | 138.1351 | IWP_9999 | 0 | 0 | 15194.8659 | 15194.8659
Summary | Summary | Summary | Summary | Summary | Field | 600 | 150-40-F-410 | 150-40-F-410 - Field Flange Boltup |  | Bolt torquing and tensioning | 15% of bolt-up labor | 0.15 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 198.3296 | 0 | 198.3296 | 0 | IWP_9999 | 0 | 15469.7108 | 0 | 15469.7108
Summary | Summary | Summary | Summary | Summary | Field | 600 | 150-70-F-710 | 150-70-F-710 - Field Hydrotest |  | Field Hydrotest | 5% of Field Labor | 0.05 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 285.076 | 0 | 285.076 | 0 | IWP_9999 | 0 | 22235.93 | 0 | 22235.93
Summary | Summary | Summary | Summary | Summary | Field | 600 | 150-90-F-910 | 150-90-F-910 - Field Flushing, Chemical Cleaning |  | Flushing & Drying on Site | 3% of Field Labor | 0.03 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 171.0456 | 0 | 171.0456 | 0 | IWP_9999 | 0 | 13341.558 | 0 | 13341.558
Electrical Bulks MTO Input Required - Wire & Cable
Example - Imaginary Project with made up quantities for Illustration Purposes
Piping Labor Summary by Isometric (WBS_L)
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## WBS1-Project Level Summary
WBS1 | Location | CBS | COA | Description | Units | Quantity | Dia_Inch | Material | STD_UNIT_HR | PF | WR | Location Hours | S/C Rate_$ | Total Cost
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.585 | 1 | 110 | 0.585 |  | 64.35 | 0.585
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.781 | 1 | 110 | 1.781 |  | 195.91 | 1.781
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 1390 | 2780 | CS | 1.1765 | 1 | 110 | 1635.335 |  | 179886.85 | 1635.335
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 151 | 453 | CS | 1.3715 | 1 | 110 | 207.0965 |  | 22780.615 | 207.0965
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 12 | 36 | CS | 1.586 | 1 | 110 | 19.032 |  | 2093.52 | 19.032
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | EA | 19 | 76 | CS | 1.6835 | 1 | 110 | 31.9865 |  | 3518.515 | 31.9865
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 122 | 488 | CS | 2.119 | 1 | 110 | 258.518 |  | 28436.98 | 258.518
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 34 | 204 | CS | 2.431 | 1 | 110 | 82.654 |  | 9091.94 | 82.654
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 242 | 1452 | CS | 2.9315 | 1 | 110 | 709.423 |  | 78036.53 | 709.423
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 58 | 464 | CS | 3.0095 | 1 | 110 | 174.551 |  | 19200.61 | 174.551
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 62 | 496 | CS | 3.848 | 1 | 110 | 238.576 |  | 26243.36 | 238.576
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 74 | 740 | CS | 5.915 | 1 | 110 | 437.71 |  | 48148.1 | 437.71
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | EA | 8 | 80 | CS | 4.1782 | 1 | 110 | 33.4256 |  | 3676.816 | 33.4256
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 280 | 3360 | CS | 7.683 | 1 | 110 | 2151.24 |  | 236636.4 | 2151.24
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 74 | 888 | CS | 4.7255 | 1 | 110 | 349.687 |  | 38465.57 | 349.687
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 24 | 336 | CS | 10.2115 | 1 | 110 | 245.076 |  | 26958.36 | 245.076
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 96 | 1536 | CS | 14.365 | 1 | 110 | 1379.04 |  | 151694.4 | 1379.04
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | EA | 14 | 224 | CS | 8.8313 | 1 | 110 | 123.6387 |  | 13600.2533 | 123.6387
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | EA | 26 | 416 | CS | 16.12 | 1 | 110 | 419.12 |  | 46103.2 | 419.12
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 112 | 2240 | CS | 21.7588 | 1 | 110 | 2436.98 |  | 268067.8 | 2436.98
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | EA | 6 | 120 | CS | 13.6121 | 1 | 110 | 81.6725 |  | 8983.975 | 81.6725
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | EA | 12 | 288 | CS | 18.3647 | 1 | 110 | 220.376 |  | 24241.36 | 220.376
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | EA | 51 | 1224 | CS | 33.1998 | 1 | 110 | 1693.1915 |  | 186251.065 | 1693.1915
Proj_A | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | EA | 10 | 240 | CS | 17.7732 | 1 | 110 | 177.7317 |  | 19550.4833 | 177.7317
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 22 | 16.5 | CS | 0.65 | 1 | 110 | 14.3 |  | 1573 | 14.3
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 42 | 31.5 | CS | 0.65 | 1 | 110 | 27.3 |  | 3003 | 27.3
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | EA | 8 | 6 | CS | 0.65 | 1 | 110 | 5.2 |  | 572 | 5.2
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 58 | 43.5 | CS | 0.65 | 1 | 110 | 37.7 |  | 4147 | 37.7
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL6000 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6 | 1.56
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 35 | 26.25 | CS | 0.78 | 1 | 110 | 27.3 |  | 3003 | 27.3
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 101 | 75.75 | CS | 0.78 | 1 | 110 | 78.78 |  | 8665.8 | 78.78
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 44 | 44 | CS | 0.78 | 1 | 110 | 34.32 |  | 3775.2 | 34.32
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 158 | 158 | CS | 0.78 | 1 | 110 | 123.24 |  | 13556.4 | 123.24
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6 | 9.36
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 371 | 371 | CS | 0.78 | 1 | 110 | 289.38 |  | 31831.8 | 289.38
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 20 | 20 | CS | 0.91 | 1 | 110 | 18.2 |  | 2002 | 18.2
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 300 | 300 | CS | 0.91 | 1 | 110 | 273 |  | 30030 | 273
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 30 | 30 | CS | 0.78 | 1 | 110 | 23.4 |  | 2574 | 23.4
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 471 | 471 | CS | 0.91 | 1 | 110 | 428.61 |  | 47147.1 | 428.61
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | EA | 8 | 12 | CS | 1.04 | 1 | 110 | 8.32 |  | 915.2 | 8.32
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | EA | 20 | 30 | CS | 1.04 | 1 | 110 | 20.8 |  | 2288 | 20.8
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 15 | 22.5 | CS | 1.3 | 1 | 110 | 19.5 |  | 2145 | 19.5
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 3 | 4.5 | CS | 1.04 | 1 | 110 | 3.12 |  | 343.2 | 3.12
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 58 | 116 | CS | 1.69 | 1 | 110 | 98.02 |  | 10782.2 | 98.02
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 30 | 60 | CS | 1.17 | 1 | 110 | 35.1 |  | 3861 | 35.1
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 7 | 21 | CS | 2.21 | 1 | 110 | 15.47 |  | 1701.7 | 15.47
Proj_A | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.56 | 1 | 110 | 3.12 |  | 343.2 | 3.12
Proj_A | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 9 | 6.75 | CS | 2.47 | 1 | 110 | 22.23 |  | 2445.3 | 22.23
Proj_A | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL6000 | EA | 2 | 1.5 | CS | 3.38 | 1 | 110 | 6.76 |  | 743.6 | 6.76
Proj_A | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 24 | 24 | CS | 2.86 | 1 | 110 | 68.64 |  | 7550.4 | 68.64
Proj_A | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 20 | 20 | CS | 3.77 | 1 | 110 | 75.4 |  | 8294 | 75.4
Proj_A | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 20 | 40 | CS | 4.42 | 1 | 110 | 88.4 |  | 9724 | 88.4
Proj_A | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 128 | 256 | CS | 5.46 | 1 | 110 | 698.88 |  | 76876.8 | 698.88
Proj_A | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 7 | 21 | CS | 7.67 | 1 | 110 | 53.69 |  | 5905.9 | 53.69
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 9 | 4.5 | NA | 0.26 | 1 | 110 | 2.34 |  | 257.4 | 2.34
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 38 | 19 | NA | 0.26 | 1 | 110 | 9.88 |  | 1086.8 | 9.88
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 20 | 15 | NA | 0.26 | 1 | 110 | 5.2 |  | 572 | 5.2
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 42 | 31.5 | NA | 0.26 | 1 | 110 | 10.92 |  | 1201.2 | 10.92
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 55 | 41.25 | NA | 0.26 | 1 | 110 | 14.3 |  | 1573 | 14.3
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 Sch160 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2 | 0.52
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 44 | 44 | NA | 0.39 | 1 | 110 | 17.16 |  | 1887.6 | 17.16
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 32 | 32 | NA | 0.39 | 1 | 110 | 12.48 |  | 1372.8 | 12.48
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 91 | 91 | NA | 0.39 | 1 | 110 | 35.49 |  | 3903.9 | 35.49
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 30 | 30 | NA | 0.39 | 1 | 110 | 11.7 |  | 1287 | 11.7
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 38 | 38 | NA | 0.39 | 1 | 110 | 14.82 |  | 1630.2 | 14.82
Proj_A | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 7 | 14 | NA | 0.429 | 1 | 110 | 3.003 |  | 330.33 | 3.003
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | LM | 5.132 | 0 | NA | 0.16635 | 1 | 110 | 0.85369 |  | 93.906 | 0.85369
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 29.546 | 0 | NA | 0.17914 | 1 | 110 | 5.2929 |  | 582.2242 | 5.2929
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 11.59 | 0 | NA | 0.15355 | 1 | 110 | 1.7797 |  | 195.7619 | 1.7797
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1.5 SchXST | LM | 3.46 | 0 | NA | 0.17488 | 1 | 110 | 0.60508 |  | 66.5583 | 0.60508
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 428.165 | 0 | NA | 0.18767 | 1 | 110 | 80.3551 |  | 8839.0605 | 80.3551
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 105.754 | 0 | NA | 0.17488 | 1 | 110 | 18.494 |  | 2034.3371 | 18.494
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchSTD | LM | 10.831 | 0 | NA | 0.19194 | 1 | 110 | 2.0789 |  | 228.6774 | 2.0789
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 85.427 | 0 | NA | 0.24739 | 1 | 110 | 21.1336 |  | 2324.692 | 21.1336
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchSTD | LM | 11.731 | 0 | NA | 0.21753 | 1 | 110 | 2.5518 |  | 280.7033 | 2.5518
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 171.341 | 0 | NA | 0.29857 | 1 | 110 | 51.1575 |  | 5627.3199 | 51.1575
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 35.417 | 0 | NA | 0.26871 | 1 | 110 | 9.517 |  | 1046.8744 | 9.517
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 22.012 | 0 | NA | 0.37535 | 1 | 110 | 8.2621 |  | 908.8337 | 8.2621
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 45.668 | 0 | NA | 0.46918 | 1 | 110 | 21.4266 |  | 2356.9314 | 21.4266
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 SchSTD | LM | 5.322 | 0 | NA | 0.33696 | 1 | 110 | 1.7933 |  | 197.2624 | 1.7933
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 304.543 | 0 | NA | 0.57155 | 1 | 110 | 174.0616 |  | 19146.7774 | 174.0616
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 77.687 | 0 | NA | 0.40947 | 1 | 110 | 31.8104 |  | 3499.1443 | 31.8104
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 16.032 | 0 | NA | 0.67818 | 1 | 110 | 10.8726 |  | 1195.9888 | 10.8726
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 111.045 | 0 | NA | 0.79335 | 1 | 110 | 88.0971 |  | 9690.6793 | 88.0971
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchSTD | LM | 43.76 | 0 | NA | 0.58861 | 1 | 110 | 25.7576 |  | 2833.3398 | 25.7576
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchXST | LM | 7.064 | 0 | NA | 0.79335 | 1 | 110 | 5.6042 |  | 616.4614 | 5.6042
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 132.578 | 0 | NA | 1.0279 | 1 | 110 | 136.2819 |  | 14991.0058 | 136.2819
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 SchXST | LM | 2.414 | 0 | NA | 1.0279 | 1 | 110 | 2.4814 |  | 272.9585 | 2.4814
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch40 | LM | 14.46 | 0 | NA | 0.89571 | 1 | 110 | 12.952 |  | 1424.7211 | 12.952
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch80 | LM | 103.42 | 0 | NA | 1.1644 | 1 | 110 | 120.425 |  | 13246.7533 | 120.425
Proj_A | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 SchXST | LM | 12.399 | 0 | NA | 1.1644 | 1 | 110 | 14.4377 |  | 1588.1502 | 14.4377
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 163 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 8150 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 497 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 24850 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 46 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2300 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 20 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 5000 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 106 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 26500 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1500 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 45 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 11250 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 931 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 46550 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 14 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 7000 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 22 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 11000 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 152 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 7600 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 40 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2000 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 72 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 5400 | 0
Proj_A | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 53 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 5300 | 0
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 34 | 0 | NA | 5.6 | 1 | 110 | 190.4 |  | 20944 | 190.4
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 11 | 0 | NA | 6 | 1 | 110 | 66 |  | 7260 | 66
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchSTD | EA | 1 | 0 | NA | 7 | 1 | 110 | 7 |  | 770 | 7
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 8 | 0 | NA | 8.4 | 1 | 110 | 67.2 |  | 7392 | 67.2
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchSTD | EA | 1 | 0 | NA | 8.8 | 1 | 110 | 8.8 |  | 968 | 8.8
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 19 | 0 | NA | 12 | 1 | 110 | 228 |  | 25080 | 228
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | EA | 4 | 0 | NA | 9.8 | 1 | 110 | 39.2 |  | 4312 | 39.2
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchXST | EA | 2 | 0 | NA | 16 | 1 | 110 | 32 |  | 3520 | 32
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | EA | 5 | 0 | NA | 14.6 | 1 | 110 | 73 |  | 8030 | 73
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 26 | 0 | NA | 19 | 1 | 110 | 494 |  | 54340 | 494
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 8 | 0 | NA | 12.2 | 1 | 110 | 97.6 |  | 10736 | 97.6
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 9 | 0 | NA | 17.6 | 1 | 110 | 158.4 |  | 17424 | 158.4
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 SchSTD | EA | 3 | 0 | NA | 15.6 | 1 | 110 | 46.8 |  | 5148 | 46.8
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 12 | 0 | NA | 41.2 | 1 | 110 | 494.4 |  | 54384 | 494.4
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch40 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532 | 41.2
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch80 | EA | 8 | 0 | NA | 62.6 | 1 | 110 | 500.8 |  | 55088 | 500.8
Proj_A | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 SchXST | EA | 1 | 0 | NA | 30.8 | 1 | 110 | 30.8 |  | 3388 | 30.8
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 34 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 17000 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 11 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 6600 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 9 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 6300 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 20 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 18000 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 6600 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 10 | EA | 5 | 0 | CS | 0 | 1 | 110 | 0 | 1500 | 7500 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 34 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 57800 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 12 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 25200 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 12 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 32400 | 0
Proj_A | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 10 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 28800 | 0
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 1 SchXST | LM | 0.4305 | 0 | NA | 1.0151 | 1 | 110 | 0.43702 |  | 48.072 | 0.43702
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 70.1272 | 0 | NA | 1.1943 | 1 | 110 | 83.7518 |  | 9212.6972 | 83.7518
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 10 Sch80 | LM | 8.4778 | 0 | NA | 2.9857 | 1 | 110 | 25.3123 |  | 2784.3477 | 25.3123
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 10 SchSTD | LM | 6.1203 | 0 | NA | 2.1497 | 1 | 110 | 13.1569 |  | 1447.2565 | 13.1569
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 12 Sch80 | LM | 208.8342 | 0 | NA | 3.6724 | 1 | 110 | 766.9278 |  | 84362.0542 | 766.9278
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 12 SchSTD | LM | 15.456 | 0 | NA | 2.6274 | 1 | 110 | 40.6095 |  | 4467.0425 | 40.6095
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 16 Sch80 | LM | 101.8256 | 0 | NA | 5.1056 | 1 | 110 | 519.8771 |  | 57186.4841 | 519.8771
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchSTD | LM | 50.324 | 0 | NA | 3.7919 | 1 | 110 | 190.8211 |  | 20990.3259 | 190.8211
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchXST | LM | 8.1236 | 0 | NA | 5.1056 | 1 | 110 | 41.4756 |  | 4562.3117 | 41.4756
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 20 Sch80 | LM | 93.656 | 0 | NA | 6.6283 | 1 | 110 | 620.7778 |  | 68285.5619 | 620.7778
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 20 SchXST | LM | 2.7761 | 0 | NA | 6.6283 | 1 | 110 | 18.4008 |  | 2024.0833 | 18.4008
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch40 | LM | 16.629 | 0 | NA | 5.7923 | 1 | 110 | 96.3198 |  | 10595.1759 | 96.3198
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch80 | LM | 118.933 | 0 | NA | 7.4941 | 1 | 110 | 891.2996 |  | 98042.9574 | 891.2996
Proj_A | Module | 500 | 150-20-M-210 | Install Spools - NB 24 SchXST | LM | 14.2588 | 0 | NA | 7.4941 | 1 | 110 | 106.8577 |  | 11754.3476 | 106.8577
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 2000psi | EA | 4 | 0 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6 | 1.56
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5 | 0.65
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 8 | 0 | NA | 0.39 | 1 | 110 | 3.12 |  | 343.2 | 3.12
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 1 | 110 | 0.78 |  | 85.8 | 0.78
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL3000 | EA | 3 | 0 | NA | 0.91 | 1 | 110 | 2.73 |  | 300.3 | 2.73
Proj_A | Module | 500 | 150-30-M-310 | Install Blind - NB 2 CL150 | EA | 2 | 0 | NA | 0.65 | 1 | 110 | 1.3 |  | 143 | 1.3
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5 | 0.65
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 12 | 0 | NA | 1.04 | 1 | 110 | 12.48 |  | 1372.8 | 12.48
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 19 | 0 | NA | 1.69 | 1 | 110 | 32.11 |  | 3532.1 | 32.11
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 10 CL600 | EA | 4 | 0 | NA | 6.63 | 1 | 110 | 26.52 |  | 2917.2 | 26.52
Proj_A | Module | 500 | 150-30-M-310 | Install Blind - NB 10 CL600 | EA | 2 | 0 | NA | 6.63 | 1 | 110 | 13.26 |  | 1458.6 | 13.26
Proj_A | Module | 500 | 150-30-M-310 | Install Inlines - NB 16 CL300 | EA | 4 | 0 | NA | 9.23 | 1 | 110 | 36.92 |  | 4061.2 | 36.92
Proj_A | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL300 | EA | 3 | 0 | NA | 9.23 | 1 | 110 | 27.69 |  | 3045.9 | 27.69
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL300 | EA | 3 | 0 | NA | 9.23 | 1 | 110 | 27.69 |  | 3045.9 | 27.69
Proj_A | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL600 | EA | 2 | 0 | NA | 11.44 | 1 | 110 | 22.88 |  | 2516.8 | 22.88
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL600 | EA | 1 | 0 | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4 | 11.44
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 20 CL600 | EA | 3 | 0 | NA | 15.47 | 1 | 110 | 46.41 |  | 5105.1 | 46.41
Proj_A | Module | 500 | 150-30-M-310 | Install valve - NB 24 CL600 | EA | 1 | 0 | NA | 17.68 | 1 | 110 | 17.68 |  | 1944.8 | 17.68
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4 | 1.04
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35 | 0.585
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 9 | 0 | NA | 1.04 | 1 | 110 | 9.36 |  | 1029.6 | 9.36
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | EA | 5 | 0 | NA | 1.17 | 1 | 110 | 5.85 |  | 643.5 | 5.85
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 13 | 0 | NA | 0.91 | 1 | 110 | 11.83 |  | 1301.3 | 11.83
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 22 | 0 | NA | 1.04 | 1 | 110 | 22.88 |  | 2516.8 | 22.88
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 40 | 0 | NA | 1.17 | 1 | 110 | 46.8 |  | 5148 | 46.8
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 3 CL300 | EA | 1 | 0 | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7 | 1.17
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 0 | NA | 3.12 | 1 | 110 | 3.12 |  | 343.2 | 3.12
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL300 | EA | 1 | 0 | NA | 3.9 | 1 | 110 | 3.9 |  | 429 | 3.9
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 10 | 0 | NA | 4.16 | 1 | 110 | 41.6 |  | 4576 | 41.6
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 17 | 0 | NA | 5.33 | 1 | 110 | 90.61 |  | 9967.1 | 90.61
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | EA | 13.5 | 0 | NA | 6.37 | 1 | 110 | 85.995 |  | 9459.45 | 85.995
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 16.5 | 0 | NA | 6.76 | 1 | 110 | 111.54 |  | 12269.4 | 111.54
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 16.5 | 0 | NA | 8.58 | 1 | 110 | 141.57 |  | 15572.7 | 141.57
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | EA | 2 | 0 | NA | 9.62 | 1 | 110 | 19.24 |  | 2116.4 | 19.24
Proj_A | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | EA | 14 | 0 | NA | 10.27 | 1 | 110 | 143.78 |  | 15815.8 | 143.78
Proj_A | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 1 | 110 | 0.8 |  | 88 | 0.8
Proj_A | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 15 | 0 | NA | 1 | 1 | 110 | 15 |  | 1650 | 15
Proj_A | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 6 | 0 | NA | 1.8233 | 1 | 110 | 10.9396 |  | 1203.3512 | 10.9396
Proj_A | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 12 | EA | 15 | 0 | NA | 1.9144 | 1 | 110 | 28.7163 |  | 3158.7969 | 28.7163
Proj_A | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 17 | 0 | NA | 2.1107 | 1 | 110 | 35.8811 |  | 3946.9167 | 35.8811
Proj_A | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 0 | NA | 2.327 | 1 | 110 | 13.962 |  | 1535.8149 | 13.962
Proj_A | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 22 | 0 | NA | 2.5655 | 1 | 110 | 56.4412 |  | 6208.5319 | 56.4412
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | EA | 7 | 14 | CS | 1.6003 | 0.75 | 78 | 8.4016 |  | 655.3229 | 11.2021
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 4 SchXST | EA | 1 | 4 | CS | 2.99 | 0.75 | 78 | 2.2425 |  | 174.915 | 2.99
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchSTD | EA | 1 | 6 | CS | 3.3501 | 0.75 | 78 | 2.5126 |  | 195.9809 | 3.3501
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 13 | 78 | CS | 4.2237 | 0.75 | 78 | 41.1811 |  | 3212.1238 | 54.9081
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 8 SchSTD | EA | 1 | 8 | CS | 4.2887 | 0.75 | 78 | 3.2165 |  | 250.889 | 4.2887
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 8 | 96 | CS | 11.3555 | 0.75 | 78 | 68.133 |  | 5314.374 | 90.844
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 SchSTD | EA | 1 | 12 | CS | 7.1656 | 0.75 | 78 | 5.3742 |  | 419.1876 | 7.1656
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 16 Sch80 | EA | 2 | 32 | CS | 20.3905 | 0.75 | 78 | 30.5858 |  | 2385.6885 | 40.781
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 16 SchSTD | EA | 1 | 16 | CS | 11.6532 | 0.75 | 78 | 8.7399 |  | 681.7122 | 11.6532
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 20 Sch80 | EA | 1 | 20 | CS | 31.2637 | 0.75 | 78 | 23.4478 |  | 1828.9264 | 31.2637
Proj_A | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 24 Sch80 | EA | 2 | 48 | CS | 40.3455 | 0.75 | 78 | 60.5183 |  | 4720.4235 | 80.691
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | LM | 5.3886 | 0 | NA | 1.045 | 0.75 | 78 | 4.2233 |  | 329.4181 | 5.6311
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 31.0233 | 0 | NA | 1.1644 | 0.75 | 78 | 27.0933 |  | 2113.2754 | 36.1244
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 11.739 | 0 | NA | 1.0151 | 0.75 | 78 | 8.9376 |  | 697.1296 | 11.9167
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 1.5 SchXST | LM | 3.633 | 0 | NA | 1.1047 | 0.75 | 78 | 3.0101 |  | 234.7851 | 4.0134
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 400.8543 | 0 | NA | 1.1943 | 0.75 | 78 | 359.0504 |  | 28005.9318 | 478.7339
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 116.3294 | 0 | NA | 1.1644 | 0.75 | 78 | 101.5928 |  | 7924.2393 | 135.4571
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchSTD | LM | 11.9141 | 0 | NA | 1.2241 | 0.75 | 78 | 10.9384 |  | 853.1956 | 14.5845
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 93.9697 | 0 | NA | 1.5526 | 0.75 | 78 | 109.4208 |  | 8534.826 | 145.8945
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchSTD | LM | 12.9041 | 0 | NA | 1.4033 | 0.75 | 78 | 13.5811 |  | 1059.3246 | 18.1081
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 188.4751 | 0 | NA | 1.9109 | 0.75 | 78 | 270.1114 |  | 21068.6857 | 360.1485
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 38.9587 | 0 | NA | 1.7019 | 0.75 | 78 | 49.7265 |  | 3878.6697 | 66.302
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 24.2132 | 0 | NA | 2.4184 | 0.75 | 78 | 43.9184 |  | 3425.6319 | 58.5578
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 44.0404 | 0 | NA | 2.9857 | 0.75 | 78 | 98.6189 |  | 7692.274 | 131.4919
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 141.3902 | 0 | NA | 3.6724 | 0.75 | 78 | 389.4335 |  | 30375.8129 | 519.2447
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 73.8841 | 0 | NA | 2.6274 | 0.75 | 78 | 145.5936 |  | 11356.2999 | 194.1248
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 18.4368 | 0 | NA | 4.3591 | 0.75 | 78 | 60.2764 |  | 4701.559 | 80.3685
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 25.8762 | 0 | NA | 5.1056 | 0.75 | 78 | 99.0843 |  | 7728.572 | 132.1123
Proj_A | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 58.8087 | 0 | NA | 6.6283 | 0.75 | 78 | 292.3502 |  | 22803.3179 | 389.8003
Proj_A | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | LM | 165.517 | 0 | NA | 1.0237 | 0.75 | 78 | 127.0763 |  | 9911.9544 | 169.4351
Proj_A | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | LM | 32.1585 | 0 | NA | 1.3222 | 0.75 | 78 | 31.891 |  | 2487.4991 | 42.5214
Proj_A | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | LM | 64.1047 | 0 | NA | 1.1943 | 0.75 | 78 | 57.4194 |  | 4478.7142 | 76.5592
Proj_A | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 249.1412 | 0 | NA | 1.6208 | 0.75 | 78 | 302.8587 |  | 23622.9754 | 403.8115
Proj_A | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 8 SchSTD | LM | 19.1103 | 0 | NA | 1.4502 | 0.75 | 78 | 20.7853 |  | 1621.257 | 27.7138
Proj_A | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 92.3277 | 0 | NA | 3.1137 | 0.75 | 78 | 215.6085 |  | 16817.4661 | 287.4781
Proj_A | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 SchSTD | LM | 18.4242 | 0 | NA | 2.218 | 0.75 | 78 | 30.648 |  | 2390.5413 | 40.864
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 17 | 0 | NA | 0.39 | 0.75 | 78 | 4.9725 |  | 387.855 | 6.63
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 41 | 0 | NA | 0.65 | 0.75 | 78 | 19.9875 |  | 1559.025 | 26.65
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 CL800 | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1 | 2.6
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 36 | 0 | NA | 0.39 | 0.75 | 78 | 10.53 |  | 821.34 | 14.04
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 95 | 0 | NA | 0.78 | 0.75 | 78 | 55.575 |  | 4334.85 | 74.1
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL300 | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815 | 0.39
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 12 | 0 | NA | 0.78 | 0.75 | 78 | 7.02 |  | 547.56 | 9.36
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 6 | 0 | NA | 0.78 | 0.75 | 78 | 3.51 |  | 273.78 | 4.68
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 17 | 0 | NA | 0.91 | 0.75 | 78 | 11.6025 |  | 904.995 | 15.47
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 1.5 2000psi | EA | 4 | 0 | NA | 0.52 | 0.75 | 78 | 1.56 |  | 121.68 | 2.08
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 6 | 0 | NA | 0.65 | 0.75 | 78 | 2.925 |  | 228.15 | 3.9
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 28 | 0 | NA | 0.65 | 0.75 | 78 | 13.65 |  | 1064.7 | 18.2
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68 | 2.08
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 8 | 0 | NA | 1.04 | 0.75 | 78 | 6.24 |  | 486.72 | 8.32
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 0.75 | 78 | 2.535 |  | 197.73 | 3.38
Proj_A | Field | 600 | 150-30-F-310 | Install Inlines - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865 | 1.69
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 96 | 0 | NA | 1.69 | 0.75 | 78 | 121.68 |  | 9491.04 | 162.24
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26 | 1.56
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 4 | 0 | NA | 1.56 | 0.75 | 78 | 4.68 |  | 365.04 | 6.24
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL300 | EA | 2 | 0 | NA | 1.95 | 0.75 | 78 | 2.925 |  | 228.15 | 3.9
Proj_A | Field | 600 | 150-30-F-310 | Install Inlines - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075 | 1.95
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL300 | EA | 2 | 0 | NA | 1.95 | 0.75 | 78 | 2.925 |  | 228.15 | 3.9
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 6 | 0 | NA | 3.38 | 0.75 | 78 | 15.21 |  | 1186.38 | 20.28
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 6 | 0 | NA | 3.38 | 0.75 | 78 | 15.21 |  | 1186.38 | 20.28
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL150 | EA | 2 | 0 | NA | 2.86 | 0.75 | 78 | 4.29 |  | 334.62 | 5.72
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31 | 2.86
Proj_A | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 4 | 0 | NA | 4.29 | 0.75 | 78 | 12.87 |  | 1003.86 | 17.16
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 8 | 0 | NA | 4.29 | 0.75 | 78 | 25.74 |  | 2007.72 | 34.32
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 8 CL150 | EA | 1 | 0 | NA | 3.64 | 0.75 | 78 | 2.73 |  | 212.94 | 3.64
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL300 | EA | 1 | 0 | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57 | 4.42
Proj_A | Field | 600 | 150-30-F-310 | Install Inlines - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82 | 10.92
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 11 | 0 | NA | 5.46 | 0.75 | 78 | 45.045 |  | 3513.51 | 60.06
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 3 | 0 | NA | 6.63 | 0.75 | 78 | 14.9175 |  | 1163.565 | 19.89
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 4 | 0 | NA | 6.63 | 0.75 | 78 | 19.89 |  | 1551.42 | 26.52
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL150 | EA | 2 | 0 | NA | 5.59 | 0.75 | 78 | 8.385 |  | 654.03 | 11.18
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL150 | EA | 4 | 0 | NA | 5.59 | 0.75 | 78 | 16.77 |  | 1308.06 | 22.36
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 4 | 0 | NA | 8.19 | 0.75 | 78 | 24.57 |  | 1916.46 | 32.76
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 14 | 0 | NA | 8.19 | 0.75 | 78 | 85.995 |  | 6707.61 | 114.66
Proj_A | Field | 600 | 150-30-F-310 | Install Inlines - NB 16 CL600 | EA | 6 | 0 | NA | 11.44 | 0.75 | 78 | 51.48 |  | 4015.44 | 68.64
Proj_A | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 6 | 0 | NA | 15.47 | 0.75 | 78 | 69.615 |  | 5429.97 | 92.82
Proj_A | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 6 | 0 | NA | 15.47 | 0.75 | 78 | 69.615 |  | 5429.97 | 92.82
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235 | 0.91
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84 | 1.04
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 8.5 | 0 | NA | 1.17 | 0.75 | 78 | 7.4587 |  | 581.7825 | 9.945
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 9.5 | 0 | NA | 0.91 | 0.75 | 78 | 6.4837 |  | 505.7325 | 8.645
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 8 | 0 | NA | 1.04 | 0.75 | 78 | 6.24 |  | 486.72 | 8.32
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 118 | 0 | NA | 1.17 | 0.75 | 78 | 103.545 |  | 8076.51 | 138.06
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175 | 0.455
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84 | 1.04
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 116.5 | 0 | NA | 0.91 | 0.75 | 78 | 79.5113 |  | 6201.8775 | 106.015
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 26 | 0 | NA | 1.04 | 0.75 | 78 | 20.28 |  | 1581.84 | 27.04
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 227.5 | 0 | NA | 1.17 | 0.75 | 78 | 199.6312 |  | 15571.2375 | 266.175
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 20 | 0 | NA | 1.04 | 0.75 | 78 | 15.6 |  | 1216.8 | 20.8
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 11 | 0 | NA | 1.17 | 0.75 | 78 | 9.6525 |  | 752.895 | 12.87
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 5 | 0 | NA | 1.3 | 0.75 | 78 | 4.875 |  | 380.25 | 6.5
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | EA | 2.5 | 0 | NA | 1.56 | 0.75 | 78 | 2.925 |  | 228.15 | 3.9
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 32 | 0 | NA | 1.95 | 0.75 | 78 | 46.8 |  | 3650.4 | 62.4
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 9 | 0 | NA | 1.95 | 0.75 | 78 | 13.1625 |  | 1026.675 | 17.55
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 61 | 0 | NA | 2.34 | 0.75 | 78 | 107.055 |  | 8350.29 | 142.74
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 5.5 | 0 | NA | 2.73 | 0.75 | 78 | 11.2612 |  | 878.3775 | 15.015
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 0 | NA | 3.12 | 0.75 | 78 | 2.34 |  | 182.52 | 3.12
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 35 | 0 | NA | 3.38 | 0.75 | 78 | 88.725 |  | 6920.55 | 118.3
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 12 | 0 | NA | 4.16 | 0.75 | 78 | 37.44 |  | 2920.32 | 49.92
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 16.5 | 0 | NA | 4.42 | 0.75 | 78 | 54.6975 |  | 4266.405 | 72.93
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL300 | EA | 1.5 | 0 | NA | 4.94 | 0.75 | 78 | 5.5575 |  | 433.485 | 7.41
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 69 | 0 | NA | 5.33 | 0.75 | 78 | 275.8275 |  | 21514.545 | 367.77
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 9 | 0 | NA | 5.98 | 0.75 | 78 | 40.365 |  | 3148.47 | 53.82
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 16.5 | 0 | NA | 6.76 | 0.75 | 78 | 83.655 |  | 6525.09 | 111.54
Proj_A | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 15 | 0 | NA | 8.58 | 0.75 | 78 | 96.525 |  | 7528.95 | 128.7
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 0.75 | EA | 2 | 0 | NA | 0.3 | 0.75 | 78 | 0.45 |  | 35.1 | 0.6
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 44 | 0 | NA | 0.4 | 0.75 | 78 | 13.2 |  | 1029.6 | 17.6
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1.5 | EA | 2 | 0 | NA | 0.5 | 0.75 | 78 | 0.75 |  | 58.5 | 1
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 176 | 0 | NA | 1 | 0.75 | 78 | 132 |  | 10296 | 176
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 38 | 0 | NA | 1.5 | 0.75 | 78 | 42.75 |  | 3334.5 | 57
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 27 | 0 | NA | 1.5 | 0.75 | 78 | 30.375 |  | 2369.25 | 40.5
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 94 | 0 | NA | 1.6538 | 0.75 | 78 | 116.5894 |  | 9093.9713 | 155.4525
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 18 | 0 | NA | 1.7364 | 0.75 | 78 | 23.4419 |  | 1828.4687 | 31.2559
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 15 | 0 | NA | 1.8233 | 0.75 | 78 | 20.5117 |  | 1599.9101 | 27.3489
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 42 | 0 | NA | 1.9144 | 0.75 | 78 | 60.3043 |  | 4703.7357 | 80.4057
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 6 | 0 | NA | 2.0101 | 0.75 | 78 | 9.0456 |  | 705.5604 | 12.0609
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 10 | 0 | NA | 2.1107 | 0.75 | 78 | 15.8299 |  | 1234.7306 | 21.1065
Proj_A | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 0 | NA | 2.327 | 0.75 | 78 | 10.4715 |  | 816.7743 | 13.962
Proj_A | Field | 600 | 150-60-F-610 | Field X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500 | 0
Proj_A | Field | 600 | 150-60-F-610 | Field X-Ray - NB 2 | EA | 7 | 0 | NA | 0 | 0.75 | 78 | 0 | 750 | 5250 | 0
Proj_A | Field | 600 | 150-60-F-610 | Field X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 0.75 | 78 | 0 | 1000 | 2000 | 0
Proj_A | Field | 600 | 150-60-F-610 | Field X-Ray - NB 8 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500 | 0
Proj_A | Field | 300 | 150-80-F-810 | Field Coating - NB 2 | LM | 165.517 | 0 | CS | 0 | 0.75 | 78 | 0 | 60 | 9931.02 | 0
Proj_A | Field | 300 | 150-80-F-810 | Field Coating - NB 4 | LM | 32.1585 | 0 | CS | 0 | 0.75 | 78 | 0 | 80 | 2572.68 | 0
Proj_A | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 313.2459 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 31324.59 | 0
Proj_A | Field | 300 | 150-80-F-810 | Field Coating - NB 8 | LM | 19.1103 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 2293.236 | 0
Proj_A | Field | 300 | 150-80-F-810 | Field Coating - NB 12 | LM | 110.7519 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 13290.228 | 0
Proj_A | Spool Fabrication | 400 | 150-50-S-510 | Pipe Supports Labor (shoes, lugs, guides, etc.) | of Labor hours | 5% | 0 |  | 0 | 0 | 0 | 963.9511 |  | 106034.6258 | 0
Proj_A | Module | 500 | 150-70-F-710 | Hydrotest of module assembly | of Module Labor | 5% | 0 |  | 0 | 0 | 0 | 230.2252 |  | 25324.7765 | 0
Proj_A | Module | 500 | 150-90-F-910 | Flushing & Drying Module Piping | of Module Labor | 3% | 0 |  | 0 | 0 | 0 | 138.1351 |  | 15194.8659 | 0
Proj_A | Field | 600 | 150-40-F-410 | Bolt torquing and tensioning | of bolt-up labor | 15% | 0 |  | 0 | 0 | 0 | 198.3296 |  | 15469.7108 | 0
Proj_A | Field | 600 | 150-70-F-710 | Field Hydrotest | of Field Labor | 5% | 0 |  | 0 | 0 | 0 | 285.076 |  | 22235.93 | 0
Proj_A | Field | 600 | 150-90-F-910 | Flushing & Drying on Site | of Field Labor | 3% | 0 |  | 0 | 0 | 0 | 171.0456 |  | 13341.558 | 0
Project Level Summary (Also WBS1 Summary in the Example Project)
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## WBS2-Summary By Area
WBS1 | WBS2 | Location | CBS | COA | Description | Units | Quantity | Dia_Inch | Material | STD_UNIT_HR | PF | Wage Rate | Location Hours | S/C Rate_$ | Total Cost
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.585 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 79 | 158 | CS | 1.1765 | 1 | 110 | 92.9435 |  | 10223.785
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 15 | 45 | CS | 1.3715 | 1 | 110 | 20.5725 |  | 2262.975
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 122 | 488 | CS | 2.119 | 1 | 110 | 258.518 |  | 28436.98
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 112 | 672 | CS | 2.9315 | 1 | 110 | 328.328 |  | 36116.08
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 40 | 400 | CS | 5.915 | 1 | 110 | 236.6 |  | 26026
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 6 | 4.5 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 22 | 22 | CS | 0.78 | 1 | 110 | 17.16 |  | 1887.6
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 22 | 22 | CS | 0.91 | 1 | 110 | 20.02 |  | 2202.2
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 49 | 49 | CS | 0.91 | 1 | 110 | 44.59 |  | 4904.9
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 8 | 16 | CS | 1.69 | 1 | 110 | 13.52 |  | 1487.2
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 5 | 5 | CS | 3.77 | 1 | 110 | 18.85 |  | 2073.5
Proj_A | Area_1 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 7 | 14 | CS | 5.46 | 1 | 110 | 38.22 |  | 4204.2
Proj_A | Area_1 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 6 | 3 | NA | 0.26 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_1 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_1 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 8 | 8 | NA | 0.39 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_1 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.32 | 0 | NA | 0.17914 | 1 | 110 | 0.41561 |  | 45.7172
Proj_A | Area_1 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 16.602 | 0 | NA | 0.18767 | 1 | 110 | 3.1158 |  | 342.7326
Proj_A | Area_1 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 14.149 | 0 | NA | 0.17488 | 1 | 110 | 2.4743 |  | 272.1773
Proj_A | Area_1 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 85.427 | 0 | NA | 0.24739 | 1 | 110 | 21.1336 |  | 2324.692
Proj_A | Area_1 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 80.536 | 0 | NA | 0.29857 | 1 | 110 | 24.0457 |  | 2645.0285
Proj_A | Area_1 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 34.345 | 0 | NA | 0.46918 | 1 | 110 | 16.1141 |  | 1772.5499
Proj_A | Area_1 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 27 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1350
Proj_A | Area_1 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1750
Proj_A | Area_1 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 48 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2400
Proj_A | Area_1 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 15 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 750
Proj_A | Area_1 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 21 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1050
Proj_A | Area_1 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 1200
Proj_A | Area_1 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_1 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_1 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 8 | 0 | NA | 8.4 | 1 | 110 | 67.2 |  | 7392
Proj_A | Area_1 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 9 | 0 | NA | 12 | 1 | 110 | 108 |  | 11880
Proj_A | Area_1 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | EA | 5 | 0 | NA | 14.6 | 1 | 110 | 73 |  | 8030
Proj_A | Area_1 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_1 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_1 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 8 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 5600
Proj_A | Area_1 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 9 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 8100
Proj_A | Area_1 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 10 | EA | 5 | 0 | CS | 0 | 1 | 110 | 0 | 1500 | 7500
Proj_A | Area_1 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 4 SchXST | EA | 1 | 4 | CS | 2.99 | 0.75 | 78 | 2.2425 |  | 174.915
Proj_A | Area_1 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 7 | 42 | CS | 4.2237 | 0.75 | 78 | 22.1744 |  | 1729.6051
Proj_A | Area_1 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.436 | 0 | NA | 1.1644 | 0.75 | 78 | 2.1274 |  | 165.9378
Proj_A | Area_1 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 18.2622 | 0 | NA | 1.1943 | 0.75 | 78 | 16.3577 |  | 1275.8998
Proj_A | Area_1 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 15.5639 | 0 | NA | 1.1644 | 0.75 | 78 | 13.5923 |  | 1060.1969
Proj_A | Area_1 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 93.9697 | 0 | NA | 1.5526 | 0.75 | 78 | 109.4208 |  | 8534.826
Proj_A | Area_1 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 88.5896 | 0 | NA | 1.9109 | 0.75 | 78 | 126.9614 |  | 9902.9869
Proj_A | Area_1 | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 39.4967 | 0 | NA | 2.9857 | 0.75 | 78 | 88.4444 |  | 6898.6617
Proj_A | Area_1 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | LM | 32.1585 | 0 | NA | 1.3222 | 0.75 | 78 | 31.891 |  | 2487.4991
Proj_A | Area_1 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 140.844 | 0 | NA | 1.6208 | 0.75 | 78 | 171.2114 |  | 13354.4927
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 4 | 0 | NA | 0.39 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 6 | 0 | NA | 0.78 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL300 | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 12 | 0 | NA | 1.69 | 0.75 | 78 | 15.21 |  | 1186.38
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 6 | 0 | NA | 3.38 | 0.75 | 78 | 15.21 |  | 1186.38
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 6 | 0 | NA | 3.38 | 0.75 | 78 | 15.21 |  | 1186.38
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL300 | EA | 1 | 0 | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 2 | 0 | NA | 6.63 | 0.75 | 78 | 9.945 |  | 775.71
Proj_A | Area_1 | Field | 600 | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 3 | 0 | NA | 6.63 | 0.75 | 78 | 14.9175 |  | 1163.565
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 18 | 0 | NA | 1.17 | 0.75 | 78 | 15.795 |  | 1232.01
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3.5 | 0 | NA | 0.91 | 0.75 | 78 | 2.3887 |  | 186.3225
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 24.5 | 0 | NA | 1.17 | 0.75 | 78 | 21.4987 |  | 1676.9025
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 1.5 | 0 | NA | 1.04 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 32 | 0 | NA | 1.95 | 0.75 | 78 | 46.8 |  | 3650.4
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 20 | 0 | NA | 2.34 | 0.75 | 78 | 35.1 |  | 2737.8
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 0 | NA | 3.12 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_1 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 9 | 0 | NA | 4.16 | 0.75 | 78 | 28.08 |  | 2190.24
Proj_A | Area_1 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_1 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | NA | 1 | 0.75 | 78 | 3.75 |  | 292.5
Proj_A | Area_1 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 5 | 0 | NA | 1.5 | 0.75 | 78 | 5.625 |  | 438.75
Proj_A | Area_1 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 24 | 0 | NA | 1.5 | 0.75 | 78 | 27 |  | 2106
Proj_A | Area_1 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 47 | 0 | NA | 1.6538 | 0.75 | 78 | 58.2947 |  | 4546.9856
Proj_A | Area_1 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 13 | 0 | NA | 1.8233 | 0.75 | 78 | 17.7768 |  | 1386.5888
Proj_A | Area_1 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1000 | 1000
Proj_A | Area_1 | Field | 300 | 150-80-F-810 | Field Coating - NB 4 | LM | 32.1585 | 0 | CS | 0 | 0.75 | 78 | 0 | 80 | 2572.68
Proj_A | Area_1 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 140.844 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 14084.4
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 87 | 174 | CS | 1.1765 | 1 | 110 | 102.3555 |  | 11259.105
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 18 | CS | 1.3715 | 1 | 110 | 8.229 |  | 905.19
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 4 | 24 | CS | 2.431 | 1 | 110 | 9.724 |  | 1069.64
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 40 | 240 | CS | 2.9315 | 1 | 110 | 117.26 |  | 12898.6
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 41 | 328 | CS | 3.0095 | 1 | 110 | 123.3895 |  | 13572.845
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 2 | 16 | CS | 3.848 | 1 | 110 | 7.696 |  | 846.56
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 14 | 140 | CS | 5.915 | 1 | 110 | 82.81 |  | 9109.1
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 122 | 1464 | CS | 7.683 | 1 | 110 | 937.326 |  | 103105.86
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 60 | 720 | CS | 4.7255 | 1 | 110 | 283.53 |  | 31188.3
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 10 | 160 | CS | 14.365 | 1 | 110 | 143.65 |  | 15801.5
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 3 | 2.25 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 3 | 2.25 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 25 | 25 | CS | 0.78 | 1 | 110 | 19.5 |  | 2145
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 36 | 36 | CS | 0.91 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 7 | 7 | CS | 0.78 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 28 | 28 | CS | 0.91 | 1 | 110 | 25.48 |  | 2802.8
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.17 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 2.86 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 4 | 4 | CS | 3.77 | 1 | 110 | 15.08 |  | 1658.8
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 3 | 6 | CS | 4.42 | 1 | 110 | 13.26 |  | 1458.6
Proj_A | Area_10 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 9 | 18 | CS | 5.46 | 1 | 110 | 49.14 |  | 5405.4
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 4 | 2 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 5 | 3.75 | NA | 0.26 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 Sch160 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.942 | 0 | NA | 0.17914 | 1 | 110 | 0.16875 |  | 18.5628
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 0.86 | 0 | NA | 0.15355 | 1 | 110 | 0.13205 |  | 14.5259
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 41.826 | 0 | NA | 0.18767 | 1 | 110 | 7.8496 |  | 863.4581
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 1.791 | 0 | NA | 0.17488 | 1 | 110 | 0.31321 |  | 34.4526
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 49.987 | 0 | NA | 0.29857 | 1 | 110 | 14.9247 |  | 1641.7135
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 32.501 | 0 | NA | 0.26871 | 1 | 110 | 8.7335 |  | 960.6818
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 3.951 | 0 | NA | 0.46918 | 1 | 110 | 1.8537 |  | 203.9116
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 82.425 | 0 | NA | 0.57155 | 1 | 110 | 47.11 |  | 5182.1028
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 62.617 | 0 | NA | 0.40947 | 1 | 110 | 25.6397 |  | 2820.3679
Proj_A | Area_10 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 14.773 | 0 | NA | 0.79335 | 1 | 110 | 11.7201 |  | 1289.2107
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 27 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1350
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 72 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 18000
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 60 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 3000
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 12 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 900
Proj_A | Area_10 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 24 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 2400
Proj_A | Area_10 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 4 | 0 | NA | 5.6 | 1 | 110 | 22.4 |  | 2464
Proj_A | Area_10 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 6 | 0 | NA | 12 | 1 | 110 | 72 |  | 7920
Proj_A | Area_10 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | EA | 4 | 0 | NA | 9.8 | 1 | 110 | 39.2 |  | 4312
Proj_A | Area_10 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 9 | 0 | NA | 19 | 1 | 110 | 171 |  | 18810
Proj_A | Area_10 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 7 | 0 | NA | 12.2 | 1 | 110 | 85.4 |  | 9394
Proj_A | Area_10 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 2 | 0 | NA | 17.6 | 1 | 110 | 35.2 |  | 3872
Proj_A | Area_10 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 4 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 2000
Proj_A | Area_10 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 5400
Proj_A | Area_10 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 4 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 4400
Proj_A | Area_10 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 16 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 27200
Proj_A | Area_10 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 4200
Proj_A | Area_10 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 6 | 36 | CS | 4.2237 | 0.75 | 78 | 19.0066 |  | 1482.5187
Proj_A | Area_10 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 4 | 48 | CS | 11.3555 | 0.75 | 78 | 34.0665 |  | 2657.187
Proj_A | Area_10 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 SchSTD | EA | 1 | 12 | CS | 7.1656 | 0.75 | 78 | 5.3742 |  | 419.1876
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.9891 | 0 | NA | 1.1644 | 0.75 | 78 | 0.8638 |  | 67.3765
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 0.903 | 0 | NA | 1.0151 | 0.75 | 78 | 0.6875 |  | 53.6254
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 46.0086 | 0 | NA | 1.1943 | 0.75 | 78 | 41.2105 |  | 3214.4191
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 1.9701 | 0 | NA | 1.1644 | 0.75 | 78 | 1.7205 |  | 134.2012
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 54.9857 | 0 | NA | 1.9109 | 0.75 | 78 | 78.8023 |  | 6146.5755
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 35.7511 | 0 | NA | 1.7019 | 0.75 | 78 | 45.6324 |  | 3559.3259
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 4.5436 | 0 | NA | 2.9857 | 0.75 | 78 | 10.1745 |  | 793.6122
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 94.7887 | 0 | NA | 3.6724 | 0.75 | 78 | 261.0783 |  | 20364.1082
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 72.0096 | 0 | NA | 2.6274 | 0.75 | 78 | 141.8998 |  | 11068.1811
Proj_A | Area_10 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 16.9889 | 0 | NA | 5.1056 | 0.75 | 78 | 65.0536 |  | 5074.1831
Proj_A | Area_10 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 108.2972 | 0 | NA | 1.6208 | 0.75 | 78 | 131.6472 |  | 10268.4826
Proj_A | Area_10 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 92.3277 | 0 | NA | 3.1137 | 0.75 | 78 | 215.6085 |  | 16817.4661
Proj_A | Area_10 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 SchSTD | LM | 18.4242 | 0 | NA | 2.218 | 0.75 | 78 | 30.648 |  | 2390.5413
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 6 | 0 | NA | 0.78 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 5 | 0 | NA | 0.78 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 5 | 0 | NA | 0.65 | 0.75 | 78 | 2.4375 |  | 190.125
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 9 | 0 | NA | 1.69 | 0.75 | 78 | 11.4075 |  | 889.785
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL150 | EA | 2 | 0 | NA | 5.59 | 0.75 | 78 | 8.385 |  | 654.03
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL150 | EA | 4 | 0 | NA | 5.59 | 0.75 | 78 | 16.77 |  | 1308.06
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 3 | 0 | NA | 8.19 | 0.75 | 78 | 18.4275 |  | 1437.345
Proj_A | Area_10 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 6 | 0 | NA | 8.19 | 0.75 | 78 | 36.855 |  | 2874.69
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 18 | 0 | NA | 1.17 | 0.75 | 78 | 15.795 |  | 1232.01
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 16.5 | 0 | NA | 0.91 | 0.75 | 78 | 11.2612 |  | 878.3775
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 4 | 0 | NA | 1.04 | 0.75 | 78 | 3.12 |  | 243.36
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 19 | 0 | NA | 1.17 | 0.75 | 78 | 16.6725 |  | 1300.455
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 1 | 0 | NA | 1.3 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 2 | 0 | NA | 1.95 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 13 | 0 | NA | 2.34 | 0.75 | 78 | 22.815 |  | 1779.57
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 4 | 0 | NA | 2.73 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 7 | 0 | NA | 3.38 | 0.75 | 78 | 17.745 |  | 1384.11
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 3 | 0 | NA | 4.16 | 0.75 | 78 | 9.36 |  | 730.08
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 16 | 0 | NA | 4.42 | 0.75 | 78 | 53.04 |  | 4137.12
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL300 | EA | 1.5 | 0 | NA | 4.94 | 0.75 | 78 | 5.5575 |  | 433.485
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 40.5 | 0 | NA | 5.33 | 0.75 | 78 | 161.8988 |  | 12628.1025
Proj_A | Area_10 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 1.5 | 0 | NA | 6.76 | 0.75 | 78 | 7.605 |  | 593.19
Proj_A | Area_10 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_10 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 14 | 0 | NA | 1 | 0.75 | 78 | 10.5 |  | 819
Proj_A | Area_10 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 1 | 0 | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
Proj_A | Area_10 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 33 | 0 | NA | 1.6538 | 0.75 | 78 | 40.9303 |  | 3192.5644
Proj_A | Area_10 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 3 | 0 | NA | 1.7364 | 0.75 | 78 | 3.907 |  | 304.7448
Proj_A | Area_10 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 2 | 0 | NA | 1.8233 | 0.75 | 78 | 2.7349 |  | 213.3213
Proj_A | Area_10 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 36 | 0 | NA | 1.9144 | 0.75 | 78 | 51.6894 |  | 4031.7735
Proj_A | Area_10 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 3 | 0 | NA | 2.1107 | 0.75 | 78 | 4.749 |  | 370.4192
Proj_A | Area_10 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500
Proj_A | Area_10 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 108.2972 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 10829.72
Proj_A | Area_10 | Field | 300 | 150-80-F-810 | Field Coating - NB 12 | LM | 110.7519 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 13290.228
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 182 | 364 | CS | 1.1765 | 1 | 110 | 214.123 |  | 23553.53
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 62 | 186 | CS | 1.3715 | 1 | 110 | 85.033 |  | 9353.63
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 4 | 32 | CS | 3.0095 | 1 | 110 | 12.038 |  | 1324.18
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 20 | 200 | CS | 5.915 | 1 | 110 | 118.3 |  | 13013
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | EA | 8 | 80 | CS | 4.1782 | 1 | 110 | 33.4256 |  | 3676.816
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 60 | 720 | CS | 7.683 | 1 | 110 | 460.98 |  | 50707.8
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | EA | 26 | 416 | CS | 16.12 | 1 | 110 | 419.12 |  | 46103.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | EA | 12 | 288 | CS | 18.3647 | 1 | 110 | 220.376 |  | 24241.36
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 16 | 12 | CS | 0.65 | 1 | 110 | 10.4 |  | 1144
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | EA | 8 | 6 | CS | 0.65 | 1 | 110 | 5.2 |  | 572
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 33 | 24.75 | CS | 0.65 | 1 | 110 | 21.45 |  | 2359.5
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL6000 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 6 | 4.5 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 49 | 36.75 | CS | 0.78 | 1 | 110 | 38.22 |  | 4204.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 24 | 24 | CS | 0.78 | 1 | 110 | 18.72 |  | 2059.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 41 | 41 | CS | 0.78 | 1 | 110 | 31.98 |  | 3517.8
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 7 | 7 | CS | 0.91 | 1 | 110 | 6.37 |  | 700.7
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 75 | 75 | CS | 0.91 | 1 | 110 | 68.25 |  | 7507.5
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 14 | 14 | CS | 0.78 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 21 | 21 | CS | 0.91 | 1 | 110 | 19.11 |  | 2102.1
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | EA | 8 | 12 | CS | 1.04 | 1 | 110 | 8.32 |  | 915.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | EA | 20 | 30 | CS | 1.04 | 1 | 110 | 20.8 |  | 2288
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 14 | 21 | CS | 1.3 | 1 | 110 | 18.2 |  | 2002
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 2 | 3 | CS | 1.04 | 1 | 110 | 2.08 |  | 228.8
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 4 | 8 | CS | 1.69 | 1 | 110 | 6.76 |  | 743.6
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.17 | 1 | 110 | 14.04 |  | 1544.4
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 2 | 6 | CS | 2.21 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.56 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL6000 | EA | 2 | 1.5 | CS | 3.38 | 1 | 110 | 6.76 |  | 743.6
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 2.86 | 1 | 110 | 17.16 |  | 1887.6
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 7 | 7 | CS | 3.77 | 1 | 110 | 26.39 |  | 2902.9
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 12 | 24 | CS | 4.42 | 1 | 110 | 53.04 |  | 5834.4
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 12 | 24 | CS | 5.46 | 1 | 110 | 65.52 |  | 7207.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 2 | 6 | CS | 7.67 | 1 | 110 | 15.34 |  | 1687.4
Proj_A | Area_2 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 9 | 4.5 | NA | 0.26 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 12 | 9 | NA | 0.26 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 14 | 10.5 | NA | 0.26 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_2 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 24 | 24 | NA | 0.39 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_2 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 18 | 18 | NA | 0.39 | 1 | 110 | 7.02 |  | 772.2
Proj_A | Area_2 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 16 | 16 | NA | 0.39 | 1 | 110 | 6.24 |  | 686.4
Proj_A | Area_2 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | LM | 5.132 | 0 | NA | 0.16635 | 1 | 110 | 0.85369 |  | 93.906
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.96 | 0 | NA | 0.17914 | 1 | 110 | 0.17198 |  | 18.9175
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 5.208 | 0 | NA | 0.15355 | 1 | 110 | 0.79969 |  | 87.9662
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1.5 SchXST | LM | 3.46 | 0 | NA | 0.17488 | 1 | 110 | 0.60508 |  | 66.5583
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 66.553 | 0 | NA | 0.18767 | 1 | 110 | 12.4902 |  | 1373.9236
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 50.242 | 0 | NA | 0.17488 | 1 | 110 | 8.7862 |  | 966.4804
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 7.372 | 0 | NA | 0.46918 | 1 | 110 | 3.4588 |  | 380.4699
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 SchSTD | LM | 5.322 | 0 | NA | 0.33696 | 1 | 110 | 1.7933 |  | 197.2624
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 181.595 | 0 | NA | 0.57155 | 1 | 110 | 103.7907 |  | 11416.9724
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchXST | LM | 7.064 | 0 | NA | 0.79335 | 1 | 110 | 5.6042 |  | 616.4614
Proj_A | Area_2 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch40 | LM | 14.46 | 0 | NA | 0.89571 | 1 | 110 | 12.952 |  | 1424.7211
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 110 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 5500
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 161 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 8050
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 44 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2200
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 11 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2750
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2500
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 26 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 6500
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 193 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 9650
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 12 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 6000
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 68 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 3400
Proj_A | Area_2 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 400
Proj_A | Area_2 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 4 | 0 | NA | 5.6 | 1 | 110 | 22.4 |  | 2464
Proj_A | Area_2 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 5 | 0 | NA | 6 | 1 | 110 | 30 |  | 3300
Proj_A | Area_2 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 13 | 0 | NA | 19 | 1 | 110 | 247 |  | 27170
Proj_A | Area_2 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch40 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_2 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 4 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 2000
Proj_A | Area_2 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 5 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 3000
Proj_A | Area_2 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 13 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 22100
Proj_A | Area_2 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 2880
Proj_A | Area_2 | Module | 500 | 150-20-M-210 | Install Spools - NB 1 SchXST | LM | 0.4305 | 0 | NA | 1.0151 | 1 | 110 | 0.43702 |  | 48.072
Proj_A | Area_2 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 62.6593 | 0 | NA | 1.1943 | 1 | 110 | 74.833 |  | 8231.6299
Proj_A | Area_2 | Module | 500 | 150-20-M-210 | Install Spools - NB 10 Sch80 | LM | 8.4778 | 0 | NA | 2.9857 | 1 | 110 | 25.3123 |  | 2784.3477
Proj_A | Area_2 | Module | 500 | 150-20-M-210 | Install Spools - NB 10 SchSTD | LM | 6.1203 | 0 | NA | 2.1497 | 1 | 110 | 13.1569 |  | 1447.2565
Proj_A | Area_2 | Module | 500 | 150-20-M-210 | Install Spools - NB 12 Sch80 | LM | 208.8342 | 0 | NA | 3.6724 | 1 | 110 | 766.9278 |  | 84362.0542
Proj_A | Area_2 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchXST | LM | 8.1236 | 0 | NA | 5.1056 | 1 | 110 | 41.4756 |  | 4562.3117
Proj_A | Area_2 | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch40 | LM | 16.629 | 0 | NA | 5.7923 | 1 | 110 | 96.3198 |  | 10595.1759
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 2000psi | EA | 4 | 0 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 6 | 0 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL3000 | EA | 3 | 0 | NA | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 12 | 0 | NA | 1.04 | 1 | 110 | 12.48 |  | 1372.8
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 6 | 0 | NA | 1.69 | 1 | 110 | 10.14 |  | 1115.4
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install Blind - NB 10 CL600 | EA | 2 | 0 | NA | 6.63 | 1 | 110 | 13.26 |  | 1458.6
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 10 CL600 | EA | 4 | 0 | NA | 6.63 | 1 | 110 | 26.52 |  | 2917.2
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL300 | EA | 3 | 0 | NA | 9.23 | 1 | 110 | 27.69 |  | 3045.9
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install Inlines - NB 16 CL300 | EA | 4 | 0 | NA | 9.23 | 1 | 110 | 36.92 |  | 4061.2
Proj_A | Area_2 | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL300 | EA | 3 | 0 | NA | 9.23 | 1 | 110 | 27.69 |  | 3045.9
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 9 | 0 | NA | 1.04 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | EA | 5 | 0 | NA | 1.17 | 1 | 110 | 5.85 |  | 643.5
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 9.5 | 0 | NA | 0.91 | 1 | 110 | 8.645 |  | 950.95
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 22 | 0 | NA | 1.04 | 1 | 110 | 22.88 |  | 2516.8
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 11 | 0 | NA | 1.17 | 1 | 110 | 12.87 |  | 1415.7
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 3 CL300 | EA | 1 | 0 | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 0 | NA | 3.12 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL300 | EA | 1 | 0 | NA | 3.9 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 10 | 0 | NA | 4.16 | 1 | 110 | 41.6 |  | 4576
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 15.5 | 0 | NA | 5.33 | 1 | 110 | 82.615 |  | 9087.65
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | EA | 13.5 | 0 | NA | 6.37 | 1 | 110 | 85.995 |  | 9459.45
Proj_A | Area_2 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | EA | 2 | 0 | NA | 9.62 | 1 | 110 | 19.24 |  | 2116.4
Proj_A | Area_2 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 1 | 110 | 0.8 |  | 88
Proj_A | Area_2 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 13 | 0 | NA | 1 | 1 | 110 | 13 |  | 1430
Proj_A | Area_2 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 6 | 0 | NA | 1.8233 | 1 | 110 | 10.9396 |  | 1203.3512
Proj_A | Area_2 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 12 | EA | 15 | 0 | NA | 1.9144 | 1 | 110 | 28.7163 |  | 3158.7969
Proj_A | Area_2 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 2 | 0 | NA | 2.1107 | 1 | 110 | 4.2213 |  | 464.3431
Proj_A | Area_2 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 2 | 0 | NA | 2.5655 | 1 | 110 | 5.131 |  | 564.412
Proj_A | Area_2 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 4 | 48 | CS | 11.3555 | 0.75 | 78 | 34.0665 |  | 2657.187
Proj_A | Area_2 | Field | 600 | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | LM | 5.3886 | 0 | NA | 1.045 | 0.75 | 78 | 4.2233 |  | 329.4181
Proj_A | Area_2 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.008 | 0 | NA | 1.1644 | 0.75 | 78 | 0.88031 |  | 68.6639
Proj_A | Area_2 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 5.0379 | 0 | NA | 1.0151 | 0.75 | 78 | 3.8356 |  | 299.1796
Proj_A | Area_2 | Field | 600 | 150-20-F-210 | Install Spools - NB 1.5 SchXST | LM | 3.633 | 0 | NA | 1.1047 | 0.75 | 78 | 3.0101 |  | 234.7851
Proj_A | Area_2 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 10.549 | 0 | NA | 1.1943 | 0.75 | 78 | 9.4489 |  | 737.0124
Proj_A | Area_2 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 55.2662 | 0 | NA | 1.1644 | 0.75 | 78 | 48.2651 |  | 3764.6768
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 10 | 0 | NA | 0.39 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 CL800 | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 18 | 0 | NA | 0.39 | 0.75 | 78 | 5.265 |  | 410.67
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install valve - NB 1.5 2000psi | EA | 4 | 0 | NA | 0.52 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 6 | 0 | NA | 1.04 | 0.75 | 78 | 4.68 |  | 365.04
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install Inlines - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_2 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 5 | 0 | NA | 1.04 | 0.75 | 78 | 3.9 |  | 304.2
Proj_A | Area_2 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 22 | 0 | NA | 1.04 | 0.75 | 78 | 17.16 |  | 1338.48
Proj_A | Area_2 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 8.5 | 0 | NA | 1.17 | 0.75 | 78 | 7.4588 |  | 581.7825
Proj_A | Area_2 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 0.75 | EA | 2 | 0 | NA | 0.3 | 0.75 | 78 | 0.45 |  | 35.1
Proj_A | Area_2 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_2 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1.5 | EA | 2 | 0 | NA | 0.5 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_2 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_2 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 13 | 0 | NA | 1.5 | 0.75 | 78 | 14.625 |  | 1140.75
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 160 | 320 | CS | 1.1765 | 1 | 110 | 188.24 |  | 20706.4
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 16 | 48 | CS | 1.3715 | 1 | 110 | 21.944 |  | 2413.84
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | EA | 19 | 76 | CS | 1.6835 | 1 | 110 | 31.9865 |  | 3518.515
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 13 | 104 | CS | 3.0095 | 1 | 110 | 39.1235 |  | 4303.585
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 6 | 72 | CS | 4.7255 | 1 | 110 | 28.353 |  | 3118.83
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 44 | 704 | CS | 14.365 | 1 | 110 | 632.06 |  | 69526.6
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | EA | 14 | 224 | CS | 8.8313 | 1 | 110 | 123.6387 |  | 13600.2533
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 52 | 1040 | CS | 21.7588 | 1 | 110 | 1131.455 |  | 124460.05
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | EA | 6 | 120 | CS | 13.6121 | 1 | 110 | 81.6725 |  | 8983.975
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | EA | 51 | 1224 | CS | 33.1998 | 1 | 110 | 1693.1915 |  | 186251.065
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | EA | 10 | 240 | CS | 17.7732 | 1 | 110 | 177.7317 |  | 19550.4833
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 4 | 3 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 18 | 18 | CS | 0.78 | 1 | 110 | 14.04 |  | 1544.4
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 20 | 20 | CS | 0.91 | 1 | 110 | 18.2 |  | 2002
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.17 | 1 | 110 | 7.02 |  | 772.2
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 2.47 | 1 | 110 | 4.94 |  | 543.4
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 2.86 | 1 | 110 | 14.3 |  | 1573
Proj_A | Area_3 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 17 | 34 | CS | 5.46 | 1 | 110 | 92.82 |  | 10210.2
Proj_A | Area_3 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 4 | 2 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_3 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_3 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_3 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_3 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 5 | 5 | NA | 0.39 | 1 | 110 | 1.95 |  | 214.5
Proj_A | Area_3 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 2.77 | 0 | NA | 0.15355 | 1 | 110 | 0.42534 |  | 46.7869
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 104.369 | 0 | NA | 0.18767 | 1 | 110 | 19.5873 |  | 2154.5991
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 5.507 | 0 | NA | 0.17488 | 1 | 110 | 0.96305 |  | 105.9354
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchSTD | LM | 10.831 | 0 | NA | 0.19194 | 1 | 110 | 2.0789 |  | 228.6774
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 2.916 | 0 | NA | 0.26871 | 1 | 110 | 0.78357 |  | 86.1927
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 13.44 | 0 | NA | 0.40947 | 1 | 110 | 5.5033 |  | 605.3587
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 88.544 | 0 | NA | 0.79335 | 1 | 110 | 70.246 |  | 7727.0612
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchSTD | LM | 43.76 | 0 | NA | 0.58861 | 1 | 110 | 25.7576 |  | 2833.3398
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 81.44 | 0 | NA | 1.0279 | 1 | 110 | 83.7152 |  | 9208.6735
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 SchXST | LM | 2.414 | 0 | NA | 1.0279 | 1 | 110 | 2.4814 |  | 272.9585
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch80 | LM | 103.42 | 0 | NA | 1.1644 | 1 | 110 | 120.425 |  | 13246.7533
Proj_A | Area_3 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 SchXST | LM | 12.399 | 0 | NA | 1.1644 | 1 | 110 | 14.4377 |  | 1588.1502
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 49 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2450
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2000
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 135 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 6750
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 4000
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 5000
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 800
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 19 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 950
Proj_A | Area_3 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 13 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 1300
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 10 | 0 | NA | 5.6 | 1 | 110 | 56 |  | 6160
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchSTD | EA | 1 | 0 | NA | 7 | 1 | 110 | 7 |  | 770
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 0 | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 7 | 0 | NA | 17.6 | 1 | 110 | 123.2 |  | 13552
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 SchSTD | EA | 3 | 0 | NA | 15.6 | 1 | 110 | 46.8 |  | 5148
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 6 | 0 | NA | 41.2 | 1 | 110 | 247.2 |  | 27192
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch80 | EA | 8 | 0 | NA | 62.6 | 1 | 110 | 500.8 |  | 55088
Proj_A | Area_3 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 SchXST | EA | 1 | 0 | NA | 30.8 | 1 | 110 | 30.8 |  | 3388
Proj_A | Area_3 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 10 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 5000
Proj_A | Area_3 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_3 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 700
Proj_A | Area_3 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_3 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 10 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 21000
Proj_A | Area_3 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 16200
Proj_A | Area_3 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 9 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 25920
Proj_A | Area_3 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 7.4679 | 0 | NA | 1.1943 | 1 | 110 | 8.9188 |  | 981.0673
Proj_A | Area_3 | Module | 500 | 150-20-M-210 | Install Spools - NB 12 SchSTD | LM | 15.456 | 0 | NA | 2.6274 | 1 | 110 | 40.6095 |  | 4467.0425
Proj_A | Area_3 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 Sch80 | LM | 101.8256 | 0 | NA | 5.1056 | 1 | 110 | 519.8771 |  | 57186.4841
Proj_A | Area_3 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchSTD | LM | 50.324 | 0 | NA | 3.7919 | 1 | 110 | 190.8211 |  | 20990.3259
Proj_A | Area_3 | Module | 500 | 150-20-M-210 | Install Spools - NB 20 Sch80 | LM | 93.656 | 0 | NA | 6.6283 | 1 | 110 | 620.7778 |  | 68285.5619
Proj_A | Area_3 | Module | 500 | 150-20-M-210 | Install Spools - NB 20 SchXST | LM | 2.7761 | 0 | NA | 6.6283 | 1 | 110 | 18.4008 |  | 2024.0833
Proj_A | Area_3 | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch80 | LM | 118.933 | 0 | NA | 7.4941 | 1 | 110 | 891.2996 |  | 98042.9574
Proj_A | Area_3 | Module | 500 | 150-20-M-210 | Install Spools - NB 24 SchXST | LM | 14.2588 | 0 | NA | 7.4941 | 1 | 110 | 106.8577 |  | 11754.3476
Proj_A | Area_3 | Module | 500 | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_3 | Module | 500 | 150-30-M-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_3 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 13 | 0 | NA | 1.69 | 1 | 110 | 21.97 |  | 2416.7
Proj_A | Area_3 | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL600 | EA | 2 | 0 | NA | 11.44 | 1 | 110 | 22.88 |  | 2516.8
Proj_A | Area_3 | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL600 | EA | 1 | 0 | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4
Proj_A | Area_3 | Module | 500 | 150-30-M-310 | Install valve - NB 20 CL600 | EA | 3 | 0 | NA | 15.47 | 1 | 110 | 46.41 |  | 5105.1
Proj_A | Area_3 | Module | 500 | 150-30-M-310 | Install valve - NB 24 CL600 | EA | 1 | 0 | NA | 17.68 | 1 | 110 | 17.68 |  | 1944.8
Proj_A | Area_3 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_3 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3.5 | 0 | NA | 0.91 | 1 | 110 | 3.185 |  | 350.35
Proj_A | Area_3 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 29 | 0 | NA | 1.17 | 1 | 110 | 33.93 |  | 3732.3
Proj_A | Area_3 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 1.5 | 0 | NA | 5.33 | 1 | 110 | 7.995 |  | 879.45
Proj_A | Area_3 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 16.5 | 0 | NA | 6.76 | 1 | 110 | 111.54 |  | 12269.4
Proj_A | Area_3 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 16.5 | 0 | NA | 8.58 | 1 | 110 | 141.57 |  | 15572.7
Proj_A | Area_3 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | EA | 14 | 0 | NA | 10.27 | 1 | 110 | 143.78 |  | 15815.8
Proj_A | Area_3 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 1 | 110 | 2 |  | 220
Proj_A | Area_3 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 15 | 0 | NA | 2.1107 | 1 | 110 | 31.6598 |  | 3482.5735
Proj_A | Area_3 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 0 | NA | 2.327 | 1 | 110 | 13.962 |  | 1535.8149
Proj_A | Area_3 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 20 | 0 | NA | 2.5655 | 1 | 110 | 51.3102 |  | 5644.1199
Proj_A | Area_3 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | EA | 7 | 14 | CS | 1.6003 | 0.75 | 78 | 8.4016 |  | 655.3229
Proj_A | Area_3 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 8 SchSTD | EA | 1 | 8 | CS | 4.2887 | 0.75 | 78 | 3.2165 |  | 250.889
Proj_A | Area_3 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 16 Sch80 | EA | 2 | 32 | CS | 20.3905 | 0.75 | 78 | 30.5858 |  | 2385.6885
Proj_A | Area_3 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 16 SchSTD | EA | 1 | 16 | CS | 11.6532 | 0.75 | 78 | 8.7399 |  | 681.7122
Proj_A | Area_3 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 20 Sch80 | EA | 1 | 20 | CS | 31.2637 | 0.75 | 78 | 23.4478 |  | 1828.9264
Proj_A | Area_3 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 24 Sch80 | EA | 2 | 48 | CS | 40.3455 | 0.75 | 78 | 60.5183 |  | 4720.4235
Proj_A | Area_3 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 2.9085 | 0 | NA | 1.0151 | 0.75 | 78 | 2.2144 |  | 172.7235
Proj_A | Area_3 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 107.338 | 0 | NA | 1.1943 | 0.75 | 78 | 96.144 |  | 7499.2353
Proj_A | Area_3 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 6.0577 | 0 | NA | 1.1644 | 0.75 | 78 | 5.2903 |  | 412.6443
Proj_A | Area_3 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchSTD | LM | 11.9141 | 0 | NA | 1.2241 | 0.75 | 78 | 10.9384 |  | 853.1956
Proj_A | Area_3 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 3.2076 | 0 | NA | 1.7019 | 0.75 | 78 | 4.0942 |  | 319.3438
Proj_A | Area_3 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | LM | 165.517 | 0 | NA | 1.0237 | 0.75 | 78 | 127.0763 |  | 9911.9544
Proj_A | Area_3 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 8 SchSTD | LM | 19.1103 | 0 | NA | 1.4502 | 0.75 | 78 | 20.7853 |  | 1621.257
Proj_A | Area_3 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_3 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 4 | 0 | NA | 0.39 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_3 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 8 | 0 | NA | 0.65 | 0.75 | 78 | 3.9 |  | 304.2
Proj_A | Area_3 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 3 | 0 | NA | 0.65 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_3 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 2 | 0 | NA | 1.56 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_3 | Field | 600 | 150-30-F-310 | Install Blind - NB 8 CL150 | EA | 1 | 0 | NA | 3.64 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_3 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 3 | 0 | NA | 0.91 | 0.75 | 78 | 2.0475 |  | 159.705
Proj_A | Area_3 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_3 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 37.5 | 0 | NA | 0.91 | 0.75 | 78 | 25.5937 |  | 1996.3125
Proj_A | Area_3 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.9488 |  | 308.0025
Proj_A | Area_3 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 5.5 | 0 | NA | 1.04 | 0.75 | 78 | 4.29 |  | 334.62
Proj_A | Area_3 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_3 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | EA | 2.5 | 0 | NA | 1.56 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_3 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 1.5 | 0 | NA | 2.73 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_3 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 80 | 0 | NA | 1 | 0.75 | 78 | 60 |  | 4680
Proj_A | Area_3 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 6 | 0 | NA | 1.5 | 0.75 | 78 | 6.75 |  | 526.5
Proj_A | Area_3 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 3 | 0 | NA | 1.5 | 0.75 | 78 | 3.375 |  | 263.25
Proj_A | Area_3 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 5 | 0 | NA | 1.7364 | 0.75 | 78 | 6.5116 |  | 507.908
Proj_A | Area_3 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 2 | EA | 7 | 0 | NA | 0 | 0.75 | 78 | 0 | 750 | 5250
Proj_A | Area_3 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 8 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500
Proj_A | Area_3 | Field | 300 | 150-80-F-810 | Field Coating - NB 2 | LM | 165.517 | 0 | CS | 0 | 0.75 | 78 | 0 | 60 | 9931.02
Proj_A | Area_3 | Field | 300 | 150-80-F-810 | Field Coating - NB 8 | LM | 19.1103 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 2293.236
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 326 | 652 | CS | 1.1765 | 1 | 110 | 383.539 |  | 42189.29
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 6 | 18 | CS | 1.586 | 1 | 110 | 9.516 |  | 1046.76
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 24 | 336 | CS | 10.2115 | 1 | 110 | 245.076 |  | 26958.36
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 42 | 672 | CS | 14.365 | 1 | 110 | 603.33 |  | 66366.3
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 60 | 1200 | CS | 21.7588 | 1 | 110 | 1305.525 |  | 143607.75
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 14 | 10.5 | CS | 0.65 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 10 | 7.5 | CS | 0.65 | 1 | 110 | 6.5 |  | 715
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 15 | 11.25 | CS | 0.78 | 1 | 110 | 11.7 |  | 1287
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 15 | 11.25 | CS | 0.78 | 1 | 110 | 11.7 |  | 1287
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 66 | 66 | CS | 0.78 | 1 | 110 | 51.48 |  | 5662.8
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 123 | 123 | CS | 0.78 | 1 | 110 | 95.94 |  | 10553.4
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 57 | 57 | CS | 0.91 | 1 | 110 | 51.87 |  | 5705.7
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 192 | 192 | CS | 0.91 | 1 | 110 | 174.72 |  | 19219.2
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 22 | 44 | CS | 1.69 | 1 | 110 | 37.18 |  | 4089.8
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 3 | 9 | CS | 2.21 | 1 | 110 | 6.63 |  | 729.3
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 6 | 4.5 | CS | 2.47 | 1 | 110 | 14.82 |  | 1630.2
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 3 | 3 | CS | 3.77 | 1 | 110 | 11.31 |  | 1244.1
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 34 | 68 | CS | 5.46 | 1 | 110 | 185.64 |  | 20420.4
Proj_A | Area_4 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 3 | 9 | CS | 7.67 | 1 | 110 | 23.01 |  | 2531.1
Proj_A | Area_4 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 12 | 6 | NA | 0.26 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_4 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 14 | 10.5 | NA | 0.26 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 8 | 6 | NA | 0.26 | 1 | 110 | 2.08 |  | 228.8
Proj_A | Area_4 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 18 | 18 | NA | 0.39 | 1 | 110 | 7.02 |  | 772.2
Proj_A | Area_4 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 26 | 26 | NA | 0.39 | 1 | 110 | 10.14 |  | 1115.4
Proj_A | Area_4 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 14 | 14 | NA | 0.39 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_4 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 6 | 12 | NA | 0.429 | 1 | 110 | 2.574 |  | 283.14
Proj_A | Area_4 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 14.96 | 0 | NA | 0.17914 | 1 | 110 | 2.68 |  | 294.7971
Proj_A | Area_4 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 80.648 | 0 | NA | 0.18767 | 1 | 110 | 15.1355 |  | 1664.9015
Proj_A | Area_4 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 16.032 | 0 | NA | 0.67818 | 1 | 110 | 10.8726 |  | 1195.9888
Proj_A | Area_4 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 7.728 | 0 | NA | 0.79335 | 1 | 110 | 6.131 |  | 674.4074
Proj_A | Area_4 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 51.138 | 0 | NA | 1.0279 | 1 | 110 | 52.5667 |  | 5782.3323
Proj_A | Area_4 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 30 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1500
Proj_A | Area_4 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 67 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 3350
Proj_A | Area_4 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1500
Proj_A | Area_4 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2250
Proj_A | Area_4 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 202 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 10100
Proj_A | Area_4 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 3000
Proj_A | Area_4 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 7 | 0 | NA | 5.6 | 1 | 110 | 39.2 |  | 4312
Proj_A | Area_4 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 6 | 0 | NA | 41.2 | 1 | 110 | 247.2 |  | 27192
Proj_A | Area_4 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 7 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 3500
Proj_A | Area_4 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 16200
Proj_A | Area_4 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 15.708 | 0 | NA | 1.1644 | 0.75 | 78 | 13.7181 |  | 1070.0128
Proj_A | Area_4 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 88.7128 | 0 | NA | 1.1943 | 0.75 | 78 | 79.4612 |  | 6197.9742
Proj_A | Area_4 | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 18.4368 | 0 | NA | 4.3591 | 0.75 | 78 | 60.2764 |  | 4701.559
Proj_A | Area_4 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 8.8872 | 0 | NA | 5.1056 | 0.75 | 78 | 34.0306 |  | 2654.3889
Proj_A | Area_4 | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 58.8087 | 0 | NA | 6.6283 | 0.75 | 78 | 292.3502 |  | 22803.3179
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 14 | 0 | NA | 0.65 | 0.75 | 78 | 6.825 |  | 532.35
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 42 | 0 | NA | 0.78 | 0.75 | 78 | 24.57 |  | 1916.46
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 6 | 0 | NA | 0.78 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 4 | 0 | NA | 0.91 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 37 | 0 | NA | 1.69 | 0.75 | 78 | 46.8975 |  | 3658.005
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install Inlines - NB 16 CL600 | EA | 6 | 0 | NA | 11.44 | 0.75 | 78 | 51.48 |  | 4015.44
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 6 | 0 | NA | 15.47 | 0.75 | 78 | 69.615 |  | 5429.97
Proj_A | Area_4 | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 6 | 0 | NA | 15.47 | 0.75 | 78 | 69.615 |  | 5429.97
Proj_A | Area_4 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 4.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.9488 |  | 308.0025
Proj_A | Area_4 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 45.5 | 0 | NA | 1.17 | 0.75 | 78 | 39.9262 |  | 3114.2475
Proj_A | Area_4 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 18 | 0 | NA | 0.91 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_4 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 70 | 0 | NA | 1.17 | 0.75 | 78 | 61.425 |  | 4791.15
Proj_A | Area_4 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 1.5 | 0 | NA | 1.3 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_4 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 9 | 0 | NA | 5.98 | 0.75 | 78 | 40.365 |  | 3148.47
Proj_A | Area_4 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 15 | 0 | NA | 6.76 | 0.75 | 78 | 76.05 |  | 5931.9
Proj_A | Area_4 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 15 | 0 | NA | 8.58 | 0.75 | 78 | 96.525 |  | 7528.95
Proj_A | Area_4 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 14 | 0 | NA | 0.4 | 0.75 | 78 | 4.2 |  | 327.6
Proj_A | Area_4 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 27 | 0 | NA | 1 | 0.75 | 78 | 20.25 |  | 1579.5
Proj_A | Area_4 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 6 | 0 | NA | 2.0101 | 0.75 | 78 | 9.0456 |  | 705.5604
Proj_A | Area_4 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 7 | 0 | NA | 2.1107 | 0.75 | 78 | 11.0809 |  | 864.3114
Proj_A | Area_4 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 0 | NA | 2.327 | 0.75 | 78 | 10.4715 |  | 816.7743
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 169 | 338 | CS | 1.1765 | 1 | 110 | 198.8285 |  | 21871.135
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 18 | CS | 1.3715 | 1 | 110 | 8.229 |  | 905.19
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 6 | 18 | CS | 1.586 | 1 | 110 | 9.516 |  | 1046.76
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 32 | 192 | CS | 2.9315 | 1 | 110 | 93.808 |  | 10318.88
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 28 | 224 | CS | 3.848 | 1 | 110 | 107.744 |  | 11851.84
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 34 | 408 | CS | 7.683 | 1 | 110 | 261.222 |  | 28734.42
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 7 | 5.25 | CS | 0.78 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 23 | 23 | CS | 0.78 | 1 | 110 | 17.94 |  | 1973.4
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 6 | 6 | CS | 0.91 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 38 | 38 | CS | 0.91 | 1 | 110 | 34.58 |  | 3803.8
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 7 | 14 | CS | 1.69 | 1 | 110 | 11.83 |  | 1301.3
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 2 | 6 | CS | 2.21 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 17 | 34 | CS | 5.46 | 1 | 110 | 92.82 |  | 10210.2
Proj_A | Area_5 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 2 | 6 | CS | 7.67 | 1 | 110 | 15.34 |  | 1687.4
Proj_A | Area_5 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_5 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_5 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_5 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_5 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.508 | 0 | NA | 0.17914 | 1 | 110 | 0.27015 |  | 29.7162
Proj_A | Area_5 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 19.85 | 0 | NA | 0.18767 | 1 | 110 | 3.7253 |  | 409.7844
Proj_A | Area_5 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 5.618 | 0 | NA | 0.17488 | 1 | 110 | 0.98246 |  | 108.0707
Proj_A | Area_5 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 13.406 | 0 | NA | 0.29857 | 1 | 110 | 4.0026 |  | 440.2907
Proj_A | Area_5 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 11.814 | 0 | NA | 0.37535 | 1 | 110 | 4.4343 |  | 487.7777
Proj_A | Area_5 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 14.108 | 0 | NA | 0.57155 | 1 | 110 | 8.0634 |  | 886.9773
Proj_A | Area_5 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 13 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 650
Proj_A | Area_5 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1250
Proj_A | Area_5 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 36 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1800
Proj_A | Area_5 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_5 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 375
Proj_A | Area_5 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 600
Proj_A | Area_5 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_5 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_5 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_5 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchXST | EA | 2 | 0 | NA | 16 | 1 | 110 | 32 |  | 3520
Proj_A | Area_5 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 0 | NA | 19 | 1 | 110 | 19 |  | 2090
Proj_A | Area_5 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_5 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_5 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_5 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 2200
Proj_A | Area_5 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_5 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.5834 | 0 | NA | 1.1644 | 0.75 | 78 | 1.3828 |  | 107.8596
Proj_A | Area_5 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 21.835 | 0 | NA | 1.1943 | 0.75 | 78 | 19.5579 |  | 1525.5157
Proj_A | Area_5 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 6.1798 | 0 | NA | 1.1644 | 0.75 | 78 | 5.3969 |  | 420.9616
Proj_A | Area_5 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 14.7466 | 0 | NA | 1.9109 | 0.75 | 78 | 21.134 |  | 1648.4484
Proj_A | Area_5 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 12.9954 | 0 | NA | 2.4184 | 0.75 | 78 | 23.5713 |  | 1838.5615
Proj_A | Area_5 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 16.2242 | 0 | NA | 3.6724 | 0.75 | 78 | 44.6866 |  | 3485.5546
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 7 | 0 | NA | 0.78 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install Inlines - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 12 | 0 | NA | 1.69 | 0.75 | 78 | 15.21 |  | 1186.38
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_5 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 4 | 0 | NA | 5.46 | 0.75 | 78 | 16.38 |  | 1277.64
Proj_A | Area_5 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_5 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 6.5 | 0 | NA | 1.17 | 0.75 | 78 | 5.7038 |  | 444.8925
Proj_A | Area_5 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.7062 |  | 133.0875
Proj_A | Area_5 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 46 | 0 | NA | 1.17 | 0.75 | 78 | 40.365 |  | 3148.47
Proj_A | Area_5 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 2 | 0 | NA | 1.3 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_5 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 9.5 | 0 | NA | 2.34 | 0.75 | 78 | 16.6725 |  | 1300.455
Proj_A | Area_5 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 12 | 0 | NA | 3.38 | 0.75 | 78 | 30.42 |  | 2372.76
Proj_A | Area_5 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 6 | 0 | NA | 5.33 | 0.75 | 78 | 23.985 |  | 1870.83
Proj_A | Area_5 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_5 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 7 | 0 | NA | 1 | 0.75 | 78 | 5.25 |  | 409.5
Proj_A | Area_5 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 4 | 0 | NA | 1.6538 | 0.75 | 78 | 4.9613 |  | 386.9775
Proj_A | Area_5 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 4 | 0 | NA | 1.7364 | 0.75 | 78 | 5.2093 |  | 406.3264
Proj_A | Area_5 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | NA | 1.9144 | 0.75 | 78 | 4.3075 |  | 335.9811
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 80 | 160 | CS | 1.1765 | 1 | 110 | 94.12 |  | 10353.2
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 8 | 48 | CS | 2.9315 | 1 | 110 | 23.452 |  | 2579.72
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 168 | CS | 7.683 | 1 | 110 | 107.562 |  | 11831.82
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 6 | 4.5 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 14 | 14 | CS | 0.78 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 26 | 26 | CS | 0.78 | 1 | 110 | 20.28 |  | 2230.8
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 12 | 12 | CS | 0.91 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 41 | 41 | CS | 0.91 | 1 | 110 | 37.31 |  | 4104.1
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 5 | 10 | CS | 1.69 | 1 | 110 | 8.45 |  | 929.5
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 2.86 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_6 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_6 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_6 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_6 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_6 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 9 | 9 | NA | 0.39 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_6 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_6 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.23 | 0 | NA | 0.17914 | 1 | 110 | 0.39949 |  | 43.9437
Proj_A | Area_6 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 18.974 | 0 | NA | 0.18767 | 1 | 110 | 3.5609 |  | 391.7002
Proj_A | Area_6 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 9.587 | 0 | NA | 0.29857 | 1 | 110 | 2.8624 |  | 314.864
Proj_A | Area_6 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 14.374 | 0 | NA | 0.57155 | 1 | 110 | 8.2155 |  | 903.7009
Proj_A | Area_6 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 19 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 950
Proj_A | Area_6 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_6 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 22 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1100
Proj_A | Area_6 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_6 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_6 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_6 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 2 | 0 | NA | 19 | 1 | 110 | 38 |  | 4180
Proj_A | Area_6 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_6 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_6 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 3400
Proj_A | Area_6 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.3415 | 0 | NA | 1.1644 | 0.75 | 78 | 2.0449 |  | 159.5006
Proj_A | Area_6 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 20.8714 | 0 | NA | 1.1943 | 0.75 | 78 | 18.6948 |  | 1458.1932
Proj_A | Area_6 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 10.5457 | 0 | NA | 1.9109 | 0.75 | 78 | 15.1135 |  | 1178.8509
Proj_A | Area_6 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 16.5301 | 0 | NA | 3.6724 | 0.75 | 78 | 45.5291 |  | 3551.2732
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 3 | 0 | NA | 0.39 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 8 | 0 | NA | 0.78 | 0.75 | 78 | 4.68 |  | 365.04
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 6 | 0 | NA | 1.69 | 0.75 | 78 | 7.605 |  | 593.19
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 1 | 0 | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_6 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 3 | 0 | NA | 8.19 | 0.75 | 78 | 18.4275 |  | 1437.345
Proj_A | Area_6 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 8.5 | 0 | NA | 1.17 | 0.75 | 78 | 7.4587 |  | 581.7825
Proj_A | Area_6 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 4.5 | 0 | NA | 0.91 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_6 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 18 | 0 | NA | 1.17 | 0.75 | 78 | 15.795 |  | 1232.01
Proj_A | Area_6 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | NA | 2.34 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_6 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 7 | 0 | NA | 5.33 | 0.75 | 78 | 27.9825 |  | 2182.635
Proj_A | Area_6 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_6 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | NA | 1 | 0.75 | 78 | 3.75 |  | 292.5
Proj_A | Area_6 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 1 | 0 | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 150 | 300 | CS | 1.1765 | 1 | 110 | 176.475 |  | 19412.25
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 12 | CS | 1.3715 | 1 | 110 | 5.486 |  | 603.46
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 32 | 192 | CS | 2.9315 | 1 | 110 | 93.808 |  | 10318.88
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 28 | 224 | CS | 3.848 | 1 | 110 | 107.744 |  | 11851.84
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 32 | 384 | CS | 7.683 | 1 | 110 | 245.856 |  | 27044.16
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 6 | 4.5 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 18 | 18 | CS | 0.78 | 1 | 110 | 14.04 |  | 1544.4
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 36 | 36 | CS | 0.78 | 1 | 110 | 28.08 |  | 3088.8
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 24 | 24 | CS | 0.91 | 1 | 110 | 21.84 |  | 2402.4
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 42 | 42 | CS | 0.91 | 1 | 110 | 38.22 |  | 4204.2
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 6 | 12 | CS | 1.69 | 1 | 110 | 10.14 |  | 1115.4
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 2.86 | 1 | 110 | 17.16 |  | 1887.6
Proj_A | Area_7 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 20 | 40 | CS | 5.46 | 1 | 110 | 109.2 |  | 12012
Proj_A | Area_7 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 4 | 2 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_7 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_7 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_7 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_7 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_7 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 3.868 | 0 | NA | 0.17914 | 1 | 110 | 0.69292 |  | 76.2216
Proj_A | Area_7 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 36.259 | 0 | NA | 0.18767 | 1 | 110 | 6.8048 |  | 748.5327
Proj_A | Area_7 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 8.919 | 0 | NA | 0.29857 | 1 | 110 | 2.663 |  | 292.925
Proj_A | Area_7 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 10.198 | 0 | NA | 0.37535 | 1 | 110 | 3.8278 |  | 421.0561
Proj_A | Area_7 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 9.129 | 0 | NA | 0.57155 | 1 | 110 | 5.2177 |  | 573.945
Proj_A | Area_7 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 45 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2250
Proj_A | Area_7 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1250
Proj_A | Area_7 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 107 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 5350
Proj_A | Area_7 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_7 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 375
Proj_A | Area_7 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 600
Proj_A | Area_7 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 0 | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
Proj_A | Area_7 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_7 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 0 | NA | 19 | 1 | 110 | 19 |  | 2090
Proj_A | Area_7 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1000
Proj_A | Area_7 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_7 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_7 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 4.0614 | 0 | NA | 1.1644 | 0.75 | 78 | 3.5469 |  | 276.6584
Proj_A | Area_7 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 39.8849 | 0 | NA | 1.1943 | 0.75 | 78 | 35.7254 |  | 2786.583
Proj_A | Area_7 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 9.8109 | 0 | NA | 1.9109 | 0.75 | 78 | 14.0604 |  | 1096.7113
Proj_A | Area_7 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 11.2178 | 0 | NA | 2.4184 | 0.75 | 78 | 20.3471 |  | 1587.0704
Proj_A | Area_7 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 10.4983 | 0 | NA | 3.6724 | 0.75 | 78 | 28.9158 |  | 2255.4315
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 12 | 0 | NA | 0.78 | 0.75 | 78 | 7.02 |  | 547.56
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 14 | 0 | NA | 1.69 | 0.75 | 78 | 17.745 |  | 1384.11
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install Inlines - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_7 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 4 | 0 | NA | 5.46 | 0.75 | 78 | 16.38 |  | 1277.64
Proj_A | Area_7 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 9 | 0 | NA | 1.17 | 0.75 | 78 | 7.8975 |  | 616.005
Proj_A | Area_7 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 7.5 | 0 | NA | 0.91 | 0.75 | 78 | 5.1187 |  | 399.2625
Proj_A | Area_7 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 31 | 0 | NA | 1.17 | 0.75 | 78 | 27.2025 |  | 2121.795
Proj_A | Area_7 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_7 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 9.5 | 0 | NA | 2.34 | 0.75 | 78 | 16.6725 |  | 1300.455
Proj_A | Area_7 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 14 | 0 | NA | 3.38 | 0.75 | 78 | 35.49 |  | 2768.22
Proj_A | Area_7 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 6 | 0 | NA | 5.33 | 0.75 | 78 | 23.985 |  | 1870.83
Proj_A | Area_7 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_7 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 15 | 0 | NA | 1 | 0.75 | 78 | 11.25 |  | 877.5
Proj_A | Area_7 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 2 | 0 | NA | 1.6538 | 0.75 | 78 | 2.4806 |  | 193.4888
Proj_A | Area_7 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 6 | 0 | NA | 1.7364 | 0.75 | 78 | 7.814 |  | 609.4896
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 124 | 248 | CS | 1.1765 | 1 | 110 | 145.886 |  | 16047.46
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 18 | 108 | CS | 2.9315 | 1 | 110 | 52.767 |  | 5804.37
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 32 | CS | 3.848 | 1 | 110 | 15.392 |  | 1693.12
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 18 | 216 | CS | 7.683 | 1 | 110 | 138.294 |  | 15212.34
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 96 | CS | 4.7255 | 1 | 110 | 37.804 |  | 4158.44
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 3 | 2.25 | CS | 0.65 | 1 | 110 | 1.95 |  | 214.5
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 6 | 4.5 | CS | 0.65 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 5 | 3.75 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 9 | 6.75 | CS | 0.78 | 1 | 110 | 7.02 |  | 772.2
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 7 | 7 | CS | 0.78 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 20 | 20 | CS | 0.78 | 1 | 110 | 15.6 |  | 1716
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 57 | 57 | CS | 0.78 | 1 | 110 | 44.46 |  | 4890.6
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 45 | 45 | CS | 0.91 | 1 | 110 | 40.95 |  | 4504.5
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 60 | 60 | CS | 0.91 | 1 | 110 | 54.6 |  | 6006
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.17 | 1 | 110 | 7.02 |  | 772.2
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 5 | 10 | CS | 4.42 | 1 | 110 | 22.1 |  | 2431
Proj_A | Area_8 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 3 | 1.5 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 3 | 2.25 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 6 | 4.5 | NA | 0.26 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 9 | 6.75 | NA | 0.26 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 10 | 10 | NA | 0.39 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_8 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.758 | 0 | NA | 0.17914 | 1 | 110 | 0.49408 |  | 54.3483
Proj_A | Area_8 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 2.752 | 0 | NA | 0.15355 | 1 | 110 | 0.42257 |  | 46.4829
Proj_A | Area_8 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 21.675 | 0 | NA | 0.18767 | 1 | 110 | 4.0678 |  | 447.4598
Proj_A | Area_8 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 8.906 | 0 | NA | 0.29857 | 1 | 110 | 2.6591 |  | 292.4981
Proj_A | Area_8 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 2.912 | 0 | NA | 0.57155 | 1 | 110 | 1.6644 |  | 183.079
Proj_A | Area_8 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 1.63 | 0 | NA | 0.40947 | 1 | 110 | 0.66743 |  | 73.4178
Proj_A | Area_8 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_8 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 85 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 4250
Proj_A | Area_8 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 11 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2750
Proj_A | Area_8 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 91 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 4550
Proj_A | Area_8 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 225
Proj_A | Area_8 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_8 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_8 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_8 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_8 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.8959 | 0 | NA | 1.1644 | 0.75 | 78 | 2.529 |  | 197.2657
Proj_A | Area_8 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 2.8896 | 0 | NA | 1.0151 | 0.75 | 78 | 2.2 |  | 171.6011
Proj_A | Area_8 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 23.8425 | 0 | NA | 1.1943 | 0.75 | 78 | 21.356 |  | 1665.7709
Proj_A | Area_8 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 9.7966 | 0 | NA | 1.9109 | 0.75 | 78 | 14.0399 |  | 1095.1128
Proj_A | Area_8 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 3.3488 | 0 | NA | 3.6724 | 0.75 | 78 | 9.2237 |  | 719.4454
Proj_A | Area_8 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 1.8745 | 0 | NA | 2.6274 | 0.75 | 78 | 3.6938 |  | 288.1188
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 3 | 0 | NA | 0.39 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 6 | 0 | NA | 0.65 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 4 | 0 | NA | 0.39 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 11 | 0 | NA | 0.78 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 4 | 0 | NA | 0.91 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 5 | 0 | NA | 0.65 | 0.75 | 78 | 2.4375 |  | 190.125
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 6 | 0 | NA | 1.69 | 0.75 | 78 | 7.605 |  | 593.19
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 3 | 0 | NA | 4.29 | 0.75 | 78 | 9.6525 |  | 752.895
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 1 | 0 | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_8 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 5 | 0 | NA | 8.19 | 0.75 | 78 | 30.7125 |  | 2395.575
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 5.5 | 0 | NA | 0.91 | 0.75 | 78 | 3.7538 |  | 292.7925
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 10.5 | 0 | NA | 1.17 | 0.75 | 78 | 9.2138 |  | 718.6725
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 12.5 | 0 | NA | 0.91 | 0.75 | 78 | 8.5312 |  | 665.4375
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 13.5 | 0 | NA | 1.17 | 0.75 | 78 | 11.8463 |  | 924.0075
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 6.5 | 0 | NA | 2.34 | 0.75 | 78 | 11.4075 |  | 889.785
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 2 | 0 | NA | 3.38 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 0.5 | 0 | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
Proj_A | Area_8 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 9.5 | 0 | NA | 5.33 | 0.75 | 78 | 37.9763 |  | 2962.1475
Proj_A | Area_8 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 8 | 0 | NA | 0.4 | 0.75 | 78 | 2.4 |  | 187.2
Proj_A | Area_8 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 12 | 0 | NA | 1 | 0.75 | 78 | 9 |  | 702
Proj_A | Area_8 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | NA | 1.9144 | 0.75 | 78 | 2.8716 |  | 223.9874
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.781 | 1 | 110 | 1.781 |  | 195.91
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 33 | 66 | CS | 1.1765 | 1 | 110 | 38.8245 |  | 4270.695
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 42 | 126 | CS | 1.3715 | 1 | 110 | 57.603 |  | 6336.33
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 30 | 180 | CS | 2.431 | 1 | 110 | 72.93 |  | 8022.3
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 1 | 1.5 | CS | 1.3 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 1 | 1.5 | CS | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_9 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.17 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_9 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_9 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_9 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_9 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 21.409 | 0 | NA | 0.18767 | 1 | 110 | 4.0179 |  | 441.9685
Proj_A | Area_9 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 28.447 | 0 | NA | 0.17488 | 1 | 110 | 4.9747 |  | 547.2208
Proj_A | Area_9 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchSTD | LM | 11.731 | 0 | NA | 0.21753 | 1 | 110 | 2.5518 |  | 280.7033
Proj_A | Area_9 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_9 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_9 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_9 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 37 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1850
Proj_A | Area_9 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 42 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2100
Proj_A | Area_9 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 30 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 2250
Proj_A | Area_9 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 3 | 0 | NA | 5.6 | 1 | 110 | 16.8 |  | 1848
Proj_A | Area_9 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 3 | 0 | NA | 6 | 1 | 110 | 18 |  | 1980
Proj_A | Area_9 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchSTD | EA | 1 | 0 | NA | 8.8 | 1 | 110 | 8.8 |  | 968
Proj_A | Area_9 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1500
Proj_A | Area_9 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 1800
Proj_A | Area_9 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_9 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchSTD | EA | 1 | 6 | CS | 3.3501 | 0.75 | 78 | 2.5126 |  | 195.9809
Proj_A | Area_9 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 23.5499 | 0 | NA | 1.1943 | 0.75 | 78 | 21.094 |  | 1645.3282
Proj_A | Area_9 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 31.2917 | 0 | NA | 1.1644 | 0.75 | 78 | 27.3277 |  | 2131.5585
Proj_A | Area_9 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchSTD | LM | 12.9041 | 0 | NA | 1.4033 | 0.75 | 78 | 13.5811 |  | 1059.3246
Proj_A | Area_9 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | LM | 64.1047 | 0 | NA | 1.1943 | 0.75 | 78 | 57.4194 |  | 4478.7142
Proj_A | Area_9 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_9 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_9 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_9 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 7 | 0 | NA | 0.65 | 0.75 | 78 | 3.4125 |  | 266.175
Proj_A | Area_9 | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_9 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 2 | 0 | NA | 1.56 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_9 | Field | 600 | 150-30-F-310 | Install Blind - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_9 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_9 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_9 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 14 | 0 | NA | 0.91 | 0.75 | 78 | 9.555 |  | 745.29
Proj_A | Area_9 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 12.5 | 0 | NA | 1.04 | 0.75 | 78 | 9.75 |  | 760.5
Proj_A | Area_9 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 7 | 0 | NA | 1.95 | 0.75 | 78 | 10.2375 |  | 798.525
Proj_A | Area_9 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 9 | 0 | NA | 1 | 0.75 | 78 | 6.75 |  | 526.5
Proj_A | Area_9 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 13 | 0 | NA | 1.5 | 0.75 | 78 | 14.625 |  | 1140.75
Proj_A | Area_9 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 8 | 0 | NA | 1.6538 | 0.75 | 78 | 9.9225 |  | 773.955
Proj_A | Area_9 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1000 | 1000
Proj_A | Area_9 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 64.1047 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 6410.47
Summary | Summary | Spool Fabrication | 400 | 150-50-S-510 | Pipe Supports Labor (shoes, lugs, guides, etc.) | of Labor hours | 0.05 | 0 |  | 0 | 0 | 0 | 963.9511 |  | 106034.6258
Summary | Summary | Module | 500 | 150-70-F-710 | Hydrotest of module assembly | of Module Labor | 0.05 | 0 |  | 0 | 0 | 0 | 230.2252 |  | 25324.7765
Summary | Summary | Module | 500 | 150-90-F-910 | Flushing & Drying Module Piping | of Module Labor | 0.03 | 0 |  | 0 | 0 | 0 | 138.1351 |  | 15194.8659
Summary | Summary | Field | 600 | 150-40-F-410 | Bolt torquing and tensioning | of bolt-up labor | 0.15 | 0 |  | 0 | 0 | 0 | 198.3296 |  | 15469.7108
Summary | Summary | Field | 600 | 150-70-F-710 | Field Hydrotest | of Field Labor | 0.05 | 0 |  | 0 | 0 | 0 | 285.076 |  | 22235.93
Summary | Summary | Field | 600 | 150-90-F-910 | Flushing & Drying on Site | of Field Labor | 0.03 | 0 |  | 0 | 0 | 0 | 171.0456 |  | 13341.558
Area Level Summary (Also WBS2 Summary in the Example Project)
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## WBS3-Summary By Service
WBS1 | WBS2 | WBS3 | Location | CBS | COA | Description | Units | Quantity | Dia-Inch | Material | STD_UNIT_HR | PF | WR | Location Hours | S/C Rate_$ | Total Cost
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 40 | 80 | CS | 1.1765 | 1 | 110 | 47.06 |  | 5176.6
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 16 | 16 | CS | 0.91 | 1 | 110 | 14.56 |  | 1601.6
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.32 | 0 | NA | 0.17914 | 1 | 110 | 0.41561 |  | 45.7172
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 10.477 | 0 | NA | 0.18767 | 1 | 110 | 1.9663 |  | 216.2877
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 14 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 700
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 33 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1650
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_1 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_1 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.436 | 0 | NA | 1.1644 | 0.75 | 78 | 2.1274 |  | 165.9378
Proj_A | Area_1 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 11.5247 | 0 | NA | 1.1943 | 0.75 | 78 | 10.3228 |  | 805.1802
Proj_A | Area_1 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_1 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 4 | 0 | NA | 0.39 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_1 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 6 | 0 | NA | 0.78 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_1 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_1 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | NA | 1.17 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_1 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_1 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | NA | 1 | 0.75 | 78 | 3 |  | 234
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 15 | 45 | CS | 1.3715 | 1 | 110 | 20.5725 |  | 2262.975
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 14.149 | 0 | NA | 0.17488 | 1 | 110 | 2.4743 |  | 272.1773
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 15 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 750
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_1 | FL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_1 | FL | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 15.5639 | 0 | NA | 1.1644 | 0.75 | 78 | 13.5923 |  | 1060.1969
Proj_A | Area_1 | FL | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL300 | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_1 | FL | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_1 | FL | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_1 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_1 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_1 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 1.5 | 0 | NA | 1.04 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_1 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_1 | FL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 5 | 0 | NA | 1.5 | 0.75 | 78 | 5.625 |  | 438.75
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 28 | 112 | CS | 2.119 | 1 | 110 | 59.332 |  | 6526.52
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 12 | 12 | CS | 0.91 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.079 | 0 | NA | 0.18767 | 1 | 110 | 0.2025 |  | 22.2749
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 8.645 | 0 | NA | 0.24739 | 1 | 110 | 2.1387 |  | 235.253
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 1 | 0 | NA | 8.4 | 1 | 110 | 8.4 |  | 924
Proj_A | Area_1 | GH | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 700
Proj_A | Area_1 | GH | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1869 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0631 |  | 82.9235
Proj_A | Area_1 | GH | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 9.5095 | 0 | NA | 1.5526 | 0.75 | 78 | 11.0731 |  | 863.7032
Proj_A | Area_1 | GH | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | LM | 15.3076 | 0 | NA | 1.3222 | 0.75 | 78 | 15.1803 |  | 1184.0615
Proj_A | Area_1 | GH | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | GH | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_1 | GH | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 3 | 0 | NA | 1.69 | 0.75 | 78 | 3.8025 |  | 296.595
Proj_A | Area_1 | GH | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_1 | GH | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 5.5 | 0 | NA | 1.17 | 0.75 | 78 | 4.8263 |  | 376.4475
Proj_A | Area_1 | GH | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 4 | 0 | NA | 1.95 | 0.75 | 78 | 5.85 |  | 456.3
Proj_A | Area_1 | GH | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 7 | 0 | NA | 1.5 | 0.75 | 78 | 7.875 |  | 614.25
Proj_A | Area_1 | GH | Field | 300 | 150-80-F-810 | Field Coating - NB 4 | LM | 15.3076 | 0 | CS | 0 | 0.75 | 78 | 0 | 80 | 1224.608
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.585 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 14 | 28 | CS | 1.1765 | 1 | 110 | 16.471 |  | 1811.81
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 62 | 248 | CS | 2.119 | 1 | 110 | 131.378 |  | 14451.58
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 12 | 72 | CS | 2.9315 | 1 | 110 | 35.178 |  | 3869.58
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 40 | 400 | CS | 5.915 | 1 | 110 | 236.6 |  | 26026
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 2 | 2 | CS | 3.77 | 1 | 110 | 7.54 |  | 829.4
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 7 | 14 | CS | 5.46 | 1 | 110 | 38.22 |  | 4204.2
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 67.034 | 0 | NA | 0.24739 | 1 | 110 | 16.5834 |  | 1824.1704
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 3.149 | 0 | NA | 0.29857 | 1 | 110 | 0.9402 |  | 103.422
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 34.345 | 0 | NA | 0.46918 | 1 | 110 | 16.1141 |  | 1772.5499
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1750
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 11 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 550
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 150
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 6 | 0 | NA | 8.4 | 1 | 110 | 50.4 |  | 5544
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | EA | 5 | 0 | NA | 14.6 | 1 | 110 | 73 |  | 8030
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 4200
Proj_A | Area_1 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 10 | EA | 5 | 0 | CS | 0 | 1 | 110 | 0 | 1500 | 7500
Proj_A | Area_1 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 73.7374 | 0 | NA | 1.5526 | 0.75 | 78 | 85.8618 |  | 6697.2213
Proj_A | Area_1 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 3.4639 | 0 | NA | 1.9109 | 0.75 | 78 | 4.9643 |  | 387.212
Proj_A | Area_1 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 39.4967 | 0 | NA | 2.9857 | 0.75 | 78 | 88.4444 |  | 6898.6617
Proj_A | Area_1 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 2 | 0 | NA | 0.78 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_1 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 4 | 0 | NA | 1.69 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_1 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 6 | 0 | NA | 3.38 | 0.75 | 78 | 15.21 |  | 1186.38
Proj_A | Area_1 | HPG | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 6 | 0 | NA | 3.38 | 0.75 | 78 | 15.21 |  | 1186.38
Proj_A | Area_1 | HPG | Field | 600 | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 2 | 0 | NA | 6.63 | 0.75 | 78 | 9.945 |  | 775.71
Proj_A | Area_1 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 3 | 0 | NA | 6.63 | 0.75 | 78 | 14.9175 |  | 1163.565
Proj_A | Area_1 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 5 | 0 | NA | 1.17 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_1 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 8.5 | 0 | NA | 1.17 | 0.75 | 78 | 7.4588 |  | 581.7825
Proj_A | Area_1 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 23 | 0 | NA | 1.95 | 0.75 | 78 | 33.6375 |  | 2623.725
Proj_A | Area_1 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 1 | 0 | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 9 | 0 | NA | 4.16 | 0.75 | 78 | 28.08 |  | 2190.24
Proj_A | Area_1 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 11 | 0 | NA | 1.5 | 0.75 | 78 | 12.375 |  | 965.25
Proj_A | Area_1 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 13 | 0 | NA | 1.8233 | 0.75 | 78 | 17.7768 |  | 1386.5888
Proj_A | Area_1 | IA | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 10 | CS | 1.1765 | 1 | 110 | 5.8825 |  | 647.075
Proj_A | Area_1 | IA | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 3.967 | 0 | NA | 0.18767 | 1 | 110 | 0.7445 |  | 81.895
Proj_A | Area_1 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_1 | IA | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 4.3637 | 0 | NA | 1.1943 | 0.75 | 78 | 3.9086 |  | 304.8726
Proj_A | Area_1 | IA | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | IA | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.7062 |  | 133.0875
Proj_A | Area_1 | IA | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 32 | 128 | CS | 2.119 | 1 | 110 | 67.808 |  | 7458.88
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 100 | 600 | CS | 2.9315 | 1 | 110 | 293.15 |  | 32246.5
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 6 | 6 | CS | 0.91 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 16 | 16 | CS | 0.91 | 1 | 110 | 14.56 |  | 1601.6
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 2 | 2 | CS | 3.77 | 1 | 110 | 7.54 |  | 829.4
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.079 | 0 | NA | 0.18767 | 1 | 110 | 0.2025 |  | 22.2749
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 9.748 | 0 | NA | 0.24739 | 1 | 110 | 2.4115 |  | 265.2686
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 77.387 | 0 | NA | 0.29857 | 1 | 110 | 23.1055 |  | 2541.6065
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 14 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 1050
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 1 | 0 | NA | 8.4 | 1 | 110 | 8.4 |  | 924
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 9 | 0 | NA | 12 | 1 | 110 | 108 |  | 11880
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 700
Proj_A | Area_1 | LG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 9 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 8100
Proj_A | Area_1 | LG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 4 SchXST | EA | 1 | 4 | CS | 2.99 | 0.75 | 78 | 2.2425 |  | 174.915
Proj_A | Area_1 | LG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 7 | 42 | CS | 4.2237 | 0.75 | 78 | 22.1744 |  | 1729.6051
Proj_A | Area_1 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1869 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0631 |  | 82.9235
Proj_A | Area_1 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 10.7228 | 0 | NA | 1.5526 | 0.75 | 78 | 12.4859 |  | 973.9015
Proj_A | Area_1 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 85.1257 | 0 | NA | 1.9109 | 0.75 | 78 | 121.9971 |  | 9515.7749
Proj_A | Area_1 | LG | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | LM | 16.8509 | 0 | NA | 1.3222 | 0.75 | 78 | 16.7107 |  | 1303.4376
Proj_A | Area_1 | LG | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 140.844 | 0 | NA | 1.6208 | 0.75 | 78 | 171.2114 |  | 13354.4927
Proj_A | Area_1 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 2 | 0 | NA | 0.78 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_1 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_1 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 3 | 0 | NA | 1.69 | 0.75 | 78 | 3.8025 |  | 296.595
Proj_A | Area_1 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 7.5 | 0 | NA | 1.17 | 0.75 | 78 | 6.5813 |  | 513.3375
Proj_A | Area_1 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 5.5 | 0 | NA | 1.17 | 0.75 | 78 | 4.8263 |  | 376.4475
Proj_A | Area_1 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 5 | 0 | NA | 1.95 | 0.75 | 78 | 7.3125 |  | 570.375
Proj_A | Area_1 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 19 | 0 | NA | 2.34 | 0.75 | 78 | 33.345 |  | 2600.91
Proj_A | Area_1 | LG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 6 | 0 | NA | 1.5 | 0.75 | 78 | 6.75 |  | 526.5
Proj_A | Area_1 | LG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 47 | 0 | NA | 1.6538 | 0.75 | 78 | 58.2947 |  | 4546.9856
Proj_A | Area_1 | LG | Field | 600 | 150-60-F-610 | Field X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1000 | 1000
Proj_A | Area_1 | LG | Field | 300 | 150-80-F-810 | Field Coating - NB 4 | LM | 16.8509 | 0 | CS | 0 | 0.75 | 78 | 0 | 80 | 1348.072
Proj_A | Area_1 | LG | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 140.844 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 14084.4
Proj_A | Area_1 | TR | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL300 | EA | 1 | 0 | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57
Proj_A | Area_1 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 0 | NA | 3.12 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_10 | BD | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | BD | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.14 | 0 | NA | 0.18767 | 1 | 110 | 0.026274 |  | 2.8902
Proj_A | Area_10 | BD | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_10 | BD | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.154 | 0 | NA | 1.1943 | 0.75 | 78 | 0.13794 |  | 10.7593
Proj_A | Area_10 | BD | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 19 | 38 | CS | 1.1765 | 1 | 110 | 22.3535 |  | 2458.885
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 18 | CS | 1.3715 | 1 | 110 | 8.229 |  | 905.19
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.942 | 0 | NA | 0.17914 | 1 | 110 | 0.16875 |  | 18.5628
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 0.86 | 0 | NA | 0.15355 | 1 | 110 | 0.13205 |  | 14.5259
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 12.226 | 0 | NA | 0.18767 | 1 | 110 | 2.2945 |  | 252.3942
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 1.791 | 0 | NA | 0.17488 | 1 | 110 | 0.31321 |  | 34.4526
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_10 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_10 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.9891 | 0 | NA | 1.1644 | 0.75 | 78 | 0.8638 |  | 67.3765
Proj_A | Area_10 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 0.903 | 0 | NA | 1.0151 | 0.75 | 78 | 0.6875 |  | 53.6254
Proj_A | Area_10 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 13.4486 | 0 | NA | 1.1943 | 0.75 | 78 | 12.0461 |  | 939.5947
Proj_A | Area_10 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 1.9701 | 0 | NA | 1.1644 | 0.75 | 78 | 1.7205 |  | 134.2012
Proj_A | Area_10 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_10 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 6 | 0 | NA | 0.78 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_10 | DL | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_10 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 1 | 0 | NA | 1.3 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_10 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_10 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | NA | 1 | 0.75 | 78 | 3.75 |  | 292.5
Proj_A | Area_10 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 1 | 0 | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
Proj_A | Area_10 | GH | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_10 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | GH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_10 | GH | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | GH | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.2 | 0 | NA | 0.18767 | 1 | 110 | 0.037535 |  | 4.1288
Proj_A | Area_10 | GH | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_10 | GH | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 14 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 700
Proj_A | Area_10 | GH | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.22 | 0 | NA | 1.1943 | 0.75 | 78 | 0.19706 |  | 15.3704
Proj_A | Area_10 | GH | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_10 | GH | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_10 | GH | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 4 | 0 | NA | 1.04 | 0.75 | 78 | 3.12 |  | 243.36
Proj_A | Area_10 | GH | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 4 | 24 | CS | 2.431 | 1 | 110 | 9.724 |  | 1069.64
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 19 | 152 | CS | 3.0095 | 1 | 110 | 57.1805 |  | 6289.855
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 6.637 | 0 | NA | 0.26871 | 1 | 110 | 1.7835 |  | 196.18
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 300
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 19 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 1900
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | EA | 1 | 0 | NA | 9.8 | 1 | 110 | 9.8 |  | 1078
Proj_A | Area_10 | GHH | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 1100
Proj_A | Area_10 | GHH | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 7.3007 | 0 | NA | 1.7019 | 0.75 | 78 | 9.3185 |  | 726.8467
Proj_A | Area_10 | GHH | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_10 | GHH | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_10 | GHH | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 2 | 0 | NA | 1.95 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_10 | GHH | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 3 | 0 | NA | 2.73 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 20 | 120 | CS | 2.9315 | 1 | 110 | 58.63 |  | 6449.3
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 19 | 152 | CS | 3.0095 | 1 | 110 | 57.1805 |  | 6289.855
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 2 | 16 | CS | 3.848 | 1 | 110 | 7.696 |  | 846.56
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 14 | 140 | CS | 5.915 | 1 | 110 | 82.81 |  | 9109.1
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 88 | 1056 | CS | 7.683 | 1 | 110 | 676.104 |  | 74371.44
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 16 | 192 | CS | 4.7255 | 1 | 110 | 75.608 |  | 8316.88
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 10 | 160 | CS | 14.365 | 1 | 110 | 143.65 |  | 15801.5
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | CS | 0.78 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 19 | 19 | CS | 0.91 | 1 | 110 | 17.29 |  | 1901.9
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 18 | 18 | CS | 0.91 | 1 | 110 | 16.38 |  | 1801.8
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 3 | 3 | CS | 3.77 | 1 | 110 | 11.31 |  | 1244.1
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 8 | 16 | CS | 5.46 | 1 | 110 | 43.68 |  | 4804.8
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 24.85 | 0 | NA | 0.29857 | 1 | 110 | 7.4195 |  | 816.1438
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 22.923 | 0 | NA | 0.26871 | 1 | 110 | 6.1597 |  | 677.5702
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 3.951 | 0 | NA | 0.46918 | 1 | 110 | 1.8537 |  | 203.9116
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 51.987 | 0 | NA | 0.57155 | 1 | 110 | 29.7132 |  | 3268.4498
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 13.685 | 0 | NA | 0.40947 | 1 | 110 | 5.6036 |  | 616.3939
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 14.773 | 0 | NA | 0.79335 | 1 | 110 | 11.7201 |  | 1289.2107
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 23 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 5750
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 300
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 200
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 3 | 0 | NA | 12 | 1 | 110 | 36 |  | 3960
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | EA | 3 | 0 | NA | 9.8 | 1 | 110 | 29.4 |  | 3234
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 6 | 0 | NA | 19 | 1 | 110 | 114 |  | 12540
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 0 | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 2 | 0 | NA | 17.6 | 1 | 110 | 35.2 |  | 3872
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 2700
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 3300
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 7 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 11900
Proj_A | Area_10 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 4200
Proj_A | Area_10 | HPG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 3 | 18 | CS | 4.2237 | 0.75 | 78 | 9.5033 |  | 741.2593
Proj_A | Area_10 | HPG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 3 | 36 | CS | 11.3555 | 0.75 | 78 | 25.5499 |  | 1992.8902
Proj_A | Area_10 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 27.335 | 0 | NA | 1.9109 | 0.75 | 78 | 39.1749 |  | 3055.6425
Proj_A | Area_10 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 25.2153 | 0 | NA | 1.7019 | 0.75 | 78 | 32.1846 |  | 2510.3974
Proj_A | Area_10 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 4.5436 | 0 | NA | 2.9857 | 0.75 | 78 | 10.1745 |  | 793.6122
Proj_A | Area_10 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 59.785 | 0 | NA | 3.6724 | 0.75 | 78 | 164.667 |  | 12844.0266
Proj_A | Area_10 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 15.7377 | 0 | NA | 2.6274 | 0.75 | 78 | 31.0123 |  | 2418.9606
Proj_A | Area_10 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 16.9889 | 0 | NA | 5.1056 | 0.75 | 78 | 65.0536 |  | 5074.1831
Proj_A | Area_10 | HPG | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 54.1486 | 0 | NA | 1.6208 | 0.75 | 78 | 65.8236 |  | 5134.2413
Proj_A | Area_10 | HPG | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 57.1262 | 0 | NA | 3.1137 | 0.75 | 78 | 133.4042 |  | 10405.5257
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 8 | 0 | NA | 1.69 | 0.75 | 78 | 10.14 |  | 790.92
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 2 | 0 | NA | 8.19 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_10 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 4 | 0 | NA | 8.19 | 0.75 | 78 | 24.57 |  | 1916.46
Proj_A | Area_10 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 14 | 0 | NA | 1.17 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_10 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 14 | 0 | NA | 1.17 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_10 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 6 | 0 | NA | 2.34 | 0.75 | 78 | 10.53 |  | 821.34
Proj_A | Area_10 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 6.5 | 0 | NA | 3.38 | 0.75 | 78 | 16.4775 |  | 1285.245
Proj_A | Area_10 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 3 | 0 | NA | 4.16 | 0.75 | 78 | 9.36 |  | 730.08
Proj_A | Area_10 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL300 | EA | 1.5 | 0 | NA | 4.94 | 0.75 | 78 | 5.5575 |  | 433.485
Proj_A | Area_10 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 24.5 | 0 | NA | 5.33 | 0.75 | 78 | 97.9388 |  | 7639.2225
Proj_A | Area_10 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 1.5 | 0 | NA | 6.76 | 0.75 | 78 | 7.605 |  | 593.19
Proj_A | Area_10 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 16 | 0 | NA | 1.6538 | 0.75 | 78 | 19.845 |  | 1547.91
Proj_A | Area_10 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 3 | 0 | NA | 1.7364 | 0.75 | 78 | 3.907 |  | 304.7448
Proj_A | Area_10 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 2 | 0 | NA | 1.8233 | 0.75 | 78 | 2.7349 |  | 213.3213
Proj_A | Area_10 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 17 | 0 | NA | 1.9144 | 0.75 | 78 | 24.4089 |  | 1903.893
Proj_A | Area_10 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 3 | 0 | NA | 2.1107 | 0.75 | 78 | 4.749 |  | 370.4192
Proj_A | Area_10 | HPG | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 54.1486 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 5414.86
Proj_A | Area_10 | HPG | Field | 300 | 150-80-F-810 | Field Coating - NB 12 | LM | 57.1262 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 6855.15
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 30 | 60 | CS | 1.1765 | 1 | 110 | 35.295 |  | 3882.45
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 Sch160 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 29.26 | 0 | NA | 0.18767 | 1 | 110 | 5.4913 |  | 604.045
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 30 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1500
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 3 | 0 | NA | 5.6 | 1 | 110 | 16.8 |  | 1848
Proj_A | Area_10 | IA | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1500
Proj_A | Area_10 | IA | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 32.186 | 0 | NA | 1.1943 | 0.75 | 78 | 28.8294 |  | 2248.6947
Proj_A | Area_10 | IA | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_10 | IA | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | IA | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_10 | IA | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 9.5 | 0 | NA | 0.91 | 0.75 | 78 | 6.4837 |  | 505.7325
Proj_A | Area_10 | IA | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 8 | 0 | NA | 1 | 0.75 | 78 | 6 |  | 468
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 20 | 120 | CS | 2.9315 | 1 | 110 | 58.63 |  | 6449.3
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 3 | 24 | CS | 3.0095 | 1 | 110 | 9.0285 |  | 993.135
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 34 | 408 | CS | 7.683 | 1 | 110 | 261.222 |  | 28734.42
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 44 | 528 | CS | 4.7255 | 1 | 110 | 207.922 |  | 22871.42
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 3 | 6 | CS | 4.42 | 1 | 110 | 13.26 |  | 1458.6
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 25.137 | 0 | NA | 0.29857 | 1 | 110 | 7.5052 |  | 825.5697
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 2.941 | 0 | NA | 0.26871 | 1 | 110 | 0.79029 |  | 86.9316
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 30.438 | 0 | NA | 0.57155 | 1 | 110 | 17.3968 |  | 1913.6529
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 48.932 | 0 | NA | 0.40947 | 1 | 110 | 20.0361 |  | 2203.974
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 49 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 12250
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 300
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 300
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 3 | 0 | NA | 12 | 1 | 110 | 36 |  | 3960
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 3 | 0 | NA | 19 | 1 | 110 | 57 |  | 6270
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 6 | 0 | NA | 12.2 | 1 | 110 | 73.2 |  | 8052
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 2700
Proj_A | Area_10 | LG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 9 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 15300
Proj_A | Area_10 | LG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 3 | 18 | CS | 4.2237 | 0.75 | 78 | 9.5033 |  | 741.2593
Proj_A | Area_10 | LG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 1 | 12 | CS | 11.3555 | 0.75 | 78 | 8.5166 |  | 664.2967
Proj_A | Area_10 | LG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 SchSTD | EA | 1 | 12 | CS | 7.1656 | 0.75 | 78 | 5.3742 |  | 419.1876
Proj_A | Area_10 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 27.6507 | 0 | NA | 1.9109 | 0.75 | 78 | 39.6273 |  | 3090.933
Proj_A | Area_10 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 3.2351 | 0 | NA | 1.7019 | 0.75 | 78 | 4.1293 |  | 322.0817
Proj_A | Area_10 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 35.0037 | 0 | NA | 3.6724 | 0.75 | 78 | 96.4113 |  | 7520.0816
Proj_A | Area_10 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 56.2718 | 0 | NA | 2.6274 | 0.75 | 78 | 110.8874 |  | 8649.2205
Proj_A | Area_10 | LG | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 54.1486 | 0 | NA | 1.6208 | 0.75 | 78 | 65.8236 |  | 5134.2413
Proj_A | Area_10 | LG | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 35.2015 | 0 | NA | 3.1137 | 0.75 | 78 | 82.2044 |  | 6411.9404
Proj_A | Area_10 | LG | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 SchSTD | LM | 18.4242 | 0 | NA | 2.218 | 0.75 | 78 | 30.648 |  | 2390.5413
Proj_A | Area_10 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_10 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_10 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 3 | 0 | NA | 0.65 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_10 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | LG | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL150 | EA | 2 | 0 | NA | 5.59 | 0.75 | 78 | 8.385 |  | 654.03
Proj_A | Area_10 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL150 | EA | 4 | 0 | NA | 5.59 | 0.75 | 78 | 16.77 |  | 1308.06
Proj_A | Area_10 | LG | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 1 | 0 | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_10 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 2 | 0 | NA | 8.19 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_10 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 6 | 0 | NA | 0.91 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_10 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 6 | 0 | NA | 2.34 | 0.75 | 78 | 10.53 |  | 821.34
Proj_A | Area_10 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 1 | 0 | NA | 2.73 | 0.75 | 78 | 2.0475 |  | 159.705
Proj_A | Area_10 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 16 | 0 | NA | 4.42 | 0.75 | 78 | 53.04 |  | 4137.12
Proj_A | Area_10 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 10 | 0 | NA | 5.33 | 0.75 | 78 | 39.975 |  | 3118.05
Proj_A | Area_10 | LG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 17 | 0 | NA | 1.6538 | 0.75 | 78 | 21.0853 |  | 1644.6544
Proj_A | Area_10 | LG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 19 | 0 | NA | 1.9144 | 0.75 | 78 | 27.2805 |  | 2127.8804
Proj_A | Area_10 | LG | Field | 600 | 150-60-F-610 | Field X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500
Proj_A | Area_10 | LG | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 54.1486 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 5414.86
Proj_A | Area_10 | LG | Field | 300 | 150-80-F-810 | Field Coating - NB 12 | LM | 53.6257 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 6435.078
Proj_A | Area_10 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 1 | 0 | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 0.5 | 0 | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 6 | 0 | NA | 5.33 | 0.75 | 78 | 23.985 |  | 1870.83
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 86 | 172 | CS | 1.1765 | 1 | 110 | 101.179 |  | 11129.69
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 42 | 126 | CS | 1.3715 | 1 | 110 | 57.603 |  | 6336.33
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 12 | 9 | CS | 0.65 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | EA | 8 | 6 | CS | 0.65 | 1 | 110 | 5.2 |  | 572
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 30 | 22.5 | CS | 0.65 | 1 | 110 | 19.5 |  | 2145
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL6000 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 4 | 3 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 39 | 29.25 | CS | 0.78 | 1 | 110 | 30.42 |  | 3346.2
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 22 | 22 | CS | 0.78 | 1 | 110 | 17.16 |  | 1887.6
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 26 | 26 | CS | 0.78 | 1 | 110 | 20.28 |  | 2230.8
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 6 | 6 | CS | 0.91 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 40 | 40 | CS | 0.91 | 1 | 110 | 36.4 |  | 4004
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | EA | 8 | 12 | CS | 1.04 | 1 | 110 | 8.32 |  | 915.2
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | EA | 20 | 30 | CS | 1.04 | 1 | 110 | 20.8 |  | 2288
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 14 | 21 | CS | 1.3 | 1 | 110 | 18.2 |  | 2002
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 2 | 3 | CS | 1.04 | 1 | 110 | 2.08 |  | 228.8
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.56 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL6000 | EA | 2 | 1.5 | CS | 3.38 | 1 | 110 | 6.76 |  | 743.6
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 6 | 6 | CS | 3.77 | 1 | 110 | 22.62 |  | 2488.2
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 8 | 6 | NA | 0.26 | 1 | 110 | 2.08 |  | 228.8
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 9 | 6.75 | NA | 0.26 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 10 | 10 | NA | 0.39 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | LM | 5.132 | 0 | NA | 0.16635 | 1 | 110 | 0.85369 |  | 93.906
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.96 | 0 | NA | 0.17914 | 1 | 110 | 0.17198 |  | 18.9175
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 4.798 | 0 | NA | 0.15355 | 1 | 110 | 0.73674 |  | 81.041
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1.5 SchXST | LM | 3.46 | 0 | NA | 0.17488 | 1 | 110 | 0.60508 |  | 66.5583
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 9.59 | 0 | NA | 0.18767 | 1 | 110 | 1.7998 |  | 197.9765
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 33.223 | 0 | NA | 0.17488 | 1 | 110 | 5.8099 |  | 639.0943
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 96 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 4800
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 99 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 4950
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 44 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2200
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 83 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 4150
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 44 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2200
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 3 | 0 | NA | 6 | 1 | 110 | 18 |  | 1980
Proj_A | Area_2 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 1800
Proj_A | Area_2 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | LM | 5.3886 | 0 | NA | 1.045 | 0.75 | 78 | 4.2233 |  | 329.4181
Proj_A | Area_2 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.008 | 0 | NA | 1.1644 | 0.75 | 78 | 0.88031 |  | 68.6639
Proj_A | Area_2 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 5.0379 | 0 | NA | 1.0151 | 0.75 | 78 | 3.8356 |  | 299.1796
Proj_A | Area_2 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1.5 SchXST | LM | 3.633 | 0 | NA | 1.1047 | 0.75 | 78 | 3.0101 |  | 234.7851
Proj_A | Area_2 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 10.549 | 0 | NA | 1.1943 | 0.75 | 78 | 9.4489 |  | 737.0124
Proj_A | Area_2 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 36.5453 | 0 | NA | 1.1644 | 0.75 | 78 | 31.9157 |  | 2489.4283
Proj_A | Area_2 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 10 | 0 | NA | 0.39 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_2 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_2 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 CL800 | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_2 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 16 | 0 | NA | 0.39 | 0.75 | 78 | 4.68 |  | 365.04
Proj_A | Area_2 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_2 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1.5 2000psi | EA | 4 | 0 | NA | 0.52 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_2 | DL | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_2 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 6 | 0 | NA | 1.04 | 0.75 | 78 | 4.68 |  | 365.04
Proj_A | Area_2 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_2 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 4 | 0 | NA | 1.04 | 0.75 | 78 | 3.12 |  | 243.36
Proj_A | Area_2 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 22 | 0 | NA | 1.04 | 0.75 | 78 | 17.16 |  | 1338.48
Proj_A | Area_2 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 4 | 0 | NA | 1.17 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_2 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 0.75 | EA | 2 | 0 | NA | 0.3 | 0.75 | 78 | 0.45 |  | 35.1
Proj_A | Area_2 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_2 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1.5 | EA | 2 | 0 | NA | 0.5 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_2 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_2 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 8 | 0 | NA | 1.5 | 0.75 | 78 | 9 |  | 702
Proj_A | Area_2 | FL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 16 | 48 | CS | 1.3715 | 1 | 110 | 21.944 |  | 2413.84
Proj_A | Area_2 | FL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 17.019 | 0 | NA | 0.17488 | 1 | 110 | 2.9762 |  | 327.386
Proj_A | Area_2 | FL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 800
Proj_A | Area_2 | FL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 2 | 0 | NA | 6 | 1 | 110 | 12 |  | 1320
Proj_A | Area_2 | FL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 1200
Proj_A | Area_2 | FL | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 18.7209 | 0 | NA | 1.1644 | 0.75 | 78 | 16.3493 |  | 1275.2485
Proj_A | Area_2 | FL | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | FL | Field | 600 | 150-30-F-310 | Install Inlines - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | FL | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 4.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.9488 |  | 308.0025
Proj_A | Area_2 | FL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 5 | 0 | NA | 1.5 | 0.75 | 78 | 5.625 |  | 438.75
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 56 | 112 | CS | 1.1765 | 1 | 110 | 65.884 |  | 7247.24
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 12 | CS | 1.3715 | 1 | 110 | 5.486 |  | 603.46
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 4 | 32 | CS | 3.0095 | 1 | 110 | 12.038 |  | 1324.18
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 20 | 200 | CS | 5.915 | 1 | 110 | 118.3 |  | 13013
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | EA | 8 | 80 | CS | 4.1782 | 1 | 110 | 33.4256 |  | 3676.816
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 60 | 720 | CS | 7.683 | 1 | 110 | 460.98 |  | 50707.8
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | EA | 26 | 416 | CS | 16.12 | 1 | 110 | 419.12 |  | 46103.2
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | EA | 12 | 288 | CS | 18.3647 | 1 | 110 | 220.376 |  | 24241.36
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 3 | 2.25 | CS | 0.65 | 1 | 110 | 1.95 |  | 214.5
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 10 | 7.5 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 15 | 15 | CS | 0.78 | 1 | 110 | 11.7 |  | 1287
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 31 | 31 | CS | 0.91 | 1 | 110 | 28.21 |  | 3103.1
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 8 | 8 | CS | 0.78 | 1 | 110 | 6.24 |  | 686.4
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 13 | 13 | CS | 0.91 | 1 | 110 | 11.83 |  | 1301.3
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.17 | 1 | 110 | 11.7 |  | 1287
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 2 | 6 | CS | 2.21 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 12 | 24 | CS | 4.42 | 1 | 110 | 53.04 |  | 5834.4
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 12 | 24 | CS | 5.46 | 1 | 110 | 65.52 |  | 7207.2
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 2 | 6 | CS | 7.67 | 1 | 110 | 15.34 |  | 1687.4
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 9 | 4.5 | NA | 0.26 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 5 | 3.75 | NA | 0.26 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 0.41 | 0 | NA | 0.15355 | 1 | 110 | 0.062956 |  | 6.9251
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.3 | 0 | NA | 0.18767 | 1 | 110 | 0.056302 |  | 6.1932
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 7.372 | 0 | NA | 0.46918 | 1 | 110 | 3.4588 |  | 380.4699
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 SchSTD | LM | 5.322 | 0 | NA | 0.33696 | 1 | 110 | 1.7933 |  | 197.2624
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 181.595 | 0 | NA | 0.57155 | 1 | 110 | 103.7907 |  | 11416.9724
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchXST | LM | 7.064 | 0 | NA | 0.79335 | 1 | 110 | 5.6042 |  | 616.4614
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch40 | LM | 14.46 | 0 | NA | 0.89571 | 1 | 110 | 12.952 |  | 1424.7211
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 14 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 700
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 48 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2400
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 11 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2750
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2500
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 26 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 6500
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 70 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 3500
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 12 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 6000
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 400
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 13 | 0 | NA | 19 | 1 | 110 | 247 |  | 27170
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch40 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 13 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 22100
Proj_A | Area_2 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 2880
Proj_A | Area_2 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 1 SchXST | LM | 0.4305 | 0 | NA | 1.0151 | 1 | 110 | 0.43702 |  | 48.072
Proj_A | Area_2 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 0.33 | 0 | NA | 1.1943 | 1 | 110 | 0.39411 |  | 43.3525
Proj_A | Area_2 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 10 Sch80 | LM | 8.4778 | 0 | NA | 2.9857 | 1 | 110 | 25.3123 |  | 2784.3477
Proj_A | Area_2 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 10 SchSTD | LM | 6.1203 | 0 | NA | 2.1497 | 1 | 110 | 13.1569 |  | 1447.2565
Proj_A | Area_2 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 12 Sch80 | LM | 208.8342 | 0 | NA | 3.6724 | 1 | 110 | 766.9278 |  | 84362.0542
Proj_A | Area_2 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchXST | LM | 8.1236 | 0 | NA | 5.1056 | 1 | 110 | 41.4756 |  | 4562.3117
Proj_A | Area_2 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch40 | LM | 16.629 | 0 | NA | 5.7923 | 1 | 110 | 96.3198 |  | 10595.1759
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 2000psi | EA | 4 | 0 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL3000 | EA | 3 | 0 | NA | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 12 | 0 | NA | 1.04 | 1 | 110 | 12.48 |  | 1372.8
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 6 | 0 | NA | 1.69 | 1 | 110 | 10.14 |  | 1115.4
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 10 CL600 | EA | 4 | 0 | NA | 6.63 | 1 | 110 | 26.52 |  | 2917.2
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install Blind - NB 10 CL600 | EA | 2 | 0 | NA | 6.63 | 1 | 110 | 13.26 |  | 1458.6
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL300 | EA | 3 | 0 | NA | 9.23 | 1 | 110 | 27.69 |  | 3045.9
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install Inlines - NB 16 CL300 | EA | 4 | 0 | NA | 9.23 | 1 | 110 | 36.92 |  | 4061.2
Proj_A | Area_2 | HPG | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL300 | EA | 3 | 0 | NA | 9.23 | 1 | 110 | 27.69 |  | 3045.9
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 9 | 0 | NA | 1.04 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | EA | 5 | 0 | NA | 1.17 | 1 | 110 | 5.85 |  | 643.5
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 22 | 0 | NA | 1.04 | 1 | 110 | 22.88 |  | 2516.8
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 11 | 0 | NA | 1.17 | 1 | 110 | 12.87 |  | 1415.7
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 3 CL300 | EA | 1 | 0 | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 0 | NA | 3.12 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL300 | EA | 1 | 0 | NA | 3.9 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 10 | 0 | NA | 4.16 | 1 | 110 | 41.6 |  | 4576
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 15.5 | 0 | NA | 5.33 | 1 | 110 | 82.615 |  | 9087.65
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | EA | 13.5 | 0 | NA | 6.37 | 1 | 110 | 85.995 |  | 9459.45
Proj_A | Area_2 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | EA | 2 | 0 | NA | 9.62 | 1 | 110 | 19.24 |  | 2116.4
Proj_A | Area_2 | HPG | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 1 | 110 | 0.8 |  | 88
Proj_A | Area_2 | HPG | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 6 | 0 | NA | 1.8233 | 1 | 110 | 10.9396 |  | 1203.3512
Proj_A | Area_2 | HPG | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 12 | EA | 15 | 0 | NA | 1.9144 | 1 | 110 | 28.7163 |  | 3158.7969
Proj_A | Area_2 | HPG | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 2 | 0 | NA | 2.1107 | 1 | 110 | 4.2213 |  | 464.3431
Proj_A | Area_2 | HPG | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 2 | 0 | NA | 2.5655 | 1 | 110 | 5.131 |  | 564.412
Proj_A | Area_2 | HPG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 4 | 48 | CS | 11.3555 | 0.75 | 78 | 34.0665 |  | 2657.187
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 40 | 80 | CS | 1.1765 | 1 | 110 | 47.06 |  | 5176.6
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 2.86 | 1 | 110 | 17.16 |  | 1887.6
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 12 | 12 | NA | 0.39 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 8 | 8 | NA | 0.39 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 12 | 12 | NA | 0.39 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 56.663 | 0 | NA | 0.18767 | 1 | 110 | 10.6341 |  | 1169.7539
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 40 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2000
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 4 | 0 | NA | 5.6 | 1 | 110 | 22.4 |  | 2464
Proj_A | Area_2 | IA | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 4 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 2000
Proj_A | Area_2 | IA | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 62.3293 | 0 | NA | 1.1943 | 1 | 110 | 74.4389 |  | 8188.2774
Proj_A | Area_2 | IA | Module | 500 | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 6 | 0 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | IA | Module | 500 | 150-30-M-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | IA | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | IA | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 9.5 | 0 | NA | 0.91 | 1 | 110 | 8.645 |  | 950.95
Proj_A | Area_2 | IA | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 13 | 0 | NA | 1 | 1 | 110 | 13 |  | 1430
Proj_A | Area_2 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_2 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | TR | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | TR | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_2 | TR | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_2 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_3 | BD | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | EA | 19 | 76 | CS | 1.6835 | 1 | 110 | 31.9865 |  | 3518.515
Proj_A | Area_3 | BD | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 13 | 104 | CS | 3.0095 | 1 | 110 | 39.1235 |  | 4303.585
Proj_A | Area_3 | BD | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchSTD | LM | 10.831 | 0 | NA | 0.19194 | 1 | 110 | 2.0789 |  | 228.6774
Proj_A | Area_3 | BD | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 2.916 | 0 | NA | 0.26871 | 1 | 110 | 0.78357 |  | 86.1927
Proj_A | Area_3 | BD | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 19 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 950
Proj_A | Area_3 | BD | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 13 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 1300
Proj_A | Area_3 | BD | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchSTD | EA | 1 | 0 | NA | 7 | 1 | 110 | 7 |  | 770
Proj_A | Area_3 | BD | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 700
Proj_A | Area_3 | BD | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 8 SchSTD | EA | 1 | 8 | CS | 4.2887 | 0.75 | 78 | 3.2165 |  | 250.889
Proj_A | Area_3 | BD | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchSTD | LM | 11.9141 | 0 | NA | 1.2241 | 0.75 | 78 | 10.9384 |  | 853.1956
Proj_A | Area_3 | BD | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 3.2076 | 0 | NA | 1.7019 | 0.75 | 78 | 4.0942 |  | 319.3438
Proj_A | Area_3 | BD | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 8 SchSTD | LM | 19.1103 | 0 | NA | 1.4502 | 0.75 | 78 | 20.7853 |  | 1621.257
Proj_A | Area_3 | BD | Field | 600 | 150-30-F-310 | Install Blind - NB 8 CL150 | EA | 1 | 0 | NA | 3.64 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_3 | BD | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | EA | 2.5 | 0 | NA | 1.56 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_3 | BD | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 1.5 | 0 | NA | 2.73 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_3 | BD | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 3 | 0 | NA | 1.5 | 0.75 | 78 | 3.375 |  | 263.25
Proj_A | Area_3 | BD | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 5 | 0 | NA | 1.7364 | 0.75 | 78 | 6.5116 |  | 507.908
Proj_A | Area_3 | BD | Field | 600 | 150-60-F-610 | Field X-Ray - NB 8 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500
Proj_A | Area_3 | BD | Field | 300 | 150-80-F-810 | Field Coating - NB 8 | LM | 19.1103 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 2293.236
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 116 | 232 | CS | 1.1765 | 1 | 110 | 136.474 |  | 15012.14
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 16 | 48 | CS | 1.3715 | 1 | 110 | 21.944 |  | 2413.84
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 4 | 3 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 16 | 16 | CS | 0.78 | 1 | 110 | 12.48 |  | 1372.8
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 15 | 15 | CS | 0.91 | 1 | 110 | 13.65 |  | 1501.5
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.17 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 2.47 | 1 | 110 | 4.94 |  | 543.4
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 2.86 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 2.77 | 0 | NA | 0.15355 | 1 | 110 | 0.42534 |  | 46.7869
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 97.58 | 0 | NA | 0.18767 | 1 | 110 | 18.3132 |  | 2014.4466
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 5.507 | 0 | NA | 0.17488 | 1 | 110 | 0.96305 |  | 105.9354
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 42 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2100
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 119 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 5950
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 800
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 10 | 0 | NA | 5.6 | 1 | 110 | 56 |  | 6160
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 10 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 5000
Proj_A | Area_3 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_3 | DL | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | EA | 7 | 14 | CS | 1.6003 | 0.75 | 78 | 8.4016 |  | 655.3229
Proj_A | Area_3 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 2.9085 | 0 | NA | 1.0151 | 0.75 | 78 | 2.2144 |  | 172.7235
Proj_A | Area_3 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 107.338 | 0 | NA | 1.1943 | 0.75 | 78 | 96.144 |  | 7499.2353
Proj_A | Area_3 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 6.0577 | 0 | NA | 1.1644 | 0.75 | 78 | 5.2903 |  | 412.6443
Proj_A | Area_3 | DL | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | LM | 165.517 | 0 | NA | 1.0237 | 0.75 | 78 | 127.0763 |  | 9911.9544
Proj_A | Area_3 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_3 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 4 | 0 | NA | 0.39 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_3 | DL | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 3 | 0 | NA | 0.65 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_3 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 7 | 0 | NA | 0.65 | 0.75 | 78 | 3.4125 |  | 266.175
Proj_A | Area_3 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_3 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 2.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.7062 |  | 133.0875
Proj_A | Area_3 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 36.5 | 0 | NA | 0.91 | 0.75 | 78 | 24.9112 |  | 1943.0775
Proj_A | Area_3 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 3.5 | 0 | NA | 1.04 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_3 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_3 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 80 | 0 | NA | 1 | 0.75 | 78 | 60 |  | 4680
Proj_A | Area_3 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 6 | 0 | NA | 1.5 | 0.75 | 78 | 6.75 |  | 526.5
Proj_A | Area_3 | DL | Field | 600 | 150-60-F-610 | Field X-Ray - NB 2 | EA | 7 | 0 | NA | 0 | 0.75 | 78 | 0 | 750 | 5250
Proj_A | Area_3 | DL | Field | 300 | 150-80-F-810 | Field Coating - NB 2 | LM | 165.517 | 0 | CS | 0 | 0.75 | 78 | 0 | 60 | 9931.02
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 34 | 68 | CS | 1.1765 | 1 | 110 | 40.001 |  | 4400.11
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 6 | 72 | CS | 4.7255 | 1 | 110 | 28.353 |  | 3118.83
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 44 | 704 | CS | 14.365 | 1 | 110 | 632.06 |  | 69526.6
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | EA | 14 | 224 | CS | 8.8313 | 1 | 110 | 123.6387 |  | 13600.2533
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 52 | 1040 | CS | 21.7588 | 1 | 110 | 1131.455 |  | 124460.05
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | EA | 6 | 120 | CS | 13.6121 | 1 | 110 | 81.6725 |  | 8983.975
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | EA | 51 | 1224 | CS | 33.1998 | 1 | 110 | 1693.1915 |  | 186251.065
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | EA | 10 | 240 | CS | 17.7732 | 1 | 110 | 177.7317 |  | 19550.4833
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 17 | 34 | CS | 5.46 | 1 | 110 | 92.82 |  | 10210.2
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 13.44 | 0 | NA | 0.40947 | 1 | 110 | 5.5033 |  | 605.3587
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 88.544 | 0 | NA | 0.79335 | 1 | 110 | 70.246 |  | 7727.0612
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchSTD | LM | 43.76 | 0 | NA | 0.58861 | 1 | 110 | 25.7576 |  | 2833.3398
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 81.44 | 0 | NA | 1.0279 | 1 | 110 | 83.7152 |  | 9208.6735
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 SchXST | LM | 2.414 | 0 | NA | 1.0279 | 1 | 110 | 2.4814 |  | 272.9585
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch80 | LM | 103.42 | 0 | NA | 1.1644 | 1 | 110 | 120.425 |  | 13246.7533
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 SchXST | LM | 12.399 | 0 | NA | 1.1644 | 1 | 110 | 14.4377 |  | 1588.1502
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2000
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 4000
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 5000
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 0 | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 7 | 0 | NA | 17.6 | 1 | 110 | 123.2 |  | 13552
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 SchSTD | EA | 3 | 0 | NA | 15.6 | 1 | 110 | 46.8 |  | 5148
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 6 | 0 | NA | 41.2 | 1 | 110 | 247.2 |  | 27192
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch80 | EA | 8 | 0 | NA | 62.6 | 1 | 110 | 500.8 |  | 55088
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 SchXST | EA | 1 | 0 | NA | 30.8 | 1 | 110 | 30.8 |  | 3388
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 10 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 21000
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 16200
Proj_A | Area_3 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 9 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 25920
Proj_A | Area_3 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 12 SchSTD | LM | 15.456 | 0 | NA | 2.6274 | 1 | 110 | 40.6095 |  | 4467.0425
Proj_A | Area_3 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 16 Sch80 | LM | 101.8256 | 0 | NA | 5.1056 | 1 | 110 | 519.8771 |  | 57186.4841
Proj_A | Area_3 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchSTD | LM | 50.324 | 0 | NA | 3.7919 | 1 | 110 | 190.8211 |  | 20990.3259
Proj_A | Area_3 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 20 Sch80 | LM | 93.656 | 0 | NA | 6.6283 | 1 | 110 | 620.7778 |  | 68285.5619
Proj_A | Area_3 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 20 SchXST | LM | 2.7761 | 0 | NA | 6.6283 | 1 | 110 | 18.4008 |  | 2024.0833
Proj_A | Area_3 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch80 | LM | 118.933 | 0 | NA | 7.4941 | 1 | 110 | 891.2996 |  | 98042.9574
Proj_A | Area_3 | HPG | Module | 500 | 150-20-M-210 | Install Spools - NB 24 SchXST | LM | 14.2588 | 0 | NA | 7.4941 | 1 | 110 | 106.8577 |  | 11754.3476
Proj_A | Area_3 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 13 | 0 | NA | 1.69 | 1 | 110 | 21.97 |  | 2416.7
Proj_A | Area_3 | HPG | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL600 | EA | 2 | 0 | NA | 11.44 | 1 | 110 | 22.88 |  | 2516.8
Proj_A | Area_3 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL600 | EA | 1 | 0 | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4
Proj_A | Area_3 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 20 CL600 | EA | 3 | 0 | NA | 15.47 | 1 | 110 | 46.41 |  | 5105.1
Proj_A | Area_3 | HPG | Module | 500 | 150-30-M-310 | Install valve - NB 24 CL600 | EA | 1 | 0 | NA | 17.68 | 1 | 110 | 17.68 |  | 1944.8
Proj_A | Area_3 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_3 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 29 | 0 | NA | 1.17 | 1 | 110 | 33.93 |  | 3732.3
Proj_A | Area_3 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 1.5 | 0 | NA | 5.33 | 1 | 110 | 7.995 |  | 879.45
Proj_A | Area_3 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 16.5 | 0 | NA | 6.76 | 1 | 110 | 111.54 |  | 12269.4
Proj_A | Area_3 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 16.5 | 0 | NA | 8.58 | 1 | 110 | 141.57 |  | 15572.7
Proj_A | Area_3 | HPG | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | EA | 14 | 0 | NA | 10.27 | 1 | 110 | 143.78 |  | 15815.8
Proj_A | Area_3 | HPG | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 15 | 0 | NA | 2.1107 | 1 | 110 | 31.6598 |  | 3482.5735
Proj_A | Area_3 | HPG | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 0 | NA | 2.327 | 1 | 110 | 13.962 |  | 1535.8149
Proj_A | Area_3 | HPG | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 20 | 0 | NA | 2.5655 | 1 | 110 | 51.3102 |  | 5644.1199
Proj_A | Area_3 | HPG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 16 Sch80 | EA | 2 | 32 | CS | 20.3905 | 0.75 | 78 | 30.5858 |  | 2385.6885
Proj_A | Area_3 | HPG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 16 SchSTD | EA | 1 | 16 | CS | 11.6532 | 0.75 | 78 | 8.7399 |  | 681.7122
Proj_A | Area_3 | HPG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 20 Sch80 | EA | 1 | 20 | CS | 31.2637 | 0.75 | 78 | 23.4478 |  | 1828.9264
Proj_A | Area_3 | HPG | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 24 Sch80 | EA | 2 | 48 | CS | 40.3455 | 0.75 | 78 | 60.5183 |  | 4720.4235
Proj_A | Area_3 | IA | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_3 | IA | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 2 | 2 | CS | 2.86 | 1 | 110 | 5.72 |  | 629.2
Proj_A | Area_3 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 3 | 3 | NA | 0.39 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_3 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | IA | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 6.789 | 0 | NA | 0.18767 | 1 | 110 | 1.2741 |  | 140.1525
Proj_A | Area_3 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_3 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_3 | IA | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 7.4679 | 0 | NA | 1.1943 | 1 | 110 | 8.9188 |  | 981.0673
Proj_A | Area_3 | IA | Module | 500 | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_3 | IA | Module | 500 | 150-30-M-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_3 | IA | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3.5 | 0 | NA | 0.91 | 1 | 110 | 3.185 |  | 350.35
Proj_A | Area_3 | IA | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 1 | 110 | 2 |  | 220
Proj_A | Area_3 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_3 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.17 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_3 | TR | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 3 | 1.5 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_3 | TR | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_3 | TR | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_3 | TR | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_3 | TR | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_3 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_3 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_3 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_3 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | NA | 1.17 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_3 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 234 | 468 | CS | 1.1765 | 1 | 110 | 275.301 |  | 30283.11
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 10 | 7.5 | CS | 0.65 | 1 | 110 | 6.5 |  | 715
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 6 | 4.5 | CS | 0.65 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 15 | 11.25 | CS | 0.78 | 1 | 110 | 11.7 |  | 1287
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 7 | 5.25 | CS | 0.78 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 63 | 63 | CS | 0.78 | 1 | 110 | 49.14 |  | 5405.4
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 12 | 12 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 103 | 103 | CS | 0.78 | 1 | 110 | 80.34 |  | 8837.4
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 39 | 39 | CS | 0.91 | 1 | 110 | 35.49 |  | 3903.9
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 136 | 136 | CS | 0.91 | 1 | 110 | 123.76 |  | 13613.6
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 6 | 12 | CS | 1.69 | 1 | 110 | 10.14 |  | 1115.4
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 6 | 4.5 | CS | 2.47 | 1 | 110 | 14.82 |  | 1630.2
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 10 | 7.5 | NA | 0.26 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 15 | 15 | NA | 0.39 | 1 | 110 | 5.85 |  | 643.5
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 15 | 15 | NA | 0.39 | 1 | 110 | 5.85 |  | 643.5
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 14.371 | 0 | NA | 0.17914 | 1 | 110 | 2.5745 |  | 283.1904
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 80.648 | 0 | NA | 0.18767 | 1 | 110 | 15.1355 |  | 1664.9015
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 30 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1500
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 57 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2850
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 188 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 9400
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 7 | 0 | NA | 5.6 | 1 | 110 | 39.2 |  | 4312
Proj_A | Area_4 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 7 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 3500
Proj_A | Area_4 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 15.0896 | 0 | NA | 1.1644 | 0.75 | 78 | 13.178 |  | 1027.8847
Proj_A | Area_4 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 88.7128 | 0 | NA | 1.1943 | 0.75 | 78 | 79.4612 |  | 6197.9742
Proj_A | Area_4 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 10 | 0 | NA | 0.65 | 0.75 | 78 | 4.875 |  | 380.25
Proj_A | Area_4 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 39 | 0 | NA | 0.78 | 0.75 | 78 | 22.815 |  | 1779.57
Proj_A | Area_4 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 6 | 0 | NA | 0.78 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_4 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 3 | 0 | NA | 1.69 | 0.75 | 78 | 3.8025 |  | 296.595
Proj_A | Area_4 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_4 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 22.5 | 0 | NA | 1.17 | 0.75 | 78 | 19.7438 |  | 1540.0125
Proj_A | Area_4 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 18 | 0 | NA | 0.91 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_4 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 19 | 0 | NA | 1.17 | 0.75 | 78 | 16.6725 |  | 1300.455
Proj_A | Area_4 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 14 | 0 | NA | 0.4 | 0.75 | 78 | 4.2 |  | 327.6
Proj_A | Area_4 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 27 | 0 | NA | 1 | 0.75 | 78 | 20.25 |  | 1579.5
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 92 | 184 | CS | 1.1765 | 1 | 110 | 108.238 |  | 11906.18
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 6 | 18 | CS | 1.586 | 1 | 110 | 9.516 |  | 1046.76
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 24 | 336 | CS | 10.2115 | 1 | 110 | 245.076 |  | 26958.36
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 42 | 672 | CS | 14.365 | 1 | 110 | 603.33 |  | 66366.3
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 60 | 1200 | CS | 21.7588 | 1 | 110 | 1305.525 |  | 143607.75
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 8 | 6 | CS | 0.78 | 1 | 110 | 6.24 |  | 686.4
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 3 | 3 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 20 | 20 | CS | 0.78 | 1 | 110 | 15.6 |  | 1716
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 18 | 18 | CS | 0.91 | 1 | 110 | 16.38 |  | 1801.8
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 56 | 56 | CS | 0.91 | 1 | 110 | 50.96 |  | 5605.6
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 16 | 32 | CS | 1.69 | 1 | 110 | 27.04 |  | 2974.4
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 3 | 9 | CS | 2.21 | 1 | 110 | 6.63 |  | 729.3
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 3 | 3 | CS | 3.77 | 1 | 110 | 11.31 |  | 1244.1
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 34 | 68 | CS | 5.46 | 1 | 110 | 185.64 |  | 20420.4
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 3 | 9 | CS | 7.67 | 1 | 110 | 23.01 |  | 2531.1
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 12 | 6 | NA | 0.26 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 3 | 3 | NA | 0.39 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 11 | 11 | NA | 0.39 | 1 | 110 | 4.29 |  | 471.9
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 8 | 8 | NA | 0.39 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 6 | 12 | NA | 0.429 | 1 | 110 | 2.574 |  | 283.14
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.589 | 0 | NA | 0.17914 | 1 | 110 | 0.10551 |  | 11.6066
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 16.032 | 0 | NA | 0.67818 | 1 | 110 | 10.8726 |  | 1195.9888
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 7.728 | 0 | NA | 0.79335 | 1 | 110 | 6.131 |  | 674.4074
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 51.138 | 0 | NA | 1.0279 | 1 | 110 | 52.5667 |  | 5782.3323
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1500
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2250
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 14 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 700
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 3000
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 6 | 0 | NA | 41.2 | 1 | 110 | 247.2 |  | 27192
Proj_A | Area_4 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 16200
Proj_A | Area_4 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.61845 | 0 | NA | 1.1644 | 0.75 | 78 | 0.5401 |  | 42.1282
Proj_A | Area_4 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 18.4368 | 0 | NA | 4.3591 | 0.75 | 78 | 60.2764 |  | 4701.559
Proj_A | Area_4 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 8.8872 | 0 | NA | 5.1056 | 0.75 | 78 | 34.0306 |  | 2654.3889
Proj_A | Area_4 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 58.8087 | 0 | NA | 6.6283 | 0.75 | 78 | 292.3502 |  | 22803.3179
Proj_A | Area_4 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_4 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_4 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_4 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 4 | 0 | NA | 0.91 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_4 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 34 | 0 | NA | 1.69 | 0.75 | 78 | 43.095 |  | 3361.41
Proj_A | Area_4 | HPG | Field | 600 | 150-30-F-310 | Install Inlines - NB 16 CL600 | EA | 6 | 0 | NA | 11.44 | 0.75 | 78 | 51.48 |  | 4015.44
Proj_A | Area_4 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 6 | 0 | NA | 15.47 | 0.75 | 78 | 69.615 |  | 5429.97
Proj_A | Area_4 | HPG | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 6 | 0 | NA | 15.47 | 0.75 | 78 | 69.615 |  | 5429.97
Proj_A | Area_4 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_4 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 23 | 0 | NA | 1.17 | 0.75 | 78 | 20.1825 |  | 1574.235
Proj_A | Area_4 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 51 | 0 | NA | 1.17 | 0.75 | 78 | 44.7525 |  | 3490.695
Proj_A | Area_4 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 1.5 | 0 | NA | 1.3 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_4 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 9 | 0 | NA | 5.98 | 0.75 | 78 | 40.365 |  | 3148.47
Proj_A | Area_4 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 15 | 0 | NA | 6.76 | 0.75 | 78 | 76.05 |  | 5931.9
Proj_A | Area_4 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 15 | 0 | NA | 8.58 | 0.75 | 78 | 96.525 |  | 7528.95
Proj_A | Area_4 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 6 | 0 | NA | 2.0101 | 0.75 | 78 | 9.0456 |  | 705.5604
Proj_A | Area_4 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 7 | 0 | NA | 2.1107 | 0.75 | 78 | 11.0809 |  | 864.3114
Proj_A | Area_4 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 0 | NA | 2.327 | 0.75 | 78 | 10.4715 |  | 816.7743
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 126 | 252 | CS | 1.1765 | 1 | 110 | 148.239 |  | 16306.29
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.586 | 1 | 110 | 3.172 |  | 348.92
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 18 | 18 | CS | 0.78 | 1 | 110 | 14.04 |  | 1544.4
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 26 | 26 | CS | 0.91 | 1 | 110 | 23.66 |  | 2602.6
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 4 | 8 | CS | 1.69 | 1 | 110 | 6.76 |  | 743.6
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.508 | 0 | NA | 0.17914 | 1 | 110 | 0.27015 |  | 29.7162
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 18.052 | 0 | NA | 0.18767 | 1 | 110 | 3.3879 |  | 372.6664
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 20 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1000
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_5 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_5 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.5834 | 0 | NA | 1.1644 | 0.75 | 78 | 1.3828 |  | 107.8596
Proj_A | Area_5 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 19.8572 | 0 | NA | 1.1943 | 0.75 | 78 | 17.7864 |  | 1387.3355
Proj_A | Area_5 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 7 | 0 | NA | 0.78 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_5 | DL | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | Field | 600 | 150-30-F-310 | Install Inlines - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 8 | 0 | NA | 1.69 | 0.75 | 78 | 10.14 |  | 790.92
Proj_A | Area_5 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_5 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 33 | 0 | NA | 1.17 | 0.75 | 78 | 28.9575 |  | 2258.685
Proj_A | Area_5 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_5 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 7 | 0 | NA | 1 | 0.75 | 78 | 5.25 |  | 409.5
Proj_A | Area_5 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
Proj_A | Area_5 | FL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 9 | 18 | CS | 1.1765 | 1 | 110 | 10.5885 |  | 1164.735
Proj_A | Area_5 | FL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 18 | CS | 1.3715 | 1 | 110 | 8.229 |  | 905.19
Proj_A | Area_5 | FL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.798 | 0 | NA | 0.18767 | 1 | 110 | 0.33744 |  | 37.118
Proj_A | Area_5 | FL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 5.618 | 0 | NA | 0.17488 | 1 | 110 | 0.98246 |  | 108.0707
Proj_A | Area_5 | FL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_5 | FL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_5 | FL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_5 | FL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_5 | FL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.9778 | 0 | NA | 1.1943 | 0.75 | 78 | 1.7715 |  | 138.1802
Proj_A | Area_5 | FL | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 6.1798 | 0 | NA | 1.1644 | 0.75 | 78 | 5.3969 |  | 420.9616
Proj_A | Area_5 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.7062 |  | 133.0875
Proj_A | Area_5 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 34 | 68 | CS | 1.1765 | 1 | 110 | 40.001 |  | 4400.11
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 4 | 12 | CS | 1.586 | 1 | 110 | 6.344 |  | 697.84
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 32 | 192 | CS | 2.9315 | 1 | 110 | 93.808 |  | 10318.88
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 28 | 224 | CS | 3.848 | 1 | 110 | 107.744 |  | 11851.84
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 34 | 408 | CS | 7.683 | 1 | 110 | 261.222 |  | 28734.42
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 3 | 2.25 | CS | 0.65 | 1 | 110 | 1.95 |  | 214.5
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 6 | 4.5 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 12 | 12 | CS | 0.91 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 2 | 6 | CS | 2.21 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 17 | 34 | CS | 5.46 | 1 | 110 | 92.82 |  | 10210.2
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 2 | 6 | CS | 7.67 | 1 | 110 | 15.34 |  | 1687.4
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 3 | 2.25 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 3 | 2.25 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 13.406 | 0 | NA | 0.29857 | 1 | 110 | 4.0026 |  | 440.2907
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 11.814 | 0 | NA | 0.37535 | 1 | 110 | 4.4343 |  | 487.7777
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 14.108 | 0 | NA | 0.57155 | 1 | 110 | 8.0634 |  | 886.9773
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1250
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 350
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 375
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 600
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchXST | EA | 2 | 0 | NA | 16 | 1 | 110 | 32 |  | 3520
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 0 | NA | 19 | 1 | 110 | 19 |  | 2090
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 2200
Proj_A | Area_5 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_5 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 14.7466 | 0 | NA | 1.9109 | 0.75 | 78 | 21.134 |  | 1648.4484
Proj_A | Area_5 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 12.9954 | 0 | NA | 2.4184 | 0.75 | 78 | 23.5713 |  | 1838.5615
Proj_A | Area_5 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 16.2242 | 0 | NA | 3.6724 | 0.75 | 78 | 44.6866 |  | 3485.5546
Proj_A | Area_5 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 3 | 0 | NA | 0.65 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_5 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_5 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 4 | 0 | NA | 1.69 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_5 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_5 | HPG | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_5 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 4 | 0 | NA | 5.46 | 0.75 | 78 | 16.38 |  | 1277.64
Proj_A | Area_5 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_5 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_5 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 13 | 0 | NA | 1.17 | 0.75 | 78 | 11.4075 |  | 889.785
Proj_A | Area_5 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 1 | 0 | NA | 1.3 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_5 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 9.5 | 0 | NA | 2.34 | 0.75 | 78 | 16.6725 |  | 1300.455
Proj_A | Area_5 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 12 | 0 | NA | 3.38 | 0.75 | 78 | 30.42 |  | 2372.76
Proj_A | Area_5 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 6 | 0 | NA | 5.33 | 0.75 | 78 | 23.985 |  | 1870.83
Proj_A | Area_5 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 3 | 0 | NA | 1.6538 | 0.75 | 78 | 3.7209 |  | 290.2331
Proj_A | Area_5 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 4 | 0 | NA | 1.7364 | 0.75 | 78 | 5.2093 |  | 406.3264
Proj_A | Area_5 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | NA | 1.9144 | 0.75 | 78 | 4.3075 |  | 335.9811
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 58 | 116 | CS | 1.1765 | 1 | 110 | 68.237 |  | 7506.07
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 14 | 14 | CS | 0.78 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 16 | 16 | CS | 0.78 | 1 | 110 | 12.48 |  | 1372.8
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 20 | 20 | CS | 0.91 | 1 | 110 | 18.2 |  | 2002
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.23 | 0 | NA | 0.17914 | 1 | 110 | 0.39949 |  | 43.9437
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 8.403 | 0 | NA | 0.18767 | 1 | 110 | 1.577 |  | 173.472
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_6 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_6 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.3415 | 0 | NA | 1.1644 | 0.75 | 78 | 2.0449 |  | 159.5006
Proj_A | Area_6 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 9.2433 | 0 | NA | 1.1943 | 0.75 | 78 | 8.2793 |  | 645.7888
Proj_A | Area_6 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_6 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 8 | 0 | NA | 0.78 | 0.75 | 78 | 4.68 |  | 365.04
Proj_A | Area_6 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_6 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_6 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 10.5 | 0 | NA | 1.17 | 0.75 | 78 | 9.2138 |  | 718.6725
Proj_A | Area_6 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_6 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 8 | 48 | CS | 2.9315 | 1 | 110 | 23.452 |  | 2579.72
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 168 | CS | 7.683 | 1 | 110 | 107.562 |  | 11831.82
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 4 | 3 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 21 | 21 | CS | 0.91 | 1 | 110 | 19.11 |  | 2102.1
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 9.587 | 0 | NA | 0.29857 | 1 | 110 | 2.8624 |  | 314.864
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 14.374 | 0 | NA | 0.57155 | 1 | 110 | 8.2155 |  | 903.7009
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 2 | 0 | NA | 19 | 1 | 110 | 38 |  | 4180
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_6 | HPG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 3400
Proj_A | Area_6 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 10.5457 | 0 | NA | 1.9109 | 0.75 | 78 | 15.1135 |  | 1178.8509
Proj_A | Area_6 | HPG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 16.5301 | 0 | NA | 3.6724 | 0.75 | 78 | 45.5291 |  | 3551.2732
Proj_A | Area_6 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_6 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_6 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 4 | 0 | NA | 1.69 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_6 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_6 | HPG | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 3 | 0 | NA | 8.19 | 0.75 | 78 | 18.4275 |  | 1437.345
Proj_A | Area_6 | HPG | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 1 | 0 | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_6 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 5.5 | 0 | NA | 1.17 | 0.75 | 78 | 4.8263 |  | 376.4475
Proj_A | Area_6 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 7.5 | 0 | NA | 1.17 | 0.75 | 78 | 6.5813 |  | 513.3375
Proj_A | Area_6 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | NA | 2.34 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_6 | HPG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 7 | 0 | NA | 5.33 | 0.75 | 78 | 27.9825 |  | 2182.635
Proj_A | Area_6 | HPG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 1 | 0 | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 2.86 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 10.571 | 0 | NA | 0.18767 | 1 | 110 | 1.9839 |  | 218.2283
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_6 | IA | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_6 | IA | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 11.6281 | 0 | NA | 1.1943 | 0.75 | 78 | 10.4154 |  | 812.4043
Proj_A | Area_6 | IA | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 3 | 0 | NA | 0.39 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | IA | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_6 | IA | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 4.5 | 0 | NA | 0.91 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_6 | IA | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | NA | 1 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 106 | 212 | CS | 1.1765 | 1 | 110 | 124.709 |  | 13717.99
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 12 | CS | 1.3715 | 1 | 110 | 5.486 |  | 603.46
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 16 | 16 | CS | 0.78 | 1 | 110 | 12.48 |  | 1372.8
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 26 | 26 | CS | 0.78 | 1 | 110 | 20.28 |  | 2230.8
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 16 | 16 | CS | 0.91 | 1 | 110 | 14.56 |  | 1601.6
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 18 | 18 | CS | 0.91 | 1 | 110 | 16.38 |  | 1801.8
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 2.86 | 1 | 110 | 17.16 |  | 1887.6
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 3.868 | 0 | NA | 0.17914 | 1 | 110 | 0.69292 |  | 76.2216
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 36.116 | 0 | NA | 0.18767 | 1 | 110 | 6.778 |  | 745.5806
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 37 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1850
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 96 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 4800
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 0 | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
Proj_A | Area_7 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1000
Proj_A | Area_7 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 4.0614 | 0 | NA | 1.1644 | 0.75 | 78 | 3.5469 |  | 276.6584
Proj_A | Area_7 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 39.7276 | 0 | NA | 1.1943 | 0.75 | 78 | 35.5845 |  | 2775.5932
Proj_A | Area_7 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_7 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 10 | 0 | NA | 0.78 | 0.75 | 78 | 5.85 |  | 456.3
Proj_A | Area_7 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | DL | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_7 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 7.5 | 0 | NA | 0.91 | 0.75 | 78 | 5.1187 |  | 399.2625
Proj_A | Area_7 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 5.5 | 0 | NA | 1.17 | 0.75 | 78 | 4.8263 |  | 376.4475
Proj_A | Area_7 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_7 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 4 | 0 | NA | 0.4 | 0.75 | 78 | 1.2 |  | 93.6
Proj_A | Area_7 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 15 | 0 | NA | 1 | 0.75 | 78 | 11.25 |  | 877.5
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 44 | 88 | CS | 1.1765 | 1 | 110 | 51.766 |  | 5694.26
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 32 | 192 | CS | 2.9315 | 1 | 110 | 93.808 |  | 10318.88
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 28 | 224 | CS | 3.848 | 1 | 110 | 107.744 |  | 11851.84
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 32 | 384 | CS | 7.683 | 1 | 110 | 245.856 |  | 27044.16
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 4 | 3 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 24 | 24 | CS | 0.91 | 1 | 110 | 21.84 |  | 2402.4
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 6 | 12 | CS | 1.69 | 1 | 110 | 10.14 |  | 1115.4
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 20 | 40 | CS | 5.46 | 1 | 110 | 109.2 |  | 12012
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 4 | 2 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.143 | 0 | NA | 0.18767 | 1 | 110 | 0.026837 |  | 2.9521
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 8.919 | 0 | NA | 0.29857 | 1 | 110 | 2.663 |  | 292.925
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 10.198 | 0 | NA | 0.37535 | 1 | 110 | 3.8278 |  | 421.0561
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 9.129 | 0 | NA | 0.57155 | 1 | 110 | 5.2177 |  | 573.945
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1250
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 11 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 550
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 375
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 600
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 0 | NA | 19 | 1 | 110 | 19 |  | 2090
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_7 | LG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_7 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.1573 | 0 | NA | 1.1943 | 0.75 | 78 | 0.1409 |  | 10.9899
Proj_A | Area_7 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 9.8109 | 0 | NA | 1.9109 | 0.75 | 78 | 14.0604 |  | 1096.7113
Proj_A | Area_7 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 11.2178 | 0 | NA | 2.4184 | 0.75 | 78 | 20.3471 |  | 1587.0704
Proj_A | Area_7 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 10.4983 | 0 | NA | 3.6724 | 0.75 | 78 | 28.9158 |  | 2255.4315
Proj_A | Area_7 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_7 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 2 | 0 | NA | 0.78 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_7 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_7 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 14 | 0 | NA | 1.69 | 0.75 | 78 | 17.745 |  | 1384.11
Proj_A | Area_7 | LG | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_7 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_7 | LG | Field | 600 | 150-30-F-310 | Install Inlines - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_7 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 4 | 0 | NA | 5.46 | 0.75 | 78 | 16.38 |  | 1277.64
Proj_A | Area_7 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 7 | 0 | NA | 1.17 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_7 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 25.5 | 0 | NA | 1.17 | 0.75 | 78 | 22.3762 |  | 1745.3475
Proj_A | Area_7 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 9.5 | 0 | NA | 2.34 | 0.75 | 78 | 16.6725 |  | 1300.455
Proj_A | Area_7 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 14 | 0 | NA | 3.38 | 0.75 | 78 | 35.49 |  | 2768.22
Proj_A | Area_7 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 6 | 0 | NA | 5.33 | 0.75 | 78 | 23.985 |  | 1870.83
Proj_A | Area_7 | LG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 2 | 0 | NA | 1.6538 | 0.75 | 78 | 2.4806 |  | 193.4888
Proj_A | Area_7 | LG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 6 | 0 | NA | 1.7364 | 0.75 | 78 | 7.814 |  | 609.4896
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 96 | 192 | CS | 1.1765 | 1 | 110 | 112.944 |  | 12423.84
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 3 | 2.25 | CS | 0.65 | 1 | 110 | 1.95 |  | 214.5
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 3 | 2.25 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 3 | 2.25 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 7 | 7 | CS | 0.78 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 19 | 19 | CS | 0.78 | 1 | 110 | 14.82 |  | 1630.2
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 37 | 37 | CS | 0.78 | 1 | 110 | 28.86 |  | 3174.6
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 20 | 20 | CS | 0.91 | 1 | 110 | 18.2 |  | 2002
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 28 | 28 | CS | 0.91 | 1 | 110 | 25.48 |  | 2802.8
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 3 | 2.25 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 5 | 3.75 | NA | 0.26 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.758 | 0 | NA | 0.17914 | 1 | 110 | 0.49408 |  | 54.3483
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 2.752 | 0 | NA | 0.15355 | 1 | 110 | 0.42257 |  | 46.4829
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 20.895 | 0 | NA | 0.18767 | 1 | 110 | 3.9214 |  | 431.3575
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 51 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2550
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 69 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 3450
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_8 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_8 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.8959 | 0 | NA | 1.1644 | 0.75 | 78 | 2.529 |  | 197.2657
Proj_A | Area_8 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 2.8896 | 0 | NA | 1.0151 | 0.75 | 78 | 2.2 |  | 171.6011
Proj_A | Area_8 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 22.9845 | 0 | NA | 1.1943 | 0.75 | 78 | 20.5875 |  | 1605.8262
Proj_A | Area_8 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_8 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 3 | 0 | NA | 0.65 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_8 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 4 | 0 | NA | 0.39 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_8 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 10 | 0 | NA | 0.78 | 0.75 | 78 | 5.85 |  | 456.3
Proj_A | Area_8 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_8 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 1.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.0237 |  | 79.8525
Proj_A | Area_8 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_8 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 4.5 | 0 | NA | 0.91 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_8 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.9488 |  | 308.0025
Proj_A | Area_8 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 8 | 0 | NA | 0.4 | 0.75 | 78 | 2.4 |  | 187.2
Proj_A | Area_8 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 12 | 0 | NA | 1 | 0.75 | 78 | 9 |  | 702
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 28 | 56 | CS | 1.1765 | 1 | 110 | 32.942 |  | 3623.62
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 18 | 108 | CS | 2.9315 | 1 | 110 | 52.767 |  | 5804.37
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 32 | CS | 3.848 | 1 | 110 | 15.392 |  | 1693.12
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 18 | 216 | CS | 7.683 | 1 | 110 | 138.294 |  | 15212.34
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 96 | CS | 4.7255 | 1 | 110 | 37.804 |  | 4158.44
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 3 | 2.25 | CS | 0.65 | 1 | 110 | 1.95 |  | 214.5
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 6 | 4.5 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 20 | 20 | CS | 0.78 | 1 | 110 | 15.6 |  | 1716
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 25 | 25 | CS | 0.91 | 1 | 110 | 22.75 |  | 2502.5
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 32 | 32 | CS | 0.91 | 1 | 110 | 29.12 |  | 3203.2
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.17 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 5 | 10 | CS | 4.42 | 1 | 110 | 22.1 |  | 2431
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 3 | 1.5 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 3 | 2.25 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 4 | 3 | NA | 0.26 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 9 | 9 | NA | 0.39 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.78 | 0 | NA | 0.18767 | 1 | 110 | 0.14639 |  | 16.1024
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 8.906 | 0 | NA | 0.29857 | 1 | 110 | 2.6591 |  | 292.4981
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 2.912 | 0 | NA | 0.57155 | 1 | 110 | 1.6644 |  | 183.079
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 1.63 | 0 | NA | 0.40947 | 1 | 110 | 0.66743 |  | 73.4178
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 34 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1700
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 11 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2750
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 22 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1100
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 225
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_8 | LG | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_8 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.858 | 0 | NA | 1.1943 | 0.75 | 78 | 0.76852 |  | 59.9447
Proj_A | Area_8 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 9.7966 | 0 | NA | 1.9109 | 0.75 | 78 | 14.0399 |  | 1095.1128
Proj_A | Area_8 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 3.3488 | 0 | NA | 3.6724 | 0.75 | 78 | 9.2237 |  | 719.4454
Proj_A | Area_8 | LG | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 1.8745 | 0 | NA | 2.6274 | 0.75 | 78 | 3.6938 |  | 288.1188
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 3 | 0 | NA | 0.65 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 4 | 0 | NA | 0.91 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 5 | 0 | NA | 0.65 | 0.75 | 78 | 2.4375 |  | 190.125
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 6 | 0 | NA | 1.69 | 0.75 | 78 | 7.605 |  | 593.19
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 3 | 0 | NA | 4.29 | 0.75 | 78 | 9.6525 |  | 752.895
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 1 | 0 | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_8 | LG | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 5 | 0 | NA | 8.19 | 0.75 | 78 | 30.7125 |  | 2395.575
Proj_A | Area_8 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 4 | 0 | NA | 0.91 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_8 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 7.5 | 0 | NA | 1.17 | 0.75 | 78 | 6.5812 |  | 513.3375
Proj_A | Area_8 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 8 | 0 | NA | 0.91 | 0.75 | 78 | 5.46 |  | 425.88
Proj_A | Area_8 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 9 | 0 | NA | 1.17 | 0.75 | 78 | 7.8975 |  | 616.005
Proj_A | Area_8 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 6.5 | 0 | NA | 2.34 | 0.75 | 78 | 11.4075 |  | 889.785
Proj_A | Area_8 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 2 | 0 | NA | 3.38 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_8 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 0.5 | 0 | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
Proj_A | Area_8 | LG | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 9.5 | 0 | NA | 5.33 | 0.75 | 78 | 37.9763 |  | 2962.1475
Proj_A | Area_8 | LG | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | NA | 1.9144 | 0.75 | 78 | 2.8716 |  | 223.9874
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.781 | 1 | 110 | 1.781 |  | 195.91
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 33 | 66 | CS | 1.1765 | 1 | 110 | 38.8245 |  | 4270.695
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 8 | 24 | CS | 1.3715 | 1 | 110 | 10.972 |  | 1206.92
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 1 | 1.5 | CS | 1.3 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 1 | 1.5 | CS | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 21.409 | 0 | NA | 0.18767 | 1 | 110 | 4.0179 |  | 441.9685
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 4.138 | 0 | NA | 0.17488 | 1 | 110 | 0.72364 |  | 79.6006
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 36 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1800
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 3 | 0 | NA | 5.6 | 1 | 110 | 16.8 |  | 1848
Proj_A | Area_9 | DL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1500
Proj_A | Area_9 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 23.5499 | 0 | NA | 1.1943 | 0.75 | 78 | 21.094 |  | 1645.3282
Proj_A | Area_9 | DL | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 4.5518 | 0 | NA | 1.1644 | 0.75 | 78 | 3.9752 |  | 310.0639
Proj_A | Area_9 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_9 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_9 | DL | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_9 | DL | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 6 | 0 | NA | 0.65 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_9 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 13 | 0 | NA | 0.91 | 0.75 | 78 | 8.8725 |  | 692.055
Proj_A | Area_9 | DL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_9 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 9 | 0 | NA | 1 | 0.75 | 78 | 6.75 |  | 526.5
Proj_A | Area_9 | DL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 4 | 0 | NA | 1.5 | 0.75 | 78 | 4.5 |  | 351
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 34 | 102 | CS | 1.3715 | 1 | 110 | 46.631 |  | 5129.41
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 30 | 180 | CS | 2.431 | 1 | 110 | 72.93 |  | 8022.3
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 24.309 | 0 | NA | 0.17488 | 1 | 110 | 4.2511 |  | 467.6202
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchSTD | LM | 11.731 | 0 | NA | 0.21753 | 1 | 110 | 2.5518 |  | 280.7033
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 34 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1700
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 30 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 2250
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 3 | 0 | NA | 6 | 1 | 110 | 18 |  | 1980
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchSTD | EA | 1 | 0 | NA | 8.8 | 1 | 110 | 8.8 |  | 968
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 1800
Proj_A | Area_9 | FL | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_9 | FL | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchSTD | EA | 1 | 6 | CS | 3.3501 | 0.75 | 78 | 2.5126 |  | 195.9809
Proj_A | Area_9 | FL | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 26.7399 | 0 | NA | 1.1644 | 0.75 | 78 | 23.3525 |  | 1821.4945
Proj_A | Area_9 | FL | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchSTD | LM | 12.9041 | 0 | NA | 1.4033 | 0.75 | 78 | 13.5811 |  | 1059.3246
Proj_A | Area_9 | FL | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | LM | 64.1047 | 0 | NA | 1.1943 | 0.75 | 78 | 57.4194 |  | 4478.7142
Proj_A | Area_9 | FL | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_9 | FL | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 2 | 0 | NA | 1.56 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_9 | FL | Field | 600 | 150-30-F-310 | Install Blind - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_9 | FL | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_9 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 10.5 | 0 | NA | 1.04 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_9 | FL | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 7 | 0 | NA | 1.95 | 0.75 | 78 | 10.2375 |  | 798.525
Proj_A | Area_9 | FL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 9 | 0 | NA | 1.5 | 0.75 | 78 | 10.125 |  | 789.75
Proj_A | Area_9 | FL | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 8 | 0 | NA | 1.6538 | 0.75 | 78 | 9.9225 |  | 773.955
Proj_A | Area_9 | FL | Field | 600 | 150-60-F-610 | Field X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1000 | 1000
Proj_A | Area_9 | FL | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 64.1047 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 6410.47
Proj_A | Area_9 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_9 | TR | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_9 | TR | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | TR | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_9 | TR | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_9 | TR | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_9 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | TR | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Summary | Summary | Summary | Spool Fabrication | 400 | 150-50-S-510 | Pipe Supports Labor (shoes, lugs, guides, etc.) | of Labor hours | 0.05 | 0 |  | 0 | 0 | 0 | 963.9511 |  | 106034.6258
Summary | Summary | Summary | Module | 500 | 150-70-F-710 | Hydrotest of module assembly | of Module Labor | 0.05 | 0 |  | 0 | 0 | 0 | 230.2252 |  | 25324.7765
Summary | Summary | Summary | Module | 500 | 150-90-F-910 | Flushing & Drying Module Piping | of Module Labor | 0.03 | 0 |  | 0 | 0 | 0 | 138.1351 |  | 15194.8659
Summary | Summary | Summary | Field | 600 | 150-40-F-410 | Bolt torquing and tensioning | of bolt-up labor | 0.15 | 0 |  | 0 | 0 | 0 | 198.3296 |  | 15469.7108
Summary | Summary | Summary | Field | 600 | 150-70-F-710 | Field Hydrotest | of Field Labor | 0.05 | 0 |  | 0 | 0 | 0 | 285.076 |  | 22235.93
Summary | Summary | Summary | Field | 600 | 150-90-F-910 | Flushing & Drying on Site | of Field Labor | 0.03 | 0 |  | 0 | 0 | 0 | 171.0456 |  | 13341.558
WBS3 Summary (Summary by Fluid Service in the Example Project)
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## WBS4-Summary By Line No
WBS1 | WBS2 | WBS3 | WBS4 | Location | CBS | COA | Description | Units | Quantity | Dia-Inch | Material | STD_UNIT_HR | PF | WR | Location Hours | S/C Rate_$ | Total Cost
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 4.712 | 0 | NA | 0.18767 | 1 | 110 | 0.88432 |  | 97.2748
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 800
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_1 | DL | DL-XP01-8001 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_1 | DL | DL-XP01-8001 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 5.1832 | 0 | NA | 1.1943 | 0.75 | 78 | 4.6427 |  | 362.1275
Proj_A | Area_1 | DL | DL-XP01-8001 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_1 | DL | DL-XP01-8001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_1 | DL | DL-XP01-8001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_1 | DL | DL-XP01-8001 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_1 | DL | DL-XP01-8002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_1 | DL | DL-XP01-8002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | DL | DL-XP01-8002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | DL | DL-XP01-8002 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | DL | DL-XP01-8002 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | DL | DL-XP01-8002 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 4.005 | 0 | NA | 0.18767 | 1 | 110 | 0.75163 |  | 82.6794
Proj_A | Area_1 | DL | DL-XP01-8002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | DL | DL-XP01-8002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 800
Proj_A | Area_1 | DL | DL-XP01-8002 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 4.4055 | 0 | NA | 1.1943 | 0.75 | 78 | 3.9461 |  | 307.793
Proj_A | Area_1 | DL | DL-XP01-8002 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_1 | DL | DL-XP01-8002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_1 | DL | DL-XP01-8002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_1 | DL | DL-XP01-8002 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.26 | 0 | NA | 0.17914 | 1 | 110 | 0.22572 |  | 24.8292
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.897 | 0 | NA | 0.18767 | 1 | 110 | 0.16834 |  | 18.5177
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_1 | DL | DL-ZL01-8084 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | DL | DL-ZL01-8084 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.323 | 0 | NA | 1.1644 | 0.75 | 78 | 1.1554 |  | 90.1214
Proj_A | Area_1 | DL | DL-ZL01-8084 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.9867 | 0 | NA | 1.1943 | 0.75 | 78 | 0.8838 |  | 68.9364
Proj_A | Area_1 | DL | DL-ZL01-8084 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | DL | DL-ZL01-8084 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | DL | DL-ZL01-8084 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_1 | DL | DL-ZL01-8084 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_1 | DL | DL-ZL01-8084 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_1 | DL | DL-ZL01-8084 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.06 | 0 | NA | 0.17914 | 1 | 110 | 0.18989 |  | 20.888
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.863 | 0 | NA | 0.18767 | 1 | 110 | 0.16196 |  | 17.8158
Proj_A | Area_1 | DL | DL-ZL01-8085 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_1 | DL | DL-ZL01-8085 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.113 | 0 | NA | 1.1644 | 0.75 | 78 | 0.97201 |  | 75.8164
Proj_A | Area_1 | DL | DL-ZL01-8085 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.9493 | 0 | NA | 1.1943 | 0.75 | 78 | 0.8503 |  | 66.3234
Proj_A | Area_1 | DL | DL-ZL01-8085 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | DL | DL-ZL01-8085 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | DL | DL-ZL01-8085 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_1 | DL | DL-ZL01-8085 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_1 | DL | DL-ZL01-8085 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_1 | DL | DL-ZL01-8085 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_1 | FL | FL-XP01-8123 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_1 | FL | FL-XP01-8123 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 10 | 30 | CS | 1.3715 | 1 | 110 | 13.715 |  | 1508.65
Proj_A | Area_1 | FL | FL-XP01-8123 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 10.292 | 0 | NA | 0.17488 | 1 | 110 | 1.7998 |  | 197.9821
Proj_A | Area_1 | FL | FL-XP01-8123 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | FL | FL-XP01-8123 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_1 | FL | FL-XP01-8123 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_1 | FL | FL-XP01-8123 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_1 | FL | FL-XP01-8123 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 11.3212 | 0 | NA | 1.1644 | 0.75 | 78 | 9.887 |  | 771.1885
Proj_A | Area_1 | FL | FL-XP01-8123 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_1 | FL | FL-XP01-8123 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 1.5 | 0 | NA | 1.04 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_1 | FL | FL-XP01-8123 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 5 | 0 | NA | 1.5 | 0.75 | 78 | 5.625 |  | 438.75
Proj_A | Area_1 | FL | FL-YP01-8121 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 5 | 15 | CS | 1.3715 | 1 | 110 | 6.8575 |  | 754.325
Proj_A | Area_1 | FL | FL-YP01-8121 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | FL | FL-YP01-8121 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | FL | FL-YP01-8121 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | FL | FL-YP01-8121 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_1 | FL | FL-YP01-8121 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 3.857 | 0 | NA | 0.17488 | 1 | 110 | 0.6745 |  | 74.1952
Proj_A | Area_1 | FL | FL-YP01-8121 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_1 | FL | FL-YP01-8121 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_1 | FL | FL-YP01-8121 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 4.2427 | 0 | NA | 1.1644 | 0.75 | 78 | 3.7052 |  | 289.0084
Proj_A | Area_1 | FL | FL-YP01-8121 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL300 | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_1 | FL | FL-YP01-8121 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_1 | FL | FL-YP01-8121 | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_1 | FL | FL-YP01-8121 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_1 | FL | FL-YP01-8121 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_1 | GH | GH-ZL01-3001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_1 | GH | GH-ZL01-3001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 10 | 40 | CS | 2.119 | 1 | 110 | 21.19 |  | 2330.9
Proj_A | Area_1 | GH | GH-ZL01-3001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | GH | GH-ZL01-3001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_1 | GH | GH-ZL01-3001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | GH | GH-ZL01-3001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 0.991 | 0 | NA | 0.24739 | 1 | 110 | 0.24516 |  | 26.9677
Proj_A | Area_1 | GH | GH-ZL01-3001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_1 | GH | GH-ZL01-3001 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 1.0901 | 0 | NA | 1.5526 | 0.75 | 78 | 1.2693 |  | 99.0087
Proj_A | Area_1 | GH | GH-ZL01-3001 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_1 | GH | GH-ZL01-3001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_1 | GH | GH-ZL01-3001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_1 | GH | GH-ZL01-3001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_1 | GH | GH-ZL01-3001 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 1 | 0 | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 18 | 72 | CS | 2.119 | 1 | 110 | 38.142 |  | 4195.62
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 7.654 | 0 | NA | 0.24739 | 1 | 110 | 1.8935 |  | 208.2853
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 1 | 0 | NA | 8.4 | 1 | 110 | 8.4 |  | 924
Proj_A | Area_1 | GH | GH-ZL01-3002 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 700
Proj_A | Area_1 | GH | GH-ZL01-3002 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 8.4194 | 0 | NA | 1.5526 | 0.75 | 78 | 9.8038 |  | 764.6945
Proj_A | Area_1 | GH | GH-ZL01-3002 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | LM | 15.3076 | 0 | NA | 1.3222 | 0.75 | 78 | 15.1803 |  | 1184.0615
Proj_A | Area_1 | GH | GH-ZL01-3002 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_1 | GH | GH-ZL01-3002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_1 | GH | GH-ZL01-3002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | GH | GH-ZL01-3002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | NA | 1.95 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_1 | GH | GH-ZL01-3002 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 6 | 0 | NA | 1.5 | 0.75 | 78 | 6.75 |  | 526.5
Proj_A | Area_1 | GH | GH-ZL01-3002 | Field | 300 | 150-80-F-810 | Field Coating - NB 4 | LM | 15.3076 | 0 | CS | 0 | 0.75 | 78 | 0 | 80 | 1224.608
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.079 | 0 | NA | 0.18767 | 1 | 110 | 0.2025 |  | 22.2749
Proj_A | Area_1 | GH | GH-ZL01-3003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | GH | GH-ZL01-3003 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1869 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0631 |  | 82.9235
Proj_A | Area_1 | GH | GH-ZL01-3003 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | GH | GH-ZL01-3003 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_1 | GH | GH-ZL01-3003 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_1 | GH | GH-ZL01-3003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_1 | GH | GH-ZL01-3003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 6 | 24 | CS | 2.119 | 1 | 110 | 12.714 |  | 1398.54
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 1.3 | 0 | NA | 0.24739 | 1 | 110 | 0.3216 |  | 35.3764
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 1.43 | 0 | NA | 1.5526 | 0.75 | 78 | 1.6651 |  | 129.8802
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | NA | 1.95 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 6 | 24 | CS | 2.119 | 1 | 110 | 12.714 |  | 1398.54
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 1.8 | 0 | NA | 0.24739 | 1 | 110 | 0.4453 |  | 48.9827
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 1.98 | 0 | NA | 1.5526 | 0.75 | 78 | 2.3056 |  | 179.8341
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5005 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | NA | 1.95 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.585 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 4 | 16 | CS | 2.119 | 1 | 110 | 8.476 |  | 932.36
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 20 | 200 | CS | 5.915 | 1 | 110 | 118.3 |  | 13013
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 5 | 10 | CS | 5.46 | 1 | 110 | 27.3 |  | 3003
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 14.087 | 0 | NA | 0.46918 | 1 | 110 | 6.6094 |  | 727.0319
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1000
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | EA | 2 | 0 | NA | 14.6 | 1 | 110 | 29.2 |  | 3212
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 10 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 1500 | 3000
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 16.2001 | 0 | NA | 2.9857 | 0.75 | 78 | 36.2765 |  | 2829.5661
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 5 | 0 | NA | 1.17 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 0.5 | 0 | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 3.5 | 0 | NA | 4.16 | 0.75 | 78 | 10.92 |  | 851.76
Proj_A | Area_1 | HPG | HPG-ZL01-5016 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 8 | 0 | NA | 1.8233 | 0.75 | 78 | 10.9396 |  | 853.2854
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 2 | 8 | CS | 2.119 | 1 | 110 | 4.238 |  | 466.18
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 20 | 200 | CS | 5.915 | 1 | 110 | 118.3 |  | 13013
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 20.258 | 0 | NA | 0.46918 | 1 | 110 | 9.5047 |  | 1045.518
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 750
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | EA | 3 | 0 | NA | 14.6 | 1 | 110 | 43.8 |  | 4818
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 10 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 1500 | 4500
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 23.2967 | 0 | NA | 2.9857 | 0.75 | 78 | 52.1679 |  | 4069.0956
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 2 | 0 | NA | 6.63 | 0.75 | 78 | 9.945 |  | 775.71
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 0.5 | 0 | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 5.5 | 0 | NA | 4.16 | 0.75 | 78 | 17.16 |  | 1338.48
Proj_A | Area_1 | HPG | HPG-ZL01-5017 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 5 | 0 | NA | 1.8233 | 0.75 | 78 | 6.8372 |  | 533.3034
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 4 | 16 | CS | 2.119 | 1 | 110 | 8.476 |  | 932.36
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 1.739 | 0 | NA | 0.24739 | 1 | 110 | 0.43021 |  | 47.3227
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 1.9129 | 0 | NA | 1.5526 | 0.75 | 78 | 2.2274 |  | 173.7397
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | NA | 1.95 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_1 | HPG | HPG-ZL01-5032 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 1 | 0 | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 18 | 72 | CS | 2.119 | 1 | 110 | 38.142 |  | 4195.62
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 36 | CS | 2.9315 | 1 | 110 | 17.589 |  | 1934.79
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 29.601 | 0 | NA | 0.24739 | 1 | 110 | 7.3229 |  | 805.5206
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 1.65 | 0 | NA | 0.29857 | 1 | 110 | 0.49264 |  | 54.1906
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 3 | 0 | NA | 8.4 | 1 | 110 | 25.2 |  | 2772
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 2100
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 32.5611 | 0 | NA | 1.5526 | 0.75 | 78 | 37.915 |  | 2957.3716
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 1.815 | 0 | NA | 1.9109 | 0.75 | 78 | 2.6012 |  | 202.8897
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 5 | 0 | NA | 1.95 | 0.75 | 78 | 7.3125 |  | 570.375
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_1 | HPG | HPG-ZL01-5045 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 8 | 0 | NA | 1.5 | 0.75 | 78 | 9 |  | 702
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 18 | 72 | CS | 2.119 | 1 | 110 | 38.142 |  | 4195.62
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 36 | CS | 2.9315 | 1 | 110 | 17.589 |  | 1934.79
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 30.505 | 0 | NA | 0.24739 | 1 | 110 | 7.5466 |  | 830.1208
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 1.499 | 0 | NA | 0.29857 | 1 | 110 | 0.44756 |  | 49.2314
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 3 | 0 | NA | 8.4 | 1 | 110 | 25.2 |  | 2772
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 2100
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 33.5555 | 0 | NA | 1.5526 | 0.75 | 78 | 39.0729 |  | 3047.6883
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 1.6489 | 0 | NA | 1.9109 | 0.75 | 78 | 2.3631 |  | 184.3223
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 5 | 0 | NA | 1.95 | 0.75 | 78 | 7.3125 |  | 570.375
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_1 | HPG | HPG-ZL01-5046 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 2 | 0 | NA | 1.5 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 4 | 16 | CS | 2.119 | 1 | 110 | 8.476 |  | 932.36
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 2.089 | 0 | NA | 0.24739 | 1 | 110 | 0.51679 |  | 56.8472
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 2.2979 | 0 | NA | 1.5526 | 0.75 | 78 | 2.6757 |  | 208.7075
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | Field | 600 | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | Field | 600 | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_1 | HPG | HPG-ZL01-5053 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | NA | 1.95 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_1 | IA | IA-XP02-9003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 10 | CS | 1.1765 | 1 | 110 | 5.8825 |  | 647.075
Proj_A | Area_1 | IA | IA-XP02-9003 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 3.967 | 0 | NA | 0.18767 | 1 | 110 | 0.7445 |  | 81.895
Proj_A | Area_1 | IA | IA-XP02-9003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_1 | IA | IA-XP02-9003 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 4.3637 | 0 | NA | 1.1943 | 0.75 | 78 | 3.9086 |  | 304.8726
Proj_A | Area_1 | IA | IA-XP02-9003 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | IA | IA-XP02-9003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.7062 |  | 133.0875
Proj_A | Area_1 | IA | IA-XP02-9003 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 2 | 8 | CS | 2.119 | 1 | 110 | 4.238 |  | 466.18
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 52 | 312 | CS | 2.9315 | 1 | 110 | 152.438 |  | 16768.18
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 38.509 | 0 | NA | 0.29857 | 1 | 110 | 11.4977 |  | 1264.7438
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 525
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 5 | 0 | NA | 12 | 1 | 110 | 60 |  | 6600
Proj_A | Area_1 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 5 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 4500
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 3 | 18 | CS | 4.2237 | 0.75 | 78 | 9.5033 |  | 741.2593
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 42.3599 | 0 | NA | 1.9109 | 0.75 | 78 | 60.7077 |  | 4735.2007
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 69.762 | 0 | NA | 1.6208 | 0.75 | 78 | 84.8034 |  | 6614.6667
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 0.5 | 0 | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 9.5 | 0 | NA | 2.34 | 0.75 | 78 | 16.6725 |  | 1300.455
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 35 | 0 | NA | 1.6538 | 0.75 | 78 | 43.4109 |  | 3386.0531
Proj_A | Area_1 | LG | LG-ZL01-4008 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 69.762 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 6976.2
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 2 | 8 | CS | 2.119 | 1 | 110 | 4.238 |  | 466.18
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 48 | 288 | CS | 2.9315 | 1 | 110 | 140.712 |  | 15478.32
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 38.878 | 0 | NA | 0.29857 | 1 | 110 | 11.6078 |  | 1276.8628
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 525
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 4 | 0 | NA | 12 | 1 | 110 | 48 |  | 5280
Proj_A | Area_1 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 4 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 3600
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 4 | 24 | CS | 4.2237 | 0.75 | 78 | 12.6711 |  | 988.3458
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 42.7658 | 0 | NA | 1.9109 | 0.75 | 78 | 61.2894 |  | 4780.5742
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 71.082 | 0 | NA | 1.6208 | 0.75 | 78 | 86.408 |  | 6739.826
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 0.5 | 0 | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 9.5 | 0 | NA | 2.34 | 0.75 | 78 | 16.6725 |  | 1300.455
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 12 | 0 | NA | 1.6538 | 0.75 | 78 | 14.8838 |  | 1160.9325
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1000 | 1000
Proj_A | Area_1 | LG | LG-ZL01-4009 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 71.082 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 7108.2
Proj_A | Area_1 | LG | LG-ZL01-4011 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_1 | LG | LG-ZL01-4011 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 10 | 40 | CS | 2.119 | 1 | 110 | 21.19 |  | 2330.9
Proj_A | Area_1 | LG | LG-ZL01-4011 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4011 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_1 | LG | LG-ZL01-4011 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | LG | LG-ZL01-4011 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 1.741 | 0 | NA | 0.24739 | 1 | 110 | 0.4307 |  | 47.3772
Proj_A | Area_1 | LG | LG-ZL01-4011 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_1 | LG | LG-ZL01-4011 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 1.9151 | 0 | NA | 1.5526 | 0.75 | 78 | 2.23 |  | 173.9395
Proj_A | Area_1 | LG | LG-ZL01-4011 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_1 | LG | LG-ZL01-4011 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_1 | LG | LG-ZL01-4011 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_1 | LG | LG-ZL01-4011 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_1 | LG | LG-ZL01-4011 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 1 | 0 | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 18 | 72 | CS | 2.119 | 1 | 110 | 38.142 |  | 4195.62
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 8.007 | 0 | NA | 0.24739 | 1 | 110 | 1.9808 |  | 217.8914
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 1 | 0 | NA | 8.4 | 1 | 110 | 8.4 |  | 924
Proj_A | Area_1 | LG | LG-ZL01-4012 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 700
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 4 SchXST | EA | 1 | 4 | CS | 2.99 | 0.75 | 78 | 2.2425 |  | 174.915
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 8.8077 | 0 | NA | 1.5526 | 0.75 | 78 | 10.2559 |  | 799.962
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | LM | 16.8509 | 0 | NA | 1.3222 | 0.75 | 78 | 16.7107 |  | 1303.4376
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 3 | 0 | NA | 1.95 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 5 | 0 | NA | 1.5 | 0.75 | 78 | 5.625 |  | 438.75
Proj_A | Area_1 | LG | LG-ZL01-4012 | Field | 300 | 150-80-F-810 | Field Coating - NB 4 | LM | 16.8509 | 0 | CS | 0 | 0.75 | 78 | 0 | 80 | 1348.072
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.079 | 0 | NA | 0.18767 | 1 | 110 | 0.2025 |  | 22.2749
Proj_A | Area_1 | LG | LG-ZL01-4020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_1 | LG | LG-ZL01-4020 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1869 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0631 |  | 82.9235
Proj_A | Area_1 | LG | LG-ZL01-4020 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_1 | LG | LG-ZL01-4020 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_1 | LG | LG-ZL01-4020 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_1 | LG | LG-ZL01-4020 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_1 | LG | LG-ZL01-4020 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_1 | TR | TR-YP01-8087 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL300 | EA | 1 | 0 | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57
Proj_A | Area_1 | TR | TR-YP01-8087 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 0 | NA | 3.12 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_10 | BD | BD-XP01-6002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | BD | BD-XP01-6002 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.14 | 0 | NA | 0.18767 | 1 | 110 | 0.026274 |  | 2.8902
Proj_A | Area_10 | BD | BD-XP01-6002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_10 | BD | BD-XP01-6002 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.154 | 0 | NA | 1.1943 | 0.75 | 78 | 0.13794 |  | 10.7593
Proj_A | Area_10 | BD | BD-XP01-6002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.942 | 0 | NA | 0.17914 | 1 | 110 | 0.16875 |  | 18.5628
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 3.212 | 0 | NA | 0.18767 | 1 | 110 | 0.60281 |  | 66.3087
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_10 | DL | DL-ZL01-8077 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | DL | DL-ZL01-8077 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.9891 | 0 | NA | 1.1644 | 0.75 | 78 | 0.8638 |  | 67.3765
Proj_A | Area_10 | DL | DL-ZL01-8077 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 3.5332 | 0 | NA | 1.1943 | 0.75 | 78 | 3.1647 |  | 246.8492
Proj_A | Area_10 | DL | DL-ZL01-8077 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | DL | DL-ZL01-8077 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | DL | DL-ZL01-8077 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_10 | DL | DL-ZL01-8077 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_10 | DL | DL-ZL01-8077 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_10 | DL | DL-ZL01-8077 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 0.86 | 0 | NA | 0.15355 | 1 | 110 | 0.13205 |  | 14.5259
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 6.069 | 0 | NA | 0.18767 | 1 | 110 | 1.139 |  | 125.2888
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_10 | DL | DL-ZL02-8078 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_10 | DL | DL-ZL02-8078 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 0.903 | 0 | NA | 1.0151 | 0.75 | 78 | 0.6875 |  | 53.6254
Proj_A | Area_10 | DL | DL-ZL02-8078 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 6.6759 | 0 | NA | 1.1943 | 0.75 | 78 | 5.9797 |  | 466.4159
Proj_A | Area_10 | DL | DL-ZL02-8078 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | DL | DL-ZL02-8078 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | DL | DL-ZL02-8078 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_10 | DL | DL-ZL02-8078 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_10 | DL | DL-ZL02-8078 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_10 | DL | DL-ZL02-8078 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_10 | DL | DL-ZL02-8083 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 14 | CS | 1.1765 | 1 | 110 | 8.2355 |  | 905.905
Proj_A | Area_10 | DL | DL-ZL02-8083 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 18 | CS | 1.3715 | 1 | 110 | 8.229 |  | 905.19
Proj_A | Area_10 | DL | DL-ZL02-8083 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.945 | 0 | NA | 0.18767 | 1 | 110 | 0.5527 |  | 60.7967
Proj_A | Area_10 | DL | DL-ZL02-8083 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 1.791 | 0 | NA | 0.17488 | 1 | 110 | 0.31321 |  | 34.4526
Proj_A | Area_10 | DL | DL-ZL02-8083 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | DL | DL-ZL02-8083 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | DL | DL-ZL02-8083 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 3.2395 | 0 | NA | 1.1943 | 0.75 | 78 | 2.9017 |  | 226.3297
Proj_A | Area_10 | DL | DL-ZL02-8083 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 1.9701 | 0 | NA | 1.1644 | 0.75 | 78 | 1.7205 |  | 134.2012
Proj_A | Area_10 | DL | DL-ZL02-8083 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | DL | DL-ZL02-8083 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | DL | DL-ZL02-8083 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 1 | 0 | NA | 1.3 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_10 | DL | DL-ZL02-8083 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_10 | DL | DL-ZL02-8083 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 1 | 0 | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
Proj_A | Area_10 | GH | GH-YP01-3004 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_10 | GH | GH-YP01-3004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | GH | GH-YP01-3004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_10 | GH | GH-YP01-3004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | GH | GH-YP01-3004 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.2 | 0 | NA | 0.18767 | 1 | 110 | 0.037535 |  | 4.1288
Proj_A | Area_10 | GH | GH-YP01-3004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_10 | GH | GH-YP01-3004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 14 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 700
Proj_A | Area_10 | GH | GH-YP01-3004 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.22 | 0 | NA | 1.1943 | 0.75 | 78 | 0.19706 |  | 15.3704
Proj_A | Area_10 | GH | GH-YP01-3004 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_10 | GH | GH-YP01-3004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_10 | GH | GH-YP01-3004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 4 | 0 | NA | 1.04 | 0.75 | 78 | 3.12 |  | 243.36
Proj_A | Area_10 | GH | GH-YP01-3004 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 4 | 24 | CS | 2.431 | 1 | 110 | 9.724 |  | 1069.64
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 19 | 152 | CS | 3.0095 | 1 | 110 | 57.1805 |  | 6289.855
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 6.637 | 0 | NA | 0.26871 | 1 | 110 | 1.7835 |  | 196.18
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 300
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 19 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 1900
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | EA | 1 | 0 | NA | 9.8 | 1 | 110 | 9.8 |  | 1078
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 1100
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 7.3007 | 0 | NA | 1.7019 | 0.75 | 78 | 9.3185 |  | 726.8467
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 2 | 0 | NA | 1.95 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_10 | GHH | GHH-XP01-1001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 3 | 0 | NA | 2.73 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_10 | HPG | HPG-YP01-5015 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 96 | CS | 4.7255 | 1 | 110 | 37.804 |  | 4158.44
Proj_A | Area_10 | HPG | HPG-YP01-5015 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 1.686 | 0 | NA | 0.40947 | 1 | 110 | 0.69036 |  | 75.9401
Proj_A | Area_10 | HPG | HPG-YP01-5015 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2000
Proj_A | Area_10 | HPG | HPG-YP01-5015 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 1.9389 | 0 | NA | 2.6274 | 0.75 | 78 | 3.8207 |  | 298.0174
Proj_A | Area_10 | HPG | HPG-YP01-5015 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL300 | EA | 1.5 | 0 | NA | 4.94 | 0.75 | 78 | 5.5575 |  | 433.485
Proj_A | Area_10 | HPG | HPG-YP01-5015 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 1 | 8 | CS | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 2 | 16 | CS | 3.848 | 1 | 110 | 7.696 |  | 846.56
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 32 | 384 | CS | 7.683 | 1 | 110 | 245.856 |  | 27044.16
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 24.628 | 0 | NA | 0.57155 | 1 | 110 | 14.0761 |  | 1548.3752
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1250
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 3 | 0 | NA | 19 | 1 | 110 | 57 |  | 6270
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 5100
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 28.3222 | 0 | NA | 3.6724 | 0.75 | 78 | 78.0083 |  | 6084.6498
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 1 | 0 | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 2 | 0 | NA | 3.38 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 5.5 | 0 | NA | 5.33 | 0.75 | 78 | 21.9863 |  | 1714.9275
Proj_A | Area_10 | HPG | HPG-ZL01-5010 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | NA | 1.9144 | 0.75 | 78 | 4.3075 |  | 335.9811
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 8 | 96 | CS | 7.683 | 1 | 110 | 61.464 |  | 6761.04
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 1.416 | 0 | NA | 0.57155 | 1 | 110 | 0.80932 |  | 89.0247
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 1.6284 | 0 | NA | 3.6724 | 0.75 | 78 | 4.4851 |  | 349.8402
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 2 | 0 | NA | 8.19 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 1 | 0 | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 4 | 0 | NA | 5.33 | 0.75 | 78 | 15.99 |  | 1247.22
Proj_A | Area_10 | HPG | HPG-ZL01-5011 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 1 | 0 | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 10 | 120 | CS | 7.683 | 1 | 110 | 76.83 |  | 8451.3
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 6.603 | 0 | NA | 0.57155 | 1 | 110 | 3.7739 |  | 415.1341
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 0 | NA | 19 | 1 | 110 | 19 |  | 2090
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 7.5934 | 0 | NA | 3.6724 | 0.75 | 78 | 20.9148 |  | 1631.3522
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 1 | 0 | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 2 | 0 | NA | 8.19 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 5 | 0 | NA | 5.33 | 0.75 | 78 | 19.9875 |  | 1559.025
Proj_A | Area_10 | HPG | HPG-ZL01-5013 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | NA | 1.9144 | 0.75 | 78 | 2.8716 |  | 223.9874
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 4 | 48 | CS | 7.683 | 1 | 110 | 30.732 |  | 3380.52
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 10 | 160 | CS | 14.365 | 1 | 110 | 143.65 |  | 15801.5
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 14.773 | 0 | NA | 0.79335 | 1 | 110 | 11.7201 |  | 1289.2107
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 2 | 0 | NA | 17.6 | 1 | 110 | 35.2 |  | 3872
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 4200
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 16.9889 | 0 | NA | 5.1056 | 0.75 | 78 | 65.0536 |  | 5074.1831
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 1 | 0 | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 1.5 | 0 | NA | 6.76 | 0.75 | 78 | 7.605 |  | 593.19
Proj_A | Area_10 | HPG | HPG-ZL01-5014 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 3 | 0 | NA | 2.1107 | 0.75 | 78 | 4.749 |  | 370.4192
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 1 | 10 | CS | 5.915 | 1 | 110 | 5.915 |  | 650.65
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 0.333 | 0 | NA | 0.46918 | 1 | 110 | 0.15624 |  | 17.1862
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 0.38295 | 0 | NA | 2.9857 | 0.75 | 78 | 0.85753 |  | 66.8876
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | Field | 600 | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | Field | 600 | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
Proj_A | Area_10 | HPG | HPG-ZL01-5039 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 1.5 | 0 | NA | 4.16 | 0.75 | 78 | 4.68 |  | 365.04
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 60 | CS | 2.9315 | 1 | 110 | 29.315 |  | 3224.65
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 6.408 | 0 | NA | 0.29857 | 1 | 110 | 1.9132 |  | 210.4567
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 150
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 2 | 12 | CS | 4.2237 | 0.75 | 78 | 6.3355 |  | 494.1729
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 7.0488 | 0 | NA | 1.9109 | 0.75 | 78 | 10.1019 |  | 787.95
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 36.8324 | 0 | NA | 1.6208 | 0.75 | 78 | 44.7739 |  | 3492.3605
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | NA | 2.34 | 0.75 | 78 | 5.265 |  | 410.67
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 12 | 0 | NA | 1.6538 | 0.75 | 78 | 14.8838 |  | 1160.9325
Proj_A | Area_10 | HPG | HPG-ZL01-5045 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 36.8324 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 3683.24
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 60 | CS | 2.9315 | 1 | 110 | 29.315 |  | 3224.65
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 18.442 | 0 | NA | 0.29857 | 1 | 110 | 5.5062 |  | 605.6871
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 150
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 2 | 0 | NA | 12 | 1 | 110 | 24 |  | 2640
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 1800
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 1 | 6 | CS | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 20.2862 | 0 | NA | 1.9109 | 0.75 | 78 | 29.073 |  | 2267.6925
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 17.3162 | 0 | NA | 1.6208 | 0.75 | 78 | 21.0498 |  | 1641.8809
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | NA | 2.34 | 0.75 | 78 | 5.265 |  | 410.67
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 4 | 0 | NA | 1.6538 | 0.75 | 78 | 4.9613 |  | 386.9775
Proj_A | Area_10 | HPG | HPG-ZL01-5046 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 17.3162 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 1731.62
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 13 | 130 | CS | 5.915 | 1 | 110 | 76.895 |  | 8458.45
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 34 | 408 | CS | 7.683 | 1 | 110 | 261.222 |  | 28734.42
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 3.618 | 0 | NA | 0.46918 | 1 | 110 | 1.6975 |  | 186.7255
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 19.34 | 0 | NA | 0.57155 | 1 | 110 | 11.0538 |  | 1215.9159
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1250
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 2 | 0 | NA | 19 | 1 | 110 | 38 |  | 4180
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 3400
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 3 | 36 | CS | 11.3555 | 0.75 | 78 | 25.5499 |  | 1992.8902
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 4.1607 | 0 | NA | 2.9857 | 0.75 | 78 | 9.317 |  | 726.7247
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 22.241 | 0 | NA | 3.6724 | 0.75 | 78 | 61.2588 |  | 4778.1844
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 57.1262 | 0 | NA | 3.1137 | 0.75 | 78 | 133.4042 |  | 10405.5257
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 1.5 | 0 | NA | 4.16 | 0.75 | 78 | 4.68 |  | 365.04
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 6.5 | 0 | NA | 5.33 | 0.75 | 78 | 25.9838 |  | 2026.7325
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 2 | 0 | NA | 1.8233 | 0.75 | 78 | 2.7349 |  | 213.3213
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 9 | 0 | NA | 1.9144 | 0.75 | 78 | 12.9224 |  | 1007.9434
Proj_A | Area_10 | HPG | HPG-ZL01-5047 | Field | 300 | 150-80-F-810 | Field Coating - NB 12 | LM | 57.1262 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 6855.15
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_10 | HPG | HPG-ZL01-5051 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 16 | 128 | CS | 3.0095 | 1 | 110 | 48.152 |  | 5296.72
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 22.923 | 0 | NA | 0.26871 | 1 | 110 | 6.1597 |  | 677.5702
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 200
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | EA | 3 | 0 | NA | 9.8 | 1 | 110 | 29.4 |  | 3234
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 3300
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 25.2153 | 0 | NA | 1.7019 | 0.75 | 78 | 32.1846 |  | 2510.3974
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 1 | 0 | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 4 | 0 | NA | 3.38 | 0.75 | 78 | 10.14 |  | 790.92
Proj_A | Area_10 | HPG | HPG-ZL02-5009 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 3 | 0 | NA | 1.7364 | 0.75 | 78 | 3.907 |  | 304.7448
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 2 | 16 | CS | 3.0095 | 1 | 110 | 6.019 |  | 662.09
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 96 | CS | 4.7255 | 1 | 110 | 37.804 |  | 4158.44
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 11.999 | 0 | NA | 0.40947 | 1 | 110 | 4.9132 |  | 540.4538
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 0 | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 13.7988 | 0 | NA | 2.6274 | 0.75 | 78 | 27.1916 |  | 2120.9433
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 0.5 | 0 | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 2 | 0 | NA | 5.33 | 0.75 | 78 | 7.995 |  | 623.61
Proj_A | Area_10 | HPG | HPG-ZL02-5012 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | NA | 1.9144 | 0.75 | 78 | 2.8716 |  | 223.9874
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_10 | HPG | HPG-ZL02-5052 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_10 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_10 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 3.85 | 0 | NA | 0.18767 | 1 | 110 | 0.72254 |  | 79.4796
Proj_A | Area_10 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_10 | IA | IA-XP02-9001 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 4.235 | 0 | NA | 1.1943 | 0.75 | 78 | 3.7933 |  | 295.8809
Proj_A | Area_10 | IA | IA-XP02-9001 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | IA | IA-XP02-9001 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | IA | IA-XP02-9001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_10 | IA | IA-XP02-9001 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_10 | IA | IA-XP02-9007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_10 | IA | IA-XP02-9007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 11.732 | 0 | NA | 0.18767 | 1 | 110 | 2.2018 |  | 242.196
Proj_A | Area_10 | IA | IA-XP02-9007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_10 | IA | IA-XP02-9007 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_10 | IA | IA-XP02-9007 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_10 | IA | IA-XP02-9007 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 12.9052 | 0 | NA | 1.1943 | 0.75 | 78 | 11.5594 |  | 901.6297
Proj_A | Area_10 | IA | IA-XP02-9007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.0237 |  | 79.8525
Proj_A | Area_10 | IA | IA-XP02-9007 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_10 | IA | IA-XP02-9008 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_10 | IA | IA-XP02-9008 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 6.374 | 0 | NA | 0.18767 | 1 | 110 | 1.1962 |  | 131.5852
Proj_A | Area_10 | IA | IA-XP02-9008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_10 | IA | IA-XP02-9008 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_10 | IA | IA-XP02-9008 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_10 | IA | IA-XP02-9008 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 7.0114 | 0 | NA | 1.1943 | 0.75 | 78 | 6.2802 |  | 489.8558
Proj_A | Area_10 | IA | IA-XP02-9008 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | IA | IA-XP02-9008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3.5 | 0 | NA | 0.91 | 0.75 | 78 | 2.3887 |  | 186.3225
Proj_A | Area_10 | IA | IA-XP02-9008 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 Sch160 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 7.304 | 0 | NA | 0.18767 | 1 | 110 | 1.3708 |  | 150.7842
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_10 | IA | IA-XP02-9009 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_10 | IA | IA-XP02-9009 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 8.0344 | 0 | NA | 1.1943 | 0.75 | 78 | 7.1965 |  | 561.3283
Proj_A | Area_10 | IA | IA-XP02-9009 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_10 | IA | IA-XP02-9009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.7062 |  | 133.0875
Proj_A | Area_10 | IA | IA-XP02-9009 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | NA | 1 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_10 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 18 | 216 | CS | 4.7255 | 1 | 110 | 85.059 |  | 9356.49
Proj_A | Area_10 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 2 | CS | 4.42 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_10 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 20.519 | 0 | NA | 0.40947 | 1 | 110 | 8.4019 |  | 924.2079
Proj_A | Area_10 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 18 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 4500
Proj_A | Area_10 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_10 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 2 | 0 | NA | 12.2 | 1 | 110 | 24.4 |  | 2684
Proj_A | Area_10 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 3400
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 SchSTD | EA | 1 | 12 | CS | 7.1656 | 0.75 | 78 | 5.3742 |  | 419.1876
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 23.5968 | 0 | NA | 2.6274 | 0.75 | 78 | 46.4992 |  | 3626.9385
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 SchSTD | LM | 18.4242 | 0 | NA | 2.218 | 0.75 | 78 | 30.648 |  | 2390.5413
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 4.5 | 0 | NA | 4.42 | 0.75 | 78 | 14.9175 |  | 1163.565
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 6 | 0 | NA | 1.9144 | 0.75 | 78 | 8.6149 |  | 671.9622
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500
Proj_A | Area_10 | LG | LG-XP01-4001 | Field | 300 | 150-80-F-810 | Field Coating - NB 12 | LM | 18.4242 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 2210.898
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 18 | 216 | CS | 4.7255 | 1 | 110 | 85.059 |  | 9356.49
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 2 | CS | 4.42 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 23.572 | 0 | NA | 0.40947 | 1 | 110 | 9.652 |  | 1061.7198
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 18 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 4500
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 3 | 0 | NA | 12.2 | 1 | 110 | 36.6 |  | 4026
Proj_A | Area_10 | LG | LG-XP01-4010 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 5100
Proj_A | Area_10 | LG | LG-XP01-4010 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 27.1078 | 0 | NA | 2.6274 | 0.75 | 78 | 53.4178 |  | 4166.5868
Proj_A | Area_10 | LG | LG-XP01-4010 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_10 | LG | LG-XP01-4010 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | LG | LG-XP01-4010 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL150 | EA | 2 | 0 | NA | 5.59 | 0.75 | 78 | 8.385 |  | 654.03
Proj_A | Area_10 | LG | LG-XP01-4010 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL150 | EA | 1 | 0 | NA | 5.59 | 0.75 | 78 | 4.1925 |  | 327.015
Proj_A | Area_10 | LG | LG-XP01-4010 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_10 | LG | LG-XP01-4010 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 7 | 0 | NA | 4.42 | 0.75 | 78 | 23.205 |  | 1809.99
Proj_A | Area_10 | LG | LG-XP01-4010 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | NA | 1.9144 | 0.75 | 78 | 2.8716 |  | 223.9874
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 3 | 24 | CS | 3.0095 | 1 | 110 | 9.0285 |  | 993.135
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 96 | CS | 4.7255 | 1 | 110 | 37.804 |  | 4158.44
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 2 | CS | 4.42 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 2.941 | 0 | NA | 0.26871 | 1 | 110 | 0.79029 |  | 86.9316
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 4.841 | 0 | NA | 0.40947 | 1 | 110 | 1.9822 |  | 218.0462
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2000
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 300
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 0 | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
Proj_A | Area_10 | LG | LG-XP01-4013 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_10 | LG | LG-XP01-4013 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 3.2351 | 0 | NA | 1.7019 | 0.75 | 78 | 4.1293 |  | 322.0817
Proj_A | Area_10 | LG | LG-XP01-4013 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 5.5671 | 0 | NA | 2.6274 | 0.75 | 78 | 10.9705 |  | 855.6952
Proj_A | Area_10 | LG | LG-XP01-4013 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_10 | LG | LG-XP01-4013 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL150 | EA | 1 | 0 | NA | 5.59 | 0.75 | 78 | 4.1925 |  | 327.015
Proj_A | Area_10 | LG | LG-XP01-4013 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL150 | EA | 2 | 0 | NA | 5.59 | 0.75 | 78 | 8.385 |  | 654.03
Proj_A | Area_10 | LG | LG-XP01-4013 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_10 | LG | LG-XP01-4013 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 1 | 0 | NA | 2.73 | 0.75 | 78 | 2.0475 |  | 159.705
Proj_A | Area_10 | LG | LG-XP01-4013 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 4.5 | 0 | NA | 4.42 | 0.75 | 78 | 14.9175 |  | 1163.565
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 34 | 408 | CS | 7.683 | 1 | 110 | 261.222 |  | 28734.42
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 30.438 | 0 | NA | 0.57155 | 1 | 110 | 17.3968 |  | 1913.6529
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1250
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 3 | 0 | NA | 19 | 1 | 110 | 57 |  | 6270
Proj_A | Area_10 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 5100
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 1 | 12 | CS | 11.3555 | 0.75 | 78 | 8.5166 |  | 664.2967
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 35.0037 | 0 | NA | 3.6724 | 0.75 | 78 | 96.4113 |  | 7520.0816
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 35.2015 | 0 | NA | 3.1137 | 0.75 | 78 | 82.2044 |  | 6411.9404
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 1 | 0 | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 2 | 0 | NA | 8.19 | 0.75 | 78 | 12.285 |  | 958.23
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 10 | 0 | NA | 5.33 | 0.75 | 78 | 39.975 |  | 3118.05
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 11 | 0 | NA | 1.9144 | 0.75 | 78 | 15.794 |  | 1231.9308
Proj_A | Area_10 | LG | LG-ZL01-4002 | Field | 300 | 150-80-F-810 | Field Coating - NB 12 | LM | 35.2015 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 4224.18
Proj_A | Area_10 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 60 | CS | 2.9315 | 1 | 110 | 29.315 |  | 3224.65
Proj_A | Area_10 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 6.439 | 0 | NA | 0.29857 | 1 | 110 | 1.9225 |  | 211.4749
Proj_A | Area_10 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 150
Proj_A | Area_10 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_10 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_10 | LG | LG-ZL01-4008 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 2 | 12 | CS | 4.2237 | 0.75 | 78 | 6.3355 |  | 494.1729
Proj_A | Area_10 | LG | LG-ZL01-4008 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 7.0829 | 0 | NA | 1.9109 | 0.75 | 78 | 10.1508 |  | 791.7619
Proj_A | Area_10 | LG | LG-ZL01-4008 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 36.8324 | 0 | NA | 1.6208 | 0.75 | 78 | 44.7739 |  | 3492.3605
Proj_A | Area_10 | LG | LG-ZL01-4008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | NA | 2.34 | 0.75 | 78 | 5.265 |  | 410.67
Proj_A | Area_10 | LG | LG-ZL01-4008 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 13 | 0 | NA | 1.6538 | 0.75 | 78 | 16.1241 |  | 1257.6769
Proj_A | Area_10 | LG | LG-ZL01-4008 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 36.8324 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 3683.24
Proj_A | Area_10 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 60 | CS | 2.9315 | 1 | 110 | 29.315 |  | 3224.65
Proj_A | Area_10 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 18.698 | 0 | NA | 0.29857 | 1 | 110 | 5.5827 |  | 614.0949
Proj_A | Area_10 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 150
Proj_A | Area_10 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 2 | 0 | NA | 12 | 1 | 110 | 24 |  | 2640
Proj_A | Area_10 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 1800
Proj_A | Area_10 | LG | LG-ZL01-4009 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 1 | 6 | CS | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
Proj_A | Area_10 | LG | LG-ZL01-4009 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 20.5678 | 0 | NA | 1.9109 | 0.75 | 78 | 29.4766 |  | 2299.1712
Proj_A | Area_10 | LG | LG-ZL01-4009 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 17.3162 | 0 | NA | 1.6208 | 0.75 | 78 | 21.0498 |  | 1641.8809
Proj_A | Area_10 | LG | LG-ZL01-4009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | NA | 2.34 | 0.75 | 78 | 5.265 |  | 410.67
Proj_A | Area_10 | LG | LG-ZL01-4009 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 4 | 0 | NA | 1.6538 | 0.75 | 78 | 4.9613 |  | 386.9775
Proj_A | Area_10 | LG | LG-ZL01-4009 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 17.3162 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 1731.62
Proj_A | Area_10 | TR | TR-ZL01-8086 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8102 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8104 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8105 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8106 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 1 | 0 | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
Proj_A | Area_10 | TR | TR-ZL01-8107 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8108 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8109 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8110 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8111 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8112 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_10 | TR | TR-ZL01-8113 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_10 | TR | TR-ZL01-8114 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_10 | TR | TR-ZL02-8115 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 0.5 | 0 | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 11 | 22 | CS | 1.1765 | 1 | 110 | 12.9415 |  | 1423.565
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 20 | 60 | CS | 1.3715 | 1 | 110 | 27.43 |  | 3017.3
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL6000 | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 SchXST | EA | 1 | 3 | CS | 1.56 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL6000 | EA | 1 | 0.75 | CS | 3.38 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 16.661 | 0 | NA | 0.17488 | 1 | 110 | 2.9136 |  | 320.4994
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 11 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 550
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 21 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1050
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_2 | DL | DL-YP01-8004 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_2 | DL | DL-YP01-8004 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 18.3271 | 0 | NA | 1.1644 | 0.75 | 78 | 16.0054 |  | 1248.4232
Proj_A | Area_2 | DL | DL-YP01-8004 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | DL | DL-YP01-8004 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_2 | DL | DL-YP01-8004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_2 | DL | DL-YP01-8004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_2 | DL | DL-YP01-8004 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 4 | 0 | NA | 1.5 | 0.75 | 78 | 4.5 |  | 351
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 22 | 66 | CS | 1.3715 | 1 | 110 | 30.173 |  | 3319.03
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL6000 | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 SchXST | EA | 1 | 3 | CS | 1.56 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL6000 | EA | 1 | 0.75 | CS | 3.38 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.083 | 0 | NA | 0.18767 | 1 | 110 | 0.015577 |  | 1.7135
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 16.562 | 0 | NA | 0.17488 | 1 | 110 | 2.8963 |  | 318.595
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 800
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 23 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1150
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 2 | 0 | NA | 6 | 1 | 110 | 12 |  | 1320
Proj_A | Area_2 | DL | DL-YP01-8005 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 1200
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.0913 | 0 | NA | 1.1943 | 0.75 | 78 | 0.081779 |  | 6.3787
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 18.2182 | 0 | NA | 1.1644 | 0.75 | 78 | 15.9103 |  | 1241.0051
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 2.5 | 0 | NA | 1.04 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_2 | DL | DL-YP01-8005 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 4 | 0 | NA | 1.5 | 0.75 | 78 | 4.5 |  | 351
Proj_A | Area_2 | DL | DL-YP01-8006 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 11 | 22 | CS | 1.1765 | 1 | 110 | 12.9415 |  | 1423.565
Proj_A | Area_2 | DL | DL-YP01-8006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_2 | DL | DL-YP01-8006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | DL | DL-YP01-8006 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | DL | DL-YP01-8006 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.161 | 0 | NA | 0.18767 | 1 | 110 | 0.21789 |  | 23.9677
Proj_A | Area_2 | DL | DL-YP01-8006 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | DL | DL-YP01-8006 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 12 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 600
Proj_A | Area_2 | DL | DL-YP01-8006 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.2771 | 0 | NA | 1.1943 | 0.75 | 78 | 1.1439 |  | 89.2254
Proj_A | Area_2 | DL | DL-YP01-8006 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | DL | DL-YP01-8006 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8006 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8006 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 3 | 0 | NA | 1.04 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 9 | 9 | CS | 0.91 | 1 | 110 | 8.19 |  | 900.9
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 1.958 | 0 | NA | 0.15355 | 1 | 110 | 0.30065 |  | 33.0718
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.634 | 0 | NA | 0.18767 | 1 | 110 | 0.11898 |  | 13.0883
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 21 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1050
Proj_A | Area_2 | DL | DL-YP01-8007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_2 | DL | DL-YP01-8007 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 2.0559 | 0 | NA | 1.0151 | 0.75 | 78 | 1.5653 |  | 122.0912
Proj_A | Area_2 | DL | DL-YP01-8007 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.6974 | 0 | NA | 1.1943 | 0.75 | 78 | 0.62467 |  | 48.7243
Proj_A | Area_2 | DL | DL-YP01-8007 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | DL | DL-YP01-8007 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 3 | 0 | NA | 0.39 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | DL | DL-YP01-8007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8007 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 16 | 16 | CS | 0.78 | 1 | 110 | 12.48 |  | 1372.8
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 9 | 9 | CS | 0.91 | 1 | 110 | 8.19 |  | 900.9
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 2.84 | 0 | NA | 0.15355 | 1 | 110 | 0.43608 |  | 47.9693
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.634 | 0 | NA | 0.18767 | 1 | 110 | 0.11898 |  | 13.0883
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 33 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1650
Proj_A | Area_2 | DL | DL-YP01-8008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_2 | DL | DL-YP01-8008 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 2.982 | 0 | NA | 1.0151 | 0.75 | 78 | 2.2704 |  | 177.0884
Proj_A | Area_2 | DL | DL-YP01-8008 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.6974 | 0 | NA | 1.1943 | 0.75 | 78 | 0.62467 |  | 48.7243
Proj_A | Area_2 | DL | DL-YP01-8008 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | DL | DL-YP01-8008 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 3 | 0 | NA | 0.39 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | DL | DL-YP01-8008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8008 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
Proj_A | Area_2 | DL | DL-YP01-8009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_2 | DL | DL-YP01-8009 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8009 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_2 | DL | DL-YP01-8009 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | DL | DL-YP01-8009 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | DL | DL-YP01-8009 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.078 | 0 | NA | 0.18767 | 1 | 110 | 0.20231 |  | 22.2543
Proj_A | Area_2 | DL | DL-YP01-8009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | DL | DL-YP01-8009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_2 | DL | DL-YP01-8009 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1858 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0621 |  | 82.8466
Proj_A | Area_2 | DL | DL-YP01-8009 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | DL | DL-YP01-8009 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 2.5 | 0 | NA | 1.04 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 4 | 3 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | EA | 4 | 6 | CS | 1.04 | 1 | 110 | 4.16 |  | 457.6
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | EA | 10 | 15 | CS | 1.04 | 1 | 110 | 10.4 |  | 1144
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 7 | 10.5 | CS | 1.3 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 1 | 1.5 | CS | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1.5 SchXST | LM | 1.73 | 0 | NA | 0.17488 | 1 | 110 | 0.30254 |  | 33.2792
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.33 | 0 | NA | 0.18767 | 1 | 110 | 0.061932 |  | 6.8125
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 22 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1100
Proj_A | Area_2 | DL | DL-YP01-8010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_2 | DL | DL-YP01-8010 | Field | 600 | 150-20-F-210 | Install Spools - NB 1.5 SchXST | LM | 1.8165 | 0 | NA | 1.1047 | 0.75 | 78 | 1.505 |  | 117.3926
Proj_A | Area_2 | DL | DL-YP01-8010 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.363 | 0 | NA | 1.1943 | 0.75 | 78 | 0.32514 |  | 25.3612
Proj_A | Area_2 | DL | DL-YP01-8010 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_2 | DL | DL-YP01-8010 | Field | 600 | 150-30-F-310 | Install valve - NB 1.5 2000psi | EA | 2 | 0 | NA | 0.52 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8010 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8010 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8010 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1.5 | EA | 1 | 0 | NA | 0.5 | 0.75 | 78 | 0.375 |  | 29.25
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 2 | 2 | CS | 3.77 | 1 | 110 | 7.54 |  | 829.4
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.718 | 0 | NA | 0.18767 | 1 | 110 | 0.13475 |  | 14.8224
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_2 | DL | DL-YP01-8011 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_2 | DL | DL-YP01-8011 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.7898 | 0 | NA | 1.1943 | 0.75 | 78 | 0.70743 |  | 55.1799
Proj_A | Area_2 | DL | DL-YP01-8011 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_2 | DL | DL-YP01-8011 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8011 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 3 | 0 | NA | 1.04 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 13 | 9.75 | CS | 0.65 | 1 | 110 | 8.45 |  | 929.5
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 12 | 9 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | LM | 2.566 | 0 | NA | 0.16635 | 1 | 110 | 0.42685 |  | 46.953
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.013 | 0 | NA | 0.18767 | 1 | 110 | 0.19011 |  | 20.9124
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 33 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1650
Proj_A | Area_2 | DL | DL-YP01-8012 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | LM | 2.6943 | 0 | NA | 1.045 | 0.75 | 78 | 2.1117 |  | 164.7091
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1143 | 0 | NA | 1.1943 | 0.75 | 78 | 0.99809 |  | 77.8513
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 CL800 | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 0.75 | EA | 1 | 0 | NA | 0.3 | 0.75 | 78 | 0.225 |  | 17.55
Proj_A | Area_2 | DL | DL-YP01-8012 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | EA | 4 | 3 | CS | 0.65 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 13 | 9.75 | CS | 0.65 | 1 | 110 | 8.45 |  | 929.5
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 12 | 9 | CS | 0.78 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | LM | 2.566 | 0 | NA | 0.16635 | 1 | 110 | 0.42685 |  | 46.953
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.013 | 0 | NA | 0.18767 | 1 | 110 | 0.19011 |  | 20.9124
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 33 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1650
Proj_A | Area_2 | DL | DL-YP01-8014 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | LM | 2.6943 | 0 | NA | 1.045 | 0.75 | 78 | 2.1117 |  | 164.7091
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1143 | 0 | NA | 1.1943 | 0.75 | 78 | 0.99809 |  | 77.8513
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 CL800 | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 0.75 | 78 | 1.56 |  | 121.68
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 0.75 | EA | 1 | 0 | NA | 0.3 | 0.75 | 78 | 0.225 |  | 17.55
Proj_A | Area_2 | DL | DL-YP01-8014 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 4 | 3 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | EA | 4 | 6 | CS | 1.04 | 1 | 110 | 4.16 |  | 457.6
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | EA | 10 | 15 | CS | 1.04 | 1 | 110 | 10.4 |  | 1144
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 7 | 10.5 | CS | 1.3 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 1 | 1.5 | CS | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1.5 SchXST | LM | 1.73 | 0 | NA | 0.17488 | 1 | 110 | 0.30254 |  | 33.2792
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.33 | 0 | NA | 0.18767 | 1 | 110 | 0.061932 |  | 6.8125
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 22 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1100
Proj_A | Area_2 | DL | DL-YP01-8080 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_2 | DL | DL-YP01-8080 | Field | 600 | 150-20-F-210 | Install Spools - NB 1.5 SchXST | LM | 1.8165 | 0 | NA | 1.1047 | 0.75 | 78 | 1.505 |  | 117.3926
Proj_A | Area_2 | DL | DL-YP01-8080 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.363 | 0 | NA | 1.1943 | 0.75 | 78 | 0.32514 |  | 25.3612
Proj_A | Area_2 | DL | DL-YP01-8080 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_2 | DL | DL-YP01-8080 | Field | 600 | 150-30-F-310 | Install valve - NB 1.5 2000psi | EA | 2 | 0 | NA | 0.52 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8080 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8080 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | DL | DL-YP01-8080 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1.5 | EA | 1 | 0 | NA | 0.5 | 0.75 | 78 | 0.375 |  | 29.25
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 2 | 2 | CS | 3.77 | 1 | 110 | 7.54 |  | 829.4
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.718 | 0 | NA | 0.18767 | 1 | 110 | 0.13475 |  | 14.8224
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_2 | DL | DL-YP01-8081 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_2 | DL | DL-YP01-8081 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.7898 | 0 | NA | 1.1943 | 0.75 | 78 | 0.70743 |  | 55.1799
Proj_A | Area_2 | DL | DL-YP01-8081 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_2 | DL | DL-YP01-8081 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_2 | DL | DL-YP01-8081 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 3 | 0 | NA | 1.04 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.96 | 0 | NA | 0.17914 | 1 | 110 | 0.17198 |  | 18.9175
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.878 | 0 | NA | 0.18767 | 1 | 110 | 0.35245 |  | 38.7695
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | DL | DL-ZL01-8013 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_2 | DL | DL-ZL01-8013 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.008 | 0 | NA | 1.1644 | 0.75 | 78 | 0.88031 |  | 68.6639
Proj_A | Area_2 | DL | DL-ZL01-8013 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.0658 | 0 | NA | 1.1943 | 0.75 | 78 | 1.8504 |  | 144.3284
Proj_A | Area_2 | DL | DL-ZL01-8013 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_2 | DL | DL-ZL01-8013 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_2 | DL | DL-ZL01-8013 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_2 | DL | DL-ZL01-8013 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_2 | DL | DL-ZL01-8013 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_2 | FL | FL-YP01-8122 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 16 | 48 | CS | 1.3715 | 1 | 110 | 21.944 |  | 2413.84
Proj_A | Area_2 | FL | FL-YP01-8122 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 17.019 | 0 | NA | 0.17488 | 1 | 110 | 2.9762 |  | 327.386
Proj_A | Area_2 | FL | FL-YP01-8122 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 800
Proj_A | Area_2 | FL | FL-YP01-8122 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 2 | 0 | NA | 6 | 1 | 110 | 12 |  | 1320
Proj_A | Area_2 | FL | FL-YP01-8122 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 1200
Proj_A | Area_2 | FL | FL-YP01-8122 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 18.7209 | 0 | NA | 1.1644 | 0.75 | 78 | 16.3493 |  | 1275.2485
Proj_A | Area_2 | FL | FL-YP01-8122 | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | FL | FL-YP01-8122 | Field | 600 | 150-30-F-310 | Install Inlines - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | FL | FL-YP01-8122 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL300 | EA | 1 | 0 | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
Proj_A | Area_2 | FL | FL-YP01-8122 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 4.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.9488 |  | 308.0025
Proj_A | Area_2 | FL | FL-YP01-8122 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 5 | 0 | NA | 1.5 | 0.75 | 78 | 5.625 |  | 438.75
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | EA | 10 | 160 | CS | 16.12 | 1 | 110 | 161.2 |  | 17732
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | EA | 12 | 288 | CS | 18.3647 | 1 | 110 | 220.376 |  | 24241.36
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchXST | LM | 0.4 | 0 | NA | 0.79335 | 1 | 110 | 0.31734 |  | 34.9072
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch40 | LM | 14.46 | 0 | NA | 0.89571 | 1 | 110 | 12.952 |  | 1424.7211
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2500
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 12 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 6000
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch40 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 2880
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchXST | LM | 0.46 | 0 | NA | 5.1056 | 1 | 110 | 2.3486 |  | 258.3415
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch40 | LM | 16.629 | 0 | NA | 5.7923 | 1 | 110 | 96.3198 |  | 10595.1759
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 2 | 0 | NA | 1.04 | 1 | 110 | 2.08 |  | 228.8
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL300 | EA | 1 | 0 | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL300 | EA | 1 | 0 | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 4 | 0 | NA | 1.04 | 1 | 110 | 4.16 |  | 457.6
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | EA | 2.5 | 0 | NA | 6.37 | 1 | 110 | 15.925 |  | 1751.75
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | EA | 2 | 0 | NA | 9.62 | 1 | 110 | 19.24 |  | 2116.4
Proj_A | Area_2 | HPG | HPG-YP01-5018 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 2 | 0 | NA | 2.5655 | 1 | 110 | 5.131 |  | 564.412
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 2 | 6 | CS | 1.3715 | 1 | 110 | 2.743 |  | 301.73
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | EA | 2 | 20 | CS | 4.1782 | 1 | 110 | 8.3564 |  | 919.204
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | EA | 8 | 128 | CS | 16.12 | 1 | 110 | 128.96 |  | 14185.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 3 | CS | 2.21 | 1 | 110 | 2.21 |  | 243.1
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 2 | CS | 4.42 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 3 | CS | 7.67 | 1 | 110 | 7.67 |  | 843.7
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 SchSTD | LM | 1.2 | 0 | NA | 0.33696 | 1 | 110 | 0.40435 |  | 44.4785
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchXST | LM | 3.332 | 0 | NA | 0.79335 | 1 | 110 | 2.6434 |  | 290.7771
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2000
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 12 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 600
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-20-M-210 | Install Spools - NB 10 SchSTD | LM | 1.38 | 0 | NA | 2.1497 | 1 | 110 | 2.9666 |  | 326.3262
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchXST | LM | 3.8318 | 0 | NA | 5.1056 | 1 | 110 | 19.5635 |  | 2151.9851
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL300 | EA | 1 | 0 | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-30-M-310 | Install Inlines - NB 16 CL300 | EA | 2 | 0 | NA | 9.23 | 1 | 110 | 18.46 |  | 2030.6
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL300 | EA | 1 | 0 | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0.5 | 0 | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 2.5 | 0 | NA | 1.04 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 3 CL300 | EA | 0.5 | 0 | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL300 | EA | 0.5 | 0 | NA | 3.9 | 1 | 110 | 1.95 |  | 214.5
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | EA | 5.5 | 0 | NA | 6.37 | 1 | 110 | 35.035 |  | 3853.85
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
Proj_A | Area_2 | HPG | HPG-YP01-5020 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 2 | 6 | CS | 1.3715 | 1 | 110 | 2.743 |  | 301.73
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | EA | 2 | 20 | CS | 4.1782 | 1 | 110 | 8.3564 |  | 919.204
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | EA | 8 | 128 | CS | 16.12 | 1 | 110 | 128.96 |  | 14185.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 3 | CS | 2.21 | 1 | 110 | 2.21 |  | 243.1
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 1 | 2 | CS | 4.42 | 1 | 110 | 4.42 |  | 486.2
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 3 | CS | 7.67 | 1 | 110 | 7.67 |  | 843.7
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 SchSTD | LM | 1.2 | 0 | NA | 0.33696 | 1 | 110 | 0.40435 |  | 44.4785
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchXST | LM | 3.332 | 0 | NA | 0.79335 | 1 | 110 | 2.6434 |  | 290.7771
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2000
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 12 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 600
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-20-M-210 | Install Spools - NB 10 SchSTD | LM | 1.38 | 0 | NA | 2.1497 | 1 | 110 | 2.9666 |  | 326.3262
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchXST | LM | 3.8318 | 0 | NA | 5.1056 | 1 | 110 | 19.5635 |  | 2151.9851
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL300 | EA | 1 | 0 | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-30-M-310 | Install Inlines - NB 16 CL300 | EA | 2 | 0 | NA | 9.23 | 1 | 110 | 18.46 |  | 2030.6
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL300 | EA | 1 | 0 | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0.5 | 0 | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 2.5 | 0 | NA | 1.04 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 3 CL300 | EA | 0.5 | 0 | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL300 | EA | 0.5 | 0 | NA | 3.9 | 1 | 110 | 1.95 |  | 214.5
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | EA | 5.5 | 0 | NA | 6.37 | 1 | 110 | 35.035 |  | 3853.85
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
Proj_A | Area_2 | HPG | HPG-YP01-5022 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 2 | 16 | CS | 3.0095 | 1 | 110 | 6.019 |  | 662.09
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | EA | 2 | 20 | CS | 4.1782 | 1 | 110 | 8.3564 |  | 919.204
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.17 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 5 | 10 | CS | 4.42 | 1 | 110 | 22.1 |  | 2431
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 3 | 1.5 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 SchSTD | LM | 1.461 | 0 | NA | 0.33696 | 1 | 110 | 0.4923 |  | 54.1526
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 18 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 900
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Module | 500 | 150-20-M-210 | Install Spools - NB 10 SchSTD | LM | 1.6802 | 0 | NA | 2.1497 | 1 | 110 | 3.6118 |  | 397.3021
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 3 | 0 | NA | 1.04 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 1.5 | 0 | NA | 1.04 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 5.5 | 0 | NA | 1.04 | 1 | 110 | 5.72 |  | 629.2
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 8 CL300 | EA | 0.5 | 0 | NA | 3.12 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 0.5 | 0 | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
Proj_A | Area_2 | HPG | HPG-YP01-5023 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 2 | 16 | CS | 3.0095 | 1 | 110 | 6.019 |  | 662.09
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | EA | 2 | 20 | CS | 4.1782 | 1 | 110 | 8.3564 |  | 919.204
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.17 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 5 | 10 | CS | 4.42 | 1 | 110 | 22.1 |  | 2431
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 3 | 1.5 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 SchSTD | LM | 1.461 | 0 | NA | 0.33696 | 1 | 110 | 0.4923 |  | 54.1526
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 18 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 900
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Module | 500 | 150-20-M-210 | Install Spools - NB 10 SchSTD | LM | 1.6802 | 0 | NA | 2.1497 | 1 | 110 | 3.6118 |  | 397.3021
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 3 | 0 | NA | 1.04 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 1.5 | 0 | NA | 1.04 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 5.5 | 0 | NA | 1.04 | 1 | 110 | 5.72 |  | 629.2
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 8 CL300 | EA | 0.5 | 0 | NA | 3.12 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 0.5 | 0 | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
Proj_A | Area_2 | HPG | HPG-YP01-5024 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 9 | 9 | CS | 0.91 | 1 | 110 | 8.19 |  | 900.9
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 0.205 | 0 | NA | 0.15355 | 1 | 110 | 0.031478 |  | 3.4626
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 18 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 900
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Module | 500 | 150-20-M-210 | Install Spools - NB 1 SchXST | LM | 0.21525 | 0 | NA | 1.0151 | 1 | 110 | 0.21851 |  | 24.036
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 2.5 | 0 | NA | 1.04 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5048 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 1 | 110 | 0.4 |  | 44
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 9 | 9 | CS | 0.91 | 1 | 110 | 8.19 |  | 900.9
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 0.205 | 0 | NA | 0.15355 | 1 | 110 | 0.031478 |  | 3.4626
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 18 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 900
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Module | 500 | 150-20-M-210 | Install Spools - NB 1 SchXST | LM | 0.21525 | 0 | NA | 1.0151 | 1 | 110 | 0.21851 |  | 24.036
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 2.5 | 0 | NA | 1.04 | 1 | 110 | 2.6 |  | 286
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 1 | 0 | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_2 | HPG | HPG-YP01-5049 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 1 | 110 | 0.4 |  | 44
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 8 | 80 | CS | 5.915 | 1 | 110 | 47.32 |  | 5205.2
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 6 | CS | 5.46 | 1 | 110 | 16.38 |  | 1801.8
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.15 | 0 | NA | 0.18767 | 1 | 110 | 0.028151 |  | 3.0966
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 3.686 | 0 | NA | 0.46918 | 1 | 110 | 1.7294 |  | 190.2349
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 0.165 | 0 | NA | 1.1943 | 1 | 110 | 0.19706 |  | 21.6763
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-20-M-210 | Install Spools - NB 10 Sch80 | LM | 4.2389 | 0 | NA | 2.9857 | 1 | 110 | 12.6561 |  | 1392.1739
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 3 | 0 | NA | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-30-M-310 | Install Blind - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 1 | 110 | 6.63 |  | 729.3
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-30-M-310 | Install valve - NB 10 CL600 | EA | 2 | 0 | NA | 6.63 | 1 | 110 | 13.26 |  | 1458.6
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 5.5 | 0 | NA | 1.17 | 1 | 110 | 6.435 |  | 707.85
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 4 | 0 | NA | 4.16 | 1 | 110 | 16.64 |  | 1830.4
Proj_A | Area_2 | HPG | HPG-ZL01-5002 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 8 | 80 | CS | 5.915 | 1 | 110 | 47.32 |  | 5205.2
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 6 | CS | 5.46 | 1 | 110 | 16.38 |  | 1801.8
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.15 | 0 | NA | 0.18767 | 1 | 110 | 0.028151 |  | 3.0966
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 3.686 | 0 | NA | 0.46918 | 1 | 110 | 1.7294 |  | 190.2349
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 0.165 | 0 | NA | 1.1943 | 1 | 110 | 0.19706 |  | 21.6763
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Module | 500 | 150-20-M-210 | Install Spools - NB 10 Sch80 | LM | 4.2389 | 0 | NA | 2.9857 | 1 | 110 | 12.6561 |  | 1392.1739
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Module | 500 | 150-30-M-310 | Install valve - NB 10 CL600 | EA | 2 | 0 | NA | 6.63 | 1 | 110 | 13.26 |  | 1458.6
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Module | 500 | 150-30-M-310 | Install Blind - NB 10 CL600 | EA | 1 | 0 | NA | 6.63 | 1 | 110 | 6.63 |  | 729.3
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | NA | 1.17 | 1 | 110 | 5.265 |  | 579.15
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 4 | 0 | NA | 4.16 | 1 | 110 | 16.64 |  | 1830.4
Proj_A | Area_2 | HPG | HPG-ZL01-5003 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 1 | 0 | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 4 | 40 | CS | 5.915 | 1 | 110 | 23.66 |  | 2602.6
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 60 | 720 | CS | 7.683 | 1 | 110 | 460.98 |  | 50707.8
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 181.595 | 0 | NA | 0.57155 | 1 | 110 | 103.7907 |  | 11416.9724
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2500
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 13 | 0 | NA | 19 | 1 | 110 | 247 |  | 27170
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 13 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 22100
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Module | 500 | 150-20-M-210 | Install Spools - NB 12 Sch80 | LM | 208.8342 | 0 | NA | 3.6724 | 1 | 110 | 766.9278 |  | 84362.0542
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 1 | 0 | NA | 4.16 | 1 | 110 | 4.16 |  | 457.6
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 15.5 | 0 | NA | 5.33 | 1 | 110 | 82.615 |  | 9087.65
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 12 | EA | 15 | 0 | NA | 1.9144 | 1 | 110 | 28.7163 |  | 3158.7969
Proj_A | Area_2 | HPG | HPG-ZL01-5025 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 4 | 48 | CS | 11.3555 | 0.75 | 78 | 34.0665 |  | 2657.187
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Module | 500 | 150-30-M-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Module | 500 | 150-30-M-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 1 | 110 | 2.925 |  | 321.75
Proj_A | Area_2 | HPG | HPG-ZL01-5050 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | IA | IA-XP02-9002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_2 | IA | IA-XP02-9002 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 16.867 | 0 | NA | 0.18767 | 1 | 110 | 3.1655 |  | 348.2032
Proj_A | Area_2 | IA | IA-XP02-9002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 16 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 800
Proj_A | Area_2 | IA | IA-XP02-9002 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_2 | IA | IA-XP02-9002 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_2 | IA | IA-XP02-9002 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 18.5537 | 0 | NA | 1.1943 | 1 | 110 | 22.1584 |  | 2437.4226
Proj_A | Area_2 | IA | IA-XP02-9002 | Module | 500 | 150-30-M-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | IA | IA-XP02-9002 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_2 | IA | IA-XP02-9002 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 4.5 | 0 | NA | 0.91 | 1 | 110 | 4.095 |  | 450.45
Proj_A | Area_2 | IA | IA-XP02-9002 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | NA | 1 | 1 | 110 | 4 |  | 440
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 14 | 28 | CS | 1.1765 | 1 | 110 | 16.471 |  | 1811.81
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 2.86 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 21.621 | 0 | NA | 0.18767 | 1 | 110 | 4.0577 |  | 446.345
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 14 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 700
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 0 | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
Proj_A | Area_2 | IA | IA-XP02-9004 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1000
Proj_A | Area_2 | IA | IA-XP02-9004 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 23.7831 | 0 | NA | 1.1943 | 1 | 110 | 28.4038 |  | 3124.4153
Proj_A | Area_2 | IA | IA-XP02-9004 | Module | 500 | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 3 | 0 | NA | 0.39 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | IA | IA-XP02-9004 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | NA | 0.91 | 1 | 110 | 2.275 |  | 250.25
Proj_A | Area_2 | IA | IA-XP02-9004 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | NA | 1 | 1 | 110 | 5 |  | 550
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 2.86 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 18.175 | 0 | NA | 0.18767 | 1 | 110 | 3.411 |  | 375.2056
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_2 | IA | IA-XP02-9005 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_2 | IA | IA-XP02-9005 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 19.9925 | 0 | NA | 1.1943 | 1 | 110 | 23.8767 |  | 2626.4395
Proj_A | Area_2 | IA | IA-XP02-9005 | Module | 500 | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 3 | 0 | NA | 0.39 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_2 | IA | IA-XP02-9005 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | NA | 0.91 | 1 | 110 | 2.275 |  | 250.25
Proj_A | Area_2 | IA | IA-XP02-9005 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | NA | 1 | 1 | 110 | 4 |  | 440
Proj_A | Area_2 | TR | TR-YP01-8099 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | TR | TR-YP01-8099 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_2 | TR | TR-YP01-8099 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | TR | TR-YP01-8099 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | TR | TR-YP01-8099 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_2 | TR | TR-YP01-8099 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | TR | TR-YP01-8099 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | TR | TR-YP01-8100 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | TR | TR-YP01-8100 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_2 | TR | TR-YP01-8100 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_2 | TR | TR-YP01-8100 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_2 | TR | TR-YP01-8100 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_2 | TR | TR-YP01-8100 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_2 | TR | TR-YP01-8100 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_2 | TR | TR-ZL01-8101 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_2 | TR | TR-ZL01-8101 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_3 | BD | BD-XP01-6001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 13 | 104 | CS | 3.0095 | 1 | 110 | 39.1235 |  | 4303.585
Proj_A | Area_3 | BD | BD-XP01-6001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 2.916 | 0 | NA | 0.26871 | 1 | 110 | 0.78357 |  | 86.1927
Proj_A | Area_3 | BD | BD-XP01-6001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 13 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 1300
Proj_A | Area_3 | BD | BD-XP01-6001 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 8 SchSTD | EA | 1 | 8 | CS | 4.2887 | 0.75 | 78 | 3.2165 |  | 250.889
Proj_A | Area_3 | BD | BD-XP01-6001 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 3.2076 | 0 | NA | 1.7019 | 0.75 | 78 | 4.0942 |  | 319.3438
Proj_A | Area_3 | BD | BD-XP01-6001 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 8 SchSTD | LM | 19.1103 | 0 | NA | 1.4502 | 0.75 | 78 | 20.7853 |  | 1621.257
Proj_A | Area_3 | BD | BD-XP01-6001 | Field | 600 | 150-30-F-310 | Install Blind - NB 8 CL150 | EA | 1 | 0 | NA | 3.64 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_3 | BD | BD-XP01-6001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 1.5 | 0 | NA | 2.73 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_3 | BD | BD-XP01-6001 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 5 | 0 | NA | 1.7364 | 0.75 | 78 | 6.5116 |  | 507.908
Proj_A | Area_3 | BD | BD-XP01-6001 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 8 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500
Proj_A | Area_3 | BD | BD-XP01-6001 | Field | 300 | 150-80-F-810 | Field Coating - NB 8 | LM | 19.1103 | 0 | CS | 0 | 0.75 | 78 | 0 | 120 | 2293.236
Proj_A | Area_3 | BD | BD-XP01-6003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | EA | 19 | 76 | CS | 1.6835 | 1 | 110 | 31.9865 |  | 3518.515
Proj_A | Area_3 | BD | BD-XP01-6003 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 4 SchSTD | LM | 10.831 | 0 | NA | 0.19194 | 1 | 110 | 2.0789 |  | 228.6774
Proj_A | Area_3 | BD | BD-XP01-6003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 19 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 950
Proj_A | Area_3 | BD | BD-XP01-6003 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 4 SchSTD | EA | 1 | 0 | NA | 7 | 1 | 110 | 7 |  | 770
Proj_A | Area_3 | BD | BD-XP01-6003 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 700 | 700
Proj_A | Area_3 | BD | BD-XP01-6003 | Field | 600 | 150-20-F-210 | Install Spools - NB 4 SchSTD | LM | 11.9141 | 0 | NA | 1.2241 | 0.75 | 78 | 10.9384 |  | 853.1956
Proj_A | Area_3 | BD | BD-XP01-6003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | EA | 2.5 | 0 | NA | 1.56 | 0.75 | 78 | 2.925 |  | 228.15
Proj_A | Area_3 | BD | BD-XP01-6003 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 3 | 0 | NA | 1.5 | 0.75 | 78 | 3.375 |  | 263.25
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 36 | 72 | CS | 1.1765 | 1 | 110 | 42.354 |  | 4658.94
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 47.149 | 0 | NA | 0.18767 | 1 | 110 | 8.8486 |  | 973.3464
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 37 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1850
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 5 | 0 | NA | 5.6 | 1 | 110 | 28 |  | 3080
Proj_A | Area_3 | DL | DL-XP01-8043 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 5 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 2500
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.6003 | 0.75 | 78 | 3.6007 |  | 280.8526
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 51.8639 | 0 | NA | 1.1943 | 0.75 | 78 | 46.4552 |  | 3623.5032
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | LM | 17.7056 | 0 | NA | 1.0237 | 0.75 | 78 | 13.5935 |  | 1060.2965
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 11 | 0 | NA | 0.91 | 0.75 | 78 | 7.5075 |  | 585.585
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 19 | 0 | NA | 1 | 0.75 | 78 | 14.25 |  | 1111.5
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 0.75 | 78 | 0 | 750 | 2250
Proj_A | Area_3 | DL | DL-XP01-8043 | Field | 300 | 150-80-F-810 | Field Coating - NB 2 | LM | 17.7056 | 0 | CS | 0 | 0.75 | 78 | 0 | 60 | 1062.336
Proj_A | Area_3 | DL | DL-XP01-8045 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_3 | DL | DL-XP01-8045 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 13 | 13 | CS | 0.78 | 1 | 110 | 10.14 |  | 1115.4
Proj_A | Area_3 | DL | DL-XP01-8045 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_3 | DL | DL-XP01-8045 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | DL | DL-XP01-8045 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_3 | DL | DL-XP01-8045 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 2.77 | 0 | NA | 0.15355 | 1 | 110 | 0.42534 |  | 46.7869
Proj_A | Area_3 | DL | DL-XP01-8045 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 29 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1450
Proj_A | Area_3 | DL | DL-XP01-8045 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_3 | DL | DL-XP01-8045 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 2.9085 | 0 | NA | 1.0151 | 0.75 | 78 | 2.2144 |  | 172.7235
Proj_A | Area_3 | DL | DL-XP01-8045 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_3 | DL | DL-XP01-8045 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 1.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.0237 |  | 79.8525
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 70 | 140 | CS | 1.1765 | 1 | 110 | 82.355 |  | 9059.05
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 2.86 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 36.572 | 0 | NA | 0.18767 | 1 | 110 | 6.8636 |  | 754.9943
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 71 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 3550
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 4 | 0 | NA | 5.6 | 1 | 110 | 22.4 |  | 2464
Proj_A | Area_3 | DL | DL-XP01-8046 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 4 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 2000
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.6003 | 0.75 | 78 | 4.8009 |  | 374.4702
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 40.2292 | 0 | NA | 1.1943 | 0.75 | 78 | 36.0338 |  | 2810.6378
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | LM | 147.8114 | 0 | NA | 1.0237 | 0.75 | 78 | 113.4828 |  | 8851.6579
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 5 | 0 | NA | 0.65 | 0.75 | 78 | 2.4375 |  | 190.125
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 24 | 0 | NA | 0.91 | 0.75 | 78 | 16.38 |  | 1277.64
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 57 | 0 | NA | 1 | 0.75 | 78 | 42.75 |  | 3334.5
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 0.75 | 78 | 0 | 750 | 3000
Proj_A | Area_3 | DL | DL-XP01-8046 | Field | 300 | 150-80-F-810 | Field Coating - NB 2 | LM | 147.8114 | 0 | CS | 0 | 0.75 | 78 | 0 | 60 | 8868.684
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 18 | CS | 1.3715 | 1 | 110 | 8.229 |  | 905.19
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 0.868 | 0 | NA | 0.17488 | 1 | 110 | 0.15179 |  | 16.6973
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_3 | DL | DL-XP01-8047 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_3 | DL | DL-XP01-8047 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 0.9548 | 0 | NA | 1.1644 | 0.75 | 78 | 0.83385 |  | 65.04
Proj_A | Area_3 | DL | DL-XP01-8047 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_3 | DL | DL-XP01-8047 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_3 | DL | DL-XP01-8047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 3 | 0 | NA | 1.04 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_3 | DL | DL-XP01-8047 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 3 | 0 | NA | 1.5 | 0.75 | 78 | 3.375 |  | 263.25
Proj_A | Area_3 | DL | DL-XP01-8076 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_3 | DL | DL-XP01-8076 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 10 | 30 | CS | 1.3715 | 1 | 110 | 13.715 |  | 1508.65
Proj_A | Area_3 | DL | DL-XP01-8076 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.393 | 0 | NA | 0.18767 | 1 | 110 | 0.4491 |  | 49.4012
Proj_A | Area_3 | DL | DL-XP01-8076 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 4.639 | 0 | NA | 0.17488 | 1 | 110 | 0.81126 |  | 89.2381
Proj_A | Area_3 | DL | DL-XP01-8076 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_3 | DL | DL-XP01-8076 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_3 | DL | DL-XP01-8076 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_3 | DL | DL-XP01-8076 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_3 | DL | DL-XP01-8076 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.6323 | 0 | NA | 1.1943 | 0.75 | 78 | 2.3578 |  | 183.9073
Proj_A | Area_3 | DL | DL-XP01-8076 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 5.1029 | 0 | NA | 1.1644 | 0.75 | 78 | 4.4565 |  | 347.6043
Proj_A | Area_3 | DL | DL-XP01-8076 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | DL | DL-XP01-8076 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_3 | DL | DL-XP01-8076 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_3 | DL | DL-XP01-8076 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 3 | 0 | NA | 1.5 | 0.75 | 78 | 3.375 |  | 263.25
Proj_A | Area_3 | DL | DL-XP01-8079 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_3 | DL | DL-XP01-8079 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 11.466 | 0 | NA | 0.18767 | 1 | 110 | 2.1519 |  | 236.7047
Proj_A | Area_3 | DL | DL-XP01-8079 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_3 | DL | DL-XP01-8079 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_3 | DL | DL-XP01-8079 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_3 | DL | DL-XP01-8079 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 12.6126 | 0 | NA | 1.1943 | 0.75 | 78 | 11.2973 |  | 881.187
Proj_A | Area_3 | DL | DL-XP01-8079 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.0237 |  | 79.8525
Proj_A | Area_3 | DL | DL-XP01-8079 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | NA | 1 | 0.75 | 78 | 3 |  | 234
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 28 | 448 | CS | 14.365 | 1 | 110 | 402.22 |  | 44244.2
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 3 | 6 | CS | 5.46 | 1 | 110 | 16.38 |  | 1801.8
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 80.242 | 0 | NA | 0.79335 | 1 | 110 | 63.6597 |  | 7002.5619
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 1000
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 6 | 0 | NA | 17.6 | 1 | 110 | 105.6 |  | 11616
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 12600
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 Sch80 | LM | 92.2783 | 0 | NA | 5.1056 | 1 | 110 | 471.1328 |  | 51824.6053
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 3 | 0 | NA | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 5.5 | 0 | NA | 1.17 | 1 | 110 | 6.435 |  | 707.85
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 7 | 0 | NA | 6.76 | 1 | 110 | 47.32 |  | 5205.2
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 11 | 0 | NA | 2.1107 | 1 | 110 | 23.2172 |  | 2553.8873
Proj_A | Area_3 | HPG | HPG-ZL01-5014 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 16 Sch80 | EA | 2 | 32 | CS | 20.3905 | 0.75 | 78 | 30.5858 |  | 2385.6885
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 14 | 224 | CS | 14.365 | 1 | 110 | 201.11 |  | 22122.1
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 8.302 | 0 | NA | 0.79335 | 1 | 110 | 6.5864 |  | 724.4993
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 1 | 0 | NA | 17.6 | 1 | 110 | 17.6 |  | 1936
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 2100
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 Sch80 | LM | 9.5473 | 0 | NA | 5.1056 | 1 | 110 | 48.7444 |  | 5361.8787
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL600 | EA | 1 | 0 | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_3 | HPG | HPG-ZL01-5021 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 2.5 | 0 | NA | 6.76 | 1 | 110 | 16.9 |  | 1859
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 2 | 32 | CS | 14.365 | 1 | 110 | 28.73 |  | 3160.3
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 1 | 20 | CS | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | EA | 25 | 600 | CS | 33.1998 | 1 | 110 | 829.9958 |  | 91299.5417
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch80 | LM | 61.211 | 0 | NA | 1.1644 | 1 | 110 | 71.2757 |  | 7840.3308
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 2000
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch80 | EA | 5 | 0 | NA | 62.6 | 1 | 110 | 313 |  | 34430
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 5 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 14400
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch80 | LM | 70.3927 | 0 | NA | 7.4941 | 1 | 110 | 527.5318 |  | 58028.5
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | EA | 6 | 0 | NA | 10.27 | 1 | 110 | 61.62 |  | 6778.2
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 10 | 0 | NA | 2.5655 | 1 | 110 | 25.6551 |  | 2822.0599
Proj_A | Area_3 | HPG | HPG-ZL01-5026 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 24 Sch80 | EA | 1 | 24 | CS | 40.3455 | 0.75 | 78 | 30.2591 |  | 2360.2117
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 50 | 1000 | CS | 21.7588 | 1 | 110 | 1087.9375 |  | 119673.125
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 4 | 8 | CS | 5.46 | 1 | 110 | 21.84 |  | 2402.4
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 81.44 | 0 | NA | 1.0279 | 1 | 110 | 83.7152 |  | 9208.6735
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 3500
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 6 | 0 | NA | 41.2 | 1 | 110 | 247.2 |  | 27192
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 6 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 16200
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Module | 500 | 150-20-M-210 | Install Spools - NB 20 Sch80 | LM | 93.656 | 0 | NA | 6.6283 | 1 | 110 | 620.7778 |  | 68285.5619
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 4 | 0 | NA | 1.69 | 1 | 110 | 6.76 |  | 743.6
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Module | 500 | 150-30-M-310 | Install valve - NB 20 CL600 | EA | 3 | 0 | NA | 15.47 | 1 | 110 | 46.41 |  | 5105.1
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 8 | 0 | NA | 1.17 | 1 | 110 | 9.36 |  | 1029.6
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 14 | 0 | NA | 8.58 | 1 | 110 | 120.12 |  | 13213.2
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 0 | NA | 2.327 | 1 | 110 | 13.962 |  | 1535.8149
Proj_A | Area_3 | HPG | HPG-ZL01-5029 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 20 Sch80 | EA | 1 | 20 | CS | 31.2637 | 0.75 | 78 | 23.4478 |  | 1828.9264
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 1 | 20 | CS | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | EA | 26 | 624 | CS | 33.1998 | 1 | 110 | 863.1957 |  | 94951.5233
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 Sch80 | LM | 42.209 | 0 | NA | 1.1644 | 1 | 110 | 49.1493 |  | 5406.4225
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 2000
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 Sch80 | EA | 3 | 0 | NA | 62.6 | 1 | 110 | 187.8 |  | 20658
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 8640
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Module | 500 | 150-20-M-210 | Install Spools - NB 24 Sch80 | LM | 48.5403 | 0 | NA | 7.4941 | 1 | 110 | 363.7678 |  | 40014.4575
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Module | 500 | 150-30-M-310 | Install valve - NB 24 CL600 | EA | 1 | 0 | NA | 17.68 | 1 | 110 | 17.68 |  | 1944.8
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | NA | 1.17 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | EA | 6.5 | 0 | NA | 10.27 | 1 | 110 | 66.755 |  | 7343.05
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 9 | 0 | NA | 2.5655 | 1 | 110 | 23.0896 |  | 2539.8539
Proj_A | Area_3 | HPG | HPG-ZL01-5035 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 24 Sch80 | EA | 1 | 24 | CS | 40.3455 | 0.75 | 78 | 30.2591 |  | 2360.2117
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 2 | 24 | CS | 4.7255 | 1 | 110 | 9.451 |  | 1039.61
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | EA | 2 | 32 | CS | 8.8313 | 1 | 110 | 17.6627 |  | 1942.8933
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | EA | 2 | 40 | CS | 13.6121 | 1 | 110 | 27.2242 |  | 2994.6583
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | EA | 10 | 240 | CS | 17.7732 | 1 | 110 | 177.7317 |  | 19550.4833
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 24 SchXST | LM | 12.399 | 0 | NA | 1.1644 | 1 | 110 | 14.4377 |  | 1588.1502
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 1000
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 24 SchXST | EA | 1 | 0 | NA | 30.8 | 1 | 110 | 30.8 |  | 3388
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2880 | 2880
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Module | 500 | 150-20-M-210 | Install Spools - NB 24 SchXST | LM | 14.2588 | 0 | NA | 7.4941 | 1 | 110 | 106.8577 |  | 11754.3476
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | NA | 1.17 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 0.5 | 0 | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 0.5 | 0 | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | EA | 1.5 | 0 | NA | 10.27 | 1 | 110 | 15.405 |  | 1694.55
Proj_A | Area_3 | HPG | HPG-ZL02-5019 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 1 | 0 | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 4 | 48 | CS | 4.7255 | 1 | 110 | 18.902 |  | 2079.22
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 13.44 | 0 | NA | 0.40947 | 1 | 110 | 5.5033 |  | 605.3587
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 1 | 0 | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Module | 500 | 150-20-M-210 | Install Spools - NB 12 SchSTD | LM | 15.456 | 0 | NA | 2.6274 | 1 | 110 | 40.6095 |  | 4467.0425
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_3 | HPG | HPG-ZL02-5036 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 1 | 0 | NA | 5.33 | 1 | 110 | 5.33 |  | 586.3
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | EA | 4 | 80 | CS | 13.6121 | 1 | 110 | 54.4483 |  | 5989.3167
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 SchXST | LM | 2.414 | 0 | NA | 1.0279 | 1 | 110 | 2.4814 |  | 272.9585
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Module | 500 | 150-20-M-210 | Install Spools - NB 20 SchXST | LM | 2.7761 | 0 | NA | 6.6283 | 1 | 110 | 18.4008 |  | 2024.0833
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 1 | 110 | 1.755 |  | 193.05
Proj_A | Area_3 | HPG | HPG-ZL02-5037 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 1 | 0 | NA | 8.58 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | EA | 12 | 192 | CS | 8.8313 | 1 | 110 | 105.976 |  | 11657.36
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 SchSTD | LM | 43.76 | 0 | NA | 0.58861 | 1 | 110 | 25.7576 |  | 2833.3398
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 16 SchSTD | EA | 3 | 0 | NA | 15.6 | 1 | 110 | 46.8 |  | 5148
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 3 | 0 | CS | 0 | 1 | 110 | 0 | 2100 | 6300
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Module | 500 | 150-20-M-210 | Install Spools - NB 16 SchSTD | LM | 50.324 | 0 | NA | 3.7919 | 1 | 110 | 190.8211 |  | 20990.3259
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Module | 500 | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Module | 500 | 150-30-M-310 | Install Blind - NB 16 CL600 | EA | 1 | 0 | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Module | 500 | 150-30-M-310 | Install valve - NB 16 CL600 | EA | 1 | 0 | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 6 | 0 | NA | 6.76 | 1 | 110 | 40.56 |  | 4461.6
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 4 | 0 | NA | 2.1107 | 1 | 110 | 8.4426 |  | 928.6863
Proj_A | Area_3 | HPG | HPG-ZL02-5038 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 16 SchSTD | EA | 1 | 16 | CS | 11.6532 | 0.75 | 78 | 8.7399 |  | 681.7122
Proj_A | Area_3 | IA | IA-XP02-9006 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_3 | IA | IA-XP02-9006 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 2 | 2 | CS | 2.86 | 1 | 110 | 5.72 |  | 629.2
Proj_A | Area_3 | IA | IA-XP02-9006 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | IA | IA-XP02-9006 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 3 | 3 | NA | 0.39 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_3 | IA | IA-XP02-9006 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | IA | IA-XP02-9006 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 3.492 | 0 | NA | 0.18767 | 1 | 110 | 0.65535 |  | 72.089
Proj_A | Area_3 | IA | IA-XP02-9006 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_3 | IA | IA-XP02-9006 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_3 | IA | IA-XP02-9006 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 3.8412 | 0 | NA | 1.1943 | 1 | 110 | 4.5875 |  | 504.6232
Proj_A | Area_3 | IA | IA-XP02-9006 | Module | 500 | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 2 | 0 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_3 | IA | IA-XP02-9006 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | NA | 0.91 | 1 | 110 | 1.365 |  | 150.15
Proj_A | Area_3 | IA | IA-XP02-9006 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 1 | 110 | 1 |  | 110
Proj_A | Area_3 | IA | IA-XP02-9010 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_3 | IA | IA-XP02-9010 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 3.297 | 0 | NA | 0.18767 | 1 | 110 | 0.61876 |  | 68.0634
Proj_A | Area_3 | IA | IA-XP02-9010 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_3 | IA | IA-XP02-9010 | Module | 500 | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 3.6267 | 0 | NA | 1.1943 | 1 | 110 | 4.3313 |  | 476.4441
Proj_A | Area_3 | IA | IA-XP02-9010 | Module | 500 | 150-30-M-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_3 | IA | IA-XP02-9010 | Module | 500 | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | NA | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_3 | IA | IA-XP02-9010 | Module | 500 | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 1 | 110 | 1 |  | 110
Proj_A | Area_3 | TR | TR-XP01-8092 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_3 | TR | TR-XP01-8095 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_3 | TR | TR-XP01-8097 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_3 | TR | TR-XP01-8097 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_3 | TR | TR-XP01-8097 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_3 | TR | TR-XP01-8097 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_3 | TR | TR-XP01-8097 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_3 | TR | TR-XP01-8097 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_3 | TR | TR-XP01-8097 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_3 | TR | TR-XP01-8097 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_3 | TR | TR-XP01-8097 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_3 | TR | TR-XP01-8098 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_3 | TR | TR-XP01-8098 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_3 | TR | TR-ZL01-8088 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | TR | TR-ZL01-8091 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | TR | TR-ZL01-8116 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8089 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8090 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8093 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8094 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_3 | TR | TR-ZL02-8103 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_3 | TR | TR-ZL02-8103 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_3 | TR | TR-ZL02-8103 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_3 | TR | TR-ZL02-8103 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_3 | TR | TR-ZL02-8103 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8027 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_4 | DL | DL-XP01-8027 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.856 | 0 | NA | 0.18767 | 1 | 110 | 0.16065 |  | 17.6713
Proj_A | Area_4 | DL | DL-XP01-8027 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_4 | DL | DL-XP01-8027 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.9416 | 0 | NA | 1.1943 | 0.75 | 78 | 0.8434 |  | 65.7855
Proj_A | Area_4 | DL | DL-XP01-8027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_4 | DL | DL-XP01-8027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8027 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 25 | 50 | CS | 1.1765 | 1 | 110 | 29.4125 |  | 3235.375
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 12.718 | 0 | NA | 0.18767 | 1 | 110 | 2.3868 |  | 262.5511
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 25 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1250
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_4 | DL | DL-XP01-8028 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | DL | DL-XP01-8028 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 13.9898 | 0 | NA | 1.1943 | 0.75 | 78 | 12.5308 |  | 977.406
Proj_A | Area_4 | DL | DL-XP01-8028 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-XP01-8028 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2 | 0 | NA | 0.91 | 0.75 | 78 | 1.365 |  | 106.47
Proj_A | Area_4 | DL | DL-XP01-8028 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | DL | DL-XP01-8028 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | NA | 1 | 0.75 | 78 | 3 |  | 234
Proj_A | Area_4 | DL | DL-XP01-8029 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.1765 | 1 | 110 | 3.5295 |  | 388.245
Proj_A | Area_4 | DL | DL-XP01-8029 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.257 | 0 | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
Proj_A | Area_4 | DL | DL-XP01-8029 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_4 | DL | DL-XP01-8029 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.2827 | 0 | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
Proj_A | Area_4 | DL | DL-XP01-8029 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 23 | 46 | CS | 1.1765 | 1 | 110 | 27.0595 |  | 2976.545
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 5.813 | 0 | NA | 0.18767 | 1 | 110 | 1.0909 |  | 120.0039
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 23 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1150
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_4 | DL | DL-XP01-8031 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | DL | DL-XP01-8031 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 6.3943 | 0 | NA | 1.1943 | 0.75 | 78 | 5.7275 |  | 446.7417
Proj_A | Area_4 | DL | DL-XP01-8031 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-XP01-8031 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3 | 0 | NA | 0.91 | 0.75 | 78 | 2.0475 |  | 159.705
Proj_A | Area_4 | DL | DL-XP01-8031 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_4 | DL | DL-XP01-8031 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_4 | DL | DL-XP01-8032 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_4 | DL | DL-XP01-8032 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.856 | 0 | NA | 0.18767 | 1 | 110 | 0.16065 |  | 17.6713
Proj_A | Area_4 | DL | DL-XP01-8032 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_4 | DL | DL-XP01-8032 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.9416 | 0 | NA | 1.1943 | 0.75 | 78 | 0.8434 |  | 65.7855
Proj_A | Area_4 | DL | DL-XP01-8032 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_4 | DL | DL-XP01-8032 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8032 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 24 | 48 | CS | 1.1765 | 1 | 110 | 28.236 |  | 3105.96
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 12.427 | 0 | NA | 0.18767 | 1 | 110 | 2.3322 |  | 256.5436
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 24 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1200
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_4 | DL | DL-XP01-8033 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | DL | DL-XP01-8033 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 13.6697 | 0 | NA | 1.1943 | 0.75 | 78 | 12.2441 |  | 955.042
Proj_A | Area_4 | DL | DL-XP01-8033 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-XP01-8033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.0237 |  | 79.8525
Proj_A | Area_4 | DL | DL-XP01-8033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | DL | DL-XP01-8033 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | NA | 1 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_4 | DL | DL-XP01-8034 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.1765 | 1 | 110 | 3.5295 |  | 388.245
Proj_A | Area_4 | DL | DL-XP01-8034 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.257 | 0 | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
Proj_A | Area_4 | DL | DL-XP01-8034 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_4 | DL | DL-XP01-8034 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.2827 | 0 | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
Proj_A | Area_4 | DL | DL-XP01-8034 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 22 | 44 | CS | 1.1765 | 1 | 110 | 25.883 |  | 2847.13
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 5.813 | 0 | NA | 0.18767 | 1 | 110 | 1.0909 |  | 120.0039
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 22 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1100
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_4 | DL | DL-XP01-8039 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | DL | DL-XP01-8039 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 6.3943 | 0 | NA | 1.1943 | 0.75 | 78 | 5.7275 |  | 446.7417
Proj_A | Area_4 | DL | DL-XP01-8039 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-XP01-8039 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3 | 0 | NA | 0.91 | 0.75 | 78 | 2.0475 |  | 159.705
Proj_A | Area_4 | DL | DL-XP01-8039 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | DL | DL-XP01-8039 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_4 | DL | DL-XP01-8040 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_4 | DL | DL-XP01-8040 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.856 | 0 | NA | 0.18767 | 1 | 110 | 0.16065 |  | 17.6713
Proj_A | Area_4 | DL | DL-XP01-8040 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_4 | DL | DL-XP01-8040 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.9416 | 0 | NA | 1.1943 | 0.75 | 78 | 0.8434 |  | 65.7855
Proj_A | Area_4 | DL | DL-XP01-8040 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_4 | DL | DL-XP01-8040 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8040 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 30 | 60 | CS | 1.1765 | 1 | 110 | 35.295 |  | 3882.45
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 16.042 | 0 | NA | 0.18767 | 1 | 110 | 3.0107 |  | 331.1719
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 30 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1500
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 0 | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
Proj_A | Area_4 | DL | DL-XP01-8041 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1000
Proj_A | Area_4 | DL | DL-XP01-8041 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 17.6462 | 0 | NA | 1.1943 | 0.75 | 78 | 15.8059 |  | 1232.8626
Proj_A | Area_4 | DL | DL-XP01-8041 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-XP01-8041 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3 | 0 | NA | 0.91 | 0.75 | 78 | 2.0475 |  | 159.705
Proj_A | Area_4 | DL | DL-XP01-8041 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_4 | DL | DL-XP01-8041 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 5 | 0 | NA | 1 | 0.75 | 78 | 3.75 |  | 292.5
Proj_A | Area_4 | DL | DL-XP01-8042 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.1765 | 1 | 110 | 3.5295 |  | 388.245
Proj_A | Area_4 | DL | DL-XP01-8042 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.257 | 0 | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
Proj_A | Area_4 | DL | DL-XP01-8042 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_4 | DL | DL-XP01-8042 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.2827 | 0 | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
Proj_A | Area_4 | DL | DL-XP01-8042 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 28 | 56 | CS | 1.1765 | 1 | 110 | 32.942 |  | 3623.62
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 2.47 | 1 | 110 | 2.47 |  | 271.7
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 12.275 | 0 | NA | 0.18767 | 1 | 110 | 2.3037 |  | 253.4057
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 28 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1400
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_4 | DL | DL-XP01-8074 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | DL | DL-XP01-8074 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 13.5025 | 0 | NA | 1.1943 | 0.75 | 78 | 12.0944 |  | 943.3605
Proj_A | Area_4 | DL | DL-XP01-8074 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-XP01-8074 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 4 | 0 | NA | 0.91 | 0.75 | 78 | 2.73 |  | 212.94
Proj_A | Area_4 | DL | DL-XP01-8074 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | DL | DL-XP01-8074 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 4 | 0 | NA | 1 | 0.75 | 78 | 3 |  | 234
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 10 | CS | 1.1765 | 1 | 110 | 5.8825 |  | 647.075
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.107 | 0 | NA | 0.17914 | 1 | 110 | 0.19831 |  | 21.8142
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.082 | 0 | NA | 0.18767 | 1 | 110 | 0.20306 |  | 22.3369
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | DL | DL-ZL01-8026 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_4 | DL | DL-ZL01-8026 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.1623 | 0 | NA | 1.1644 | 0.75 | 78 | 1.0151 |  | 79.1781
Proj_A | Area_4 | DL | DL-ZL01-8026 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1902 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0661 |  | 83.1541
Proj_A | Area_4 | DL | DL-ZL01-8026 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-ZL01-8026 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_4 | DL | DL-ZL01-8026 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | DL | DL-ZL01-8026 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8026 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 14 | CS | 1.1765 | 1 | 110 | 8.2355 |  | 905.905
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 6 | 6 | CS | 0.91 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.107 | 0 | NA | 0.17914 | 1 | 110 | 0.19831 |  | 21.8142
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.082 | 0 | NA | 0.18767 | 1 | 110 | 0.20306 |  | 22.3369
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_4 | DL | DL-ZL01-8030 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_4 | DL | DL-ZL01-8030 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.1623 | 0 | NA | 1.1644 | 0.75 | 78 | 1.0151 |  | 79.1781
Proj_A | Area_4 | DL | DL-ZL01-8030 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1902 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0661 |  | 83.1541
Proj_A | Area_4 | DL | DL-ZL01-8030 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-ZL01-8030 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_4 | DL | DL-ZL01-8030 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | DL | DL-ZL01-8030 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.669 | 0 | NA | 0.18767 | 1 | 110 | 0.5009 |  | 55.099
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_4 | DL | DL-ZL01-8036 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | DL | DL-ZL01-8036 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.9359 | 0 | NA | 1.1943 | 0.75 | 78 | 2.6297 |  | 205.1185
Proj_A | Area_4 | DL | DL-ZL01-8036 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8036 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_4 | DL | DL-ZL01-8036 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8036 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_4 | DL | DL-ZL01-8036 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.669 | 0 | NA | 0.18767 | 1 | 110 | 0.5009 |  | 55.099
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_4 | DL | DL-ZL01-8037 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | DL | DL-ZL01-8037 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.9359 | 0 | NA | 1.1943 | 0.75 | 78 | 2.6297 |  | 205.1185
Proj_A | Area_4 | DL | DL-ZL01-8037 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8037 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_4 | DL | DL-ZL01-8037 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8037 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_4 | DL | DL-ZL01-8037 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 10 | CS | 1.1765 | 1 | 110 | 5.8825 |  | 647.075
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.107 | 0 | NA | 0.17914 | 1 | 110 | 0.19831 |  | 21.8142
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.082 | 0 | NA | 0.18767 | 1 | 110 | 0.20306 |  | 22.3369
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | DL | DL-ZL01-8038 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_4 | DL | DL-ZL01-8038 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.1623 | 0 | NA | 1.1644 | 0.75 | 78 | 1.0151 |  | 79.1781
Proj_A | Area_4 | DL | DL-ZL01-8038 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1902 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0661 |  | 83.1541
Proj_A | Area_4 | DL | DL-ZL01-8038 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-ZL01-8038 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_4 | DL | DL-ZL01-8038 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_4 | DL | DL-ZL01-8038 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8038 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.669 | 0 | NA | 0.18767 | 1 | 110 | 0.5009 |  | 55.099
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_4 | DL | DL-ZL01-8044 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | DL | DL-ZL01-8044 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.9359 | 0 | NA | 1.1943 | 0.75 | 78 | 2.6297 |  | 205.1185
Proj_A | Area_4 | DL | DL-ZL01-8044 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8044 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_4 | DL | DL-ZL01-8044 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8044 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_4 | DL | DL-ZL01-8044 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | CS | 0.78 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | CS | 0.91 | 1 | 110 | 15.47 |  | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.092 | 0 | NA | 0.17914 | 1 | 110 | 0.37477 |  | 41.2243
Proj_A | Area_4 | DL | DL-ZL01-8048 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 350
Proj_A | Area_4 | DL | DL-ZL01-8048 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.1966 | 0 | NA | 1.1644 | 0.75 | 78 | 1.9183 |  | 149.6301
Proj_A | Area_4 | DL | DL-ZL01-8048 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8048 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8048 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8048 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | CS | 0.78 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | CS | 0.91 | 1 | 110 | 15.47 |  | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.188 | 0 | NA | 0.17914 | 1 | 110 | 0.21282 |  | 23.4104
Proj_A | Area_4 | DL | DL-ZL01-8049 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 350
Proj_A | Area_4 | DL | DL-ZL01-8049 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.2474 | 0 | NA | 1.1644 | 0.75 | 78 | 1.0894 |  | 84.9716
Proj_A | Area_4 | DL | DL-ZL01-8049 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8049 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8049 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8049 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | CS | 0.78 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | CS | 0.91 | 1 | 110 | 15.47 |  | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.092 | 0 | NA | 0.17914 | 1 | 110 | 0.37477 |  | 41.2243
Proj_A | Area_4 | DL | DL-ZL01-8050 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 350
Proj_A | Area_4 | DL | DL-ZL01-8050 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.1966 | 0 | NA | 1.1644 | 0.75 | 78 | 1.9183 |  | 149.6301
Proj_A | Area_4 | DL | DL-ZL01-8050 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8050 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8050 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8050 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | CS | 0.78 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | CS | 0.91 | 1 | 110 | 15.47 |  | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.188 | 0 | NA | 0.17914 | 1 | 110 | 0.21282 |  | 23.4104
Proj_A | Area_4 | DL | DL-ZL01-8051 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 350
Proj_A | Area_4 | DL | DL-ZL01-8051 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.2474 | 0 | NA | 1.1644 | 0.75 | 78 | 1.0894 |  | 84.9716
Proj_A | Area_4 | DL | DL-ZL01-8051 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8051 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8051 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8051 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | CS | 0.78 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | CS | 0.91 | 1 | 110 | 15.47 |  | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.092 | 0 | NA | 0.17914 | 1 | 110 | 0.37477 |  | 41.2243
Proj_A | Area_4 | DL | DL-ZL01-8052 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 350
Proj_A | Area_4 | DL | DL-ZL01-8052 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.1966 | 0 | NA | 1.1644 | 0.75 | 78 | 1.9183 |  | 149.6301
Proj_A | Area_4 | DL | DL-ZL01-8052 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8052 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8052 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8052 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 11 | 11 | CS | 0.78 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 17 | 17 | CS | 0.91 | 1 | 110 | 15.47 |  | 1701.7
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.188 | 0 | NA | 0.17914 | 1 | 110 | 0.21282 |  | 23.4104
Proj_A | Area_4 | DL | DL-ZL01-8053 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 350
Proj_A | Area_4 | DL | DL-ZL01-8053 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.2474 | 0 | NA | 1.1644 | 0.75 | 78 | 1.0894 |  | 84.9716
Proj_A | Area_4 | DL | DL-ZL01-8053 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_4 | DL | DL-ZL01-8053 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | DL | DL-ZL01-8053 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_4 | DL | DL-ZL01-8053 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 1 | 0 | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.21 | 0 | NA | 0.17914 | 1 | 110 | 0.21676 |  | 23.8439
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.968 | 0 | NA | 0.18767 | 1 | 110 | 0.18167 |  | 19.9834
Proj_A | Area_4 | DL | DL-ZL01-8075 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_4 | DL | DL-ZL01-8075 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.2705 | 0 | NA | 1.1644 | 0.75 | 78 | 1.1096 |  | 86.5452
Proj_A | Area_4 | DL | DL-ZL01-8075 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.0648 | 0 | NA | 1.1943 | 0.75 | 78 | 0.95376 |  | 74.3929
Proj_A | Area_4 | DL | DL-ZL01-8075 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | DL | DL-ZL01-8075 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_4 | DL | DL-ZL01-8075 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | DL | DL-ZL01-8075 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | DL | DL-ZL01-8075 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 0.78 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.145 | 0 | NA | 0.17914 | 1 | 110 | 0.025976 |  | 2.8573
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.15225 | 0 | NA | 1.1644 | 0.75 | 78 | 0.13296 |  | 10.3711
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.148 | 0 | NA | 0.17914 | 1 | 110 | 0.026513 |  | 2.9164
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.1554 | 0 | NA | 1.1644 | 0.75 | 78 | 0.13571 |  | 10.5857
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5006 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.148 | 0 | NA | 0.17914 | 1 | 110 | 0.026513 |  | 2.9164
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.1554 | 0 | NA | 1.1644 | 0.75 | 78 | 0.13571 |  | 10.5857
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 2 | 1.5 | CS | 0.65 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 4 | 3 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 7 | 7 | CS | 0.78 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 2 | 1.5 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.148 | 0 | NA | 0.17914 | 1 | 110 | 0.026513 |  | 2.9164
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.1554 | 0 | NA | 1.1644 | 0.75 | 78 | 0.13571 |  | 10.5857
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 2 | 0 | NA | 0.65 | 0.75 | 78 | 0.975 |  | 76.05
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_4 | HPG | HPG-ZL01-5008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.586 | 1 | 110 | 3.172 |  | 348.92
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 56 | CS | 10.2115 | 1 | 110 | 40.846 |  | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 8 | 128 | CS | 14.365 | 1 | 110 | 114.92 |  | 12641.2
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 10 | 200 | CS | 21.7588 | 1 | 110 | 217.5875 |  | 23934.625
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 3 | CS | 2.21 | 1 | 110 | 2.21 |  | 243.1
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 3 | CS | 7.67 | 1 | 110 | 7.67 |  | 843.7
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 2.65 | 0 | NA | 0.67818 | 1 | 110 | 1.7972 |  | 197.6903
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 1.692 | 0 | NA | 0.79335 | 1 | 110 | 1.3423 |  | 147.6575
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 7.924 | 0 | NA | 1.0279 | 1 | 110 | 8.1454 |  | 895.9913
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 3.0475 | 0 | NA | 4.3591 | 0.75 | 78 | 9.9634 |  | 777.1414
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 1.9458 | 0 | NA | 5.1056 | 0.75 | 78 | 7.4508 |  | 581.1628
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 9.1126 | 0 | NA | 6.6283 | 0.75 | 78 | 45.3006 |  | 3533.4485
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 5 | 0 | NA | 1.69 | 0.75 | 78 | 6.3375 |  | 494.325
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-30-F-310 | Install Inlines - NB 16 CL600 | EA | 2 | 0 | NA | 11.44 | 0.75 | 78 | 17.16 |  | 1338.48
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 8 | 0 | NA | 1.17 | 0.75 | 78 | 7.02 |  | 547.56
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | NA | 5.98 | 0.75 | 78 | 6.7275 |  | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 4 | 0 | NA | 6.76 | 0.75 | 78 | 20.28 |  | 1581.84
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 2.5 | 0 | NA | 8.58 | 0.75 | 78 | 16.0875 |  | 1254.825
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5027 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 56 | CS | 10.2115 | 1 | 110 | 40.846 |  | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 6 | 96 | CS | 14.365 | 1 | 110 | 86.19 |  | 9480.9
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 10 | 200 | CS | 21.7588 | 1 | 110 | 217.5875 |  | 23934.625
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 4 | 8 | CS | 5.46 | 1 | 110 | 21.84 |  | 2402.4
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 2.694 | 0 | NA | 0.67818 | 1 | 110 | 1.827 |  | 200.9727
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 0.884 | 0 | NA | 0.79335 | 1 | 110 | 0.70132 |  | 77.1449
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 9.122 | 0 | NA | 1.0279 | 1 | 110 | 9.3768 |  | 1031.4528
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 3.0981 | 0 | NA | 4.3591 | 0.75 | 78 | 10.1288 |  | 790.0449
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 1.0166 | 0 | NA | 5.1056 | 0.75 | 78 | 3.8927 |  | 303.6335
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 10.4903 | 0 | NA | 6.6283 | 0.75 | 78 | 52.1495 |  | 4067.6574
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 4 | 0 | NA | 1.69 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 6 | 0 | NA | 1.17 | 0.75 | 78 | 5.265 |  | 410.67
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | NA | 5.98 | 0.75 | 78 | 6.7275 |  | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 1 | 0 | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 2.5 | 0 | NA | 8.58 | 0.75 | 78 | 16.0875 |  | 1254.825
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5028 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.586 | 1 | 110 | 3.172 |  | 348.92
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 56 | CS | 10.2115 | 1 | 110 | 40.846 |  | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 8 | 128 | CS | 14.365 | 1 | 110 | 114.92 |  | 12641.2
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 10 | 200 | CS | 21.7588 | 1 | 110 | 217.5875 |  | 23934.625
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 3 | CS | 2.21 | 1 | 110 | 2.21 |  | 243.1
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 3 | CS | 7.67 | 1 | 110 | 7.67 |  | 843.7
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 2.65 | 0 | NA | 0.67818 | 1 | 110 | 1.7972 |  | 197.6903
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 1.692 | 0 | NA | 0.79335 | 1 | 110 | 1.3423 |  | 147.6575
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 7.924 | 0 | NA | 1.0279 | 1 | 110 | 8.1454 |  | 895.9913
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 3.0475 | 0 | NA | 4.3591 | 0.75 | 78 | 9.9634 |  | 777.1414
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 1.9458 | 0 | NA | 5.1056 | 0.75 | 78 | 7.4508 |  | 581.1628
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 9.1126 | 0 | NA | 6.6283 | 0.75 | 78 | 45.3006 |  | 3533.4485
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 5 | 0 | NA | 1.69 | 0.75 | 78 | 6.3375 |  | 494.325
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-30-F-310 | Install Inlines - NB 16 CL600 | EA | 2 | 0 | NA | 11.44 | 0.75 | 78 | 17.16 |  | 1338.48
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 8 | 0 | NA | 1.17 | 0.75 | 78 | 7.02 |  | 547.56
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | NA | 5.98 | 0.75 | 78 | 6.7275 |  | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 4 | 0 | NA | 6.76 | 0.75 | 78 | 20.28 |  | 1581.84
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 2.5 | 0 | NA | 8.58 | 0.75 | 78 | 16.0875 |  | 1254.825
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 2 | 0 | NA | 2.1107 | 0.75 | 78 | 3.166 |  | 246.9461
Proj_A | Area_4 | HPG | HPG-ZL01-5030 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 14 | 28 | CS | 1.1765 | 1 | 110 | 16.471 |  | 1811.81
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 56 | CS | 10.2115 | 1 | 110 | 40.846 |  | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 6 | 96 | CS | 14.365 | 1 | 110 | 86.19 |  | 9480.9
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 10 | 200 | CS | 21.7588 | 1 | 110 | 217.5875 |  | 23934.625
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 5 | 10 | CS | 5.46 | 1 | 110 | 27.3 |  | 3003
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 2.694 | 0 | NA | 0.67818 | 1 | 110 | 1.827 |  | 200.9727
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 0.884 | 0 | NA | 0.79335 | 1 | 110 | 0.70132 |  | 77.1449
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 9.122 | 0 | NA | 1.0279 | 1 | 110 | 9.3768 |  | 1031.4528
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 3.0981 | 0 | NA | 4.3591 | 0.75 | 78 | 10.1288 |  | 790.0449
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 1.0166 | 0 | NA | 5.1056 | 0.75 | 78 | 3.8927 |  | 303.6335
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 10.4903 | 0 | NA | 6.6283 | 0.75 | 78 | 52.1495 |  | 4067.6574
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 5 | 0 | NA | 1.69 | 0.75 | 78 | 6.3375 |  | 494.325
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 7.5 | 0 | NA | 1.17 | 0.75 | 78 | 6.5813 |  | 513.3375
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | NA | 5.98 | 0.75 | 78 | 6.7275 |  | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 1 | 0 | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 2.5 | 0 | NA | 8.58 | 0.75 | 78 | 16.0875 |  | 1254.825
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5031 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.586 | 1 | 110 | 3.172 |  | 348.92
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 56 | CS | 10.2115 | 1 | 110 | 40.846 |  | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 8 | 128 | CS | 14.365 | 1 | 110 | 114.92 |  | 12641.2
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 10 | 200 | CS | 21.7588 | 1 | 110 | 217.5875 |  | 23934.625
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 3 | CS | 2.21 | 1 | 110 | 2.21 |  | 243.1
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 3 | CS | 7.67 | 1 | 110 | 7.67 |  | 843.7
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 2.65 | 0 | NA | 0.67818 | 1 | 110 | 1.7972 |  | 197.6903
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 1.692 | 0 | NA | 0.79335 | 1 | 110 | 1.3423 |  | 147.6575
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 7.924 | 0 | NA | 1.0279 | 1 | 110 | 8.1454 |  | 895.9913
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 3.0475 | 0 | NA | 4.3591 | 0.75 | 78 | 9.9634 |  | 777.1414
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 1.9458 | 0 | NA | 5.1056 | 0.75 | 78 | 7.4508 |  | 581.1628
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 9.1126 | 0 | NA | 6.6283 | 0.75 | 78 | 45.3006 |  | 3533.4485
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 5 | 0 | NA | 1.69 | 0.75 | 78 | 6.3375 |  | 494.325
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-30-F-310 | Install Inlines - NB 16 CL600 | EA | 2 | 0 | NA | 11.44 | 0.75 | 78 | 17.16 |  | 1338.48
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 8 | 0 | NA | 1.17 | 0.75 | 78 | 7.02 |  | 547.56
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | NA | 5.98 | 0.75 | 78 | 6.7275 |  | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 4 | 0 | NA | 6.76 | 0.75 | 78 | 20.28 |  | 1581.84
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 2.5 | 0 | NA | 8.58 | 0.75 | 78 | 16.0875 |  | 1254.825
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5033 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 18 | 36 | CS | 1.1765 | 1 | 110 | 21.177 |  | 2329.47
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 4 | 56 | CS | 10.2115 | 1 | 110 | 40.846 |  | 4493.06
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 6 | 96 | CS | 14.365 | 1 | 110 | 86.19 |  | 9480.9
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 10 | 200 | CS | 21.7588 | 1 | 110 | 217.5875 |  | 23934.625
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 5 | 5 | CS | 0.91 | 1 | 110 | 4.55 |  | 500.5
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 3 | 6 | CS | 1.69 | 1 | 110 | 5.07 |  | 557.7
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 7 | 14 | CS | 5.46 | 1 | 110 | 38.22 |  | 4204.2
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 3 | 1.5 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 1 | 2 | NA | 0.429 | 1 | 110 | 0.429 |  | 47.19
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 2.694 | 0 | NA | 0.67818 | 1 | 110 | 1.827 |  | 200.9727
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 0.884 | 0 | NA | 0.79335 | 1 | 110 | 0.70132 |  | 77.1449
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 9.122 | 0 | NA | 1.0279 | 1 | 110 | 9.3768 |  | 1031.4528
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 250
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 1 | 0 | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 2700 | 2700
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 3.0981 | 0 | NA | 4.3591 | 0.75 | 78 | 10.1288 |  | 790.0449
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 1.0166 | 0 | NA | 5.1056 | 0.75 | 78 | 3.8927 |  | 303.6335
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 10.4903 | 0 | NA | 6.6283 | 0.75 | 78 | 52.1495 |  | 4067.6574
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 6 | 0 | NA | 1.69 | 0.75 | 78 | 7.605 |  | 593.19
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 1 | 0 | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 3.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 9.5 | 0 | NA | 1.17 | 0.75 | 78 | 8.3363 |  | 650.2275
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 1.5 | 0 | NA | 5.98 | 0.75 | 78 | 6.7275 |  | 524.745
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 1 | 0 | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 2.5 | 0 | NA | 8.58 | 0.75 | 78 | 16.0875 |  | 1254.825
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 1 | 0 | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 1 | 0 | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
Proj_A | Area_4 | HPG | HPG-ZL01-5034 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 1 | 0 | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
Proj_A | Area_5 | DL | DL-ZL01-8057 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_5 | DL | DL-ZL01-8057 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.76 | 0 | NA | 0.18767 | 1 | 110 | 0.3303 |  | 36.3335
Proj_A | Area_5 | DL | DL-ZL01-8057 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_5 | DL | DL-ZL01-8057 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.936 | 0 | NA | 1.1943 | 0.75 | 78 | 1.7341 |  | 135.2598
Proj_A | Area_5 | DL | DL-ZL01-8057 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8057 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_5 | DL | DL-ZL01-8058 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 14 | CS | 1.1765 | 1 | 110 | 8.2355 |  | 905.905
Proj_A | Area_5 | DL | DL-ZL01-8058 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.8 | 0 | NA | 0.18767 | 1 | 110 | 0.15014 |  | 16.5152
Proj_A | Area_5 | DL | DL-ZL01-8058 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_5 | DL | DL-ZL01-8058 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.88 | 0 | NA | 1.1943 | 0.75 | 78 | 0.78823 |  | 61.4817
Proj_A | Area_5 | DL | DL-ZL01-8058 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8058 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8059 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_5 | DL | DL-ZL01-8059 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.773 | 0 | NA | 0.18767 | 1 | 110 | 0.14507 |  | 15.9579
Proj_A | Area_5 | DL | DL-ZL01-8059 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_5 | DL | DL-ZL01-8059 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.8503 | 0 | NA | 1.1943 | 0.75 | 78 | 0.76162 |  | 59.4067
Proj_A | Area_5 | DL | DL-ZL01-8059 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8059 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_5 | DL | DL-ZL01-8060 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_5 | DL | DL-ZL01-8060 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.502 | 0 | NA | 0.18767 | 1 | 110 | 0.094212 |  | 10.3633
Proj_A | Area_5 | DL | DL-ZL01-8060 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_5 | DL | DL-ZL01-8060 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.5522 | 0 | NA | 1.1943 | 0.75 | 78 | 0.49461 |  | 38.5798
Proj_A | Area_5 | DL | DL-ZL01-8060 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8060 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_5 | DL | DL-ZL01-8061 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 10 | CS | 1.1765 | 1 | 110 | 5.8825 |  | 647.075
Proj_A | Area_5 | DL | DL-ZL01-8061 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.971 | 0 | NA | 0.18767 | 1 | 110 | 0.18223 |  | 20.0454
Proj_A | Area_5 | DL | DL-ZL01-8061 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_5 | DL | DL-ZL01-8061 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.0681 | 0 | NA | 1.1943 | 0.75 | 78 | 0.95671 |  | 74.6235
Proj_A | Area_5 | DL | DL-ZL01-8061 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8061 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8063 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_5 | DL | DL-ZL01-8063 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.477 | 0 | NA | 0.18767 | 1 | 110 | 0.08952 |  | 9.8472
Proj_A | Area_5 | DL | DL-ZL01-8063 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_5 | DL | DL-ZL01-8063 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.5247 | 0 | NA | 1.1943 | 0.75 | 78 | 0.46998 |  | 36.6585
Proj_A | Area_5 | DL | DL-ZL01-8063 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8063 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8063 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
Proj_A | Area_5 | DL | DL-ZL01-8064 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 14 | CS | 1.1765 | 1 | 110 | 8.2355 |  | 905.905
Proj_A | Area_5 | DL | DL-ZL01-8064 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.314 | 0 | NA | 0.18767 | 1 | 110 | 0.058929 |  | 6.4822
Proj_A | Area_5 | DL | DL-ZL01-8064 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_5 | DL | DL-ZL01-8064 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.3454 | 0 | NA | 1.1943 | 0.75 | 78 | 0.30938 |  | 24.1316
Proj_A | Area_5 | DL | DL-ZL01-8064 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8064 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.508 | 0 | NA | 0.17914 | 1 | 110 | 0.27015 |  | 29.7162
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.791 | 0 | NA | 0.18767 | 1 | 110 | 0.33612 |  | 36.9735
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_5 | DL | DL-ZL01-8067 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_5 | DL | DL-ZL01-8067 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.5834 | 0 | NA | 1.1644 | 0.75 | 78 | 1.3828 |  | 107.8596
Proj_A | Area_5 | DL | DL-ZL01-8067 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.9701 | 0 | NA | 1.1943 | 0.75 | 78 | 1.7646 |  | 137.6422
Proj_A | Area_5 | DL | DL-ZL01-8067 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | DL | DL-ZL01-8067 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_5 | DL | DL-ZL01-8067 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_5 | DL | DL-ZL01-8067 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_5 | DL | DL-ZL01-8067 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 63 | 126 | CS | 1.1765 | 1 | 110 | 74.1195 |  | 8153.145
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.586 | 1 | 110 | 3.172 |  | 348.92
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 8 | 8 | CS | 0.78 | 1 | 110 | 6.24 |  | 686.4
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 16 | 16 | CS | 0.91 | 1 | 110 | 14.56 |  | 1601.6
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 4 | 8 | CS | 1.69 | 1 | 110 | 6.76 |  | 743.6
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 10.664 | 0 | NA | 0.18767 | 1 | 110 | 2.0013 |  | 220.1482
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_5 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 11.7304 | 0 | NA | 1.1943 | 0.75 | 78 | 10.5071 |  | 819.5516
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-30-F-310 | Install Inlines - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 13.5 | 0 | NA | 1.17 | 0.75 | 78 | 11.8463 |  | 924.0075
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | DL | DL-ZL01-8069 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 7 | 0 | NA | 1 | 0.75 | 78 | 5.25 |  | 409.5
Proj_A | Area_5 | FL | FL-XP01-8124 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 9 | 18 | CS | 1.1765 | 1 | 110 | 10.5885 |  | 1164.735
Proj_A | Area_5 | FL | FL-XP01-8124 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 6 | 18 | CS | 1.3715 | 1 | 110 | 8.229 |  | 905.19
Proj_A | Area_5 | FL | FL-XP01-8124 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.798 | 0 | NA | 0.18767 | 1 | 110 | 0.33744 |  | 37.118
Proj_A | Area_5 | FL | FL-XP01-8124 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 5.618 | 0 | NA | 0.17488 | 1 | 110 | 0.98246 |  | 108.0707
Proj_A | Area_5 | FL | FL-XP01-8124 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_5 | FL | FL-XP01-8124 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_5 | FL | FL-XP01-8124 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_5 | FL | FL-XP01-8124 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_5 | FL | FL-XP01-8124 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.9778 | 0 | NA | 1.1943 | 0.75 | 78 | 1.7715 |  | 138.1802
Proj_A | Area_5 | FL | FL-XP01-8124 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 6.1798 | 0 | NA | 1.1644 | 0.75 | 78 | 5.3969 |  | 420.9616
Proj_A | Area_5 | FL | FL-XP01-8124 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 2.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.7062 |  | 133.0875
Proj_A | Area_5 | FL | FL-XP01-8124 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 32 | CS | 3.848 | 1 | 110 | 15.392 |  | 1693.12
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 20 | 240 | CS | 7.683 | 1 | 110 | 153.66 |  | 16902.6
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 12.302 | 0 | NA | 0.57155 | 1 | 110 | 7.0312 |  | 773.4332
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 750
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 100
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 0 | NA | 19 | 1 | 110 | 19 |  | 2090
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 14.1473 | 0 | NA | 3.6724 | 0.75 | 78 | 38.9662 |  | 3039.3601
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 3.5 | 0 | NA | 5.33 | 0.75 | 78 | 13.9912 |  | 1091.3175
Proj_A | Area_5 | HPG | HPG-ZL01-5025 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 3 | 0 | NA | 1.9144 | 0.75 | 78 | 4.3075 |  | 335.9811
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_5 | HPG | HPG-ZL01-5041 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.586 | 1 | 110 | 3.172 |  | 348.92
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 8 | 48 | CS | 2.9315 | 1 | 110 | 23.452 |  | 2579.72
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 10 | 80 | CS | 3.848 | 1 | 110 | 38.48 |  | 4232.8
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 3 | CS | 2.21 | 1 | 110 | 2.21 |  | 243.1
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 3 | CS | 7.67 | 1 | 110 | 7.67 |  | 843.7
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 5.907 | 0 | NA | 0.37535 | 1 | 110 | 2.2172 |  | 243.8888
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 200
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchXST | EA | 1 | 0 | NA | 16 | 1 | 110 | 16 |  | 1760
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 1100
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 6.4977 | 0 | NA | 2.4184 | 0.75 | 78 | 11.7857 |  | 919.2807
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | NA | 1.17 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | NA | 2.34 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 5 | 0 | NA | 3.38 | 0.75 | 78 | 12.675 |  | 988.65
Proj_A | Area_5 | HPG | HPG-ZL01-5043 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 2 | 0 | NA | 1.7364 | 0.75 | 78 | 2.6047 |  | 203.1632
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 2 | 6 | CS | 1.586 | 1 | 110 | 3.172 |  | 348.92
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 8 | 48 | CS | 2.9315 | 1 | 110 | 23.452 |  | 2579.72
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 10 | 80 | CS | 3.848 | 1 | 110 | 38.48 |  | 4232.8
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 1 | 3 | CS | 2.21 | 1 | 110 | 2.21 |  | 243.1
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 6 | 12 | CS | 5.46 | 1 | 110 | 32.76 |  | 3603.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 1 | 3 | CS | 7.67 | 1 | 110 | 7.67 |  | 843.7
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 5.907 | 0 | NA | 0.37535 | 1 | 110 | 2.2172 |  | 243.8888
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 200
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 8 SchXST | EA | 1 | 0 | NA | 16 | 1 | 110 | 16 |  | 1760
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1100 | 1100
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 6.4977 | 0 | NA | 2.4184 | 0.75 | 78 | 11.7857 |  | 919.2807
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | NA | 1.17 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 0.5 | 0 | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | NA | 2.34 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 5 | 0 | NA | 3.38 | 0.75 | 78 | 12.675 |  | 988.65
Proj_A | Area_5 | HPG | HPG-ZL01-5044 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 2 | 0 | NA | 1.7364 | 0.75 | 78 | 2.6047 |  | 203.1632
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 60 | CS | 2.9315 | 1 | 110 | 29.315 |  | 3224.65
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 10.41 | 0 | NA | 0.29857 | 1 | 110 | 3.1081 |  | 341.8937
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 150
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 11.451 | 0 | NA | 1.9109 | 0.75 | 78 | 16.4109 |  | 1280.0498
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | NA | 2.34 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_5 | HPG | HPG-ZL01-5045 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 2 | 0 | NA | 1.6538 | 0.75 | 78 | 2.4806 |  | 193.4888
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 32 | CS | 3.848 | 1 | 110 | 15.392 |  | 1693.12
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 168 | CS | 7.683 | 1 | 110 | 107.562 |  | 11831.82
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 1.806 | 0 | NA | 0.57155 | 1 | 110 | 1.0322 |  | 113.5442
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 100
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 2.0769 | 0 | NA | 3.6724 | 0.75 | 78 | 5.7204 |  | 446.1945
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_5 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 2.5 | 0 | NA | 5.33 | 0.75 | 78 | 9.9938 |  | 779.5125
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 36 | CS | 2.9315 | 1 | 110 | 17.589 |  | 1934.79
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 2.996 | 0 | NA | 0.29857 | 1 | 110 | 0.89452 |  | 98.3971
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 3.2956 | 0 | NA | 1.9109 | 0.75 | 78 | 4.7231 |  | 368.3986
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2 | 0 | NA | 2.34 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_5 | HPG | HPG-ZL01-5054 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
Proj_A | Area_6 | DL | DL-ZL01-8062 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_6 | DL | DL-ZL01-8062 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.621 | 0 | NA | 0.18767 | 1 | 110 | 0.30422 |  | 33.464
Proj_A | Area_6 | DL | DL-ZL01-8062 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_6 | DL | DL-ZL01-8062 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.7831 | 0 | NA | 1.1943 | 0.75 | 78 | 1.5971 |  | 124.5774
Proj_A | Area_6 | DL | DL-ZL01-8062 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_6 | DL | DL-ZL01-8062 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.066 | 0 | NA | 0.17914 | 1 | 110 | 0.19097 |  | 21.0063
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.463 | 0 | NA | 0.18767 | 1 | 110 | 0.46224 |  | 50.8463
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_6 | DL | DL-ZL01-8065 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_6 | DL | DL-ZL01-8065 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.1193 | 0 | NA | 1.1644 | 0.75 | 78 | 0.97751 |  | 76.2456
Proj_A | Area_6 | DL | DL-ZL01-8065 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.7093 | 0 | NA | 1.1943 | 0.75 | 78 | 2.4268 |  | 189.2869
Proj_A | Area_6 | DL | DL-ZL01-8065 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_6 | DL | DL-ZL01-8065 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_6 | DL | DL-ZL01-8065 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | DL | DL-ZL01-8065 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_6 | DL | DL-ZL01-8065 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_6 | DL | DL-ZL01-8066 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_6 | DL | DL-ZL01-8066 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.35 | 0 | NA | 0.18767 | 1 | 110 | 0.065686 |  | 7.2254
Proj_A | Area_6 | DL | DL-ZL01-8066 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_6 | DL | DL-ZL01-8066 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.385 | 0 | NA | 1.1943 | 0.75 | 78 | 0.34485 |  | 26.8983
Proj_A | Area_6 | DL | DL-ZL01-8066 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_6 | DL | DL-ZL01-8066 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3 | 0 | NA | 1.17 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.164 | 0 | NA | 0.17914 | 1 | 110 | 0.20852 |  | 22.9374
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.456 | 0 | NA | 0.18767 | 1 | 110 | 0.27325 |  | 30.0577
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_6 | DL | DL-ZL01-8068 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_6 | DL | DL-ZL01-8068 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.2222 | 0 | NA | 1.1644 | 0.75 | 78 | 1.0674 |  | 83.255
Proj_A | Area_6 | DL | DL-ZL01-8068 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.6016 | 0 | NA | 1.1943 | 0.75 | 78 | 1.4346 |  | 111.8968
Proj_A | Area_6 | DL | DL-ZL01-8068 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_6 | DL | DL-ZL01-8068 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_6 | DL | DL-ZL01-8068 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | DL | DL-ZL01-8068 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_6 | DL | DL-ZL01-8068 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 22 | 44 | CS | 1.1765 | 1 | 110 | 25.883 |  | 2847.13
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.513 | 0 | NA | 0.18767 | 1 | 110 | 0.47162 |  | 51.8785
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_6 | DL | DL-ZL01-8069 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_6 | DL | DL-ZL01-8069 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.7643 | 0 | NA | 1.1943 | 0.75 | 78 | 2.476 |  | 193.1295
Proj_A | Area_6 | DL | DL-ZL01-8069 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 2 | 0 | NA | 0.78 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_6 | DL | DL-ZL01-8069 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | DL | DL-ZL01-8069 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 3.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_6 | DL | DL-ZL01-8069 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 2 | 0 | NA | 1 | 0.75 | 78 | 1.5 |  | 117
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_6 | HPG | HPG-ZL01-5040 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_6 | HPG | HPG-ZL01-5042 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 36 | CS | 2.9315 | 1 | 110 | 17.589 |  | 1934.79
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 9.437 | 0 | NA | 0.29857 | 1 | 110 | 2.8176 |  | 309.9376
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 10.3807 | 0 | NA | 1.9109 | 0.75 | 78 | 14.877 |  | 1160.4064
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | HPG | HPG-ZL01-5046 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2 | 0 | NA | 2.34 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 2 | 12 | CS | 2.9315 | 1 | 110 | 5.863 |  | 644.93
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 168 | CS | 7.683 | 1 | 110 | 107.562 |  | 11831.82
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 4 | 8 | CS | 5.46 | 1 | 110 | 21.84 |  | 2402.4
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 0.15 | 0 | NA | 0.29857 | 1 | 110 | 0.044786 |  | 4.9264
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 14.374 | 0 | NA | 0.57155 | 1 | 110 | 8.2155 |  | 903.7009
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 2 | 0 | NA | 19 | 1 | 110 | 38 |  | 4180
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 3400
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 0.165 | 0 | NA | 1.9109 | 0.75 | 78 | 0.23647 |  | 18.4445
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 16.5301 | 0 | NA | 3.6724 | 0.75 | 78 | 45.5291 |  | 3551.2732
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 1 | 0 | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 3 | 0 | NA | 8.19 | 0.75 | 78 | 18.4275 |  | 1437.345
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4.5 | 0 | NA | 1.17 | 0.75 | 78 | 3.9488 |  | 308.0025
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 0.5 | 0 | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 7 | 0 | NA | 5.33 | 0.75 | 78 | 27.9825 |  | 2182.635
Proj_A | Area_6 | HPG | HPG-ZL01-5047 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 1 | 0 | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 3 | 3 | CS | 2.86 | 1 | 110 | 8.58 |  | 943.8
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 6 | 6 | NA | 0.39 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 10.571 | 0 | NA | 0.18767 | 1 | 110 | 1.9839 |  | 218.2283
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 10 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 500
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_6 | IA | IA-XP02-9001 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_6 | IA | IA-XP02-9001 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 11.6281 | 0 | NA | 1.1943 | 0.75 | 78 | 10.4154 |  | 812.4043
Proj_A | Area_6 | IA | IA-XP02-9001 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 3 | 0 | NA | 0.39 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_6 | IA | IA-XP02-9001 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_6 | IA | IA-XP02-9001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 4.5 | 0 | NA | 0.91 | 0.75 | 78 | 3.0713 |  | 239.5575
Proj_A | Area_6 | IA | IA-XP02-9001 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | NA | 1 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 46 | 92 | CS | 1.1765 | 1 | 110 | 54.119 |  | 5953.09
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 12 | CS | 1.3715 | 1 | 110 | 5.486 |  | 603.46
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 12 | 12 | CS | 0.91 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 2.86 | 1 | 110 | 17.16 |  | 1887.6
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 4 | 4 | NA | 0.39 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 22.539 | 0 | NA | 0.18767 | 1 | 110 | 4.23 |  | 465.2963
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 28 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1400
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 46 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2300
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 0 | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
Proj_A | Area_7 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1000
Proj_A | Area_7 | DL | DL-XP01-8003 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 24.7929 | 0 | NA | 1.1943 | 0.75 | 78 | 22.2073 |  | 1732.1712
Proj_A | Area_7 | DL | DL-XP01-8003 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 4 | 0 | NA | 0.78 | 0.75 | 78 | 2.34 |  | 182.52
Proj_A | Area_7 | DL | DL-XP01-8003 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | DL | DL-XP01-8003 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | DL | DL-XP01-8003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 5 | 0 | NA | 0.91 | 0.75 | 78 | 3.4125 |  | 266.175
Proj_A | Area_7 | DL | DL-XP01-8003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_7 | DL | DL-XP01-8003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 0.5 | 0 | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
Proj_A | Area_7 | DL | DL-XP01-8003 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 9 | 0 | NA | 1 | 0.75 | 78 | 6.75 |  | 526.5
Proj_A | Area_7 | DL | DL-XP01-8017 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_7 | DL | DL-XP01-8017 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.059 | 0 | NA | 0.18767 | 1 | 110 | 0.19875 |  | 21.8621
Proj_A | Area_7 | DL | DL-XP01-8017 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_7 | DL | DL-XP01-8017 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.1649 | 0 | NA | 1.1943 | 0.75 | 78 | 1.0434 |  | 81.3865
Proj_A | Area_7 | DL | DL-XP01-8017 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8017 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8018 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_7 | DL | DL-XP01-8018 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.662 | 0 | NA | 0.18767 | 1 | 110 | 0.12424 |  | 13.6664
Proj_A | Area_7 | DL | DL-XP01-8018 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 300
Proj_A | Area_7 | DL | DL-XP01-8018 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.7282 | 0 | NA | 1.1943 | 0.75 | 78 | 0.65226 |  | 50.8761
Proj_A | Area_7 | DL | DL-XP01-8018 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8018 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8019 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 9 | 18 | CS | 1.1765 | 1 | 110 | 10.5885 |  | 1164.735
Proj_A | Area_7 | DL | DL-XP01-8019 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.446 | 0 | NA | 0.18767 | 1 | 110 | 0.27138 |  | 29.8513
Proj_A | Area_7 | DL | DL-XP01-8019 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_7 | DL | DL-XP01-8019 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.5906 | 0 | NA | 1.1943 | 0.75 | 78 | 1.4247 |  | 111.1282
Proj_A | Area_7 | DL | DL-XP01-8019 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8019 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8024 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 9 | 18 | CS | 1.1765 | 1 | 110 | 10.5885 |  | 1164.735
Proj_A | Area_7 | DL | DL-XP01-8024 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.675 | 0 | NA | 0.18767 | 1 | 110 | 0.50203 |  | 55.2228
Proj_A | Area_7 | DL | DL-XP01-8024 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 9 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 450
Proj_A | Area_7 | DL | DL-XP01-8024 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.9425 | 0 | NA | 1.1943 | 0.75 | 78 | 2.6356 |  | 205.5796
Proj_A | Area_7 | DL | DL-XP01-8024 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8024 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8024 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_7 | DL | DL-XP01-8071 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 10 | CS | 1.1765 | 1 | 110 | 5.8825 |  | 647.075
Proj_A | Area_7 | DL | DL-XP01-8071 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.897 | 0 | NA | 0.18767 | 1 | 110 | 0.16834 |  | 18.5177
Proj_A | Area_7 | DL | DL-XP01-8071 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_7 | DL | DL-XP01-8071 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.9867 | 0 | NA | 1.1943 | 0.75 | 78 | 0.8838 |  | 68.9364
Proj_A | Area_7 | DL | DL-XP01-8071 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8071 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_7 | DL | DL-XP01-8072 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 5 | 10 | CS | 1.1765 | 1 | 110 | 5.8825 |  | 647.075
Proj_A | Area_7 | DL | DL-XP01-8072 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.897 | 0 | NA | 0.18767 | 1 | 110 | 0.16834 |  | 18.5177
Proj_A | Area_7 | DL | DL-XP01-8072 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_7 | DL | DL-XP01-8072 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.9867 | 0 | NA | 1.1943 | 0.75 | 78 | 0.8838 |  | 68.9364
Proj_A | Area_7 | DL | DL-XP01-8072 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8072 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_7 | DL | DL-XP01-8073 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_7 | DL | DL-XP01-8073 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.301 | 0 | NA | 0.18767 | 1 | 110 | 0.43184 |  | 47.502
Proj_A | Area_7 | DL | DL-XP01-8073 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_7 | DL | DL-XP01-8073 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.5311 | 0 | NA | 1.1943 | 0.75 | 78 | 2.2671 |  | 176.8369
Proj_A | Area_7 | DL | DL-XP01-8073 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_7 | DL | DL-XP01-8073 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-XP01-8073 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 1.826 | 0 | NA | 0.17914 | 1 | 110 | 0.32711 |  | 35.9826
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.908 | 0 | NA | 0.18767 | 1 | 110 | 0.35808 |  | 39.3889
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_7 | DL | DL-ZL01-8016 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_7 | DL | DL-ZL01-8016 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.9173 | 0 | NA | 1.1644 | 0.75 | 78 | 1.6744 |  | 130.6045
Proj_A | Area_7 | DL | DL-ZL01-8016 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.0988 | 0 | NA | 1.1943 | 0.75 | 78 | 1.8799 |  | 146.634
Proj_A | Area_7 | DL | DL-ZL01-8016 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | DL | DL-ZL01-8016 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_7 | DL | DL-ZL01-8016 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_7 | DL | DL-ZL01-8016 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-ZL01-8016 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_7 | DL | DL-ZL01-8016 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 2.042 | 0 | NA | 0.17914 | 1 | 110 | 0.36581 |  | 40.239
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.732 | 0 | NA | 0.18767 | 1 | 110 | 0.32505 |  | 35.7555
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_7 | DL | DL-ZL01-8020 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_7 | DL | DL-ZL01-8020 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 2.1441 | 0 | NA | 1.1644 | 0.75 | 78 | 1.8725 |  | 146.0539
Proj_A | Area_7 | DL | DL-ZL01-8020 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.9052 | 0 | NA | 1.1943 | 0.75 | 78 | 1.7065 |  | 133.108
Proj_A | Area_7 | DL | DL-ZL01-8020 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | DL | DL-ZL01-8020 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_7 | DL | DL-ZL01-8020 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_7 | DL | DL-ZL01-8020 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_7 | DL | DL-ZL01-8020 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_7 | DL | DL-ZL01-8020 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 32 | CS | 3.848 | 1 | 110 | 15.392 |  | 1693.12
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 18 | 216 | CS | 7.683 | 1 | 110 | 138.294 |  | 15212.34
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 7.691 | 0 | NA | 0.57155 | 1 | 110 | 4.3958 |  | 483.5372
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 750
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 100
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 1 | 0 | NA | 19 | 1 | 110 | 19 |  | 2090
Proj_A | Area_7 | LG | LG-ZL01-4002 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 1700 | 1700
Proj_A | Area_7 | LG | LG-ZL01-4002 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 8.8446 | 0 | NA | 3.6724 | 0.75 | 78 | 24.361 |  | 1900.156
Proj_A | Area_7 | LG | LG-ZL01-4002 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_7 | LG | LG-ZL01-4002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_7 | LG | LG-ZL01-4002 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 3.5 | 0 | NA | 5.33 | 0.75 | 78 | 13.9912 |  | 1091.3175
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 14 | 28 | CS | 1.1765 | 1 | 110 | 16.471 |  | 1811.81
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 8 | 48 | CS | 2.9315 | 1 | 110 | 23.452 |  | 2579.72
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 10 | 80 | CS | 3.848 | 1 | 110 | 38.48 |  | 4232.8
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 7 | 14 | CS | 5.46 | 1 | 110 | 38.22 |  | 4204.2
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 5.099 | 0 | NA | 0.37535 | 1 | 110 | 1.9139 |  | 210.528
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_7 | LG | LG-ZL01-4003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 200
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 5.6089 | 0 | NA | 2.4184 | 0.75 | 78 | 10.1735 |  | 793.5352
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 2 | 0 | NA | 0.78 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 4 | 0 | NA | 1.69 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-30-F-310 | Install Inlines - NB 8 CL600 | EA | 1 | 0 | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 7.5 | 0 | NA | 1.17 | 0.75 | 78 | 6.5813 |  | 513.3375
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | NA | 2.34 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 6 | 0 | NA | 3.38 | 0.75 | 78 | 15.21 |  | 1186.38
Proj_A | Area_7 | LG | LG-ZL01-4003 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 3 | 0 | NA | 1.7364 | 0.75 | 78 | 3.907 |  | 304.7448
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 14 | 28 | CS | 1.1765 | 1 | 110 | 16.471 |  | 1811.81
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 8 | 48 | CS | 2.9315 | 1 | 110 | 23.452 |  | 2579.72
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 10 | 80 | CS | 3.848 | 1 | 110 | 38.48 |  | 4232.8
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 2 | 4 | CS | 1.69 | 1 | 110 | 3.38 |  | 371.8
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 7 | 14 | CS | 5.46 | 1 | 110 | 38.22 |  | 4204.2
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 2 | 1 | NA | 0.26 | 1 | 110 | 0.52 |  | 57.2
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 5.099 | 0 | NA | 0.37535 | 1 | 110 | 1.9139 |  | 210.528
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_7 | LG | LG-ZL01-4004 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 200
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 5.6089 | 0 | NA | 2.4184 | 0.75 | 78 | 10.1735 |  | 793.5352
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 4 | 0 | NA | 1.69 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-30-F-310 | Install Inlines - NB 8 CL600 | EA | 1 | 0 | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 2 | 0 | NA | 5.46 | 0.75 | 78 | 8.19 |  | 638.82
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 7.5 | 0 | NA | 1.17 | 0.75 | 78 | 6.5812 |  | 513.3375
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | NA | 2.34 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 6 | 0 | NA | 3.38 | 0.75 | 78 | 15.21 |  | 1186.38
Proj_A | Area_7 | LG | LG-ZL01-4004 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 3 | 0 | NA | 1.7364 | 0.75 | 78 | 3.907 |  | 304.7448
Proj_A | Area_7 | LG | LG-ZL01-4005 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.1765 | 1 | 110 | 2.353 |  | 258.83
Proj_A | Area_7 | LG | LG-ZL01-4005 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 36 | CS | 2.9315 | 1 | 110 | 17.589 |  | 1934.79
Proj_A | Area_7 | LG | LG-ZL01-4005 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_7 | LG | LG-ZL01-4005 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 2.996 | 0 | NA | 0.29857 | 1 | 110 | 0.89452 |  | 98.3971
Proj_A | Area_7 | LG | LG-ZL01-4005 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_7 | LG | LG-ZL01-4005 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 3.2956 | 0 | NA | 1.9109 | 0.75 | 78 | 4.7231 |  | 368.3986
Proj_A | Area_7 | LG | LG-ZL01-4005 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4005 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_7 | LG | LG-ZL01-4005 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_7 | LG | LG-ZL01-4005 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2 | 0 | NA | 2.34 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_7 | LG | LG-ZL01-4005 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 32 | CS | 3.848 | 1 | 110 | 15.392 |  | 1693.12
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 14 | 168 | CS | 7.683 | 1 | 110 | 107.562 |  | 11831.82
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 1 | 2 | CS | 5.46 | 1 | 110 | 5.46 |  | 600.6
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.143 | 0 | NA | 0.18767 | 1 | 110 | 0.026837 |  | 2.9521
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 1.438 | 0 | NA | 0.57155 | 1 | 110 | 0.82189 |  | 90.4078
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 500
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_7 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 100 | 100
Proj_A | Area_7 | LG | LG-ZL01-4007 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.1573 | 0 | NA | 1.1943 | 0.75 | 78 | 0.1409 |  | 10.9899
Proj_A | Area_7 | LG | LG-ZL01-4007 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 1.6537 | 0 | NA | 3.6724 | 0.75 | 78 | 4.5548 |  | 355.2756
Proj_A | Area_7 | LG | LG-ZL01-4007 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_7 | LG | LG-ZL01-4007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 1 | 0 | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_7 | LG | LG-ZL01-4007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 2.5 | 0 | NA | 5.33 | 0.75 | 78 | 9.9938 |  | 779.5125
Proj_A | Area_7 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 4 | 8 | CS | 1.1765 | 1 | 110 | 4.706 |  | 517.66
Proj_A | Area_7 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 60 | CS | 2.9315 | 1 | 110 | 29.315 |  | 3224.65
Proj_A | Area_7 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_7 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 5.923 | 0 | NA | 0.29857 | 1 | 110 | 1.7684 |  | 194.528
Proj_A | Area_7 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_7 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 150
Proj_A | Area_7 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_7 | LG | LG-ZL01-4008 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_7 | LG | LG-ZL01-4008 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 6.5153 | 0 | NA | 1.9109 | 0.75 | 78 | 9.3373 |  | 728.3127
Proj_A | Area_7 | LG | LG-ZL01-4008 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4008 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_7 | LG | LG-ZL01-4008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_7 | LG | LG-ZL01-4008 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2.5 | 0 | NA | 2.34 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_7 | LG | LG-ZL01-4008 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4014 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_7 | LG | LG-ZL01-4014 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | LG | LG-ZL01-4014 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_7 | LG | LG-ZL01-4014 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4014 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_7 | LG | LG-ZL01-4014 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_7 | LG | LG-ZL01-4018 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_7 | LG | LG-ZL01-4018 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_7 | LG | LG-ZL01-4018 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_7 | LG | LG-ZL01-4018 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_7 | LG | LG-ZL01-4018 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_7 | LG | LG-ZL01-4018 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 39 | 78 | CS | 1.1765 | 1 | 110 | 45.8835 |  | 5047.185
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 2 | 4 | CS | 1.17 | 1 | 110 | 2.34 |  | 257.4
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 1 | 1 | CS | 2.86 | 1 | 110 | 2.86 |  | 314.6
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 9.186 | 0 | NA | 0.18767 | 1 | 110 | 1.724 |  | 189.6363
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 41 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 2050
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_8 | DL | DL-XP01-8003 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 10.1046 | 0 | NA | 1.1943 | 0.75 | 78 | 9.0508 |  | 705.9641
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3.5 | 0 | NA | 0.91 | 0.75 | 78 | 2.3887 |  | 186.3225
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1.5 | 0 | NA | 1.17 | 0.75 | 78 | 1.3163 |  | 102.6675
Proj_A | Area_8 | DL | DL-XP01-8003 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 6 | 0 | NA | 1 | 0.75 | 78 | 4.5 |  | 351
Proj_A | Area_8 | DL | DL-XP01-8021 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_8 | DL | DL-XP01-8021 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.326 | 0 | NA | 0.18767 | 1 | 110 | 0.24885 |  | 27.374
Proj_A | Area_8 | DL | DL-XP01-8021 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_8 | DL | DL-XP01-8021 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.4586 | 0 | NA | 1.1943 | 0.75 | 78 | 1.3065 |  | 101.906
Proj_A | Area_8 | DL | DL-XP01-8021 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8021 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_8 | DL | DL-XP01-8021 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 14 | 14 | CS | 0.78 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 2 | 2 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 2.752 | 0 | NA | 0.15355 | 1 | 110 | 0.42257 |  | 46.4829
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.423 | 0 | NA | 0.18767 | 1 | 110 | 0.45473 |  | 50.0205
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 32 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1600
Proj_A | Area_8 | DL | DL-XP01-8025 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_8 | DL | DL-XP01-8025 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 2.8896 | 0 | NA | 1.0151 | 0.75 | 78 | 2.2 |  | 171.6011
Proj_A | Area_8 | DL | DL-XP01-8025 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.6653 | 0 | NA | 1.1943 | 0.75 | 78 | 2.3873 |  | 186.2128
Proj_A | Area_8 | DL | DL-XP01-8025 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_8 | DL | DL-XP01-8025 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 3 | 0 | NA | 0.39 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | DL | DL-XP01-8025 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_8 | DL | DL-XP01-8025 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_8 | DL | DL-XP01-8025 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_8 | DL | DL-XP01-8025 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_8 | DL | DL-XP01-8070 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 7 | 14 | CS | 1.1765 | 1 | 110 | 8.2355 |  | 905.905
Proj_A | Area_8 | DL | DL-XP01-8070 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.301 | 0 | NA | 0.18767 | 1 | 110 | 0.24416 |  | 26.8579
Proj_A | Area_8 | DL | DL-XP01-8070 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 7 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 350
Proj_A | Area_8 | DL | DL-XP01-8070 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.4311 | 0 | NA | 1.1943 | 0.75 | 78 | 1.2819 |  | 99.9847
Proj_A | Area_8 | DL | DL-XP01-8070 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_8 | DL | DL-XP01-8070 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 10 | 10 | CS | 0.78 | 1 | 110 | 7.8 |  | 858
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 12 | 12 | CS | 0.91 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.96 | 0 | NA | 0.17914 | 1 | 110 | 0.17198 |  | 18.9175
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.049 | 0 | NA | 0.18767 | 1 | 110 | 0.38454 |  | 42.2997
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 5 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 250
Proj_A | Area_8 | DL | DL-ZL01-8022 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_8 | DL | DL-ZL01-8022 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 1.008 | 0 | NA | 1.1644 | 0.75 | 78 | 0.88031 |  | 68.6639
Proj_A | Area_8 | DL | DL-ZL01-8022 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 2.2539 | 0 | NA | 1.1943 | 0.75 | 78 | 2.0188 |  | 157.4701
Proj_A | Area_8 | DL | DL-ZL01-8022 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_8 | DL | DL-ZL01-8022 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_8 | DL | DL-ZL01-8022 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | DL | DL-ZL01-8022 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_8 | DL | DL-ZL01-8022 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_8 | DL | DL-ZL01-8022 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 8 | 16 | CS | 1.1765 | 1 | 110 | 9.412 |  | 1035.32
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.938 | 0 | NA | 0.17914 | 1 | 110 | 0.16804 |  | 18.4839
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 1.681 | 0 | NA | 0.18767 | 1 | 110 | 0.31548 |  | 34.7027
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_8 | DL | DL-ZL01-8023 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_8 | DL | DL-ZL01-8023 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.9849 | 0 | NA | 1.1644 | 0.75 | 78 | 0.86013 |  | 67.0904
Proj_A | Area_8 | DL | DL-ZL01-8023 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 1.8491 | 0 | NA | 1.1943 | 0.75 | 78 | 1.6563 |  | 129.1885
Proj_A | Area_8 | DL | DL-ZL01-8023 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_8 | DL | DL-ZL01-8023 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_8 | DL | DL-ZL01-8023 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | DL | DL-ZL01-8023 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 0.5 | 0 | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
Proj_A | Area_8 | DL | DL-ZL01-8023 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_8 | DL | DL-ZL01-8023 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 16 | 32 | CS | 1.1765 | 1 | 110 | 18.824 |  | 2070.64
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 1 | 0.75 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 6 | 6 | CS | 0.78 | 1 | 110 | 4.68 |  | 514.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 8 | 8 | CS | 0.91 | 1 | 110 | 7.28 |  | 800.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 0.86 | 0 | NA | 0.17914 | 1 | 110 | 0.15406 |  | 16.9469
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 2.929 | 0 | NA | 0.18767 | 1 | 110 | 0.54969 |  | 60.4664
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_8 | DL | DL-ZL01-8035 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_8 | DL | DL-ZL01-8035 | Field | 600 | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 0.903 | 0 | NA | 1.1644 | 0.75 | 78 | 0.78861 |  | 61.5114
Proj_A | Area_8 | DL | DL-ZL01-8035 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 3.2219 | 0 | NA | 1.1943 | 0.75 | 78 | 2.8859 |  | 225.1
Proj_A | Area_8 | DL | DL-ZL01-8035 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_8 | DL | DL-ZL01-8035 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 3 | 0 | NA | 0.78 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_8 | DL | DL-ZL01-8035 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | DL | DL-ZL01-8035 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | DL | DL-ZL01-8035 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | NA | 0.4 | 0.75 | 78 | 0.6 |  | 46.8
Proj_A | Area_8 | DL | DL-ZL01-8035 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 1 | 0 | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 10 | 20 | CS | 1.1765 | 1 | 110 | 11.765 |  | 1294.15
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 8 | 96 | CS | 4.7255 | 1 | 110 | 37.804 |  | 4158.44
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 3 | 3 | CS | 0.91 | 1 | 110 | 2.73 |  | 300.3
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 3 | 6 | CS | 1.17 | 1 | 110 | 3.51 |  | 386.1
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 5 | 10 | CS | 4.42 | 1 | 110 | 22.1 |  | 2431
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 3 | 1.5 | NA | 0.26 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 1.63 | 0 | NA | 0.40947 | 1 | 110 | 0.66743 |  | 73.4178
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 2000
Proj_A | Area_8 | LG | LG-XP01-4001 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 18 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 900
Proj_A | Area_8 | LG | LG-XP01-4001 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 1.8745 | 0 | NA | 2.6274 | 0.75 | 78 | 3.6938 |  | 288.1188
Proj_A | Area_8 | LG | LG-XP01-4001 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_8 | LG | LG-XP01-4001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 1.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.0237 |  | 79.8525
Proj_A | Area_8 | LG | LG-XP01-4001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 7 | 0 | NA | 0.91 | 0.75 | 78 | 4.7775 |  | 372.645
Proj_A | Area_8 | LG | LG-XP01-4001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 0.5 | 0 | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
Proj_A | Area_8 | LG | LG-XP01-4001 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 0.5 | 0 | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 4 | 4 | CS | 0.78 | 1 | 110 | 3.12 |  | 343.2
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 19 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 950
Proj_A | Area_8 | LG | LG-XP01-4017 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_8 | LG | LG-XP01-4017 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_8 | LG | LG-XP01-4017 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_8 | LG | LG-XP01-4017 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_8 | LG | LG-XP01-4017 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 2.5 | 0 | NA | 0.91 | 0.75 | 78 | 1.7062 |  | 133.0875
Proj_A | Area_8 | LG | LG-XP01-4017 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_8 | LG | LG-ZL01-4006 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 2 | 12 | CS | 2.9315 | 1 | 110 | 5.863 |  | 644.93
Proj_A | Area_8 | LG | LG-ZL01-4006 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 3.279 | 0 | NA | 0.29857 | 1 | 110 | 0.97901 |  | 107.6916
Proj_A | Area_8 | LG | LG-ZL01-4006 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 3.6069 | 0 | NA | 1.9109 | 0.75 | 78 | 5.1692 |  | 403.1973
Proj_A | Area_8 | LG | LG-ZL01-4006 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 2 | 0 | NA | 4.29 | 0.75 | 78 | 6.435 |  | 501.93
Proj_A | Area_8 | LG | LG-ZL01-4006 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 3 | 0 | NA | 2.34 | 0.75 | 78 | 5.265 |  | 410.67
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 12 | 24 | CS | 1.1765 | 1 | 110 | 14.118 |  | 1552.98
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 10 | 60 | CS | 2.9315 | 1 | 110 | 29.315 |  | 3224.65
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 4 | 32 | CS | 3.848 | 1 | 110 | 15.392 |  | 1693.12
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 18 | 216 | CS | 7.683 | 1 | 110 | 138.294 |  | 15212.34
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 2 | 2 | CS | 0.91 | 1 | 110 | 1.82 |  | 200.2
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 1 | 1 | CS | 3.77 | 1 | 110 | 3.77 |  | 414.7
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 4 | 8 | CS | 5.46 | 1 | 110 | 21.84 |  | 2402.4
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.484 | 0 | NA | 0.18767 | 1 | 110 | 0.090834 |  | 9.9917
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 0.82 | 0 | NA | 0.29857 | 1 | 110 | 0.24483 |  | 26.9311
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 2.912 | 0 | NA | 0.57155 | 1 | 110 | 1.6644 |  | 183.079
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 250 | 750
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_8 | LG | LG-ZL01-4007 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 150
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.5324 | 0 | NA | 1.1943 | 0.75 | 78 | 0.47688 |  | 37.1965
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 0.902 | 0 | NA | 1.9109 | 0.75 | 78 | 1.2927 |  | 100.8301
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 3.3488 | 0 | NA | 3.6724 | 0.75 | 78 | 9.2237 |  | 719.4454
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 1 | 0 | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 2 | 0 | NA | 1.69 | 0.75 | 78 | 2.535 |  | 197.73
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 1 | 0 | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 5 | 0 | NA | 8.19 | 0.75 | 78 | 30.7125 |  | 2395.575
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 4 | 0 | NA | 1.17 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 1.5 | 0 | NA | 2.34 | 0.75 | 78 | 2.6325 |  | 205.335
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 2 | 0 | NA | 3.38 | 0.75 | 78 | 5.07 |  | 395.46
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 9 | 0 | NA | 5.33 | 0.75 | 78 | 35.9775 |  | 2806.245
Proj_A | Area_8 | LG | LG-ZL01-4007 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 2 | 0 | NA | 1.9144 | 0.75 | 78 | 2.8716 |  | 223.9874
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 6 | 12 | CS | 1.1765 | 1 | 110 | 7.059 |  | 776.49
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 6 | 36 | CS | 2.9315 | 1 | 110 | 17.589 |  | 1934.79
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 2 | 4 | CS | 5.46 | 1 | 110 | 10.92 |  | 1201.2
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 0.296 | 0 | NA | 0.18767 | 1 | 110 | 0.055551 |  | 6.1106
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 4.807 | 0 | NA | 0.29857 | 1 | 110 | 1.4352 |  | 157.8754
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 75
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 1 | 0 | NA | 12 | 1 | 110 | 12 |  | 1320
Proj_A | Area_8 | LG | LG-ZL01-4009 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_8 | LG | LG-ZL01-4009 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 0.3256 | 0 | NA | 1.1943 | 0.75 | 78 | 0.29164 |  | 22.7482
Proj_A | Area_8 | LG | LG-ZL01-4009 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 5.2877 | 0 | NA | 1.9109 | 0.75 | 78 | 7.578 |  | 591.0855
Proj_A | Area_8 | LG | LG-ZL01-4009 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4009 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 1 | 0 | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
Proj_A | Area_8 | LG | LG-ZL01-4009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 2 | 0 | NA | 1.17 | 0.75 | 78 | 1.755 |  | 136.89
Proj_A | Area_8 | LG | LG-ZL01-4009 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 2 | 0 | NA | 2.34 | 0.75 | 78 | 3.51 |  | 273.78
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4015 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_8 | LG | LG-ZL01-4015 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_8 | LG | LG-ZL01-4015 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_8 | LG | LG-ZL01-4015 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4015 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_8 | LG | LG-ZL01-4015 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4016 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_8 | LG | LG-ZL01-4016 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_8 | LG | LG-ZL01-4016 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_8 | LG | LG-ZL01-4016 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4016 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_8 | LG | LG-ZL01-4016 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 5 | 5 | CS | 0.78 | 1 | 110 | 3.9 |  | 429
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 4 | 4 | CS | 0.91 | 1 | 110 | 3.64 |  | 400.4
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 10 | 10 | CS | 0.91 | 1 | 110 | 9.1 |  | 1001
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.69 | 1 | 110 | 1.69 |  | 185.9
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 2 | 2 | NA | 0.39 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_8 | LG | LG-ZL01-4019 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_8 | LG | LG-ZL01-4019 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_8 | LG | LG-ZL01-4019 | Field | 600 | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_8 | LG | LG-ZL01-4019 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 1 | 0 | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
Proj_A | Area_8 | LG | LG-ZL01-4019 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 2.5 | 0 | NA | 1.17 | 0.75 | 78 | 2.1938 |  | 171.1125
Proj_A | Area_8 | LG | LG-ZL01-4019 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 1 | 0 | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 Sch160 | EA | 1 | 2 | CS | 1.781 | 1 | 110 | 1.781 |  | 195.91
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 15 | 30 | CS | 1.1765 | 1 | 110 | 17.6475 |  | 1941.225
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 1 | 1.5 | CS | 1.3 | 1 | 110 | 1.3 |  | 143
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 1 | 1.5 | CS | 1.04 | 1 | 110 | 1.04 |  | 114.4
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 4.798 | 0 | NA | 0.18767 | 1 | 110 | 0.90046 |  | 99.0502
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 17 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 850
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 1 | 0 | NA | 5.6 | 1 | 110 | 5.6 |  | 616
Proj_A | Area_9 | DL | DL-XP01-8015 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 500
Proj_A | Area_9 | DL | DL-XP01-8015 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 5.2778 | 0 | NA | 1.1943 | 0.75 | 78 | 4.7274 |  | 368.7367
Proj_A | Area_9 | DL | DL-XP01-8015 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 4 | 0 | NA | 0.65 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_9 | DL | DL-XP01-8015 | Field | 600 | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_9 | DL | DL-XP01-8015 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | DL | DL-XP01-8015 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | DL | DL-XP01-8015 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 8.5 | 0 | NA | 0.91 | 0.75 | 78 | 5.8012 |  | 452.4975
Proj_A | Area_9 | DL | DL-XP01-8015 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 3 | 0 | NA | 1 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_9 | DL | DL-XP01-8054 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 12 | CS | 1.3715 | 1 | 110 | 5.486 |  | 603.46
Proj_A | Area_9 | DL | DL-XP01-8054 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 2.069 | 0 | NA | 0.17488 | 1 | 110 | 0.36182 |  | 39.8003
Proj_A | Area_9 | DL | DL-XP01-8054 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_9 | DL | DL-XP01-8054 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 2.2759 | 0 | NA | 1.1644 | 0.75 | 78 | 1.9876 |  | 155.032
Proj_A | Area_9 | DL | DL-XP01-8054 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_9 | DL | DL-XP01-8054 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | NA | 1.5 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_9 | DL | DL-XP01-8055 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 1 | 0.75 | CS | 0.65 | 1 | 110 | 0.65 |  | 71.5
Proj_A | Area_9 | DL | DL-XP01-8055 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 2 | 1.5 | CS | 0.78 | 1 | 110 | 1.56 |  | 171.6
Proj_A | Area_9 | DL | DL-XP01-8055 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_9 | DL | DL-XP01-8055 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | DL | DL-XP01-8055 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 1 | 0.75 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | DL | DL-XP01-8055 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 3 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 150
Proj_A | Area_9 | DL | DL-XP01-8055 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_9 | DL | DL-XP01-8055 | Field | 600 | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_9 | DL | DL-XP01-8055 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_9 | DL | DL-XP01-8055 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | DL | DL-XP01-8055 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Proj_A | Area_9 | DL | DL-XP01-8056 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 12 | CS | 1.3715 | 1 | 110 | 5.486 |  | 603.46
Proj_A | Area_9 | DL | DL-XP01-8056 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 2.069 | 0 | NA | 0.17488 | 1 | 110 | 0.36182 |  | 39.8003
Proj_A | Area_9 | DL | DL-XP01-8056 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_9 | DL | DL-XP01-8056 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 2.2759 | 0 | NA | 1.1644 | 0.75 | 78 | 1.9876 |  | 155.032
Proj_A | Area_9 | DL | DL-XP01-8056 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_9 | DL | DL-XP01-8056 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | NA | 1.5 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 18 | 36 | CS | 1.1765 | 1 | 110 | 21.177 |  | 2329.47
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 1 | 1 | CS | 0.78 | 1 | 110 | 0.78 |  | 85.8
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 1 | 1 | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 16.611 | 0 | NA | 0.18767 | 1 | 110 | 3.1174 |  | 342.9183
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 2 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 100
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 18 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 900
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 2 | 0 | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
Proj_A | Area_9 | DL | DL-XP01-8082 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 500 | 1000
Proj_A | Area_9 | DL | DL-XP01-8082 | Field | 600 | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 18.2721 | 0 | NA | 1.1943 | 0.75 | 78 | 16.3666 |  | 1276.5915
Proj_A | Area_9 | DL | DL-XP01-8082 | Field | 600 | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 1 | 0 | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
Proj_A | Area_9 | DL | DL-XP01-8082 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_9 | DL | DL-XP01-8082 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 3.5 | 0 | NA | 0.91 | 0.75 | 78 | 2.3887 |  | 186.3225
Proj_A | Area_9 | DL | DL-XP01-8082 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 6 | 0 | NA | 1 | 0.75 | 78 | 4.5 |  | 351
Proj_A | Area_9 | FL | FL-XP01-8117 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 4 | 12 | CS | 1.3715 | 1 | 110 | 5.486 |  | 603.46
Proj_A | Area_9 | FL | FL-XP01-8117 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 24 | 144 | CS | 2.431 | 1 | 110 | 58.344 |  | 6417.84
Proj_A | Area_9 | FL | FL-XP01-8117 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchSTD | LM | 6.778 | 0 | NA | 0.21753 | 1 | 110 | 1.4744 |  | 162.1862
Proj_A | Area_9 | FL | FL-XP01-8117 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 4 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 200
Proj_A | Area_9 | FL | FL-XP01-8117 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 24 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 1800
Proj_A | Area_9 | FL | FL-XP01-8117 | Field | 600 | 150-10-F-110 | Field Butt Weld - NB 6 SchSTD | EA | 1 | 6 | CS | 3.3501 | 0.75 | 78 | 2.5126 |  | 195.9809
Proj_A | Area_9 | FL | FL-XP01-8117 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchSTD | LM | 7.4558 | 0 | NA | 1.4033 | 0.75 | 78 | 7.847 |  | 612.0623
Proj_A | Area_9 | FL | FL-XP01-8117 | Field | 600 | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | LM | 64.1047 | 0 | NA | 1.1943 | 0.75 | 78 | 57.4194 |  | 4478.7142
Proj_A | Area_9 | FL | FL-XP01-8117 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 1 | 0 | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
Proj_A | Area_9 | FL | FL-XP01-8117 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 4 | 0 | NA | 1.95 | 0.75 | 78 | 5.85 |  | 456.3
Proj_A | Area_9 | FL | FL-XP01-8117 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 7 | 0 | NA | 1.6538 | 0.75 | 78 | 8.6822 |  | 677.2106
Proj_A | Area_9 | FL | FL-XP01-8117 | Field | 600 | 150-60-F-610 | Field X-Ray - NB 6 | EA | 1 | 0 | NA | 0 | 0.75 | 78 | 0 | 1000 | 1000
Proj_A | Area_9 | FL | FL-XP01-8117 | Field | 300 | 150-80-F-810 | Field Coating - NB 6 | LM | 64.1047 | 0 | CS | 0 | 0.75 | 78 | 0 | 100 | 6410.47
Proj_A | Area_9 | FL | FL-XP01-8118 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 22 | 66 | CS | 1.3715 | 1 | 110 | 30.173 |  | 3319.03
Proj_A | Area_9 | FL | FL-XP01-8118 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 19.024 | 0 | NA | 0.17488 | 1 | 110 | 3.3269 |  | 365.9552
Proj_A | Area_9 | FL | FL-XP01-8118 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 22 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 1100
Proj_A | Area_9 | FL | FL-XP01-8118 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 2 | 0 | NA | 6 | 1 | 110 | 12 |  | 1320
Proj_A | Area_9 | FL | FL-XP01-8118 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 2 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 1200
Proj_A | Area_9 | FL | FL-XP01-8118 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 20.9264 | 0 | NA | 1.1644 | 0.75 | 78 | 18.2754 |  | 1425.4849
Proj_A | Area_9 | FL | FL-XP01-8118 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_9 | FL | FL-XP01-8118 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 7 | 0 | NA | 1.04 | 0.75 | 78 | 5.46 |  | 425.88
Proj_A | Area_9 | FL | FL-XP01-8118 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 7 | 0 | NA | 1.5 | 0.75 | 78 | 7.875 |  | 614.25
Proj_A | Area_9 | FL | FL-XP01-8119 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 8 | 24 | CS | 1.3715 | 1 | 110 | 10.972 |  | 1206.92
Proj_A | Area_9 | FL | FL-XP01-8119 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 5.285 | 0 | NA | 0.17488 | 1 | 110 | 0.92423 |  | 101.6649
Proj_A | Area_9 | FL | FL-XP01-8119 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 8 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 400
Proj_A | Area_9 | FL | FL-XP01-8119 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 1 | 0 | NA | 6 | 1 | 110 | 6 |  | 660
Proj_A | Area_9 | FL | FL-XP01-8119 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 600 | 600
Proj_A | Area_9 | FL | FL-XP01-8119 | Field | 600 | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 5.8135 | 0 | NA | 1.1644 | 0.75 | 78 | 5.077 |  | 396.0097
Proj_A | Area_9 | FL | FL-XP01-8119 | Field | 600 | 150-30-F-310 | Install Blind - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_9 | FL | FL-XP01-8119 | Field | 600 | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 1 | 0 | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
Proj_A | Area_9 | FL | FL-XP01-8119 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 2.5 | 0 | NA | 1.04 | 0.75 | 78 | 1.95 |  | 152.1
Proj_A | Area_9 | FL | FL-XP01-8119 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 2 | 0 | NA | 1.5 | 0.75 | 78 | 2.25 |  | 175.5
Proj_A | Area_9 | FL | FL-XP01-8120 | Spool Fabrication | 400 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 6 | 36 | CS | 2.431 | 1 | 110 | 14.586 |  | 1604.46
Proj_A | Area_9 | FL | FL-XP01-8120 | Spool Fabrication | 400 | 150-29-S-290 | Shop handling - NB 6 SchSTD | LM | 4.953 | 0 | NA | 0.21753 | 1 | 110 | 1.0774 |  | 118.517
Proj_A | Area_9 | FL | FL-XP01-8120 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 6 | 0 | NA | 0 | 1 | 110 | 0 | 75 | 450
Proj_A | Area_9 | FL | FL-XP01-8120 | Spool Fabrication | 400 | 150-70-S-710 | Shop Hydrotest - NB 6 SchSTD | EA | 1 | 0 | NA | 8.8 | 1 | 110 | 8.8 |  | 968
Proj_A | Area_9 | FL | FL-XP01-8120 | Spool Fabrication | 400 | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 1 | 0 | CS | 0 | 1 | 110 | 0 | 900 | 900
Proj_A | Area_9 | FL | FL-XP01-8120 | Field | 600 | 150-20-F-210 | Install Spools - NB 6 SchSTD | LM | 5.4483 | 0 | NA | 1.4033 | 0.75 | 78 | 5.7341 |  | 447.2624
Proj_A | Area_9 | FL | FL-XP01-8120 | Field | 600 | 150-30-F-310 | Install valve - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_9 | FL | FL-XP01-8120 | Field | 600 | 150-30-F-310 | Install Blind - NB 6 CL150 | EA | 1 | 0 | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
Proj_A | Area_9 | FL | FL-XP01-8120 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 3 | 0 | NA | 1.95 | 0.75 | 78 | 4.3875 |  | 342.225
Proj_A | Area_9 | FL | FL-XP01-8120 | Field | 600 | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 1 | 0 | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
Proj_A | Area_9 | TR | TR-XP01-8096 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 1 | 1 | CS | 0.91 | 1 | 110 | 0.91 |  | 100.1
Proj_A | Area_9 | TR | TR-XP01-8096 | Spool Fabrication | 400 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 1 | 2 | CS | 1.17 | 1 | 110 | 1.17 |  | 128.7
Proj_A | Area_9 | TR | TR-XP01-8096 | Spool Fabrication | 400 | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 1 | 0.5 | NA | 0.26 | 1 | 110 | 0.26 |  | 28.6
Proj_A | Area_9 | TR | TR-XP01-8096 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_9 | TR | TR-XP01-8096 | Spool Fabrication | 400 | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 1 | 0 | NA | 0 | 1 | 110 | 0 | 50 | 50
Proj_A | Area_9 | TR | TR-XP01-8096 | Field | 600 | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 1 | 0 | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
Proj_A | Area_9 | TR | TR-XP01-8096 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 0.5 | 0 | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
Proj_A | Area_9 | TR | TR-XP01-8096 | Field | 600 | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 1 | 0 | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
Summary | Summary | Summary | Summary | Spool Fabrication | 400 | 150-50-S-510 | Pipe Supports Labor (shoes, lugs, guides, etc.) | of Labor hours | 0.05 | 0 |  | 0 | 0 | 0 | 963.9511 |  | 106034.6258
Summary | Summary | Summary | Summary | Module | 500 | 150-70-F-710 | Hydrotest of module assembly | of Module Labor | 0.05 | 0 |  | 0 | 0 | 0 | 230.2252 |  | 25324.7765
Summary | Summary | Summary | Summary | Module | 500 | 150-90-F-910 | Flushing & Drying Module Piping | of Module Labor | 0.03 | 0 |  | 0 | 0 | 0 | 138.1351 |  | 15194.8659
Summary | Summary | Summary | Summary | Field | 600 | 150-40-F-410 | Bolt torquing and tensioning | of bolt-up labor | 0.15 | 0 |  | 0 | 0 | 0 | 198.3296 |  | 15469.7108
Summary | Summary | Summary | Summary | Field | 600 | 150-70-F-710 | Field Hydrotest | of Field Labor | 0.05 | 0 |  | 0 | 0 | 0 | 285.076 |  | 22235.93
Summary | Summary | Summary | Summary | Field | 600 | 150-90-F-910 | Flushing & Drying on Site | of Field Labor | 0.03 | 0 |  | 0 | 0 | 0 | 171.0456 |  | 13341.558
WBS4 Summary (Summary by Line Number in the Example Project)
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## Output-Labor Detail
MTO_ID | CBS | WBS1 | WBS2 | WBS3 | WBS4 | WBS_L | Location | END | COA | Description | DIA | SCH | RATING | Units | Quantity | Dia-Inch | Material | PIPE_CLASS | STD_UNIT_HR | PF | Wage Rate | Location Hours | S/C Rate_$ | Total Cost
1500001 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500002 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500003 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500003 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500004 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.352 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.066061 |  | 7.2667
1500004 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3872 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.34682 |  | 27.052
1500005 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500005 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500006 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500007 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500007 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500007 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500008 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500008 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500009 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1500009 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500010 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500011 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500011 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500011 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500012 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500012 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500013 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.152 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.028526 |  | 3.1379
1500013 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1672 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.14976 |  | 11.6815
1500014 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1500014 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500015 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500015 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500016 | 600 | Proj_A | Area_1 | TR | TR-YP01-8087 | ISO4009 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL300 | 8 | NA | CL300 | EA | 1 | 0 | NA | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57
1500016 | 600 | Proj_A | Area_1 | TR | TR-YP01-8087 | ISO4009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL300 | 8 | NA | CL300 | EA | 1 | 0 | NA | NA | 3.12 | 0.75 | 78 | 2.34 |  | 182.52
1500017 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1500018 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500018 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500019 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500019 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500020 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500020 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500021 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500021 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500022 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500022 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500023 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500023 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500024 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500024 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500025 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1500026 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500026 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500027 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500027 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500028 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500028 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500029 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500029 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500030 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500031 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500032 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.041066 |  | 4.5173
1500032 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.21262 |  | 16.5847
1500033 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500033 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500034 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500034 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500035 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.585 | 1 | 110 | 0.585 |  | 64.35
1500035 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500036 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500036 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500037 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500037 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500038 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-30-F-310 | Install Blind - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
1500039 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.249 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.043544 |  | 4.7899
1500039 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.2739 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.2392 |  | 18.6578
1500040 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500040 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500041 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | NA | 150-30-F-310 | Install Blind - NB 3 CL300 | 3 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500042 | 600 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1500043 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500044 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500045 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1500046 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1500047 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500047 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500048 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500048 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500049 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500049 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500050 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500050 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500051 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500051 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500052 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500053 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500054 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500055 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500056 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500057 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500058 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500059 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500060 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500060 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500061 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500061 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500062 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500062 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500063 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500063 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500064 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500065 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500066 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500067 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500068 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500069 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500070 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500071 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500072 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500073 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 8.635 | 0 | NA | NA | 0.24739 | 1 | 110 | 2.1362 |  | 234.9809
1500073 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 9.4985 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 11.0603 |  | 862.7041
1500074 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.289 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.086287 |  | 9.4916
1500074 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3179 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.4556 |  | 35.5364
1500075 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500075 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500076 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1500077 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500078 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500079 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500080 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500081 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500082 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500083 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500084 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500085 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500086 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500087 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500088 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500089 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500090 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500091 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500092 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500093 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500094 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500095 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500096 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500097 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500098 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500099 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500100 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500101 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500102 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500103 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500104 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500105 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500106 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500107 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500107 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500108 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.406 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.072732 |  | 8.0005
1500108 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.4263 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.3723 |  | 29.0391
1500109 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.192 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.036033 |  | 3.9637
1500109 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2112 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.18917 |  | 14.7556
1500110 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.399 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.071478 |  | 7.8626
1500110 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.41895 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.36588 |  | 28.5384
1500111 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500111 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500112 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500112 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500113 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500113 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500114 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.079 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.2025 |  | 22.2749
1500114 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.1869 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.0631 |  | 82.9235
1500115 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500115 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500116 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500116 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500117 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500118 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500118 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500119 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.564 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.13953 |  | 15.3479
1500119 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.6204 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.72241 |  | 56.348
1500120 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500120 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500121 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500121 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500122 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | NA | 150-30-F-310 | Install Blind - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500123 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.664 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.16427 |  | 18.0692
1500123 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.7304 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.8505 |  | 66.3388
1500124 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500124 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500125 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500125 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500126 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | NA | 150-30-F-310 | Install Blind - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500127 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500127 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500128 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-30-F-310 | Install valve - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
1500128 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.16 | 0.75 | 78 | 3.12 |  | 243.36
1500129 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500130 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500131 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500131 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500132 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500132 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500133 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500133 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500134 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500134 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500135 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500135 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500136 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.21 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.051951 |  | 5.7146
1500136 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.231 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.26898 |  | 20.9806
1500137 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500137 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500138 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.21 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.051951 |  | 5.7146
1500138 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.231 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.26898 |  | 20.9806
1500139 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500139 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500140 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500140 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500141 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.015 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.2511 |  | 27.6208
1500141 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 1.1165 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 1.3001 |  | 101.4064
1500142 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.265 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.31295 |  | 34.424
1500142 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 1.3915 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 1.6203 |  | 126.3834
1500143 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500143 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500144 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500144 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500145 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.266 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.065805 |  | 7.2386
1500145 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.2926 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.34071 |  | 26.5755
1500146 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.266 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.065805 |  | 7.2386
1500146 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.2926 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.34071 |  | 26.5755
1500147 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500147 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500148 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500148 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500149 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500149 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500150 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | 4 | SchXST | NA | LM | 15.3076 | 0 | NA | NA | 1.3222 | 0.75 | 78 | 15.1803 |  | 1184.0615
1500150 | 300 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-80-F-810 | Field Coating - NB 4 | 4 | NA | NA | LM | 15.3076 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 80 | 1224.608
1500151 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500151 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500152 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500152 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500153 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500153 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500154 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.983 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.49057 |  | 53.9626
1500154 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 2.1813 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 2.54 |  | 198.1172
1500155 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500155 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500156 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500156 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500157 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500157 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500158 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500158 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500159 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500159 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500160 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500160 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500161 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500161 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500162 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500162 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500163 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.41 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.10143 |  | 11.1572
1500163 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.451 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.52516 |  | 40.9622
1500164 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500164 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500165 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.415 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.10267 |  | 11.2932
1500165 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.4565 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.53156 |  | 41.4617
1500166 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500166 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500167 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500167 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500168 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-30-F-310 | Install valve - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
1500168 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.16 | 0.75 | 78 | 3.12 |  | 243.36
1500169 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.041066 |  | 4.5173
1500169 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.21262 |  | 16.5847
1500170 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500170 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500171 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500171 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500172 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500172 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500173 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500173 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500174 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500174 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500175 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.41 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.10143 |  | 11.1572
1500175 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.451 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.52516 |  | 40.9622
1500176 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500176 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500177 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.165 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.28821 |  | 31.7027
1500177 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 1.2815 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 1.4922 |  | 116.3926
1500178 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500178 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500179 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500179 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500180 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500180 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500181 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1500182 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.306 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.054818 |  | 6.0299
1500182 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.3213 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.2806 |  | 21.8866
1500183 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500183 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500183 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500184 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500184 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500185 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.299 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.053564 |  | 5.892
1500185 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.31395 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.27418 |  | 21.386
1500186 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500186 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500186 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500187 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500187 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500188 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 8.48 | 0 | NA | NA | 0.17488 | 1 | 110 | 1.483 |  | 163.1255
1500188 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 9.328 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 8.1463 |  | 635.4138
1500189 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.276 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.051798 |  | 5.6978
1500189 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3036 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.27194 |  | 21.2112
1500190 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500190 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500191 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500191 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500192 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500192 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500193 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | NA | 150-30-F-310 | Install Blind - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500194 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | NA | 150-30-F-310 | Install valve - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500194 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500195 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500195 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500196 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 4.197 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.2531 |  | 137.8413
1500196 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 4.6167 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 6.6164 |  | 516.0777
1500197 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500197 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500198 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500198 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500199 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 4.109 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.2268 |  | 134.9511
1500199 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 4.5199 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 6.4777 |  | 505.2569
1500200 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500200 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500201 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500201 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500202 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.353 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.40397 |  | 44.4363
1500202 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.4883 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.1329 |  | 166.3696
1500203 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500203 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500204 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.175 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.05225 |  | 5.7475
1500204 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.1925 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.27588 |  | 21.5186
1500205 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500206 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500206 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500207 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500208 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.7 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.209 |  | 22.99
1500208 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.77 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.1035 |  | 86.0744
1500209 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500209 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500210 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.1 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.32843 |  | 36.1271
1500210 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.21 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.7341 |  | 135.2598
1500211 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500211 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500212 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500212 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500213 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 6.266 | 0 | NA | NA | 0.24739 | 1 | 110 | 1.5501 |  | 170.5142
1500213 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 6.8926 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 8.0259 |  | 626.0225
1500214 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500214 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500215 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500215 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500216 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.99 | 0.75 | 78 | 2.2425 |  | 174.915
1500216 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | 4 | SchXST | NA | LM | 16.8509 | 0 | NA | NA | 1.3222 | 0.75 | 78 | 16.7107 |  | 1303.4376
1500216 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Field | NA | 150-80-F-810 | Field Coating - NB 4 | 4 | NA | NA | LM | 16.8509 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 80 | 1348.072
1500217 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500217 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500218 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500218 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500219 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500219 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500220 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 4.18 | 0 | NA | NA | 0.24739 | 1 | 110 | 1.0341 |  | 113.7487
1500220 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 4.598 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 5.354 |  | 417.6147
1500221 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500221 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500222 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500222 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500223 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500223 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500224 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.079 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.2025 |  | 22.2749
1500224 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.1869 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.0631 |  | 82.9235
1500225 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500225 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500226 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500226 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500227 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500227 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500228 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500228 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500229 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.863 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.16196 |  | 17.8158
1500229 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9493 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.8503 |  | 66.3234
1500230 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.429 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.080512 |  | 8.8563
1500230 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4719 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.42269 |  | 32.9696
1500231 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500231 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500232 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500232 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500232 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500233 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500233 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500234 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1500234 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1500235 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500235 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500236 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500236 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500237 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500237 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500238 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500238 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500239 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500240 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500240 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500240 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500241 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500241 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500242 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500242 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500243 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500243 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500243 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1500244 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500244 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500245 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500245 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500246 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500246 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500247 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500247 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500248 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500249 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500249 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500249 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500250 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500250 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500251 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500251 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500252 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500252 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500253 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500253 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500254 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500254 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500255 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500255 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500255 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500256 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500256 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500257 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1500257 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1500258 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500258 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500259 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500259 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500260 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500260 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500260 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500261 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500261 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500262 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500262 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500263 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500263 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500264 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500265 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500265 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500265 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500266 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500266 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500267 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500267 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500268 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500268 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500269 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500269 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500269 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500270 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500270 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500270 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1500271 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500271 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500272 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500272 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500273 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500273 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500274 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500274 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500275 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500276 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500276 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500276 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500277 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500277 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500278 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500278 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500279 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500279 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500280 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500280 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500281 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500281 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500282 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500282 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500283 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500283 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500284 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | XP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500284 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500285 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500286 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.404 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.07065 |  | 7.7715
1500286 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.4444 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.3881 |  | 30.2721
1500287 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500287 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | XP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500288 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.408 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.24623 |  | 27.085
1500288 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.5488 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.3526 |  | 105.5027
1500289 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500290 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500291 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500291 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500292 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500292 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500293 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500293 | 600 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500294 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500294 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | XP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500295 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500295 | 600 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500296 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500296 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500297 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500297 | 600 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500298 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500298 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500299 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500299 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500300 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500301 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500301 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500302 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500302 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500303 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500303 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500304 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500304 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500305 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1500306 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.711 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13344 |  | 14.6779
1500306 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7821 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.70054 |  | 54.6419
1500307 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.142 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.58967 |  | 64.8636
1500307 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.4562 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 3.0958 |  | 241.4695
1500308 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500309 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500309 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500309 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500310 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500310 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500311 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500311 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1500312 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500312 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500313 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500313 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500314 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500314 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1500315 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500315 | 600 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500316 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500317 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500317 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500317 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500318 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500318 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500319 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.142 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.58967 |  | 64.8636
1500319 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.4562 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 3.0958 |  | 241.4695
1500320 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1500320 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500321 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.507 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.09515 |  | 10.4665
1500321 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5577 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.49954 |  | 38.9641
1500322 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500322 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500323 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500323 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500324 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500324 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1500325 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1500326 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.711 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13344 |  | 14.6779
1500326 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7821 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.70054 |  | 54.6419
1500327 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500327 | 600 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500328 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500328 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500329 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500329 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500330 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500330 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500331 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500331 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500332 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500333 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500333 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500334 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500334 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500335 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500335 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500336 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500336 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500337 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500338 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500338 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500339 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500339 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500340 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500340 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500341 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500341 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500342 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500343 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500343 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500344 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500344 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500345 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500345 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500346 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500346 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500347 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1500348 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.4 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.18767 |  | 20.6441
1500348 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.46 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 1.0301 |  | 80.3455
1500349 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 4.117 | 0 | NA | NA | 0.46918 | 1 | 110 | 1.9316 |  | 212.4789
1500349 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 4.7345 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 10.602 |  | 826.9556
1500350 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500350 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500351 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 2.03 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.95244 |  | 104.7686
1500351 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 2.3345 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 5.2276 |  | 407.7532
1500352 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500352 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500353 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500353 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500354 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500354 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500355 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 10.457 | 0 | NA | NA | 0.46918 | 1 | 110 | 4.9062 |  | 539.6871
1500355 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 12.0255 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 26.9286 |  | 2100.4311
1500356 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500356 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500357 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500357 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500358 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 2.367 | 0 | NA | NA | 0.46918 | 1 | 110 | 1.1106 |  | 122.1612
1500358 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 2.722 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 6.0954 |  | 475.4442
1500359 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500359 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500360 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 3.367 | 0 | NA | NA | 0.46918 | 1 | 110 | 1.5797 |  | 173.7713
1500360 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 3.872 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 8.6706 |  | 676.3079
1500361 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500361 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500362 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500362 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500363 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500363 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500364 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500364 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500365 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500365 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500366 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.324 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.15202 |  | 16.7217
1500366 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.3726 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 0.83436 |  | 65.0798
1500367 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500367 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500368 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 4.102 | 0 | NA | NA | 0.46918 | 1 | 110 | 1.9246 |  | 211.7048
1500368 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 4.7173 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 10.5634 |  | 823.9427
1500369 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500369 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500370 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.814 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.8511 |  | 93.6208
1500370 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 2.0861 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 4.6714 |  | 364.3666
1500371 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500371 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500372 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500372 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500373 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500373 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500374 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500374 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500375 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500376 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1500376 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500377 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500377 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500378 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500378 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500379 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500379 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500380 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.46918 |  | 51.6101
1500380 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.15 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 2.5752 |  | 200.8636
1500381 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.14075 |  | 15.483
1500381 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 0.77255 |  | 60.2591
1500382 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-30-F-310 | Install valve - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
1500382 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.16 | 0.75 | 78 | 3.12 |  | 243.36
1500383 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | NA | 150-30-F-310 | Install Blind - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
1500384 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500384 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500385 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.713 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.80371 |  | 88.4082
1500385 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.9699 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 4.4113 |  | 344.0794
1500386 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500386 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500387 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500387 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500388 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.14075 |  | 15.483
1500388 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 0.77255 |  | 60.2591
1500389 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.701 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.3289 |  | 36.1787
1500389 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.80615 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 1.8052 |  | 140.8054
1500390 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500390 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500391 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500391 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1500392 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.353 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.6348 |  | 69.8285
1500392 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.5559 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 3.4842 |  | 271.7685
1500393 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500393 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500394 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500394 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500395 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | NA | 150-30-F-310 | Install Blind - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500396 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500396 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500397 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.8 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.4453 |  | 48.9827
1500397 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 1.98 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 2.3056 |  | 179.8341
1500398 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.3 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.3216 |  | 35.3764
1500398 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 1.43 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 1.6651 |  | 129.8802
1500399 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500400 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL300 | 1 | NA | CL300 | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500400 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500401 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500401 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500402 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500402 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500403 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500403 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | YP01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500404 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500404 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500405 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.608 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.63096 |  | 69.4053
1500405 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.9688 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 3.466 |  | 270.3506
1500406 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500406 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500407 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | NA | 150-30-F-310 | Install valve - NB 3 CL300 | 3 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500407 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500408 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500408 | 600 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500409 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500409 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500410 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500410 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500411 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500411 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500412 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500412 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500413 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500413 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500414 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-30-F-310 | Install Blind - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500415 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-30-F-310 | Install valve - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500415 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500416 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500416 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500417 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.354 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.33496 |  | 36.8459
1500417 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 1.4894 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 1.7343 |  | 135.2752
1500418 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 11.499 | 0 | NA | NA | 0.24739 | 1 | 110 | 2.8447 |  | 312.9178
1500418 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 12.6489 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 14.7287 |  | 1148.8401
1500419 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500419 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500420 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500420 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500421 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500421 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500422 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500422 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500423 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500423 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500424 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-30-F-310 | Install Blind - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500425 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-30-F-310 | Install valve - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500425 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500426 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500426 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500427 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500428 | 400 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.462 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.64972 |  | 71.4697
1500428 | 600 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.8082 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 3.4111 |  | 266.0622
1500429 | 400 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500429 | 400 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500430 | 400 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.505 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.094775 |  | 10.4252
1500430 | 600 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5555 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.49757 |  | 38.8103
1500431 | 400 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500431 | 600 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1500432 | 600 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500432 | 600 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1500433 | 400 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500433 | 600 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1500434 | 400 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500434 | 600 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1500435 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500436 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500436 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500437 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500437 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500438 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500438 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500439 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500439 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500440 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500441 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1500441 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500442 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500442 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500443 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500443 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500444 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500444 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500445 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500446 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1500446 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 16.8883 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 20.5296 |  | 1601.3084
1500446 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 16.8883 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1688.83
1500447 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500447 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500448 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500448 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500449 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1500449 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 17.5483 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 21.3319 |  | 1663.888
1500449 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 17.5483 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1754.83
1500450 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500450 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500451 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500451 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500452 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1500452 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 18.4162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 22.3869 |  | 1746.1802
1500452 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 18.4162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1841.62
1500453 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500453 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500454 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500454 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500455 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1500455 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 18.4162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 22.3869 |  | 1746.1802
1500455 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 18.4162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1841.62
1500456 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500456 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500457 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500457 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500458 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1500458 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 18.4162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 22.3869 |  | 1746.1802
1500458 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 18.4162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1841.62
1500459 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500459 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500460 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1500460 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 18.4162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 22.3869 |  | 1746.1802
1500460 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 18.4162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1841.62
1500461 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500461 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500462 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500462 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500463 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500463 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500464 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500464 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500465 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500465 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500466 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500466 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500467 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500468 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500469 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500470 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500471 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500472 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500473 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500474 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500475 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500476 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500476 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500477 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500477 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500478 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500478 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500479 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500479 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500480 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 4.441 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.326 |  | 145.8549
1500480 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 4.8851 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 7.001 |  | 546.0808
1500481 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 3.841 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.1468 |  | 126.1492
1500481 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 4.2251 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 6.0552 |  | 472.3027
1500482 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500483 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500484 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 16.0413 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 19.5 |  | 1520.9979
1500484 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 16.0413 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1604.13
1500485 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500485 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500486 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500486 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500487 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500488 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500489 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500490 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1500490 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 16.7013 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 20.3023 |  | 1583.5775
1500490 | 300 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 16.7013 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1670.13
1500491 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500491 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500492 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500492 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500493 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.036 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.30932 |  | 34.0252
1500493 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.1396 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.6332 |  | 127.3902
1500494 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500494 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500495 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500496 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500497 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500498 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1500499 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500499 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500500 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500500 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500501 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500501 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500502 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500502 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500503 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500503 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500504 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500504 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500505 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500505 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500506 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500506 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500507 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.274 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.081808 |  | 8.9989
1500507 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3014 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.43195 |  | 33.692
1500508 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500508 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500509 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.318 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.094946 |  | 10.444
1500509 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3498 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.50131 |  | 39.1024
1500510 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.274 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.081808 |  | 8.9989
1500510 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3014 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.43195 |  | 33.692
1500511 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500511 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500512 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.318 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.094946 |  | 10.444
1500512 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3498 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.50131 |  | 39.1024
1500513 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500513 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500514 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500514 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500515 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500515 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500516 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 7.586 | 0 | NA | NA | 0.29857 | 1 | 110 | 2.265 |  | 249.1456
1500516 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 8.3446 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 11.959 |  | 932.801
1500517 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500517 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500518 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.436 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.13018 |  | 14.3195
1500518 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.4796 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.68733 |  | 53.6121
1500519 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.436 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.13018 |  | 14.3195
1500519 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.4796 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.68733 |  | 53.6121
1500520 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500520 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500521 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500521 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500522 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500522 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500523 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500523 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500524 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 3.444 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.0283 |  | 113.1106
1500524 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 3.7884 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 5.4293 |  | 423.4862
1500525 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500525 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500526 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.761 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.22721 |  | 24.9934
1500526 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.8371 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.1997 |  | 93.5752
1500527 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 3.444 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.0283 |  | 113.1106
1500527 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 3.7884 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 5.4293 |  | 423.4862
1500528 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500528 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500529 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.761 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.22721 |  | 24.9934
1500529 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.8371 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.1997 |  | 93.5752
1500530 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500530 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500531 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500531 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500532 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500532 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500533 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500533 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500534 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.036 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.30932 |  | 34.0252
1500534 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.1396 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.6332 |  | 127.3902
1500535 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500535 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500536 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500536 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500537 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 7.786 | 0 | NA | NA | 0.29857 | 1 | 110 | 2.3247 |  | 255.7141
1500537 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 8.5646 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 12.2743 |  | 957.3937
1500538 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500538 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500539 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500539 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500540 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.836 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.24961 |  | 27.4566
1500540 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.9196 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.3179 |  | 102.7975
1500541 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 9.136 | 0 | NA | NA | 0.29857 | 1 | 110 | 2.7277 |  | 300.0519
1500541 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 10.0496 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 14.4025 |  | 1123.3944
1500542 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 9.936 | 0 | NA | NA | 0.29857 | 1 | 110 | 2.9666 |  | 326.3262
1500542 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 10.9296 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 15.6637 |  | 1221.7651
1500543 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 4.004 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.1955 |  | 131.5026
1500543 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 4.4044 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 6.3121 |  | 492.3458
1500544 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 3.104 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.92676 |  | 101.9441
1500544 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 3.4144 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 4.8933 |  | 381.6786
1500545 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500545 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500546 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.836 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.24961 |  | 27.4566
1500546 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.9196 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.3179 |  | 102.7975
1500547 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500547 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500548 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500548 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500549 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500549 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500550 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.709 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.51026 |  | 56.1284
1500550 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.8799 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.6942 |  | 210.1446
1500551 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500551 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500552 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500552 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500553 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500554 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500554 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500555 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500555 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500556 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | NA | 150-30-F-310 | Install valve - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500556 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500557 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500557 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500558 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500559 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500559 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500560 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500560 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500561 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.289 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.086287 |  | 9.4916
1500561 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3179 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.4556 |  | 35.5364
1500562 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500562 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500563 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.21 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.36127 |  | 39.7398
1500563 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.331 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.9075 |  | 148.7858
1500564 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500564 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500565 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500565 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500566 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500566 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500567 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500567 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500568 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500568 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500569 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500569 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500570 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 11.499 | 0 | NA | NA | 0.24739 | 1 | 110 | 2.8447 |  | 312.9178
1500570 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 12.6489 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 14.7287 |  | 1148.8401
1500571 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500571 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500572 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 10.093 | 0 | NA | NA | 0.24739 | 1 | 110 | 2.4969 |  | 274.6569
1500572 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 11.1023 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 12.9278 |  | 1008.3697
1500573 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.425 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.35253 |  | 38.778
1500573 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 1.5675 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 1.8252 |  | 142.3687
1500574 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500574 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500575 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.158 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.039087 |  | 4.2996
1500575 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.1738 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.20238 |  | 15.7854
1500576 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500576 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500577 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | NA | 150-30-F-310 | Install valve - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500577 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500578 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500578 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500579 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 8.755 | 0 | NA | NA | 0.24739 | 1 | 110 | 2.1659 |  | 238.2464
1500579 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 9.6305 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 11.214 |  | 874.693
1500580 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500581 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500582 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500583 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500584 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500585 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500586 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.361 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.40636 |  | 44.6991
1500586 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.4971 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.1456 |  | 167.3533
1500587 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500587 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500588 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500588 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500589 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500589 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500590 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500590 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500591 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500591 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500592 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500592 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500593 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 1.175 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.29068 |  | 31.9748
1500593 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 1.2925 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 1.505 |  | 117.3917
1500594 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500594 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500595 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 0.158 | 0 | NA | NA | 0.24739 | 1 | 110 | 0.039087 |  | 4.2996
1500595 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 0.1738 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 0.20238 |  | 15.7854
1500596 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500596 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 2 | 8 | CS | ZL01 | 2.119 | 1 | 110 | 4.238 |  | 466.18
1500597 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchXST | 4 | SchXST | NA | LM | 7.955 | 0 | NA | NA | 0.24739 | 1 | 110 | 1.968 |  | 216.4763
1500597 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchXST | 4 | SchXST | NA | LM | 8.7505 | 0 | NA | NA | 1.5526 | 0.75 | 78 | 10.1893 |  | 794.7668
1500598 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500598 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500599 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | NA | 150-30-F-310 | Install valve - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1500599 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500600 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500600 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500601 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500601 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500602 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500602 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500603 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1500603 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1500604 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 4 | CS | ZL01 | 2.119 | 1 | 110 | 2.119 |  | 233.09
1500604 | 600 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | 4 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1500605 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500606 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500607 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500607 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500607 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500608 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500608 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500608 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500609 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500609 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500610 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500610 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500611 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500611 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | YP01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500612 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500612 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | YP01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500613 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500613 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500613 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500614 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500614 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500615 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500615 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500615 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500616 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500616 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500617 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500617 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | YP01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500618 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500618 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | YP01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500619 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1500620 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500620 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500620 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500621 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500621 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500622 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500622 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500623 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500623 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500623 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500624 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500624 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500625 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500625 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500626 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500627 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500628 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500628 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500629 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500629 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1500630 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500630 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | YP01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500631 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500631 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | YP01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500632 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500632 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | YP01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500633 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500633 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | YP01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500634 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500634 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500635 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | YP01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500635 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL300 | 0.75 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500636 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500636 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500637 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | YP01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500637 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL300 | 0.75 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500638 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500638 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500639 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-30-F-310 | Install Inlines - NB 3 CL300 | 3 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500640 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500640 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500641 | 400 | Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500641 | 400 | Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500641 | 600 | Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500642 | 400 | Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500642 | 400 | Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500643 | 400 | Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500643 | 600 | Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500644 | 400 | Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500644 | 400 | Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500644 | 600 | Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500645 | 400 | Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500645 | 400 | Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500646 | 400 | Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500646 | 600 | Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500647 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.112 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.021019 |  | 2.3121
1500647 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1232 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.11035 |  | 8.6074
1500648 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | YP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1500648 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500649 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | YP01 | 1.56 | 1 | 110 | 1.56 |  | 171.6
1500649 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500650 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | YP01 | 1.56 | 1 | 110 | 1.56 |  | 171.6
1500650 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500651 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.083 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.015577 |  | 1.7135
1500651 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.0913 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.081779 |  | 6.3787
1500652 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.083 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.015577 |  | 1.7135
1500652 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.0913 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.081779 |  | 6.3787
1500653 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1500654 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1500655 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500656 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500656 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500656 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-30-M-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500657 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500657 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500658 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1500658 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500659 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500660 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500660 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500660 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-30-M-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500661 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500661 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500662 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1500662 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500663 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500663 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1500664 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500664 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1500665 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.625 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.1173 |  | 12.9025
1500665 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6875 | 0 | NA | NA | 1.1943 | 1 | 110 | 0.82107 |  | 90.3177
1500666 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500666 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1500667 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500667 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500668 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-30-M-310 | Install Blind - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500669 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500669 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1500670 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500670 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1500671 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1500672 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 1 | 110 | 0.4 |  | 44
1500673 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.205 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.031478 |  | 3.4626
1500673 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Module | NA | 150-20-M-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.21525 | 0 | NA | NA | 1.0151 | 1 | 110 | 0.21851 |  | 24.036
1500674 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500674 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500675 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500675 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500675 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500676 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500676 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500677 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500677 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500678 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.198 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.030403 |  | 3.3443
1500678 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.2079 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.15829 |  | 12.3463
1500679 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500679 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500680 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500680 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500680 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500681 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500681 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500682 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500682 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500683 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1500684 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 1 | 110 | 0.4 |  | 44
1500685 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.205 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.031478 |  | 3.4626
1500685 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Module | NA | 150-20-M-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.21525 | 0 | NA | NA | 1.0151 | 1 | 110 | 0.21851 |  | 24.036
1500686 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.198 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.030403 |  | 3.3443
1500686 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.2079 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.15829 |  | 12.3463
1500687 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500687 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500687 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500688 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500688 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500688 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500689 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500689 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500690 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500690 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500691 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500691 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500692 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500692 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500693 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.441 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.067716 |  | 7.4487
1500693 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.46305 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.35255 |  | 27.4986
1500694 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.441 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.067716 |  | 7.4487
1500694 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.46305 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.35255 |  | 27.4986
1500695 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.88 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.13512 |  | 14.8637
1500695 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.924 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.70349 |  | 54.8725
1500696 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.88 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.13512 |  | 14.8637
1500696 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.924 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.70349 |  | 54.8725
1500697 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500697 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500698 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.88 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.13512 |  | 14.8637
1500698 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.924 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.70349 |  | 54.8725
1500699 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.88 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.13512 |  | 14.8637
1500699 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.924 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.70349 |  | 54.8725
1500700 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.634 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11898 |  | 13.0883
1500700 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6974 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.62467 |  | 48.7243
1500701 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.634 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11898 |  | 13.0883
1500701 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6974 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.62467 |  | 48.7243
1500702 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500702 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500703 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500704 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500705 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500706 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500707 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500708 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500709 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500709 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500709 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500710 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500710 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500711 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500711 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | YP01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500712 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500713 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500713 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500713 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500714 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500714 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500715 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500715 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | YP01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1500716 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500717 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500717 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1500718 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500718 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500719 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500719 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500720 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500721 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500721 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500721 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | NA | 150-30-M-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500722 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500722 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500723 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | 3 | Sch160 | NA | EA | 1 | 3 | CS | YP01 | 2.21 | 1 | 110 | 2.21 |  | 243.1
1500723 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL300 | 0.75 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500724 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500724 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500725 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500726 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500726 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500726 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | NA | 150-30-M-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1500727 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500727 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500728 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | 3 | Sch160 | NA | EA | 1 | 3 | CS | YP01 | 2.21 | 1 | 110 | 2.21 |  | 243.1
1500728 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL300 | 0.75 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500729 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500729 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500730 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500730 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500731 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500731 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500732 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500732 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500733 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500734 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500734 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500735 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500735 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500736 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.279 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.046411 |  | 5.1052
1500736 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.29295 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.2296 |  | 17.9087
1500737 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500737 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500738 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500738 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500739 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500739 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500740 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500740 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500741 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.844 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.1404 |  | 15.4436
1500741 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.8862 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.69456 |  | 54.1755
1500742 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500742 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500743 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.2 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.033269 |  | 3.6596
1500743 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.21 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.16459 |  | 12.8378
1500744 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1500745 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.897 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.16834 |  | 18.5177
1500745 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9867 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.8838 |  | 68.9364
1500746 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500746 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500747 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.279 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.046411 |  | 5.1052
1500747 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.29295 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.2296 |  | 17.9087
1500748 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500748 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500749 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 2 | 1.5 | CS | YP01 | 0.65 | 1 | 110 | 1.3 |  | 143
1500749 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500750 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 0.75 | 0.75 | NA | NA | EA | 1 | 0 | NA | NA | 0.3 | 0.75 | 78 | 0.225 |  | 17.55
1500751 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | 0.75 | CL800 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500751 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | 0.75 | CL800 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500751 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 CL800 | 0.75 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500752 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500752 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500753 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | 0.75 | CL800 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500753 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | 0.75 | CL800 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500753 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 CL800 | 0.75 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500754 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500754 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500754 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500755 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.964 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.16036 |  | 17.6394
1500755 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 1.0122 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.79331 |  | 61.8782
1500756 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500756 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500757 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500757 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500758 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500758 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500759 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500759 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500760 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500761 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500761 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500762 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500762 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500763 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.279 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.046411 |  | 5.1052
1500763 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.29295 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.2296 |  | 17.9087
1500764 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500764 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500765 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500765 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500766 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500766 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500767 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500767 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500768 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.844 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.1404 |  | 15.4436
1500768 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.8862 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.69456 |  | 54.1755
1500769 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.15 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.028151 |  | 3.0966
1500769 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.165 | 0 | NA | NA | 1.1943 | 1 | 110 | 0.19706 |  | 21.6763
1500770 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500770 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500771 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500771 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1500772 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-30-M-310 | Install valve - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 1 | 110 | 6.63 |  | 729.3
1500772 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.16 | 1 | 110 | 4.16 |  | 457.6
1500773 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-30-M-310 | Install Blind - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 1 | 110 | 6.63 |  | 729.3
1500774 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.15 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.028151 |  | 3.0966
1500774 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.165 | 0 | NA | NA | 1.1943 | 1 | 110 | 0.19706 |  | 21.6763
1500775 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500775 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500776 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1500776 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1500777 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-30-M-310 | Install valve - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 1 | 110 | 6.63 |  | 729.3
1500777 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.16 | 1 | 110 | 4.16 |  | 457.6
1500778 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-30-M-310 | Install Blind - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 1 | 110 | 6.63 |  | 729.3
1500779 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500779 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500780 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-30-M-310 | Install Blind - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1500781 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500781 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500782 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.2 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.033269 |  | 3.6596
1500782 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.21 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.16459 |  | 12.8378
1500783 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.058 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.18502 |  | 20.3522
1500783 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.1638 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.0164 |  | 79.2769
1500784 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1500785 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.897 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.16834 |  | 18.5177
1500785 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9867 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.8838 |  | 68.9364
1500786 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500786 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500787 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1500788 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1500789 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1500790 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1500791 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1500792 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1500793 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1500794 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1500795 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1.5 | 1.5 | NA | NA | EA | 1 | 0 | NA | NA | 0.5 | 0.75 | 78 | 0.375 |  | 29.25
1500796 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.423 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.073973 |  | 8.137
1500796 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-20-F-210 | Install Spools - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.44415 | 0 | NA | NA | 1.1047 | 0.75 | 78 | 0.36799 |  | 28.7035
1500797 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500797 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500798 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.236 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.041271 |  | 4.5398
1500798 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-20-F-210 | Install Spools - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.2478 | 0 | NA | NA | 1.1047 | 0.75 | 78 | 0.20531 |  | 16.0142
1500799 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.452 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.079045 |  | 8.6949
1500799 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-20-F-210 | Install Spools - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.4746 | 0 | NA | NA | 1.1047 | 0.75 | 78 | 0.39322 |  | 30.6714
1500800 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.369 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.06453 |  | 7.0983
1500800 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.4059 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.35448 |  | 27.6495
1500801 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500801 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500802 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1.5 | 1.5 | NA | NA | EA | 1 | 0 | NA | NA | 0.5 | 0.75 | 78 | 0.375 |  | 29.25
1500803 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.423 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.073973 |  | 8.137
1500803 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-20-F-210 | Install Spools - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.44415 | 0 | NA | NA | 1.1047 | 0.75 | 78 | 0.36799 |  | 28.7035
1500804 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.452 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.079045 |  | 8.6949
1500804 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-20-F-210 | Install Spools - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.4746 | 0 | NA | NA | 1.1047 | 0.75 | 78 | 0.39322 |  | 30.6714
1500805 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.058 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.18502 |  | 20.3522
1500805 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.1638 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.0164 |  | 79.2769
1500806 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500806 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500807 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.236 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.041271 |  | 4.5398
1500807 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-20-F-210 | Install Spools - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.2478 | 0 | NA | NA | 1.1047 | 0.75 | 78 | 0.20531 |  | 16.0142
1500808 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500808 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500809 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500809 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500810 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500810 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500811 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500811 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500812 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500812 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500813 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500814 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.112 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.021019 |  | 2.3121
1500814 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1232 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.11035 |  | 8.6074
1500815 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500815 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | YP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1500816 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.097 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.018204 |  | 2.0025
1500816 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1067 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.095573 |  | 7.4547
1500817 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.33 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.061932 |  | 6.8125
1500817 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.363 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.32514 |  | 25.3612
1500818 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500818 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500819 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500819 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1500820 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.116 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.02177 |  | 2.3947
1500820 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1276 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.11429 |  | 8.9149
1500821 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500821 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500822 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500822 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500823 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500823 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500824 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500824 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500825 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500825 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500826 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500826 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500827 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500827 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500828 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.097 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.018204 |  | 2.0025
1500828 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1067 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.095573 |  | 7.4547
1500829 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.33 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.061932 |  | 6.8125
1500829 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.363 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.32514 |  | 25.3612
1500830 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500830 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1500831 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500831 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500832 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.116 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.02177 |  | 2.3947
1500832 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1276 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.11429 |  | 8.9149
1500833 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500833 | 600 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500834 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500834 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500835 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500835 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500836 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500836 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500837 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500837 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500838 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500838 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500839 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500839 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500840 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500840 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500841 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500841 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500842 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500842 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500843 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500843 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1500844 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500844 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1500845 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500845 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | 3 | NA | CL3000 | EA | 1 | 3 | CS | YP01 | 7.67 | 1 | 110 | 7.67 |  | 843.7
1500846 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500846 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1500847 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500847 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | 3 | NA | CL3000 | EA | 1 | 3 | CS | YP01 | 7.67 | 1 | 110 | 7.67 |  | 843.7
1500848 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500849 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500849 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500850 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500850 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500851 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500851 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | YP01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500852 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchXST | 16 | SchXST | NA | LM | 0.4 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.31734 |  | 34.9072
1500852 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchXST | 16 | SchXST | NA | LM | 0.46 | 0 | NA | NA | 5.1056 | 1 | 110 | 2.3486 |  | 258.3415
1500853 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500853 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | YP01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1500854 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500854 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500855 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500855 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500856 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500856 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500857 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500857 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500858 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500858 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500859 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500859 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500860 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500860 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500861 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500861 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500862 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500862 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1500863 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500863 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500864 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500864 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500865 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500865 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500866 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500866 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500867 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1500867 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500868 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500868 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500869 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500869 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500870 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500870 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500871 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500871 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1500872 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500873 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500874 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500875 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500876 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500877 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500878 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500879 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500880 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500881 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500882 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500883 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500884 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 1 | 110 | 1.9144 |  | 210.5865
1500885 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
1500886 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
1500887 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
1500888 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
1500889 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1500890 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1500891 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
1500892 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 1 | 110 | 1.8233 |  | 200.5585
1500893 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500893 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500894 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500894 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500895 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500895 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500896 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500896 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500897 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | NA | 150-30-M-310 | Install Inlines - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1500897 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 6.37 | 1 | 110 | 6.37 |  | 700.7
1500898 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | NA | 150-30-M-310 | Install Inlines - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1500898 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 6.37 | 1 | 110 | 6.37 |  | 700.7
1500899 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500899 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500900 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500900 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500901 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | NA | 150-30-M-310 | Install Inlines - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1500901 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 6.37 | 1 | 110 | 6.37 |  | 700.7
1500902 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500902 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500903 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1500903 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1500904 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | NA | 150-30-M-310 | Install Inlines - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1500904 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 6.37 | 1 | 110 | 6.37 |  | 700.7
1500905 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.151 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.59136 |  | 65.0494
1500905 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.4661 | 0 | NA | NA | 1.1943 | 1 | 110 | 4.1395 |  | 455.3459
1500906 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.75 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.65579 |  | 72.1369
1500906 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.125 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 3.6024 |  | 280.9908
1500907 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.3 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.052463 |  | 5.771
1500907 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.33 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.2882 |  | 22.4793
1500908 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500908 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500909 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500909 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500910 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | 1.5 | 2000psi | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500910 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | 1.5 | 2000psi | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500910 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-30-F-310 | Install valve - NB 1.5 2000psi | 1.5 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.52 | 0.75 | 78 | 0.39 |  | 30.42
1500911 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1500911 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1500912 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500913 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500913 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500913 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500914 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500914 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500915 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500915 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 2 | 3 | CS | YP01 | 1.04 | 1 | 110 | 2.08 |  | 228.8
1500916 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.279 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.046411 |  | 5.1052
1500916 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.29295 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.2296 |  | 17.9087
1500917 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500917 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500918 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 2 | 1.5 | CS | YP01 | 0.65 | 1 | 110 | 1.3 |  | 143
1500918 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500919 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 0.75 | 0.75 | NA | NA | EA | 1 | 0 | NA | NA | 0.3 | 0.75 | 78 | 0.225 |  | 17.55
1500920 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1500920 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1500921 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | 1.5 | 2000psi | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500921 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | 1.5 | 2000psi | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500921 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-30-F-310 | Install valve - NB 1.5 2000psi | 1.5 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.52 | 0.75 | 78 | 0.39 |  | 30.42
1500922 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500922 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500923 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | 0.75 | CL800 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500923 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | 0.75 | CL800 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500923 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 CL800 | 0.75 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500924 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500924 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500925 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | 0.75 | CL800 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500925 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | 0.75 | CL800 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500925 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 CL800 | 0.75 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1500926 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500926 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500926 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500927 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 0.964 | 0 | NA | NA | 0.16635 | 1 | 110 | 0.16036 |  | 17.6394
1500927 | 600 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Field | NA | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | 0.75 | Sch160 | NA | LM | 1.0122 | 0 | NA | NA | 1.045 | 0.75 | 78 | 0.79331 |  | 61.8782
1500928 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500928 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500929 | 400 | Proj_A | Area_2 | TR | TR-ZL01-8101 | ISO4027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500929 | 600 | Proj_A | Area_2 | TR | TR-ZL01-8101 | ISO4027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500930 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500930 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500931 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500931 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500932 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.369 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.06453 |  | 7.0983
1500932 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.4059 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.35448 |  | 27.6495
1500933 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500933 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500934 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500934 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500935 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.621 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11655 |  | 12.82
1500935 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6831 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.61186 |  | 47.7252
1500936 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500936 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500937 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500937 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500938 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500938 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500939 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500939 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1500940 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500940 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500941 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1500942 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500942 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500943 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.579 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10866 |  | 11.9529
1500943 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6369 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.57048 |  | 44.4974
1500944 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1500945 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1500945 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1500946 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500946 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500947 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500947 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500948 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.254 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.047669 |  | 5.2436
1500948 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2794 | 0 | NA | NA | 1.1943 | 1 | 110 | 0.33368 |  | 36.7051
1500949 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500950 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500950 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500950 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500951 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500951 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500952 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL6000 | 0.75 | CL6000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500952 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL6000 | 0.75 | NA | CL6000 | EA | 1 | 0.75 | CS | YP01 | 3.38 | 1 | 110 | 3.38 |  | 371.8
1500953 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.386 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.24238 |  | 26.6618
1500953 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.5246 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.3315 |  | 103.8542
1500954 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.073 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.57672 |  | 63.4392
1500954 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.3803 | 0 | NA | NA | 1.1943 | 1 | 110 | 4.037 |  | 444.0742
1500955 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.745 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13982 |  | 15.3798
1500955 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8195 | 0 | NA | NA | 1.1943 | 1 | 110 | 0.97872 |  | 107.6587
1500956 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500956 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1500957 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500957 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1500958 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500959 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1500959 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1500959 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1500960 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500960 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500961 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL6000 | 0.75 | CL6000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1500961 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL6000 | 0.75 | NA | CL6000 | EA | 1 | 0.75 | CS | YP01 | 3.38 | 1 | 110 | 3.38 |  | 371.8
1500962 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.097 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.54159 |  | 59.5754
1500962 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.4067 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 2.9751 |  | 232.0609
1500963 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500963 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500964 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500964 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500965 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.75 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.65579 |  | 72.1369
1500965 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.125 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 3.6024 |  | 280.9908
1500966 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.3 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.052463 |  | 5.771
1500966 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.33 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.2882 |  | 22.4793
1500967 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500968 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500968 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500969 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500969 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1500970 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500970 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500971 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.386 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.24238 |  | 26.6618
1500971 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.5246 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.3315 |  | 103.8542
1500972 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500973 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500974 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500975 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500975 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500976 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 7.622 | 0 | NA | NA | 0.17488 | 1 | 110 | 1.3329 |  | 146.6206
1500976 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 8.3842 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 7.3221 |  | 571.1231
1500977 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500977 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500978 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500978 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500979 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500979 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500980 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500980 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500981 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500981 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500982 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500982 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500983 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500983 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500984 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500984 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1500985 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500986 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1500987 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 8.544 | 0 | NA | NA | 0.17488 | 1 | 110 | 1.4942 |  | 164.3567
1500987 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 9.3984 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 8.2078 |  | 640.2094
1500988 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500988 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500989 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.227 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.039697 |  | 4.3667
1500989 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.2497 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.21807 |  | 17.0093
1500990 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500990 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500991 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.202 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.03791 |  | 4.1701
1500991 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2222 | 0 | NA | NA | 1.1943 | 1 | 110 | 0.26537 |  | 29.1907
1500992 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1500992 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1500993 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-30-F-310 | Install valve - NB 3 CL300 | 3 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500993 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1500994 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-30-F-310 | Install Blind - NB 3 CL300 | 3 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1500995 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1500995 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1500996 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500996 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500997 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | 1.5 | 2000psi | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500997 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | 1.5 | 2000psi | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1500997 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-30-F-310 | Install valve - NB 1.5 2000psi | 1.5 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.52 | 0.75 | 78 | 0.39 |  | 30.42
1500998 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1500998 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1500999 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501000 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501000 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501000 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501001 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501001 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501002 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501002 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 2 | 3 | CS | YP01 | 1.04 | 1 | 110 | 2.08 |  | 228.8
1501003 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.577 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.48363 |  | 53.1997
1501003 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.8347 | 0 | NA | NA | 1.1943 | 1 | 110 | 3.3854 |  | 372.3981
1501004 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.176 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.03303 |  | 3.6334
1501004 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1936 | 0 | NA | NA | 1.1943 | 1 | 110 | 0.23121 |  | 25.4335
1501005 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.621 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11655 |  | 12.82
1501005 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6831 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.61186 |  | 47.7252
1501006 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501006 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501007 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501007 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501008 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501008 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501009 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 6.069 | 0 | NA | NA | 0.17488 | 1 | 110 | 1.0613 |  | 116.7463
1501009 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 6.6759 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 5.8302 |  | 454.7555
1501010 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501010 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1501011 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501011 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501012 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1501012 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1501013 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501013 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501014 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501014 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501015 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501016 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501016 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501017 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501017 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501018 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501019 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501019 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501020 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.662 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.31191 |  | 34.3104
1501020 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.8282 | 0 | NA | NA | 1.1943 | 1 | 110 | 2.1834 |  | 240.1729
1501021 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501021 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501022 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501022 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501023 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501023 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501024 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.662 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.31191 |  | 34.3104
1501024 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.8282 | 0 | NA | NA | 1.1943 | 1 | 110 | 2.1834 |  | 240.1729
1501025 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501025 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501026 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501026 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501027 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501027 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501028 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501028 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501029 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501029 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501030 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501030 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501031 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.284 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.60243 |  | 66.2674
1501031 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-20-M-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.4766 | 0 | NA | NA | 2.9857 | 1 | 110 | 4.4087 |  | 484.9569
1501032 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501032 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501033 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501033 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501034 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501034 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501034 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-30-M-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501035 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501035 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501036 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501036 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501037 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501037 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501038 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchXST | 16 | SchXST | NA | LM | 1.16 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.92028 |  | 101.2309
1501038 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchXST | 16 | SchXST | NA | LM | 1.334 | 0 | NA | NA | 5.1056 | 1 | 110 | 6.8108 |  | 749.1905
1501039 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1501040 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501040 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501040 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-30-M-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501041 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501041 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501042 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501042 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501043 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501044 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 13.388 | 0 | NA | NA | 0.18767 | 1 | 110 | 2.5126 |  | 276.3826
1501044 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 14.7268 | 0 | NA | NA | 1.1943 | 1 | 110 | 17.588 |  | 1934.678
1501045 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501045 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501046 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501046 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501047 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501047 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501048 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501048 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1501049 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.966 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18129 |  | 19.9422
1501049 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0626 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.95178 |  | 74.2392
1501050 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501050 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501051 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501051 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501052 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1501052 | 600 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1501053 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501053 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501054 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501054 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501055 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1501055 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1501056 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.619 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.10825 |  | 11.9074
1501056 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-20-F-210 | Install Spools - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.64995 | 0 | NA | NA | 1.1047 | 0.75 | 78 | 0.53851 |  | 42.0035
1501057 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | 1.5 | 2000psi | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501057 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | 1.5 | 2000psi | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501057 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-30-F-310 | Install valve - NB 1.5 2000psi | 1.5 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.52 | 0.75 | 78 | 0.39 |  | 30.42
1501058 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501058 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501059 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501060 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501060 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501060 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501061 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501061 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501062 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501062 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 2 | 3 | CS | YP01 | 1.04 | 1 | 110 | 2.08 |  | 228.8
1501063 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1501063 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1501064 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | 1.5 | SchXST | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501064 | 600 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL300 | 1.5 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501065 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501065 | 600 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501066 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501066 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501067 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501067 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501068 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501068 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501068 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501069 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501069 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501070 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501071 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501071 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501071 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501072 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501072 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501073 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | YP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501073 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501074 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | YP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501074 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501075 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501075 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501076 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501076 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501077 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501077 | 600 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501078 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501078 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501079 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501079 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501079 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | NA | 150-30-M-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501080 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501080 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501081 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501081 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501082 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501082 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501083 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501083 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501084 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501085 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501085 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501085 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | NA | 150-30-M-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501086 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501086 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501087 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501087 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | YP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501088 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501088 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501089 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | YP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501089 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501090 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501090 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501091 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501091 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501092 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501092 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501093 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchXST | 16 | SchXST | NA | LM | 1.458 | 0 | NA | NA | 0.79335 | 1 | 110 | 1.1567 |  | 127.2368
1501093 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchXST | 16 | SchXST | NA | LM | 1.6767 | 0 | NA | NA | 5.1056 | 1 | 110 | 8.5605 |  | 941.6549
1501094 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchXST | 16 | SchXST | NA | LM | 0.714 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.56645 |  | 62.3094
1501094 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchXST | 16 | SchXST | NA | LM | 0.8211 | 0 | NA | NA | 5.1056 | 1 | 110 | 4.1922 |  | 461.1397
1501095 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501095 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501096 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501096 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501097 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501097 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501098 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 SchSTD | 10 | SchSTD | NA | LM | 1.2 | 0 | NA | NA | 0.33696 | 1 | 110 | 0.40435 |  | 44.4785
1501098 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | NA | 150-20-M-210 | Install Spools - NB 10 SchSTD | 10 | SchSTD | NA | LM | 1.38 | 0 | NA | NA | 2.1497 | 1 | 110 | 2.9666 |  | 326.3262
1501099 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | 10 | SchSTD | NA | EA | 1 | 10 | CS | YP01 | 4.1782 | 1 | 110 | 4.1782 |  | 459.602
1501099 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501100 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501100 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501101 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501101 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501102 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501102 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501103 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501103 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501104 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501104 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501105 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501105 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501106 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501106 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501107 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501107 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501108 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501108 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501109 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501109 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501110 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 SchSTD | 10 | SchSTD | NA | LM | 1.461 | 0 | NA | NA | 0.33696 | 1 | 110 | 0.4923 |  | 54.1526
1501110 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | NA | 150-20-M-210 | Install Spools - NB 10 SchSTD | 10 | SchSTD | NA | LM | 1.6802 | 0 | NA | NA | 2.1497 | 1 | 110 | 3.6118 |  | 397.3021
1501111 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | YP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501111 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | 10 | SchSTD | NA | EA | 1 | 10 | CS | YP01 | 4.1782 | 1 | 110 | 4.1782 |  | 459.602
1501112 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | YP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501112 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 8 CL300 | 8 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 3.12 | 1 | 110 | 1.56 |  | 171.6
1501113 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | 10 | SchSTD | NA | EA | 1 | 10 | CS | YP01 | 4.1782 | 1 | 110 | 4.1782 |  | 459.602
1501113 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL300 | 10 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 3.9 | 1 | 110 | 1.95 |  | 214.5
1501114 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | 10 | SchSTD | NA | EA | 1 | 10 | CS | YP01 | 4.1782 | 1 | 110 | 4.1782 |  | 459.602
1501114 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501115 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501116 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501116 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501116 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501117 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501117 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501118 | 400 | Proj_A | Area_2 | TR | TR-ZL01-8101 | ISO4025 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501118 | 600 | Proj_A | Area_2 | TR | TR-ZL01-8101 | ISO4025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501119 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.632 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.11052 |  | 12.1575
1501119 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.6952 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.60713 |  | 47.3563
1501120 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501120 | 600 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501121 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501121 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501122 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-30-M-310 | Install valve - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 1 | 110 | 6.63 |  | 729.3
1501122 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.16 | 1 | 110 | 4.16 |  | 457.6
1501123 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501123 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501124 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501124 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501125 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.902 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.4232 |  | 46.5523
1501125 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-20-M-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.0373 | 0 | NA | NA | 2.9857 | 1 | 110 | 3.0971 |  | 340.6785
1501126 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.175 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.55524 |  | 61.0759
1501126 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.4925 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 3.0501 |  | 237.9055
1501127 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501127 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501128 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501128 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501129 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501130 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501130 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501131 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501131 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP02 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501132 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.284 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.60243 |  | 66.2674
1501132 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-20-M-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.4766 | 0 | NA | NA | 2.9857 | 1 | 110 | 4.4087 |  | 484.9569
1501133 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501133 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501134 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501134 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501135 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1501136 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501136 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501136 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-30-M-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501137 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501137 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501138 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501138 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501138 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-30-M-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501139 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501139 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501140 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501140 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501141 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501141 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501142 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501143 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 13.108 | 0 | NA | NA | 0.18767 | 1 | 110 | 2.46 |  | 270.6022
1501143 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 14.4188 | 0 | NA | NA | 1.1943 | 1 | 110 | 17.2201 |  | 1894.2156
1501144 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501144 | 500 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501145 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501145 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501146 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501146 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501147 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501147 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1501148 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.966 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18129 |  | 19.9422
1501148 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0626 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.95178 |  | 74.2392
1501149 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501149 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501150 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501150 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501151 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1501151 | 600 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1501152 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501152 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501153 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501153 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501154 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.619 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.10825 |  | 11.9074
1501154 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-20-F-210 | Install Spools - NB 1.5 SchXST | 1.5 | SchXST | NA | LM | 0.64995 | 0 | NA | NA | 1.1047 | 0.75 | 78 | 0.53851 |  | 42.0035
1501155 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501156 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501156 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501156 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501157 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501157 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501158 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501158 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | 1.5 | CL3000 | NA | EA | 2 | 3 | CS | YP01 | 1.04 | 1 | 110 | 2.08 |  | 228.8
1501159 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1501159 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | YP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1501160 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | 1.5 | SchXST | NA | EA | 1 | 1.5 | CS | YP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501160 | 600 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL300 | 1.5 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501161 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501161 | 600 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501162 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501162 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501163 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501163 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501164 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501164 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501165 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501165 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501166 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch40 | 24 | Sch40 | NA | LM | 0.698 | 0 | NA | NA | 0.89571 | 1 | 110 | 0.62521 |  | 68.7728
1501166 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch40 | 24 | Sch40 | NA | LM | 0.8027 | 0 | NA | NA | 5.7923 | 1 | 110 | 4.6495 |  | 511.4407
1501167 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501167 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1501168 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | NA | 150-30-M-310 | Install Blind - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1501169 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | NA | 150-30-M-310 | Install valve - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1501169 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 6.37 | 1 | 110 | 6.37 |  | 700.7
1501170 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501170 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1501171 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501171 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | 24 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 9.62 | 1 | 110 | 4.81 |  | 529.1
1501172 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501172 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | 24 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 9.62 | 1 | 110 | 4.81 |  | 529.1
1501173 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501173 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501174 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501174 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501175 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501175 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501176 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch40 | 24 | Sch40 | NA | LM | 13.762 | 0 | NA | NA | 0.89571 | 1 | 110 | 12.3268 |  | 1355.9483
1501176 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch40 | 24 | Sch40 | NA | LM | 15.8263 | 0 | NA | NA | 5.7923 | 1 | 110 | 91.6703 |  | 10083.7352
1501177 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501177 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501178 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501178 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501178 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501179 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501179 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501180 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501181 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501181 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501181 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501182 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501182 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501183 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | YP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501183 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501184 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | YP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501184 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501185 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501185 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501186 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501186 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501187 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501187 | 600 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501188 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501188 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501189 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501189 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501189 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | NA | 150-30-M-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501190 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501190 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501191 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501191 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501192 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501192 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501193 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501193 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501194 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501195 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501195 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501195 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | NA | 150-30-M-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501196 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501196 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501197 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | YP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501197 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | YP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501198 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501198 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501199 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | YP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501199 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501200 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501200 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501201 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501201 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501202 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501202 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501203 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchXST | 16 | SchXST | NA | LM | 1.458 | 0 | NA | NA | 0.79335 | 1 | 110 | 1.1567 |  | 127.2368
1501203 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchXST | 16 | SchXST | NA | LM | 1.6767 | 0 | NA | NA | 5.1056 | 1 | 110 | 8.5605 |  | 941.6549
1501204 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchXST | 16 | SchXST | NA | LM | 0.714 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.56645 |  | 62.3094
1501204 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchXST | 16 | SchXST | NA | LM | 0.8211 | 0 | NA | NA | 5.1056 | 1 | 110 | 4.1922 |  | 461.1397
1501205 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501205 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501206 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501206 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501207 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501207 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501208 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 SchSTD | 10 | SchSTD | NA | LM | 1.2 | 0 | NA | NA | 0.33696 | 1 | 110 | 0.40435 |  | 44.4785
1501208 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | NA | 150-20-M-210 | Install Spools - NB 10 SchSTD | 10 | SchSTD | NA | LM | 1.38 | 0 | NA | NA | 2.1497 | 1 | 110 | 2.9666 |  | 326.3262
1501209 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | 10 | SchSTD | NA | EA | 1 | 10 | CS | YP01 | 4.1782 | 1 | 110 | 4.1782 |  | 459.602
1501209 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501210 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501210 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501211 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchXST | 16 | SchXST | NA | LM | 1.16 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.92028 |  | 101.2309
1501211 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchXST | 16 | SchXST | NA | LM | 1.334 | 0 | NA | NA | 5.1056 | 1 | 110 | 6.8108 |  | 749.1905
1501212 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501212 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1501213 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | NA | 150-30-M-310 | Install Blind - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1501214 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | NA | 150-30-M-310 | Install valve - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1501214 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 6.37 | 1 | 110 | 6.37 |  | 700.7
1501215 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501215 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 6.37 | 1 | 110 | 3.185 |  | 350.35
1501216 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501216 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501217 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501217 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501218 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501218 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501219 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501219 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501220 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501220 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501221 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501221 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501222 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501222 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 1 | 110 | 1.04 |  | 114.4
1501223 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501223 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 1 | 110 | 0.52 |  | 57.2
1501224 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501224 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | YP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1501225 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 SchSTD | 10 | SchSTD | NA | LM | 1.461 | 0 | NA | NA | 0.33696 | 1 | 110 | 0.4923 |  | 54.1526
1501225 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | NA | 150-20-M-210 | Install Spools - NB 10 SchSTD | 10 | SchSTD | NA | LM | 1.6802 | 0 | NA | NA | 2.1497 | 1 | 110 | 3.6118 |  | 397.3021
1501226 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | YP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501226 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | 10 | SchSTD | NA | EA | 1 | 10 | CS | YP01 | 4.1782 | 1 | 110 | 4.1782 |  | 459.602
1501227 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | YP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501227 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 8 CL300 | 8 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 3.12 | 1 | 110 | 1.56 |  | 171.6
1501228 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | 10 | SchSTD | NA | EA | 1 | 10 | CS | YP01 | 4.1782 | 1 | 110 | 4.1782 |  | 459.602
1501228 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL300 | 10 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 3.9 | 1 | 110 | 1.95 |  | 214.5
1501229 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | 10 | SchSTD | NA | EA | 1 | 10 | CS | YP01 | 4.1782 | 1 | 110 | 4.1782 |  | 459.602
1501229 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501230 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501230 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | 24 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 9.62 | 1 | 110 | 4.81 |  | 529.1
1501231 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501231 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | 24 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 9.62 | 1 | 110 | 4.81 |  | 529.1
1501232 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | NA | 150-30-M-310 | Install valve - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 9.23 | 1 | 110 | 9.23 |  | 1015.3
1501232 | 500 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | 16 | NA | CL300 | EA | 1 | 0 | NA | NA | 6.37 | 1 | 110 | 6.37 |  | 700.7
1501233 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501234 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | YP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501234 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | YP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501234 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501235 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501235 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501236 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.633 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.1107 |  | 12.1767
1501236 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.6963 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.60809 |  | 47.4312
1501237 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501237 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | 3 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501238 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501238 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | YP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1501239 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.737 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13832 |  | 15.2147
1501239 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8107 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.72615 |  | 56.6401
1501240 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501240 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501241 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.562 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10547 |  | 11.602
1501241 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6182 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.55373 |  | 43.1909
1501242 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501242 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501243 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 2.114 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.36969 |  | 40.666
1501243 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 2.3254 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 2.0308 |  | 158.4039
1501244 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501244 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501245 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501245 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501246 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501246 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501246 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1501247 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501247 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501248 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1501249 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.256 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.045861 |  | 5.0447
1501249 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2688 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.23475 |  | 18.3104
1501250 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501250 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501250 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1501251 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501251 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501252 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501252 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501253 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1501253 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1501254 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.249 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.044607 |  | 4.9067
1501254 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.26145 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.22833 |  | 17.8097
1501255 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501255 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501255 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1501256 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501256 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501257 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501258 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501258 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501258 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501259 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501259 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501260 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501260 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501261 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501261 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501262 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-30-M-310 | Install valve - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 1 | 110 | 6.63 |  | 729.3
1501262 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.16 | 1 | 110 | 4.16 |  | 457.6
1501263 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501263 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501264 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1501265 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1501266 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1501267 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501267 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501268 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.626 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.10947 |  | 12.0421
1501268 | 600 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.6886 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.60137 |  | 46.9067
1501269 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501269 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501270 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501270 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501271 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501271 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501272 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501272 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501272 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | NA | 150-30-M-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501273 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501273 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501274 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501274 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501275 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501275 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501276 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501277 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501277 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501277 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | NA | 150-30-M-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501278 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501278 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501279 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501279 | 600 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501280 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501280 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501281 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501281 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501282 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501282 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501283 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501283 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501284 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501284 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501285 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501285 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501286 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501286 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501287 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501287 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501288 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 7.666 | 0 | NA | NA | 0.18767 | 1 | 110 | 1.4387 |  | 158.2573
1501288 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 8.4326 | 0 | NA | NA | 1.1943 | 1 | 110 | 10.0709 |  | 1107.8011
1501289 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501289 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501290 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.5 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.70377 |  | 77.4152
1501290 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-20-M-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.725 | 0 | NA | NA | 2.9857 | 1 | 110 | 5.1503 |  | 566.5385
1501291 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501291 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501292 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.777 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.66051 |  | 72.6563
1501292 | 600 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.1547 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 3.6284 |  | 283.0139
1501293 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501293 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | YP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501294 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501294 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501295 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501295 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501296 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501296 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501297 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.902 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.4232 |  | 46.5523
1501297 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | NA | 150-20-M-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.0373 | 0 | NA | NA | 2.9857 | 1 | 110 | 3.0971 |  | 340.6785
1501298 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501298 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501299 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | 16 | SchXST | NA | EA | 1 | 16 | CS | YP01 | 16.12 | 1 | 110 | 16.12 |  | 1773.2
1501299 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501300 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501300 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 2 | 48 | CS | YP01 | 18.3647 | 1 | 110 | 36.7293 |  | 4040.2267
1501301 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501301 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 24 | CS | YP01 | 18.3647 | 1 | 110 | 18.3647 |  | 2020.1133
1501302 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501302 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501303 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501303 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501304 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501304 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501305 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501305 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501306 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.5 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.70377 |  | 77.4152
1501306 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | NA | 150-20-M-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.725 | 0 | NA | NA | 2.9857 | 1 | 110 | 5.1503 |  | 566.5385
1501307 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501307 | 500 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501308 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501308 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501309 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501309 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP02 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501310 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 8.374 | 0 | NA | NA | 0.18767 | 1 | 110 | 1.5716 |  | 172.8733
1501310 | 500 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 9.2114 | 0 | NA | NA | 1.1943 | 1 | 110 | 11.001 |  | 1210.113
1501311 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501311 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501312 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501312 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 15.191 | 0 | NA | NA | 0.57155 | 1 | 110 | 8.6824 |  | 955.0661
1501312 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 17.4696 | 0 | NA | NA | 3.6724 | 1 | 110 | 64.1559 |  | 7057.1545
1501313 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 12.448 | 0 | NA | NA | 0.57155 | 1 | 110 | 7.1147 |  | 782.6123
1501313 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 14.3152 | 0 | NA | NA | 3.6724 | 1 | 110 | 52.5715 |  | 5782.8621
1501314 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 14.664 | 0 | NA | NA | 0.57155 | 1 | 110 | 8.3812 |  | 921.9333
1501314 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 16.8636 | 0 | NA | NA | 3.6724 | 1 | 110 | 61.9303 |  | 6812.3305
1501315 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 14.664 | 0 | NA | NA | 0.57155 | 1 | 110 | 8.3812 |  | 921.9333
1501315 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 16.8636 | 0 | NA | NA | 3.6724 | 1 | 110 | 61.9303 |  | 6812.3305
1501316 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 12.062 | 0 | NA | NA | 0.57155 | 1 | 110 | 6.894 |  | 758.3442
1501316 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 13.8713 | 0 | NA | NA | 3.6724 | 1 | 110 | 50.9413 |  | 5603.5414
1501317 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 7.63 | 0 | NA | NA | 0.57155 | 1 | 110 | 4.3609 |  | 479.7021
1501317 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 8.7745 | 0 | NA | NA | 3.6724 | 1 | 110 | 32.2237 |  | 3544.6046
1501318 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 4.431 | 0 | NA | NA | 0.57155 | 1 | 110 | 2.5325 |  | 278.5793
1501318 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 5.0957 | 0 | NA | NA | 3.6724 | 1 | 110 | 18.7134 |  | 2058.4722
1501319 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501319 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 16.664 | 0 | NA | NA | 0.57155 | 1 | 110 | 9.5243 |  | 1047.6744
1501319 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 19.1636 | 0 | NA | NA | 3.6724 | 1 | 110 | 70.3769 |  | 7741.4536
1501320 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501320 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 17.664 | 0 | NA | NA | 0.57155 | 1 | 110 | 10.0959 |  | 1110.5449
1501320 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 20.3136 | 0 | NA | NA | 3.6724 | 1 | 110 | 74.6001 |  | 8206.0152
1501321 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 5.324 | 0 | NA | NA | 0.57155 | 1 | 110 | 3.0429 |  | 334.7227
1501321 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 6.1226 | 0 | NA | NA | 3.6724 | 1 | 110 | 22.4848 |  | 2473.3257
1501322 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501323 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501323 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501324 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.674 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.5283 |  | 168.1158
1501324 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.0751 | 0 | NA | NA | 3.6724 | 1 | 110 | 11.2931 |  | 1242.2376
1501325 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501325 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501326 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501326 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501327 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501327 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501328 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501328 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501329 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501329 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501330 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501330 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501331 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501331 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501332 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501332 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501333 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501333 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501334 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501334 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501335 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.305 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17432 |  | 19.1755
1501335 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.35075 | 0 | NA | NA | 3.6724 | 1 | 110 | 1.2881 |  | 141.6913
1501336 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501336 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501337 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501338 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | NA | 150-30-M-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501338 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501339 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501339 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501340 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501340 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501341 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501341 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1501342 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.699 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.5426 |  | 169.6875
1501342 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.1038 | 0 | NA | NA | 3.6724 | 1 | 110 | 11.3987 |  | 1253.8516
1501343 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501343 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501344 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.176 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.67214 |  | 73.9357
1501344 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.3524 | 0 | NA | NA | 3.6724 | 1 | 110 | 4.9666 |  | 546.3244
1501345 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501345 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501346 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501346 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501347 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501347 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501348 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501348 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501349 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501349 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501350 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501350 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1501351 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501351 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501352 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.42 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.9547 |  | 215.0172
1501352 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.933 | 0 | NA | NA | 3.6724 | 1 | 110 | 14.4436 |  | 1588.8005
1501353 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501353 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501354 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501354 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501355 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501355 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501356 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501356 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501357 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501357 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501358 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501358 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501359 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.319 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.18232 |  | 20.0557
1501359 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.36685 | 0 | NA | NA | 3.6724 | 1 | 110 | 1.3472 |  | 148.1951
1501360 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501360 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501361 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501361 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501362 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501362 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501363 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501363 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501364 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501364 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501365 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501365 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501366 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501366 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501367 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 5.696 | 0 | NA | NA | 0.57155 | 1 | 110 | 3.2555 |  | 358.1105
1501367 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 6.5504 | 0 | NA | NA | 3.6724 | 1 | 110 | 24.0558 |  | 2646.1426
1501368 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 14.664 | 0 | NA | NA | 0.57155 | 1 | 110 | 8.3812 |  | 921.9333
1501368 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 16.8636 | 0 | NA | NA | 3.6724 | 1 | 110 | 61.9303 |  | 6812.3305
1501369 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501369 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501370 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501370 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501371 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501371 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 15.564 | 0 | NA | NA | 0.57155 | 1 | 110 | 8.8956 |  | 978.5168
1501371 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 17.8986 | 0 | NA | NA | 3.6724 | 1 | 110 | 65.7312 |  | 7230.4359
1501372 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501372 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501373 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501373 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501374 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501374 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501375 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501375 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501376 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 10.512 | 0 | NA | NA | 0.57155 | 1 | 110 | 6.0081 |  | 660.8949
1501376 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 12.0888 | 0 | NA | NA | 3.6724 | 1 | 110 | 44.3952 |  | 4883.471
1501377 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501377 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501378 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501378 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501379 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501379 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1501380 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.749 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.5712 |  | 172.8311
1501380 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.1614 | 0 | NA | NA | 3.6724 | 1 | 110 | 11.6098 |  | 1277.0797
1501381 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501381 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501382 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501382 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 1 | 110 | 2.08 |  | 228.8
1501383 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1501383 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1501384 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.075 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.61442 |  | 67.5858
1501384 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | NA | 150-20-M-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.2362 | 0 | NA | NA | 3.6724 | 1 | 110 | 4.54 |  | 499.4037
1501385 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501386 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1501386 | 500 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501387 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501388 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501389 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501390 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 5.166 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.96952 |  | 106.6472
1501390 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 5.6826 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 5.09 |  | 397.0183
1501391 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501391 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501392 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501392 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501393 | 400 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501393 | 400 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | ZL02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501394 | 400 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501394 | 600 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2079 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501395 | 400 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501395 | 400 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | ZL02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501396 | 400 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501396 | 600 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501397 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.172 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.03228 |  | 3.5508
1501397 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1892 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.16947 |  | 13.2186
1501398 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501398 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501399 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.342 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.064184 |  | 7.0603
1501399 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3762 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.33697 |  | 26.2834
1501400 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501400 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501401 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.142 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.02665 |  | 2.9315
1501401 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1562 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.13991 |  | 10.913
1501402 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501402 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501403 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.725 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.12679 |  | 13.9465
1501403 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.7975 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.69647 |  | 54.3249
1501404 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 1.719 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.46192 |  | 50.8111
1501404 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 1.8909 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 2.4135 |  | 188.2552
1501405 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.752 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.13151 |  | 14.4659
1501405 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.8272 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.72241 |  | 56.348
1501406 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.129 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.02421 |  | 2.6631
1501406 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1419 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.1271 |  | 9.9139
1501407 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501408 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501408 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1501409 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501410 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501410 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501411 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501411 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1501412 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501412 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501412 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501413 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501414 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501414 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501415 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501415 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 15.742 | 0 | NA | NA | 1.1644 | 1 | 110 | 18.3304 |  | 2016.3449
1501415 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 18.1033 | 0 | NA | NA | 7.4941 | 1 | 110 | 135.6685 |  | 14923.5374
1501416 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 1.32 | 0 | NA | NA | 1.1644 | 1 | 110 | 1.537 |  | 169.0748
1501416 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 1.518 | 0 | NA | NA | 7.4941 | 1 | 110 | 11.3761 |  | 1251.3702
1501417 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501417 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501418 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501418 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501419 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501420 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501420 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501421 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501421 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL02 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501422 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501423 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501423 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501424 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501424 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL02 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501425 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1501426 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501426 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501427 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501427 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501428 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501428 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501429 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.225 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.034549 |  | 3.8004
1501429 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.23625 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.17987 |  | 14.0299
1501430 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501430 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501431 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501431 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501432 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501432 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501433 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501433 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1501434 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501434 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501435 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501435 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501436 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501436 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501437 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501437 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501438 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501438 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501439 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501439 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501440 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501440 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501441 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501441 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501442 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501442 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501443 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501443 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501444 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501444 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501445 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501445 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501446 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501446 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501446 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501447 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501447 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501448 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501448 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501449 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501449 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501450 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501450 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501451 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501451 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501452 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501453 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501454 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501454 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501454 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501455 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501455 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501456 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501456 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP01 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1501457 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501458 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501458 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501459 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501459 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL02 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501460 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501460 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501461 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501461 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501462 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501462 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501463 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501463 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501464 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501464 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501465 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 2 | 48 | CS | ZL01 | 33.1998 | 1 | 110 | 66.3997 |  | 7303.9633
1501465 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501466 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501467 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501467 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501468 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501468 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501469 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501469 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501470 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501470 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501471 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501471 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501472 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501472 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501473 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501473 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501474 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501474 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501475 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501475 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501476 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501476 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 2 | 48 | CS | ZL01 | 33.1998 | 1 | 110 | 66.3997 |  | 7303.9633
1501477 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501478 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 2 | 40 | CS | ZL01 | 21.7588 | 1 | 110 | 43.5175 |  | 4786.925
1501478 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501479 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501479 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 2 | 40 | CS | ZL01 | 21.7588 | 1 | 110 | 43.5175 |  | 4786.925
1501480 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501480 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 2 | 40 | CS | ZL01 | 21.7588 | 1 | 110 | 43.5175 |  | 4786.925
1501481 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501481 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 2 | 40 | CS | ZL01 | 21.7588 | 1 | 110 | 43.5175 |  | 4786.925
1501482 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501482 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 2 | 40 | CS | ZL01 | 21.7588 | 1 | 110 | 43.5175 |  | 4786.925
1501483 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501483 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501484 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501485 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501486 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501487 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501487 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501488 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 2 | 40 | CS | ZL01 | 21.7588 | 1 | 110 | 43.5175 |  | 4786.925
1501488 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501489 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501489 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501490 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501490 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501491 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1501492 | 600 | Proj_A | Area_3 | TR | TR-ZL01-8116 | ISO3026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501493 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.264 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.42489 |  | 46.7381
1501493 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.4904 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.2307 |  | 173.9933
1501494 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501494 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501495 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501495 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501496 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501496 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501497 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501498 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501499 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.143 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.54964 |  | 60.4603
1501499 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.4573 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 3.0193 |  | 235.5077
1501500 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501500 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501501 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501501 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501502 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.744 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.13011 |  | 14.312
1501502 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.8184 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.71473 |  | 55.7486
1501503 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501503 | 600 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501504 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | XP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1501504 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501505 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501506 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501506 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501506 | 500 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | NA | 150-30-M-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501507 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501507 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501508 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501508 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501509 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.305 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.046833 |  | 5.1516
1501509 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.32025 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.24382 |  | 19.0183
1501510 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501511 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501511 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501512 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501512 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501513 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501514 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501514 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501515 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501515 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501516 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501516 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501517 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501518 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501518 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501519 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501519 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501520 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501520 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501521 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501521 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1501522 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501522 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1501523 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501524 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 4 | 4 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501525 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501525 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501526 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501526 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501527 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchSTD | 4 | SchSTD | NA | LM | 0.4 | 0 | NA | NA | 0.19194 | 1 | 110 | 0.076775 |  | 8.4453
1501527 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchSTD | 4 | SchSTD | NA | LM | 0.44 | 0 | NA | NA | 1.2241 | 0.75 | 78 | 0.40397 |  | 31.5094
1501528 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501528 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | 4 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.56 | 0.75 | 78 | 0.585 |  | 45.63
1501529 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501529 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | 4 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.56 | 0.75 | 78 | 0.585 |  | 45.63
1501530 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501530 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501531 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501531 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | 4 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.56 | 0.75 | 78 | 0.585 |  | 45.63
1501532 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501532 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | 4 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.56 | 0.75 | 78 | 0.585 |  | 45.63
1501533 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchSTD | 4 | SchSTD | NA | LM | 2.747 | 0 | NA | NA | 0.19194 | 1 | 110 | 0.52726 |  | 57.9981
1501533 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchSTD | 4 | SchSTD | NA | LM | 3.0217 | 0 | NA | NA | 1.2241 | 0.75 | 78 | 2.7742 |  | 216.3907
1501534 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchSTD | 4 | SchSTD | NA | LM | 5.211 | 0 | NA | NA | 0.19194 | 1 | 110 | 1.0002 |  | 110.0211
1501534 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchSTD | 4 | SchSTD | NA | LM | 5.7321 | 0 | NA | NA | 1.2241 | 0.75 | 78 | 5.2627 |  | 410.4886
1501535 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501535 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501536 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchSTD | 4 | SchSTD | NA | LM | 1.249 | 0 | NA | NA | 0.19194 | 1 | 110 | 0.23973 |  | 26.3704
1501536 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchSTD | 4 | SchSTD | NA | LM | 1.3739 | 0 | NA | NA | 1.2241 | 0.75 | 78 | 1.2614 |  | 98.3881
1501537 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501537 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501538 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501538 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501539 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchSTD | 4 | SchSTD | NA | LM | 0.934 | 0 | NA | NA | 0.19194 | 1 | 110 | 0.17927 |  | 19.7198
1501539 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchSTD | 4 | SchSTD | NA | LM | 1.0274 | 0 | NA | NA | 1.2241 | 0.75 | 78 | 0.94326 |  | 73.5744
1501540 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 4 SchSTD | 4 | SchSTD | NA | LM | 0.29 | 0 | NA | NA | 0.19194 | 1 | 110 | 0.055662 |  | 6.1228
1501540 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | NA | 150-20-F-210 | Install Spools - NB 4 SchSTD | 4 | SchSTD | NA | LM | 0.319 | 0 | NA | NA | 1.2241 | 0.75 | 78 | 0.29288 |  | 22.8443
1501541 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501541 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501542 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 4 | CS | XP01 | 1.6835 | 1 | 110 | 1.6835 |  | 185.185
1501542 | 600 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | 4 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.56 | 0.75 | 78 | 0.585 |  | 45.63
1501543 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1501544 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1501545 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1501546 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501547 | 500 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1501548 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501548 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501549 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501549 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501550 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501550 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501551 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501551 | 600 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501552 | 600 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501552 | 600 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1501553 | 600 | Proj_A | Area_3 | TR | TR-XP01-8098 | ISO4023 | Field | NA | 150-30-F-310 | Install valve - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
1501553 | 600 | Proj_A | Area_3 | TR | TR-XP01-8098 | ISO4023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1501554 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501555 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501556 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501557 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501558 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501559 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501560 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501561 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501562 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501563 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501564 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501565 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501566 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501567 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501568 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501569 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501570 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501571 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501572 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501573 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501574 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501575 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501576 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501577 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 24 | 24 | NA | NA | EA | 1 | 0 | NA | NA | 2.5655 | 1 | 110 | 2.5655 |  | 282.206
1501578 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 1 | 110 | 2.327 |  | 255.9692
1501579 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 1 | 110 | 2.327 |  | 255.9692
1501580 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 1 | 110 | 2.327 |  | 255.9692
1501581 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 1 | 110 | 2.327 |  | 255.9692
1501582 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 1 | 110 | 2.327 |  | 255.9692
1501583 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 1 | 110 | 2.327 |  | 255.9692
1501584 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501585 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501586 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501587 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501588 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501589 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501590 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501591 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501592 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501593 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501594 | 600 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501595 | 600 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501596 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501597 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501598 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501599 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501600 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501601 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501602 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501603 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501604 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501605 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501606 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501607 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501608 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501609 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501610 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501611 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501612 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501613 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501614 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501615 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501616 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501617 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501618 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501619 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501620 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501621 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501622 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501623 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501624 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501625 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501626 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501627 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501628 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501629 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501630 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501631 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 1 | 110 | 2.1107 |  | 232.1716
1501632 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 0.636 | 0 | NA | NA | 1.1644 | 1 | 110 | 0.74058 |  | 81.4633
1501632 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 0.7314 | 0 | NA | NA | 7.4941 | 1 | 110 | 5.4812 |  | 602.9329
1501633 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501633 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501634 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501634 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501635 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501635 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501636 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501636 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501637 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501637 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501638 | 400 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501638 | 500 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501639 | 500 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | NA | 150-30-M-310 | Install Blind - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501640 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501640 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501641 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | NA | 150-30-M-310 | Install Blind - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4
1501642 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501642 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1501643 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501643 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501644 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501644 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1501645 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501645 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501646 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 16.1557 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 12.4036 |  | 967.4811
1501646 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 16.1557 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 969.342
1501647 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.729 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.32449 |  | 35.6936
1501647 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.9019 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.7036 |  | 132.8774
1501648 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501648 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501649 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501650 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501650 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501651 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.597 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.16042 |  | 17.6464
1501651 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.6567 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 0.83821 |  | 65.3801
1501652 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501652 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501653 | 500 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | NA | 150-50-M-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 1 | 110 | 1 |  | 110
1501654 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501654 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501654 | 500 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | NA | 150-30-M-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501655 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501655 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501656 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501656 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501657 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.2 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.22521 |  | 24.7729
1501657 | 500 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.32 | 0 | NA | NA | 1.1943 | 1 | 110 | 1.5765 |  | 173.41
1501658 | 500 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501659 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501659 | 500 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501660 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.292 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.43015 |  | 47.3162
1501660 | 500 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.5212 | 0 | NA | NA | 1.1943 | 1 | 110 | 3.011 |  | 331.2132
1501661 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501661 | 500 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501662 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501662 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501663 | 400 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501663 | 500 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501664 | 500 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501665 | 400 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501665 | 500 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 1 | 110 | 0.455 |  | 50.05
1501666 | 400 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.297 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.61876 |  | 68.0634
1501666 | 500 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Module | NA | 150-20-M-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.6267 | 0 | NA | NA | 1.1943 | 1 | 110 | 4.3313 |  | 476.4441
1501667 | 400 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP02 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501667 | 400 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501668 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501668 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1501669 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501669 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1501670 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 2.807 | 0 | NA | NA | 1.1644 | 1 | 110 | 3.2685 |  | 359.5401
1501670 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 3.228 | 0 | NA | NA | 7.4941 | 1 | 110 | 24.1914 |  | 2661.0576
1501671 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 3.666 | 0 | NA | NA | 1.1644 | 1 | 110 | 4.2688 |  | 469.5668
1501671 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 4.2159 | 0 | NA | NA | 7.4941 | 1 | 110 | 31.5945 |  | 3475.3963
1501672 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501672 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501673 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501673 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501674 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501674 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501675 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501675 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501676 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-30-M-310 | Install Blind - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4
1501677 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501677 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501678 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-30-M-310 | Install valve - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 1 | 110 | 11.44 |  | 1258.4
1501678 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.76 | 1 | 110 | 6.76 |  | 743.6
1501679 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501679 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 16.613 | 0 | NA | NA | 0.79335 | 1 | 110 | 13.1799 |  | 1449.7839
1501679 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 19.1049 | 0 | NA | NA | 5.1056 | 1 | 110 | 97.5415 |  | 10729.5702
1501680 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501680 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501681 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501681 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501682 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501682 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 17.124 | 0 | NA | NA | 0.79335 | 1 | 110 | 13.5853 |  | 1494.3779
1501682 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 19.6926 | 0 | NA | NA | 5.1056 | 1 | 110 | 100.5418 |  | 11059.6015
1501683 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501683 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501684 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501684 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501685 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 4.2887 | 0.75 | 78 | 3.2165 |  | 250.889
1501685 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 8 SchSTD | 8 | SchSTD | NA | LM | 19.1103 | 0 | NA | NA | 1.4502 | 0.75 | 78 | 20.7853 |  | 1621.257
1501685 | 300 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-80-F-810 | Field Coating - NB 8 | 8 | NA | NA | LM | 19.1103 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 120 | 2293.236
1501686 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.312 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.4339 |  | 47.729
1501686 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.5432 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.278 |  | 177.6822
1501687 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 0.636 | 0 | NA | NA | 1.1644 | 1 | 110 | 0.74058 |  | 81.4633
1501687 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 0.7314 | 0 | NA | NA | 7.4941 | 1 | 110 | 5.4812 |  | 602.9329
1501688 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501688 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501689 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501689 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501690 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501690 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501691 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501691 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501692 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501692 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501693 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 5.882 | 0 | NA | NA | 0.18767 | 1 | 110 | 1.1039 |  | 121.4283
1501693 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 6.4702 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 5.7954 |  | 452.0445
1501694 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501694 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501695 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501695 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501696 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.233 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.043728 |  | 4.8101
1501696 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2563 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.22957 |  | 17.9066
1501697 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501697 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501698 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501699 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501699 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501700 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501700 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL02 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501701 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501702 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501702 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501703 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501703 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL02 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501704 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 10.085 | 0 | NA | NA | 1.1644 | 1 | 110 | 11.7432 |  | 1291.757
1501704 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 11.5977 | 0 | NA | NA | 7.4941 | 1 | 110 | 86.9151 |  | 9560.6578
1501705 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501705 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501706 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501706 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501707 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | NA | ZL01 | 0.429 | 1 | 110 | 0.429 |  | 47.19
1501707 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501708 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501708 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501709 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501709 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501710 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 3.822 | 0 | NA | NA | 0.79335 | 1 | 110 | 3.0322 |  | 333.5384
1501710 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 4.3953 | 0 | NA | NA | 5.1056 | 1 | 110 | 22.4405 |  | 2468.4534
1501711 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501711 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501712 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.997 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.79097 |  | 87.0062
1501712 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.1465 | 0 | NA | NA | 5.1056 | 1 | 110 | 5.8538 |  | 643.9163
1501713 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501713 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501714 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501714 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501715 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 13.402 | 0 | NA | NA | 0.79335 | 1 | 110 | 10.6324 |  | 1169.5662
1501715 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 15.4123 | 0 | NA | NA | 5.1056 | 1 | 110 | 78.6885 |  | 8655.7334
1501716 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501716 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501717 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501717 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501718 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.997 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.79097 |  | 87.0062
1501718 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.1465 | 0 | NA | NA | 5.1056 | 1 | 110 | 5.8538 |  | 643.9163
1501719 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501719 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501720 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 4.699 | 0 | NA | NA | 0.79335 | 1 | 110 | 3.7279 |  | 410.0725
1501720 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 5.4038 | 0 | NA | NA | 5.1056 | 1 | 110 | 27.5897 |  | 3034.8673
1501721 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501721 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501722 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501722 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501723 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501723 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501724 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501725 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501725 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501726 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501726 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501727 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 12.711 | 0 | NA | NA | 0.79335 | 1 | 110 | 10.0842 |  | 1109.264
1501727 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 14.6176 | 0 | NA | NA | 5.1056 | 1 | 110 | 74.6313 |  | 8209.4484
1501728 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501728 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501729 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.978 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.77589 |  | 85.3481
1501729 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.1247 | 0 | NA | NA | 5.1056 | 1 | 110 | 5.7422 |  | 631.6451
1501730 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501730 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501731 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501731 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501732 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501732 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501733 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 8.899 | 0 | NA | NA | 0.79335 | 1 | 110 | 7.06 |  | 776.5983
1501733 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 10.2338 | 0 | NA | NA | 5.1056 | 1 | 110 | 52.2496 |  | 5747.4535
1501734 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501734 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501735 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501735 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501736 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501736 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501737 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501738 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501738 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501739 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.179 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.93535 |  | 102.889
1501739 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.3558 | 0 | NA | NA | 5.1056 | 1 | 110 | 6.9224 |  | 761.4617
1501740 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501740 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501741 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.71 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.56328 |  | 61.9603
1501741 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.8165 | 0 | NA | NA | 5.1056 | 1 | 110 | 4.1687 |  | 458.5562
1501742 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501742 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 2 | 32 | CS | ZL01 | 14.365 | 1 | 110 | 28.73 |  | 3160.3
1501743 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.633 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.50219 |  | 55.2407
1501743 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.72795 | 0 | NA | NA | 5.1056 | 1 | 110 | 3.7166 |  | 408.8255
1501744 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501744 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501745 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 5.78 | 0 | NA | NA | 0.79335 | 1 | 110 | 4.5855 |  | 504.4093
1501745 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | NA | 150-20-M-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 6.647 | 0 | NA | NA | 5.1056 | 1 | 110 | 33.9367 |  | 3733.0353
1501746 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1501746 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501747 | 600 | Proj_A | Area_3 | TR | TR-ZL01-8088 | ISO4010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501748 | 600 | Proj_A | Area_3 | TR | TR-XP01-8092 | ISO4012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501749 | 600 | Proj_A | Area_3 | TR | TR-XP01-8095 | ISO4015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501750 | 600 | Proj_A | Area_3 | TR | TR-ZL01-8091 | ISO4017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501751 | 600 | Proj_A | Area_3 | TR | TR-ZL02-8094 | ISO4014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501752 | 600 | Proj_A | Area_3 | TR | TR-ZL02-8090 | ISO4016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501753 | 600 | Proj_A | Area_3 | TR | TR-ZL02-8093 | ISO4013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501754 | 600 | Proj_A | Area_3 | TR | TR-ZL02-8103 | ISO2088 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501755 | 600 | Proj_A | Area_3 | TR | TR-ZL02-8089 | ISO4011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1501756 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501757 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501757 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1501757 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501758 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501758 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501759 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501759 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501760 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1501761 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501761 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501762 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1501762 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP01 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1501763 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501764 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501765 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501766 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.811 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.33988 |  | 37.3864
1501766 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.9921 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.7843 |  | 139.1793
1501767 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501767 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501768 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501768 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501769 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.425 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.065259 |  | 7.1785
1501769 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.44625 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.33976 |  | 26.5009
1501770 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501770 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501771 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.354 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.25411 |  | 27.952
1501771 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.4894 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.3341 |  | 104.0578
1501772 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501772 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501773 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501773 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501774 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.255 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.039155 |  | 4.3071
1501774 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.26775 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.20385 |  | 15.9005
1501775 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | XP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1501775 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501776 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 1.305 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.20038 |  | 22.0422
1501776 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 1.3702 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 1.0432 |  | 81.3734
1501777 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.255 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.039155 |  | 4.3071
1501777 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.26775 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.20385 |  | 15.9005
1501778 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501778 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501779 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501779 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501780 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501780 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501781 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501781 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501782 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501782 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501783 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501783 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501783 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501784 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501784 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501785 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501785 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501785 | 600 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1501786 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501786 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1501787 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501787 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1501788 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501788 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501789 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501789 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501790 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.205 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.038473 |  | 4.232
1501790 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2255 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.20198 |  | 15.7547
1501791 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501791 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501792 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1501792 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1501793 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.391 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.07338 |  | 8.0718
1501793 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4301 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.38525 |  | 30.0492
1501794 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501794 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501795 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.141 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.026462 |  | 2.9108
1501795 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1551 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.13893 |  | 10.8362
1501796 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501796 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501797 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.009 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18936 |  | 20.8298
1501797 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.1099 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.99415 |  | 77.5438
1501798 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501799 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.738 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.1385 |  | 15.2353
1501799 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8118 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.72714 |  | 56.7169
1501800 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501800 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501801 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501801 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501802 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.6 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.16123 |  | 17.7351
1501802 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.66 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 0.84242 |  | 65.7086
1501803 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501803 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501804 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501804 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1501805 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501805 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1501806 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501806 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501807 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1501807 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1501808 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field | NA | 150-30-F-310 | Install Blind - NB 8 CL150 | 8 | NA | CL150 | EA | 1 | 0 | NA | NA | 3.64 | 0.75 | 78 | 2.73 |  | 212.94
1501809 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1501810 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501810 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501811 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | NA | 150-30-F-310 | Install valve - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
1501811 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1501812 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501812 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501813 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501813 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501814 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.143 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.025007 |  | 2.7508
1501814 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.1573 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.13737 |  | 10.7151
1501815 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501815 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501816 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1501816 | 600 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1501817 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 5.167 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.96971 |  | 106.6678
1501817 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 5.6837 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 5.091 |  | 397.0952
1501818 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501818 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501819 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501819 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501820 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501821 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501821 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501822 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501822 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501823 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501823 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501824 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501824 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501825 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501825 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501826 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501826 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501827 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501827 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501828 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 5.097 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.95657 |  | 105.2227
1501828 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 5.6067 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 5.022 |  | 391.7155
1501829 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 11.666 | 0 | NA | NA | 0.18767 | 1 | 110 | 2.1894 |  | 240.8335
1501829 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 12.8326 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 11.4943 |  | 896.5575
1501830 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501830 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501831 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501831 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501832 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.6003 | 0.75 | 78 | 1.2002 |  | 93.6175
1501832 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 19.6482 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 15.085 |  | 1176.6288
1501832 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 19.6482 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 1178.892
1501833 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501833 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501834 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501834 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501835 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.6003 | 0.75 | 78 | 1.2002 |  | 93.6175
1501835 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 17.7056 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 13.5935 |  | 1060.2965
1501835 | 300 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 17.7056 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 1062.336
1501836 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501836 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501837 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501837 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501838 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501838 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501839 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501839 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1501840 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501841 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501842 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501843 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501844 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501845 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501846 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501847 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501848 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 10.662 | 0 | NA | NA | 0.18767 | 1 | 110 | 2.001 |  | 220.1069
1501848 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 11.7282 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 10.5051 |  | 819.3979
1501849 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.266 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.23759 |  | 26.1354
1501849 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.3926 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.2474 |  | 97.2949
1501850 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501850 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501851 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501851 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501852 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501852 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1501853 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1501854 | 600 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501855 | 600 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501856 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchSTD | 16 | SchSTD | NA | LM | 3.652 | 0 | NA | NA | 0.58861 | 1 | 110 | 2.1496 |  | 236.457
1501856 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchSTD | 16 | SchSTD | NA | LM | 4.1998 | 0 | NA | NA | 3.7919 | 1 | 110 | 15.925 |  | 1751.7521
1501857 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501858 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501858 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501859 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchSTD | 16 | SchSTD | NA | LM | 1.943 | 0 | NA | NA | 0.58861 | 1 | 110 | 1.1437 |  | 125.8039
1501859 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchSTD | 16 | SchSTD | NA | LM | 2.2344 | 0 | NA | NA | 3.7919 | 1 | 110 | 8.4727 |  | 931.9973
1501860 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 2 | 32 | CS | ZL02 | 8.8313 | 1 | 110 | 17.6627 |  | 1942.8933
1501860 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501861 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501861 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501862 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501862 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501863 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchSTD | 16 | SchSTD | NA | LM | 1.824 | 0 | NA | NA | 0.58861 | 1 | 110 | 1.0736 |  | 118.099
1501863 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchSTD | 16 | SchSTD | NA | LM | 2.0976 | 0 | NA | NA | 3.7919 | 1 | 110 | 7.9538 |  | 874.9167
1501864 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501864 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501865 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501865 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchSTD | 16 | SchSTD | NA | LM | 17.595 | 0 | NA | NA | 0.58861 | 1 | 110 | 10.3566 |  | 1139.2279
1501865 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchSTD | 16 | SchSTD | NA | LM | 20.2342 | 0 | NA | NA | 3.7919 | 1 | 110 | 76.7253 |  | 8439.7803
1501866 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501866 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501867 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501867 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501868 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchSTD | 16 | SchSTD | NA | LM | 2.152 | 0 | NA | NA | 0.58861 | 1 | 110 | 1.2667 |  | 139.3361
1501868 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchSTD | 16 | SchSTD | NA | LM | 2.4748 | 0 | NA | NA | 3.7919 | 1 | 110 | 9.3841 |  | 1032.2482
1501869 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501869 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501870 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501870 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501871 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501871 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 SchSTD | 16 | SchSTD | NA | LM | 16.594 | 0 | NA | NA | 0.58861 | 1 | 110 | 9.7674 |  | 1074.4159
1501871 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Module | NA | 150-20-M-210 | Install Spools - NB 16 SchSTD | 16 | SchSTD | NA | LM | 19.0831 | 0 | NA | NA | 3.7919 | 1 | 110 | 72.3603 |  | 7959.6314
1501872 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501872 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1501873 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 8.8313 | 1 | 110 | 8.8313 |  | 971.4467
1501873 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 24 | CS | ZL02 | 17.7732 | 1 | 110 | 17.7732 |  | 1955.0483
1501874 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 24 | CS | ZL02 | 17.7732 | 1 | 110 | 17.7732 |  | 1955.0483
1501874 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1501875 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 24 | CS | ZL02 | 17.7732 | 1 | 110 | 17.7732 |  | 1955.0483
1501875 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1501876 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501876 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501877 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501877 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL02 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1501878 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | 20 | SchXST | NA | EA | 1 | 20 | CS | ZL02 | 13.6121 | 1 | 110 | 13.6121 |  | 1497.3292
1501878 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501879 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 SchXST | 20 | SchXST | NA | LM | 1.971 | 0 | NA | NA | 1.0279 | 1 | 110 | 2.0261 |  | 222.8671
1501879 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | NA | 150-20-M-210 | Install Spools - NB 20 SchXST | 20 | SchXST | NA | LM | 2.2666 | 0 | NA | NA | 6.6283 | 1 | 110 | 15.024 |  | 1652.638
1501880 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | 20 | SchXST | NA | EA | 1 | 20 | CS | ZL02 | 13.6121 | 1 | 110 | 13.6121 |  | 1497.3292
1501880 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | 20 | SchXST | NA | EA | 1 | 20 | CS | ZL02 | 13.6121 | 1 | 110 | 13.6121 |  | 1497.3292
1501881 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 SchXST | 24 | SchXST | NA | LM | 0.73 | 0 | NA | NA | 1.1644 | 1 | 110 | 0.85003 |  | 93.5035
1501881 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | NA | 150-20-M-210 | Install Spools - NB 24 SchXST | 24 | SchXST | NA | LM | 0.8395 | 0 | NA | NA | 7.4941 | 1 | 110 | 6.2913 |  | 692.0456
1501882 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 SchXST | 20 | SchXST | NA | LM | 0.443 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.45538 |  | 50.0914
1501882 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | NA | 150-20-M-210 | Install Spools - NB 20 SchXST | 20 | SchXST | NA | LM | 0.50945 | 0 | NA | NA | 6.6283 | 1 | 110 | 3.3768 |  | 371.4453
1501883 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | 20 | SchXST | NA | EA | 1 | 20 | CS | ZL02 | 13.6121 | 1 | 110 | 13.6121 |  | 1497.3292
1501883 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501884 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | 20 | SchXST | NA | EA | 1 | 20 | CS | ZL02 | 13.6121 | 1 | 110 | 13.6121 |  | 1497.3292
1501884 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501885 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | 20 | SchXST | NA | EA | 1 | 20 | CS | ZL02 | 13.6121 | 1 | 110 | 13.6121 |  | 1497.3292
1501885 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 2 | 48 | CS | ZL02 | 17.7732 | 1 | 110 | 35.5463 |  | 3910.0967
1501886 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 SchXST | 24 | SchXST | NA | LM | 1.769 | 0 | NA | NA | 1.1644 | 1 | 110 | 2.0599 |  | 226.5858
1501886 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | NA | 150-20-M-210 | Install Spools - NB 24 SchXST | 24 | SchXST | NA | LM | 2.0343 | 0 | NA | NA | 7.4941 | 1 | 110 | 15.2457 |  | 1677.0256
1501887 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501887 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 17.596 | 0 | NA | NA | 1.0279 | 1 | 110 | 18.0876 |  | 1989.6343
1501887 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 20.2354 | 0 | NA | NA | 6.6283 | 1 | 110 | 134.1258 |  | 14753.8402
1501888 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501888 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501889 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501889 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501890 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501890 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 17.596 | 0 | NA | NA | 1.0279 | 1 | 110 | 18.0876 |  | 1989.6343
1501890 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 20.2354 | 0 | NA | NA | 6.6283 | 1 | 110 | 134.1258 |  | 14753.8402
1501891 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501891 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501892 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501892 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501893 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.535 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.5779 |  | 173.5672
1501893 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.7652 | 0 | NA | NA | 6.6283 | 1 | 110 | 11.7006 |  | 1287.0621
1501894 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501894 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501895 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501895 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501896 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501896 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501897 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-30-M-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 1 | 110 | 15.47 |  | 1701.7
1501897 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 1 | 110 | 8.58 |  | 943.8
1501898 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501898 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501899 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.052 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.1652 |  | 458.1722
1501899 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.6598 | 0 | NA | NA | 6.6283 | 1 | 110 | 30.8864 |  | 3397.5086
1501900 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501900 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501901 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-30-M-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 1 | 110 | 15.47 |  | 1701.7
1501901 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 1 | 110 | 8.58 |  | 943.8
1501902 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501902 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501903 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.052 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.1652 |  | 458.1722
1501903 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.6598 | 0 | NA | NA | 6.6283 | 1 | 110 | 30.8864 |  | 3397.5086
1501904 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501904 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501905 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-30-M-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 1 | 110 | 15.47 |  | 1701.7
1501905 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 1 | 110 | 8.58 |  | 943.8
1501906 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501906 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501907 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.052 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.1652 |  | 458.1722
1501907 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.6598 | 0 | NA | NA | 6.6283 | 1 | 110 | 30.8864 |  | 3397.5086
1501908 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501909 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-30-M-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 1 | 110 | 1.69 |  | 185.9
1501909 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 1 | 110 | 1.17 |  | 128.7
1501910 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501910 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 1 | 110 | 0.585 |  | 64.35
1501911 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1501911 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501912 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 12.589 | 0 | NA | NA | 0.40947 | 1 | 110 | 5.1548 |  | 567.0283
1501912 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | NA | 150-20-M-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 14.4773 | 0 | NA | NA | 2.6274 | 1 | 110 | 38.0381 |  | 4184.1963
1501913 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1501913 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1501914 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.851 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.34846 |  | 38.3304
1501914 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | NA | 150-20-M-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.97865 | 0 | NA | NA | 2.6274 | 1 | 110 | 2.5713 |  | 282.8462
1501915 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1501915 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501916 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1501916 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 1 | 110 | 2.665 |  | 293.15
1501917 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1501917 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 2 | 48 | CS | ZL02 | 17.7732 | 1 | 110 | 35.5463 |  | 3910.0967
1501918 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 SchXST | 24 | SchXST | NA | LM | 7.455 | 0 | NA | NA | 1.1644 | 1 | 110 | 8.6808 |  | 954.8883
1501918 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | NA | 150-20-M-210 | Install Spools - NB 24 SchXST | 24 | SchXST | NA | LM | 8.5732 | 0 | NA | NA | 7.4941 | 1 | 110 | 64.2491 |  | 7067.3975
1501919 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 24 | CS | ZL02 | 17.7732 | 1 | 110 | 17.7732 |  | 1955.0483
1501919 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 24 | CS | ZL02 | 17.7732 | 1 | 110 | 17.7732 |  | 1955.0483
1501920 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 SchXST | 24 | SchXST | NA | LM | 0.738 | 0 | NA | NA | 1.1644 | 1 | 110 | 0.85935 |  | 94.5282
1501920 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | NA | 150-20-M-210 | Install Spools - NB 24 SchXST | 24 | SchXST | NA | LM | 0.8487 | 0 | NA | NA | 7.4941 | 1 | 110 | 6.3603 |  | 699.6297
1501921 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 24 | CS | ZL02 | 17.7732 | 1 | 110 | 17.7732 |  | 1955.0483
1501921 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 24 | CS | ZL02 | 17.7732 | 1 | 110 | 17.7732 |  | 1955.0483
1501922 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 SchXST | 24 | SchXST | NA | LM | 1.707 | 0 | NA | NA | 1.1644 | 1 | 110 | 1.9877 |  | 218.6444
1501922 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | NA | 150-20-M-210 | Install Spools - NB 24 SchXST | 24 | SchXST | NA | LM | 1.963 | 0 | NA | NA | 7.4941 | 1 | 110 | 14.7114 |  | 1618.2492
1501923 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1501923 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1501924 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-30-M-310 | Install valve - NB 24 CL600 | 24 | NA | CL600 | EA | 1 | 0 | NA | NA | 17.68 | 1 | 110 | 17.68 |  | 1944.8
1501924 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 1 | 0 | NA | NA | 10.27 | 1 | 110 | 10.27 |  | 1129.7
1501925 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 24 | CS | ZL02 | 17.7732 | 1 | 110 | 17.7732 |  | 1955.0483
1501925 | 500 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1501926 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 2.136 | 0 | NA | NA | 1.0279 | 1 | 110 | 2.1957 |  | 241.5241
1501926 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 2.4564 | 0 | NA | NA | 6.6283 | 1 | 110 | 16.2817 |  | 1790.9867
1501927 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501927 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501928 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1501928 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1501929 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.432 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.472 |  | 161.9207
1501929 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.6468 | 0 | NA | NA | 6.6283 | 1 | 110 | 10.9154 |  | 1200.699
1501930 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.432 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.472 |  | 161.9207
1501930 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.6468 | 0 | NA | NA | 6.6283 | 1 | 110 | 10.9154 |  | 1200.699
1501931 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 2.027 | 0 | NA | NA | 1.0279 | 1 | 110 | 2.0836 |  | 229.1992
1501931 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 2.331 | 0 | NA | NA | 6.6283 | 1 | 110 | 15.4508 |  | 1699.5928
1501932 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501932 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501933 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501933 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501934 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.6003 | 0.75 | 78 | 1.2002 |  | 93.6175
1501934 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 18.2809 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 14.0352 |  | 1094.7483
1501934 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 18.2809 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 1096.854
1501935 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501935 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501936 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501936 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501937 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501937 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501938 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501938 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501939 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501940 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501941 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501942 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501943 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501944 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501945 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501946 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501947 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.6003 | 0.75 | 78 | 1.2002 |  | 93.6175
1501947 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 16.5022 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 12.6696 |  | 988.2311
1501947 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 16.5022 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 990.132
1501948 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501949 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501950 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501951 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501952 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501953 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501953 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501954 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.726 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13625 |  | 14.9876
1501954 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7986 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.71532 |  | 55.7947
1501955 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501955 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501956 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501956 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501957 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.719 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13494 |  | 14.8431
1501957 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7909 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.70842 |  | 55.2567
1501958 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 10.004 | 0 | NA | NA | 0.18767 | 1 | 110 | 1.8775 |  | 206.5231
1501958 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 11.0044 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 9.8568 |  | 768.8292
1501959 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501959 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501960 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501960 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501961 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 16.192 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 12.4315 |  | 969.6549
1501961 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 16.192 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 971.52
1501962 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501962 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501963 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501963 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501964 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501965 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501966 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 13.9326 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 10.6968 |  | 834.3511
1501966 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 13.9326 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 835.956
1501967 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501967 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501968 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501968 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501969 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501970 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501971 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 11.029 | 0 | NA | NA | 0.18767 | 1 | 110 | 2.0698 |  | 227.6832
1501971 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 12.1319 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 10.8667 |  | 847.6026
1501972 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.769 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.51967 |  | 57.1634
1501972 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.0459 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.7283 |  | 212.8037
1501973 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501974 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501975 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501976 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501976 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501977 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501977 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501978 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 15.2482 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 11.7069 |  | 913.1356
1501978 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 15.2482 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 914.892
1501979 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501980 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501981 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501982 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501983 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.764 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14338 |  | 15.7721
1501983 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8404 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.75276 |  | 58.7151
1501984 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501985 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501985 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501986 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501986 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501987 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501987 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501988 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501988 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501989 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.6003 | 0.75 | 78 | 1.2002 |  | 93.6175
1501989 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 17.5582 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 13.4804 |  | 1051.4695
1501989 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 17.5582 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 1053.492
1501990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501990 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501991 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501991 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501992 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501993 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1501994 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501994 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501995 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501995 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501996 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | 2 | SchXST | NA | LM | 14.2934 | 0 | NA | NA | 1.0237 | 0.75 | 78 | 10.9738 |  | 855.9576
1501996 | 300 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-80-F-810 | Field Coating - NB 2 | 2 | NA | NA | LM | 14.2934 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 60 | 857.604
1501997 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.457 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.085767 |  | 9.4343
1501997 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5027 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.45027 |  | 35.1214
1501998 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501998 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1501999 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1501999 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502000 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.768 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.33181 |  | 36.4987
1502000 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.9448 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.742 |  | 135.8746
1502001 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 0.766 | 0 | NA | NA | 1.1644 | 1 | 110 | 0.89195 |  | 98.1146
1502001 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 0.8809 | 0 | NA | NA | 7.4941 | 1 | 110 | 6.6016 |  | 726.1739
1502002 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502002 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1502003 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502003 | 600 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502004 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 11.466 | 0 | NA | NA | 0.18767 | 1 | 110 | 2.1519 |  | 236.7047
1502004 | 600 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 12.6126 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 11.2973 |  | 881.187
1502005 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502005 | 600 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502006 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502006 | 600 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502007 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 6.771 | 0 | NA | NA | 1.0279 | 1 | 110 | 6.9602 |  | 765.618
1502007 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 7.7866 | 0 | NA | NA | 6.6283 | 1 | 110 | 51.6121 |  | 5677.3274
1502008 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.374 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.4962 |  | 494.5818
1502008 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 5.0301 | 0 | NA | NA | 6.6283 | 1 | 110 | 33.3409 |  | 3667.4981
1502009 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502009 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502010 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502010 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502011 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502011 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 1 | 110 | 3.38 |  | 371.8
1502012 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 1.094 | 0 | NA | NA | 1.1644 | 1 | 110 | 1.2739 |  | 140.1271
1502012 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 1.2581 | 0 | NA | NA | 7.4941 | 1 | 110 | 9.4284 |  | 1037.1204
1502013 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502013 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502014 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502014 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502015 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502015 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502016 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502016 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502017 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 13.313 | 0 | NA | NA | 1.1644 | 1 | 110 | 15.502 |  | 1705.2217
1502017 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 15.3099 | 0 | NA | NA | 7.4941 | 1 | 110 | 114.7348 |  | 12620.8267
1502018 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502018 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502019 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502019 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502020 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502020 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502021 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502021 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502022 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 13.313 | 0 | NA | NA | 1.1644 | 1 | 110 | 15.502 |  | 1705.2217
1502022 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 15.3099 | 0 | NA | NA | 7.4941 | 1 | 110 | 114.7348 |  | 12620.8267
1502023 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502023 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502024 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502024 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502025 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502025 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502026 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502026 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502027 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502027 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 21.021 | 0 | NA | NA | 1.1644 | 1 | 110 | 24.4774 |  | 2692.516
1502027 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 24.1741 | 0 | NA | NA | 7.4941 | 1 | 110 | 181.1643 |  | 19928.0701
1502028 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | Pipe to Pipe - Shop Fab | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502028 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 24 Sch80 | 24 | Sch80 | NA | LM | 19.021 | 0 | NA | NA | 1.1644 | 1 | 110 | 22.1486 |  | 2436.342
1502028 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | NA | 150-20-M-210 | Install Spools - NB 24 Sch80 | 24 | Sch80 | NA | LM | 21.8742 | 0 | NA | NA | 7.4941 | 1 | 110 | 163.9278 |  | 18032.0547
1502029 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502030 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502030 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502031 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.65 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.66816 |  | 73.4975
1502031 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.7475 | 0 | NA | NA | 6.6283 | 1 | 110 | 4.9546 |  | 545.01
1502032 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502032 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502033 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502033 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502034 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502035 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 33.1998 | 1 | 110 | 33.1998 |  | 3651.9817
1502035 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | 24 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 10.27 | 1 | 110 | 5.135 |  | 564.85
1502036 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.65 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.66816 |  | 73.4975
1502036 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.7475 | 0 | NA | NA | 6.6283 | 1 | 110 | 4.9546 |  | 545.01
1502037 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502037 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502038 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502038 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502039 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.205 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.3225 |  | 475.4724
1502039 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.8357 | 0 | NA | NA | 6.6283 | 1 | 110 | 32.0527 |  | 3525.7955
1502040 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.205 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.3225 |  | 475.4724
1502040 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.8357 | 0 | NA | NA | 6.6283 | 1 | 110 | 32.0527 |  | 3525.7955
1502041 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.205 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.3225 |  | 475.4724
1502041 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.8357 | 0 | NA | NA | 6.6283 | 1 | 110 | 32.0527 |  | 3525.7955
1502042 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.47 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.48313 |  | 53.1444
1502042 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | NA | 150-20-M-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.5405 | 0 | NA | NA | 6.6283 | 1 | 110 | 3.5826 |  | 394.0842
1502043 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502043 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502044 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502044 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502045 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502045 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502046 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502046 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502047 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502047 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502048 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502048 | 500 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Module | FLG | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 1 | 110 | 4.29 |  | 471.9
1502049 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502049 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502050 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502050 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502051 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502051 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502052 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.493 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.092523 |  | 10.1775
1502052 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5423 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.48575 |  | 37.8881
1502053 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502053 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502054 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502055 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502055 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502055 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502056 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502056 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502057 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502057 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502058 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502059 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502059 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502059 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502060 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502060 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502061 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502061 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502062 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502063 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502063 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502063 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502064 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502064 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502065 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502065 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502066 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502067 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502067 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502067 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502068 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502068 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502069 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502069 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502070 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502071 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502071 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502071 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502072 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502072 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502073 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502073 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502074 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502075 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502075 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502075 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502076 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502076 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502077 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502077 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502078 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502078 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502079 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502079 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502080 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502081 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502081 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502081 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502082 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502082 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502083 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | 3 | Sch160 | NA | EA | 1 | 3 | CS | ZL01 | 2.21 | 1 | 110 | 2.21 |  | 243.1
1502083 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502084 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1502084 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1502085 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1502085 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | 3 | NA | CL3000 | EA | 1 | 3 | CS | ZL01 | 7.67 | 1 | 110 | 7.67 |  | 843.7
1502086 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502087 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502087 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502087 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502088 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502088 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502089 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | 3 | Sch160 | NA | EA | 1 | 3 | CS | ZL01 | 2.21 | 1 | 110 | 2.21 |  | 243.1
1502089 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502090 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1502090 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1502091 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1502091 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | 3 | NA | CL3000 | EA | 1 | 3 | CS | ZL01 | 7.67 | 1 | 110 | 7.67 |  | 843.7
1502092 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502093 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502093 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502093 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502094 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502094 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502095 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | 3 | Sch160 | NA | EA | 1 | 3 | CS | ZL01 | 2.21 | 1 | 110 | 2.21 |  | 243.1
1502095 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502096 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1502096 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1502097 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1502097 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | 3 | NA | CL3000 | EA | 1 | 3 | CS | ZL01 | 7.67 | 1 | 110 | 7.67 |  | 843.7
1502098 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502098 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3039 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502099 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502099 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502100 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1502101 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1502102 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1502103 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.148 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.026513 |  | 2.9164
1502103 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1554 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.13571 |  | 10.5857
1502104 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502104 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502105 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.145 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.025976 |  | 2.8573
1502105 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.15225 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.13296 |  | 10.3711
1502106 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502106 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502107 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.148 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.026513 |  | 2.9164
1502107 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1554 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.13571 |  | 10.5857
1502108 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502108 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502109 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.148 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.026513 |  | 2.9164
1502109 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1554 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.13571 |  | 10.5857
1502110 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502110 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502111 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502111 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502111 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502112 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502112 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502112 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502113 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502113 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502114 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502114 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502115 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502116 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502116 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502116 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502117 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502117 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502118 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502118 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502119 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502120 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502120 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502120 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502121 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502121 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502121 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502122 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502122 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502123 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502123 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502124 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3053 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502125 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502125 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502125 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502126 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502126 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502127 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502127 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502128 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502129 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502129 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502130 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO2047 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502130 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO2047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502131 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502131 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502131 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502132 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502132 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502133 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502133 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502133 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502134 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.487 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.5285 |  | 168.1397
1502134 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.7101 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 8.501 |  | 663.079
1502135 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.487 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.5285 |  | 168.1397
1502135 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.7101 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 8.501 |  | 663.079
1502136 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502136 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502137 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502138 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502138 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502139 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502139 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502140 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502140 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1502141 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502141 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502142 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502143 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502143 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502144 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502144 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502145 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502145 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1502146 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502146 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502147 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502148 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502148 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502149 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502149 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502150 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502150 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1502151 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502151 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502152 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502152 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502153 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502153 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502154 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502154 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502155 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502155 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502156 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.458 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.085954 |  | 9.455
1502156 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5038 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.45126 |  | 35.1983
1502157 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502157 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502158 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502158 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502159 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1502159 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1502160 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502160 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502161 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.102 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.018273 |  | 2.01
1502161 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1071 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.093533 |  | 7.2955
1502162 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502163 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502163 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502163 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502164 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502164 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502165 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502165 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502166 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.102 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.018273 |  | 2.01
1502166 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1071 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.093533 |  | 7.2955
1502167 | 400 | Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502167 | 400 | Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502168 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502168 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502169 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.323 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.057863 |  | 6.3649
1502169 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.33915 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.29619 |  | 23.1025
1502170 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.323 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.057863 |  | 6.3649
1502170 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.33915 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.29619 |  | 23.1025
1502171 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1502171 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1502172 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502173 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502173 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502173 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502174 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502174 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502175 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502175 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502176 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.968 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18167 |  | 19.9834
1502176 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0648 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.95376 |  | 74.3929
1502177 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502177 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502178 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502178 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502179 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502179 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502180 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502180 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502181 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502181 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502182 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502182 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502182 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502183 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502183 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502184 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502184 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502185 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502185 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502186 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502186 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502187 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502187 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502188 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502188 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502189 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502189 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502190 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502190 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502191 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502191 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502192 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502192 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502193 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502193 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502194 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502194 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502195 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502195 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502196 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502196 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502196 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502197 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.624 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11711 |  | 12.8819
1502197 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6864 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.61482 |  | 47.9558
1502198 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502198 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502199 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502199 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502200 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1502201 | 400 | Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502201 | 400 | Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502202 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502202 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502203 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502203 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502204 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502204 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502205 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502205 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502205 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502206 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502206 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502207 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502207 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502208 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502208 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502209 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502209 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502210 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.624 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11711 |  | 12.8819
1502210 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6864 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.61482 |  | 47.9558
1502211 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502211 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502212 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.458 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.085954 |  | 9.455
1502212 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5038 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.45126 |  | 35.1983
1502213 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502213 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502214 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502214 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502215 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1502215 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1502216 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502216 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502217 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.102 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.018273 |  | 2.01
1502217 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1071 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.093533 |  | 7.2955
1502218 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502219 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502219 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502219 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502220 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502220 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502221 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502221 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502222 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.102 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.018273 |  | 2.01
1502222 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1071 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.093533 |  | 7.2955
1502223 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502223 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502223 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502224 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502224 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502225 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502225 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502226 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502226 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502227 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502227 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502228 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502228 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502229 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502229 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502230 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502230 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502231 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502231 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502232 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502232 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502233 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502233 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502234 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502234 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502235 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502235 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502236 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502236 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502237 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502237 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502238 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502238 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502239 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502239 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502240 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502240 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502241 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502241 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502242 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502242 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502243 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502243 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502244 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502244 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502245 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502245 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502246 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502246 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502247 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502247 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502248 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502248 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502249 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502249 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502250 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502250 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502251 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502251 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502252 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502252 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502253 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502253 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502254 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502254 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502255 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502255 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502256 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502256 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502257 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502257 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502258 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502258 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502259 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502259 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502260 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502260 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502261 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502261 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502262 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502262 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502263 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502263 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502264 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502264 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502265 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502265 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502266 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502266 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502267 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502267 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502268 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502268 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502269 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502269 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502270 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502270 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502271 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502271 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502272 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502272 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502273 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502273 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502274 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502274 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502275 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502275 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502276 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502276 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502277 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502277 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502278 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502278 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502279 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502279 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502280 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502280 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502281 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502281 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502282 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502282 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502283 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502283 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502284 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.419 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.96234 |  | 105.8575
1502284 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.6319 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 5.3351 |  | 416.1372
1502285 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502285 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502286 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502286 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502287 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502287 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502288 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502288 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502289 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502289 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502290 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502290 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502291 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.624 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11711 |  | 12.8819
1502291 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6864 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.61482 |  | 47.9558
1502292 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502292 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502293 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.458 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.085954 |  | 9.455
1502293 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5038 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.45126 |  | 35.1983
1502294 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502294 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502295 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502295 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502296 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1502296 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1502297 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502297 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502298 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.102 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.018273 |  | 2.01
1502298 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1071 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.093533 |  | 7.2955
1502299 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502300 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502300 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502300 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502301 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502301 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502302 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502302 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502303 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.102 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.018273 |  | 2.01
1502303 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1071 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.093533 |  | 7.2955
1502304 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502304 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502304 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502305 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502305 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502306 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502306 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502307 | 400 | Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502307 | 400 | Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502308 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502308 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502309 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502309 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502310 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502310 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502311 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502311 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1502311 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1502312 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502312 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502313 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502313 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502314 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502315 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502315 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502315 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502316 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502316 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502317 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502317 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502318 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.464 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.083122 |  | 9.1434
1502318 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.4872 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.42548 |  | 33.1876
1502319 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502319 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502319 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502320 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502320 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502321 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502322 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502322 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502322 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502323 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502323 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502324 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502324 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502325 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.464 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.083122 |  | 9.1434
1502325 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.4872 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.42548 |  | 33.1876
1502326 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502326 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502326 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502327 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502327 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502328 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502329 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502329 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502329 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502330 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502330 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502331 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502331 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502332 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.464 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.083122 |  | 9.1434
1502332 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.4872 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.42548 |  | 33.1876
1502333 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502333 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502333 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502334 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502334 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502335 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502336 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502336 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502336 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502337 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1