1502381 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.24 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.23271 |  | 25.5986
1502381 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.364 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.2218 |  | 95.2967
1502382 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502382 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502383 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502383 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502384 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.272 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.048727 |  | 5.3599
1502384 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2856 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.24942 |  | 19.4548
1502385 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502385 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502386 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502386 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502387 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502387 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502388 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502389 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502389 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502389 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL800 | 1 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502390 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502390 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502390 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502391 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502391 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502392 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.108 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.019347 |  | 2.1282
1502392 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1134 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.099035 |  | 7.7247
1502393 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502393 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502394 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502394 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502394 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL800 | 1 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502395 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502395 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502396 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.121 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.021676 |  | 2.3844
1502396 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.12705 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.11096 |  | 8.6545
1502397 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502397 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502398 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502398 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502399 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502399 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502400 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502400 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502401 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.701 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13156 |  | 14.4715
1502401 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7711 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.69068 |  | 53.8734
1502402 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.338 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.06055 |  | 6.6605
1502402 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.3549 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.30994 |  | 24.1754
1502403 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502403 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502404 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502404 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502405 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.544 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10209 |  | 11.2304
1502405 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5984 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.53599 |  | 41.8076
1502406 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 1.399 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.25062 |  | 27.5683
1502406 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 1.4689 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.2829 |  | 100.0634
1502407 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502407 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502408 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502408 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502409 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502409 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502410 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502410 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502411 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502411 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502412 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502412 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502413 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502413 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502414 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.184 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.034532 |  | 3.7985
1502414 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2024 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.18129 |  | 14.1408
1502415 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502415 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502416 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502416 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502417 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.24 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.23271 |  | 25.5986
1502417 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.364 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.2218 |  | 95.2967
1502418 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502418 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502419 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502419 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502420 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.272 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.048727 |  | 5.3599
1502420 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2856 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.24942 |  | 19.4548
1502421 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502421 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502422 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502422 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502423 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502423 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502424 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502425 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502425 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502425 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL800 | 1 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502426 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502426 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502426 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502427 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502427 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502428 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.108 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.019347 |  | 2.1282
1502428 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1134 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.099035 |  | 7.7247
1502429 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502429 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502430 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502430 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502430 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL800 | 1 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502431 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502431 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502432 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.121 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.021676 |  | 2.3844
1502432 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.12705 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.11096 |  | 8.6545
1502433 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502433 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502434 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502434 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502435 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502435 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502436 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502436 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502437 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.701 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13156 |  | 14.4715
1502437 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7711 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.69068 |  | 53.8734
1502438 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.338 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.06055 |  | 6.6605
1502438 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.3549 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.30994 |  | 24.1754
1502439 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502439 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502440 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502440 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502441 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.544 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10209 |  | 11.2304
1502441 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5984 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.53599 |  | 41.8076
1502442 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 1.399 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.25062 |  | 27.5683
1502442 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 1.4689 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.2829 |  | 100.0634
1502443 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502443 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502444 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502444 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502445 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502445 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502446 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502446 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502447 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502447 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502448 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502448 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502449 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502449 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502450 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.184 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.034532 |  | 3.7985
1502450 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2024 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.18129 |  | 14.1408
1502451 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502451 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502452 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502452 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502453 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.24 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.23271 |  | 25.5986
1502453 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.364 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.2218 |  | 95.2967
1502454 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502454 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502455 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502455 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502456 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502456 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502457 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502457 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502458 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502458 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502459 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.272 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.048727 |  | 5.3599
1502459 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2856 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.24942 |  | 19.4548
1502460 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502460 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502461 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502461 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502462 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502462 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502463 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502463 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502464 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502464 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502465 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502465 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502466 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502466 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502467 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 14 | 14 | NA | NA | EA | 1 | 0 | NA | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
1502468 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 14 | 14 | NA | NA | EA | 1 | 0 | NA | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
1502469 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502469 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502470 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502470 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502471 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.419 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.96234 |  | 105.8575
1502471 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.6319 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 5.3351 |  | 416.1372
1502472 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502472 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502473 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502473 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502474 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.275 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.86468 |  | 95.1151
1502474 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.4662 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 4.7937 |  | 373.9077
1502475 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502475 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502476 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502476 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502477 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502477 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502478 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502478 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502479 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502479 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502480 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.275 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.86468 |  | 95.1151
1502480 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.4662 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 4.7937 |  | 373.9077
1502481 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502481 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502482 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 14 | 14 | NA | NA | EA | 1 | 0 | NA | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
1502483 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502483 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502484 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.419 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.96234 |  | 105.8575
1502484 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.6319 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 5.3351 |  | 416.1372
1502485 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502485 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502486 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502486 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502487 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502487 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502488 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.275 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.86468 |  | 95.1151
1502488 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.4662 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 4.7937 |  | 373.9077
1502489 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502489 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502490 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1502490 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502491 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502491 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502492 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502492 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502493 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502493 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502494 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502494 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502495 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502496 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502496 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502496 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502497 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502497 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502498 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502498 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502499 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502499 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502500 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502500 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502501 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502502 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502502 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502502 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502503 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502503 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502504 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502504 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502505 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502505 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502506 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502506 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502507 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502508 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502509 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502510 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502511 | 600 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502512 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502513 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1502514 | 600 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502515 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502516 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502517 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502518 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1502519 | 600 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502520 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502521 | 400 | Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.257 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
1502521 | 600 | Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2827 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
1502522 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502523 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502524 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
1502525 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502526 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502527 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502528 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502529 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502530 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502531 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502532 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1502533 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
1502534 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
1502535 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 14 | 14 | NA | NA | EA | 1 | 0 | NA | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
1502536 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 14 | 14 | NA | NA | EA | 1 | 0 | NA | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
1502537 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 14 | 14 | NA | NA | EA | 1 | 0 | NA | NA | 2.0101 | 0.75 | 78 | 1.5076 |  | 117.5934
1502538 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
1502539 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1502540 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1502541 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1502542 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
1502543 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 20 | 20 | NA | NA | EA | 1 | 0 | NA | NA | 2.327 | 0.75 | 78 | 1.7452 |  | 136.1291
1502544 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1502545 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1502546 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1502547 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502547 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502548 | 400 | Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.257 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
1502548 | 600 | Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2827 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
1502549 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.136 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.40087 |  | 44.0957
1502549 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.3496 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.1046 |  | 164.1562
1502550 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.511 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.47125 |  | 51.8372
1502550 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.7621 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.474 |  | 192.9758
1502551 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502551 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502552 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.144 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.027025 |  | 2.9727
1502552 | 600 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1584 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.14188 |  | 11.0667
1502553 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502553 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502554 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502554 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502555 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502555 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502556 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502556 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502557 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502557 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502558 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502558 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502559 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502559 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502560 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502560 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502561 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502561 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502562 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502562 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502563 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502563 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502564 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502564 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502565 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502565 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502566 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502566 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502567 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502567 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502568 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502568 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502569 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502569 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502570 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502570 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502571 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502571 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502572 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502572 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502573 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502573 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502574 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502574 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502575 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502575 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502576 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502576 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502576 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502577 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502577 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502577 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502578 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502578 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502579 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502579 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502580 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.109 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.019527 |  | 2.1479
1502580 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.11445 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.099951 |  | 7.7962
1502581 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502581 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502582 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502582 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502583 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502583 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502584 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502584 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502585 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502585 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502586 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502586 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502587 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | NA | 150-30-F-310 | Install Inlines - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 0.75 | 78 | 8.58 |  | 669.24
1502587 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
1502588 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502588 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502589 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | NA | 150-30-F-310 | Install Inlines - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 0.75 | 78 | 8.58 |  | 669.24
1502589 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
1502590 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502590 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502591 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | NA | 150-30-F-310 | Install Inlines - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 0.75 | 78 | 8.58 |  | 669.24
1502591 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
1502592 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.53 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.099467 |  | 10.9413
1502592 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.583 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.5222 |  | 40.7317
1502593 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.53 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.099467 |  | 10.9413
1502593 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.583 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.5222 |  | 40.7317
1502594 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502594 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502595 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502595 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502596 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.075 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.85285 |  | 93.8131
1502596 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.2362 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 4.7338 |  | 369.2376
1502597 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.418 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.26612 |  | 29.2733
1502597 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.5598 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.3971 |  | 108.9764
1502598 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502598 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502599 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502599 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502600 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.075 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.85285 |  | 93.8131
1502600 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.2362 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 4.7338 |  | 369.2376
1502601 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.418 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.26612 |  | 29.2733
1502601 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.5598 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.3971 |  | 108.9764
1502602 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502602 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502603 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502603 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502604 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.075 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.85285 |  | 93.8131
1502604 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.2362 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 4.7338 |  | 369.2376
1502605 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.418 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.26612 |  | 29.2733
1502605 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.5598 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.3971 |  | 108.9764
1502606 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502606 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502607 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502607 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502608 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.157 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.029465 |  | 3.2411
1502608 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1727 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.15469 |  | 12.0658
1502609 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502609 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502610 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1502611 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.716 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13437 |  | 14.7811
1502611 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7876 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.70546 |  | 55.0262
1502612 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.716 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13437 |  | 14.7811
1502612 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7876 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.70546 |  | 55.0262
1502613 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502613 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502614 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502614 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502615 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502615 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502616 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502616 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502617 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502617 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502618 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502618 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502619 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502619 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502620 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502620 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502620 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1502621 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502621 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502622 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502622 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502623 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502623 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502624 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502624 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502625 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502625 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502626 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502626 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502627 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502627 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502628 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502628 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502629 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502629 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1502630 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.911 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.54632 |  | 60.0948
1502630 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.2021 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.8682 |  | 223.7167
1502631 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502631 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502632 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502632 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502633 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.466 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.087456 |  | 9.6201
1502633 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5126 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.45914 |  | 35.8131
1502634 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1502634 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502635 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.673 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.50165 |  | 55.1816
1502635 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.9403 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.6337 |  | 205.4259
1502636 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.448 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.084078 |  | 9.2485
1502636 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4928 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.44141 |  | 34.4298
1502637 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.377 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.070753 |  | 7.7828
1502637 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4147 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.37145 |  | 28.9733
1502638 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502638 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502639 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502639 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502640 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502640 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502641 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.673 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.50165 |  | 55.1816
1502641 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.9403 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.6337 |  | 205.4259
1502642 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.278 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.052173 |  | 5.739
1502642 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3058 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.27391 |  | 21.3649
1502643 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.255 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.047857 |  | 5.2642
1502643 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2805 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25125 |  | 19.5973
1502644 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502644 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502645 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502645 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502646 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502646 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502647 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.673 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.50165 |  | 55.1816
1502647 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.9403 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.6337 |  | 205.4259
1502648 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.34 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.063809 |  | 7.019
1502648 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.374 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.335 |  | 26.1297
1502649 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502649 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502650 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502650 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502651 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.54 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10134 |  | 11.1478
1502651 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.594 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.53205 |  | 41.5002
1502652 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502652 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502653 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502653 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502654 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502654 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502655 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | NA | 150-30-F-310 | Install Blind - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502656 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | NA | 150-30-F-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502656 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 0.75 | 78 | 6.435 |  | 501.93
1502657 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502657 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502658 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.1126 |  | 12.3864
1502658 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.66 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.59117 |  | 46.1113
1502659 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502659 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502660 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502660 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502661 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-30-F-310 | Install Blind - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502662 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-30-F-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502662 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 0.75 | 78 | 6.435 |  | 501.93
1502663 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502663 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502664 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502664 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502665 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502665 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502666 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | NA | 150-30-F-310 | Install Blind - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502667 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | NA | 150-30-F-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502667 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 0.75 | 78 | 6.435 |  | 501.93
1502668 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502668 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502669 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.1126 |  | 12.3864
1502669 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.66 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.59117 |  | 46.1113
1502670 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502670 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502671 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502671 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502672 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-30-F-310 | Install Blind - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502673 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-30-F-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502673 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 0.75 | 78 | 6.435 |  | 501.93
1502674 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502674 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502675 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502675 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502676 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502676 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502677 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | NA | 150-30-F-310 | Install Blind - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502678 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | NA | 150-30-F-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502678 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 0.75 | 78 | 6.435 |  | 501.93
1502679 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.8 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.82235 |  | 90.4585
1502679 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.92 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 4.5735 |  | 356.7338
1502680 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.1126 |  | 12.3864
1502680 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.66 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.59117 |  | 46.1113
1502681 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502681 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502682 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502682 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502683 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-30-F-310 | Install Blind - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502684 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-30-F-310 | Install valve - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 15.47 | 0.75 | 78 | 11.6025 |  | 904.995
1502684 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.58 | 0.75 | 78 | 6.435 |  | 501.93
1502685 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502685 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502686 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.673 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.50165 |  | 55.1816
1502686 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.9403 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.6337 |  | 205.4259
1502687 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502687 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502688 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502688 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502689 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502689 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502690 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | NA | 150-30-F-310 | Install Inlines - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 0.75 | 78 | 8.58 |  | 669.24
1502690 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
1502691 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502691 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502692 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502692 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502693 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | NA | 150-30-F-310 | Install Inlines - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 0.75 | 78 | 8.58 |  | 669.24
1502693 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
1502694 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502694 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502695 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502695 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502696 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | NA | 150-30-F-310 | Install Inlines - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 11.44 | 0.75 | 78 | 8.58 |  | 669.24
1502696 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.76 | 0.75 | 78 | 5.07 |  | 395.46
1502697 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502697 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502698 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.266 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.42527 |  | 46.7794
1502698 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.4926 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.2327 |  | 174.147
1502699 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502699 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502700 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502700 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502701 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.866 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.53787 |  | 59.1659
1502701 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.1526 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.8238 |  | 220.2583
1502702 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502702 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502703 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502703 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502704 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.866 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.53787 |  | 59.1659
1502704 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.1526 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.8238 |  | 220.2583
1502705 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 4.564 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.85654 |  | 94.2195
1502705 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 5.0204 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 4.4968 |  | 350.7533
1502706 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502706 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502707 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502707 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502708 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.736 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13813 |  | 15.194
1502708 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8096 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.72517 |  | 56.5632
1502709 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502709 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502710 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502710 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502711 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.126 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.58667 |  | 64.5333
1502711 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.4386 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 3.08 |  | 240.2399
1502712 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.712 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13362 |  | 14.6986
1502712 | 600 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7832 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.70152 |  | 54.7187
1502713 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502713 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502714 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502714 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502715 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.136 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.40087 |  | 44.0957
1502715 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.3496 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.1046 |  | 164.1562
1502716 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502716 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502717 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502717 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502718 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502718 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502719 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502719 | 600 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502720 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502720 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502721 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502721 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP01 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1502722 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.736 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13813 |  | 15.194
1502722 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8096 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.72517 |  | 56.5632
1502723 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502723 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502724 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502724 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502725 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.126 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.58667 |  | 64.5333
1502725 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.4386 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 3.08 |  | 240.2399
1502726 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.712 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13362 |  | 14.6986
1502726 | 600 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7832 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.70152 |  | 54.7187
1502727 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.8 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.71316 |  | 78.4474
1502727 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 4.18 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 3.7441 |  | 292.0383
1502728 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.712 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13362 |  | 14.6986
1502728 | 600 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7832 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.70152 |  | 54.7187
1502729 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | NA | ZL01 | 0.429 | 1 | 110 | 0.429 |  | 47.19
1502729 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502730 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502730 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502731 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502731 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502732 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | NA | ZL01 | 0.429 | 1 | 110 | 0.429 |  | 47.19
1502732 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502733 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502733 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502734 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502734 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502735 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | NA | ZL01 | 0.429 | 1 | 110 | 0.429 |  | 47.19
1502735 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502736 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502736 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502737 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502737 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502738 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502738 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502739 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502739 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502740 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502740 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502741 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502741 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502742 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | NA | ZL01 | 0.429 | 1 | 110 | 0.429 |  | 47.19
1502742 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502743 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502743 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502744 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502744 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502745 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502745 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502746 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502746 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502747 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.32 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.3569 |  | 149.2565
1502747 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.518 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 7.5463 |  | 588.6108
1502748 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.32 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.3569 |  | 149.2565
1502748 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.518 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 7.5463 |  | 588.6108
1502749 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.538 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.581 |  | 173.9064
1502749 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.7687 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 8.7926 |  | 685.8208
1502750 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 5.515 | 0 | NA | NA | 1.0279 | 1 | 110 | 5.6691 |  | 623.5982
1502750 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 6.3422 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 31.5286 |  | 2459.2338
1502751 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.408 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.5311 |  | 498.4262
1502751 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 5.0692 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 25.2 |  | 1965.6034
1502752 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502752 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502752 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL800 | 1 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502753 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502753 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502753 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502754 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502754 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502755 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.108 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.019347 |  | 2.1282
1502755 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1134 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.099035 |  | 7.7247
1502756 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502756 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502757 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502757 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502758 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502758 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP01 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1502759 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.655 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.3106 |  | 34.1659
1502759 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.8205 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.6306 |  | 127.1904
1502760 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502760 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502761 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502761 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502762 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502762 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502763 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502763 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502763 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502764 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502764 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502765 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502765 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502766 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.114 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.020422 |  | 2.2464
1502766 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1197 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.10454 |  | 8.1538
1502767 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502767 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502768 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502768 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502769 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502769 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | 1 | CL800 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502769 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL800 | 1 | NA | CL800 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502770 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502770 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502771 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502772 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502772 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502772 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502773 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502773 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502774 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.121 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.021676 |  | 2.3844
1502774 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.12705 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.11096 |  | 8.6545
1502775 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502775 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502776 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502776 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502777 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502777 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502778 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502778 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502779 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502779 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502780 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502780 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502781 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502781 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502782 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502782 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502783 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.257 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
1502783 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2827 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
1502784 | 400 | Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.257 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
1502784 | 600 | Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2827 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
1502785 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502785 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502786 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502786 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502787 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502787 | 600 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502788 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502788 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502789 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502789 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502790 | 400 | Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502790 | 600 | Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502791 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.8 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.82235 |  | 90.4585
1502791 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.92 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 4.5735 |  | 356.7338
1502792 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.884 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.70132 |  | 77.1449
1502792 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.0166 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 3.8927 |  | 303.6335
1502793 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502793 | 600 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502794 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.837 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15708 |  | 17.2791
1502794 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9207 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.82468 |  | 64.3253
1502795 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502796 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502796 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502797 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.156 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.029277 |  | 3.2205
1502797 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1716 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.1537 |  | 11.9889
1502798 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502798 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502799 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502799 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502800 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502800 | 600 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502801 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502801 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502801 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502802 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502802 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502802 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502803 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502803 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502804 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502804 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502805 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502805 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502806 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502806 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502807 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502807 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502808 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502808 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502809 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502809 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502809 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1502810 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502810 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502811 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502811 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502812 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502812 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502813 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502813 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502814 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502814 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502815 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502815 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502816 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502816 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502817 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502817 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502818 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502818 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502819 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.617 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.48949 |  | 53.8444
1502819 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.70955 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 2.717 |  | 211.9252
1502820 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.658 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.67638 |  | 74.4021
1502820 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.7567 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 3.7617 |  | 293.4136
1502821 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502821 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502822 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502822 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502823 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502823 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502824 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502824 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502825 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502825 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502826 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502826 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502827 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.8 | 0 | NA | NA | 0.67818 | 1 | 110 | 1.2207 |  | 134.2802
1502827 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 2.07 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 6.7676 |  | 527.8696
1502828 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502828 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502829 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 0.85 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.57646 |  | 63.4101
1502829 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 0.9775 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 3.1958 |  | 249.2718
1502830 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502830 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502831 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502831 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502832 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.228 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.040845 |  | 4.4929
1502832 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2394 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.20907 |  | 16.3077
1502833 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.22 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.039411 |  | 4.3353
1502833 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.231 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.20174 |  | 15.7355
1502834 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502834 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502835 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502835 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502836 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502836 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502837 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502837 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502838 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502838 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502839 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502839 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502840 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502840 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502841 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502841 | 600 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502842 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.144 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.027025 |  | 2.9727
1502842 | 600 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1584 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.14188 |  | 11.0667
1502843 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502843 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502844 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502844 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502845 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | NA | ZL01 | 0.429 | 1 | 110 | 0.429 |  | 47.19
1502845 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502846 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502846 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502847 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502847 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502848 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502848 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502849 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502849 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502850 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.32 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.3569 |  | 149.2565
1502850 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.518 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 7.5463 |  | 588.6108
1502851 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.32 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.3569 |  | 149.2565
1502851 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.518 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 7.5463 |  | 588.6108
1502852 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.538 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.581 |  | 173.9064
1502852 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.7687 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 8.7926 |  | 685.8208
1502853 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 5.515 | 0 | NA | NA | 1.0279 | 1 | 110 | 5.6691 |  | 623.5982
1502853 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 6.3422 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 31.5286 |  | 2459.2338
1502854 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.408 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.5311 |  | 498.4262
1502854 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 5.0692 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 25.2 |  | 1965.6034
1502855 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1502856 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1502857 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502857 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502858 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502858 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP01 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1502859 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502859 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502860 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502860 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP01 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1502861 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.656 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.31079 |  | 34.1866
1502861 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.8216 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.6316 |  | 127.2672
1502862 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502862 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502863 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502863 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502864 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502864 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502865 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502865 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502865 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502866 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502866 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502867 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502867 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502868 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.114 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.020422 |  | 2.2464
1502868 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1197 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.10454 |  | 8.1538
1502869 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502869 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502870 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502870 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502871 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502871 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502872 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502872 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502873 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502873 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502874 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502874 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502875 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.257 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
1502875 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2827 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
1502876 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502876 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502877 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502877 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502878 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502878 | 600 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502879 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502879 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502880 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502880 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502881 | 400 | Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502881 | 600 | Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502882 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.8 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.82235 |  | 90.4585
1502882 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.92 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 4.5735 |  | 356.7338
1502883 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.884 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.70132 |  | 77.1449
1502883 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.0166 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 3.8927 |  | 303.6335
1502884 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502884 | 600 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502885 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.837 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15708 |  | 17.2791
1502885 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9207 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.82468 |  | 64.3253
1502886 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502887 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502887 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502888 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.156 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.029277 |  | 3.2205
1502888 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1716 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.1537 |  | 11.9889
1502889 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502889 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502890 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502890 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502891 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502891 | 600 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502892 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502892 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502892 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502893 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502893 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502893 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502894 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502894 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502895 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502895 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502896 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502896 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502897 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502897 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502898 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502898 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502899 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502899 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502900 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502900 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502900 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1502901 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502901 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502902 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502902 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502903 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502903 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502904 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502904 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502905 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502905 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502906 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502906 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502907 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502907 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502908 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502908 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502909 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502909 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502910 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.617 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.48949 |  | 53.8444
1502910 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.70955 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 2.717 |  | 211.9252
1502911 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.658 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.67638 |  | 74.4021
1502911 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.7567 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 3.7617 |  | 293.4136
1502912 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502912 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502913 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502913 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502914 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502914 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502915 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1502915 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1502916 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502916 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502917 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502917 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502918 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.8 | 0 | NA | NA | 0.67818 | 1 | 110 | 1.2207 |  | 134.2802
1502918 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 2.07 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 6.7676 |  | 527.8696
1502919 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502919 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502920 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 0.85 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.57646 |  | 63.4101
1502920 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 0.9775 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 3.1958 |  | 249.2718
1502921 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502921 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502922 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1502922 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1502923 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.228 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.040845 |  | 4.4929
1502923 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2394 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.20907 |  | 16.3077
1502924 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.22 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.039411 |  | 4.3353
1502924 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.231 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.20174 |  | 15.7355
1502925 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502925 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502926 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502926 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502927 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502927 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502928 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502928 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502929 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502929 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502930 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502930 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502931 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502931 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502932 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502932 | 600 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502933 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.144 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.027025 |  | 2.9727
1502933 | 600 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1584 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.14188 |  | 11.0667
1502934 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502934 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502935 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502935 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502936 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | NA | ZL01 | 0.429 | 1 | 110 | 0.429 |  | 47.19
1502936 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502937 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502937 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502938 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502938 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502939 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502939 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502940 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 21.7588 | 1 | 110 | 21.7588 |  | 2393.4625
1502940 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | 20 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 8.58 | 0.75 | 78 | 3.2175 |  | 250.965
1502941 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.32 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.3569 |  | 149.2565
1502941 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.518 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 7.5463 |  | 588.6108
1502942 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.32 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.3569 |  | 149.2565
1502942 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.518 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 7.5463 |  | 588.6108
1502943 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.538 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.581 |  | 173.9064
1502943 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.7687 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 8.7926 |  | 685.8208
1502944 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.487 | 0 | NA | NA | 1.0279 | 1 | 110 | 1.5285 |  | 168.1397
1502944 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 1.7101 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 8.501 |  | 663.079
1502945 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 5.515 | 0 | NA | NA | 1.0279 | 1 | 110 | 5.6691 |  | 623.5982
1502945 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 6.3422 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 31.5286 |  | 2459.2338
1502946 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 4.408 | 0 | NA | NA | 1.0279 | 1 | 110 | 4.5311 |  | 498.4262
1502946 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 5.0692 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 25.2 |  | 1965.6034
1502947 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502947 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502948 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502948 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP01 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1502949 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502949 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502950 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1502950 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP01 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1502951 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.655 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.3106 |  | 34.1659
1502951 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.8205 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.6306 |  | 127.1904
1502952 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502952 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502953 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502953 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502954 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502954 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502955 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502955 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502955 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502956 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502956 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502957 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502957 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502958 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.114 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.020422 |  | 2.2464
1502958 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1197 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.10454 |  | 8.1538
1502959 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502959 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502960 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502960 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502961 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502961 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502962 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502962 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502963 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502963 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502964 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502964 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502965 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.257 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048232 |  | 5.3055
1502965 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2827 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25322 |  | 19.751
1502966 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502966 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502967 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502967 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502968 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502968 | 600 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502969 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502969 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502970 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502970 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502971 | 400 | Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502971 | 600 | Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502972 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.884 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.70132 |  | 77.1449
1502972 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 1.0166 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 3.8927 |  | 303.6335
1502973 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502973 | 600 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502974 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.837 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15708 |  | 17.2791
1502974 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9207 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.82468 |  | 64.3253
1502975 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502976 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502976 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1502977 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.156 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.029277 |  | 3.2205
1502977 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1716 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.1537 |  | 11.9889
1502978 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502978 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502979 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502979 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502980 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502980 | 600 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502981 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502981 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502981 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502982 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502982 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502982 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1502983 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.228 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.040845 |  | 4.4929
1502983 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2394 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.20907 |  | 16.3077
1502984 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.22 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.039411 |  | 4.3353
1502984 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.231 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.20174 |  | 15.7355
1502985 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502985 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502986 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502986 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502987 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502987 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502988 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502988 | 600 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502989 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502989 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502991 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502991 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502991 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1502992 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502992 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1502993 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502993 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502994 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502994 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1502995 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502995 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502996 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502996 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1502997 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1502997 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1502998 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1502998 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1502999 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1502999 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503000 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1503000 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1503001 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.617 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.48949 |  | 53.8444
1503001 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.70955 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 2.717 |  | 211.9252
1503002 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.658 | 0 | NA | NA | 1.0279 | 1 | 110 | 0.67638 |  | 74.4021
1503002 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Field | NA | 150-20-F-210 | Install Spools - NB 20 Sch80 | 20 | Sch80 | NA | LM | 0.7567 | 0 | NA | NA | 6.6283 | 0.75 | 78 | 3.7617 |  | 293.4136
1503003 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503003 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503004 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503004 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503005 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1503005 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1503006 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1503006 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1503007 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503007 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503008 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503008 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503009 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 1.8 | 0 | NA | NA | 0.67818 | 1 | 110 | 1.2207 |  | 134.2802
1503009 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 2.07 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 6.7676 |  | 527.8696
1503010 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1503010 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1503011 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 14 Sch80 | 14 | Sch80 | NA | LM | 0.85 | 0 | NA | NA | 0.67818 | 1 | 110 | 0.57646 |  | 63.4101
1503011 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | NA | 150-20-F-210 | Install Spools - NB 14 Sch80 | 14 | Sch80 | NA | LM | 0.9775 | 0 | NA | NA | 4.3591 | 0.75 | 78 | 3.1958 |  | 249.2718
1503012 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1503012 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1503013 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | 14 | Sch80 | NA | EA | 1 | 14 | CS | ZL01 | 10.2115 | 1 | 110 | 10.2115 |  | 1123.265
1503013 | 600 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | 14 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.98 | 0.75 | 78 | 2.2425 |  | 174.915
1503014 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503015 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503015 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503015 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503016 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503016 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503017 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | 3 | Sch160 | NA | EA | 1 | 3 | CS | ZL01 | 2.21 | 1 | 110 | 2.21 |  | 243.1
1503017 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503018 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1503018 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1503019 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1503019 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | 3 | NA | CL3000 | EA | 1 | 3 | CS | ZL01 | 7.67 | 1 | 110 | 7.67 |  | 843.7
1503020 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503021 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503021 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503021 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503022 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503022 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503023 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | 3 | Sch160 | NA | EA | 1 | 3 | CS | ZL01 | 2.21 | 1 | 110 | 2.21 |  | 243.1
1503023 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | 0.75 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503024 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1503024 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1503025 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1503025 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | 3 | NA | CL3000 | EA | 1 | 3 | CS | ZL01 | 7.67 | 1 | 110 | 7.67 |  | 843.7
1503026 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503026 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503027 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503027 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503028 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.109 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.019527 |  | 2.1479
1503028 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.11445 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.099951 |  | 7.7962
1503029 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503030 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503030 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503031 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503031 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503031 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503032 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503032 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503033 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503033 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503034 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503034 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503034 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503035 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503035 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503036 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503036 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503036 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503037 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503037 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503038 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503038 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503039 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503039 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503039 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503040 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503040 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503041 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503041 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503042 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503043 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503043 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503044 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503044 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503045 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-30-F-310 | Install Inlines - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503045 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503046 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503047 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.282 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.052924 |  | 5.8216
1503047 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3102 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.27785 |  | 21.6723
1503048 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.266 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.049921 |  | 5.4913
1503048 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2926 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.26209 |  | 20.4427
1503049 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.21 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.039411 |  | 4.3353
1503049 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.231 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.20691 |  | 16.139
1503050 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503050 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503051 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503051 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503052 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.241 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.045229 |  | 4.9752
1503052 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2651 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.23745 |  | 18.5214
1503053 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-30-F-310 | Install Inlines - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503053 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503054 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.781 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.66121 |  | 72.7332
1503054 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.1591 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 3.6322 |  | 283.3136
1503055 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503055 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503056 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.394 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.24378 |  | 26.8157
1503056 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.5334 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.3391 |  | 104.4536
1503057 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503057 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503058 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.814 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15277 |  | 16.8043
1503058 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8954 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.80202 |  | 62.5577
1503059 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503059 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503060 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503060 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503061 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503061 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503062 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.984 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18467 |  | 20.3137
1503062 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0824 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.96952 |  | 75.6225
1503063 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503063 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503064 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503064 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503065 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503065 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503066 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.248 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.046543 |  | 5.1197
1503066 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2728 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.24435 |  | 19.0593
1503067 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503068 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503069 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503070 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503070 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503071 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503071 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503072 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503072 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503073 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503073 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503074 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503074 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503075 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503075 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503076 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503076 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503077 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503077 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503078 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503079 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503079 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1503080 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503080 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503081 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503082 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.123 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.023084 |  | 2.5392
1503082 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1353 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.12119 |  | 9.4528
1503083 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503084 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.443 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.077471 |  | 8.5218
1503084 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.4873 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.42557 |  | 33.1944
1503085 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1503085 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1503086 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503086 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | 3 | SchXST | NA | EA | 1 | 3 | CS | ZL01 | 1.586 | 1 | 110 | 1.586 |  | 174.46
1503087 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503087 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503088 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | NA | 150-30-F-310 | Install Inlines - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503088 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503089 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.883 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.16572 |  | 18.2287
1503089 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9713 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.87001 |  | 67.8605
1503090 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503090 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503091 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.763 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14319 |  | 15.7514
1503091 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8393 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.75177 |  | 58.6382
1503092 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503093 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503094 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1503095 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1503096 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1503097 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 8.543 | 0 | NA | NA | 0.57155 | 1 | 110 | 4.8828 |  | 537.1029
1503097 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 9.8244 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 27.0597 |  | 2110.653
1503098 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503098 | 600 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503099 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1503100 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503100 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503101 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.235 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.044103 |  | 4.8514
1503101 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2585 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.23154 |  | 18.0603
1503102 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.162 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.030403 |  | 3.3443
1503102 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1782 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.15962 |  | 12.4501
1503103 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503103 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503104 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.152 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.028526 |  | 3.1379
1503104 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1672 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.14976 |  | 11.6815
1503105 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503106 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.613 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.30272 |  | 33.2989
1503106 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.7743 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.5893 |  | 123.9626
1503107 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503107 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3069 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503108 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503108 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503109 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503109 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503110 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503110 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503111 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503111 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503112 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503112 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503113 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503113 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503114 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503114 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503115 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503115 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503116 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.031154 |  | 3.4269
1503116 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.16356 |  | 12.7575
1503117 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.031154 |  | 3.4269
1503117 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.16356 |  | 12.7575
1503118 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503118 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503119 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503119 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503120 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503120 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503121 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503121 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503122 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.031154 |  | 3.4269
1503122 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.16356 |  | 12.7575
1503123 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503123 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503124 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503124 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503125 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503125 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503126 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503126 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503127 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503127 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503128 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.908 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.17041 |  | 18.7448
1503128 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9988 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.89464 |  | 69.7818
1503129 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503129 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503130 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503130 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503131 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.559 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10491 |  | 11.54
1503131 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6149 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.55077 |  | 42.9604
1503132 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3062 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503132 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3062 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503133 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503133 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503134 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.628 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11786 |  | 12.9645
1503134 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6908 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.61876 |  | 48.2632
1503135 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503135 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503136 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.971 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18223 |  | 20.0454
1503136 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0681 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.95671 |  | 74.6235
1503137 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503137 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503138 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.214 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.040162 |  | 4.4178
1503138 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2354 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.21085 |  | 16.4464
1503139 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503139 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503140 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.559 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10491 |  | 11.54
1503140 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6149 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.55077 |  | 42.9604
1503141 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503141 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503142 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503142 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503143 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.572 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.4827 |  | 53.0965
1503143 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.8292 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.5342 |  | 197.6638
1503144 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503144 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503145 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.242 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.045417 |  | 4.9959
1503145 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2662 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.23844 |  | 18.5982
1503146 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503146 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503147 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.292 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.054801 |  | 6.0281
1503147 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3212 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.2877 |  | 22.4408
1503148 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.996 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18692 |  | 20.5615
1503148 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0956 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.98134 |  | 76.5448
1503149 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.672 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.12612 |  | 13.8728
1503149 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7392 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.66211 |  | 51.6447
1503150 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503150 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503151 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503151 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503152 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503152 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503153 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503153 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503154 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503154 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503155 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503155 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503156 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503156 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503157 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503157 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503158 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503158 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503159 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503159 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503160 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503160 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503161 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.632 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11861 |  | 13.047
1503161 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6952 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.6227 |  | 48.5706
1503162 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3066 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503162 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3066 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503163 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503163 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503164 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503164 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503165 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503165 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503166 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503166 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503167 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503167 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503168 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503168 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503169 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503169 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503170 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503170 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503171 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503171 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503172 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503172 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503173 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503173 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503174 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503174 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503175 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503175 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503176 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503176 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503177 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503177 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503178 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503178 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503179 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503179 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503180 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503180 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503181 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503181 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503182 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503182 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503183 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.604 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11335 |  | 12.469
1503183 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6644 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.59511 |  | 46.4187
1503184 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503184 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503185 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503185 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503186 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503186 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503187 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503187 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503188 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503188 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503189 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503189 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503190 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503190 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503191 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503191 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503192 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503192 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503193 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503193 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503194 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.527 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.28658 |  | 31.5235
1503194 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.6797 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.5045 |  | 117.3533
1503195 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503195 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503196 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503196 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503197 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.031154 |  | 3.4269
1503197 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.16356 |  | 12.7575
1503198 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503199 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503199 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503200 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503200 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503201 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503202 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503202 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503203 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503203 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503204 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503205 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.834 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15652 |  | 17.2171
1503205 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9174 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.82173 |  | 64.0947
1503206 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503207 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503207 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503208 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.796 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.53623 |  | 58.9857
1503208 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.9756 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.8313 |  | 220.8424
1503209 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503209 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503210 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503210 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503211 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.386 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.11525 |  | 12.6773
1503211 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.4246 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.60851 |  | 47.4639
1503212 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503212 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 2 | 12 | CS | ZL01 | 2.9315 | 1 | 110 | 5.863 |  | 644.93
1503213 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503213 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503214 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503214 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503215 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.472 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.084555 |  | 9.3011
1503215 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.4956 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.43282 |  | 33.7598
1503216 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.472 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.084555 |  | 9.3011
1503216 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.4956 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.43282 |  | 33.7598
1503217 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.525 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.45532 |  | 50.0853
1503217 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.6775 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.4041 |  | 187.5193
1503218 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503218 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503219 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503219 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503220 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503220 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503221 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503221 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503222 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503222 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503223 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503223 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503224 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3011 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1503225 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503225 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503226 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503226 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503227 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503227 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503228 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.9 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.26871 |  | 29.5585
1503228 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.99 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.4188 |  | 110.6671
1503229 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503229 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503230 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503230 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503231 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 7.599 | 0 | NA | NA | 0.29857 | 1 | 110 | 2.2688 |  | 249.5725
1503231 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 8.3589 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 11.9795 |  | 934.3995
1503232 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1503233 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503233 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503234 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503234 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503234 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503235 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503235 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503236 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1503236 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1503237 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503237 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503237 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503238 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503238 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503239 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503239 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503239 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503240 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503240 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503241 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503242 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503242 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503242 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503243 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503243 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503244 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503244 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503245 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503245 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503246 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503246 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503247 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503247 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503248 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503248 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503248 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1503249 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503249 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503250 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503250 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503251 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503251 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503252 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503252 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503253 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503254 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503254 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503254 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503255 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503255 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503256 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503256 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503257 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503257 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503258 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503258 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503259 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503259 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503260 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503260 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503261 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503261 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503262 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503262 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503263 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503263 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503264 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503265 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503265 | 600 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503266 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.089571 |  | 9.8528
1503266 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.33 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.47294 |  | 36.889
1503267 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503267 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503268 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503268 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503269 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503269 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503270 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.603 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.34464 |  | 37.9109
1503270 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.69345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.91 |  | 148.9786
1503271 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.603 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.34464 |  | 37.9109
1503271 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.69345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.91 |  | 148.9786
1503272 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503272 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503273 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503273 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503274 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503274 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503275 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503275 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503276 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503276 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503277 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503277 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503278 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503278 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503279 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503279 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503280 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503280 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503281 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503281 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503282 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503282 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503283 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503283 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503284 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503284 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503285 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503285 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503286 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.9 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.26871 |  | 29.5585
1503286 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.99 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.4188 |  | 110.6671
1503287 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503287 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503288 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503288 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503289 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503289 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503290 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503290 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 2 | 16 | CS | ZL01 | 3.848 | 1 | 110 | 7.696 |  | 846.56
1503291 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503291 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503292 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503292 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503293 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503293 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503294 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503294 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503295 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503295 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503296 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503296 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503297 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503297 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503298 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503298 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503299 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503299 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503300 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 3.631 | 0 | NA | NA | 0.37535 | 1 | 110 | 1.3629 |  | 149.9171
1503300 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 3.9941 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 7.2446 |  | 565.0768
1503301 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503301 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503302 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503302 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503303 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503303 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503304 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503304 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 2 | 16 | CS | ZL01 | 3.848 | 1 | 110 | 7.696 |  | 846.56
1503305 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503305 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503306 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503306 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503307 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503307 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503308 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503308 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503309 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503309 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503310 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503310 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503311 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.3 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.1126 |  | 12.3864
1503311 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.33 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 0.59856 |  | 46.6877
1503312 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.3 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.1126 |  | 12.3864
1503312 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.33 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 0.59856 |  | 46.6877
1503313 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.643 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.36751 |  | 40.4257
1503313 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.73945 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.0367 |  | 158.861
1503314 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.643 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.36751 |  | 40.4257
1503314 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.73945 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.0367 |  | 158.861
1503315 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.33 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.18861 |  | 20.7473
1503315 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3795 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.0453 |  | 81.5306
1503316 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503316 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503317 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503317 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503318 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503318 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503319 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503319 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503320 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503320 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503321 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503321 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503322 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503322 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503323 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1503324 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503324 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503325 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503325 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503326 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503326 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503327 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503327 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503328 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503328 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503329 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503329 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503330 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503330 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503331 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503331 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503332 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503332 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503333 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503333 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503334 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503334 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503335 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503335 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503336 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503336 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503337 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503337 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503338 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503338 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503339 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503340 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503340 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503341 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503342 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503342 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503343 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503343 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503344 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503344 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503345 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1503345 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1503346 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1503346 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1503347 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503347 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503348 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503348 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503349 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 3.631 | 0 | NA | NA | 0.37535 | 1 | 110 | 1.3629 |  | 149.9171
1503349 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 3.9941 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 7.2446 |  | 565.0768
1503350 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 1.348 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.50597 |  | 55.6564
1503350 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 1.4828 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 2.6895 |  | 209.7834
1503351 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503351 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503352 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.628 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.23572 |  | 25.9289
1503352 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.6908 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 1.253 |  | 97.7329
1503353 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503353 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503354 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503354 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503355 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 1.348 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.50597 |  | 55.6564
1503355 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 1.4828 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 2.6895 |  | 209.7834
1503356 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503356 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503357 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503357 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503358 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.628 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.23572 |  | 25.9289
1503358 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.6908 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 1.253 |  | 97.7329
1503359 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503359 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503360 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503360 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503361 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503361 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503362 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503362 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503363 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503363 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503364 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503364 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503365 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503365 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503366 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503366 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503367 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503367 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503368 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503368 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503369 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503370 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503370 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503371 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503372 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503372 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503373 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503373 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503374 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503374 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503375 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1503375 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1503376 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1503376 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1503377 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503377 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503378 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.543 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.8819 |  | 97.0092
1503378 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.7744 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 4.8874 |  | 381.2171
1503379 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503379 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503380 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503380 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503381 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503381 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503382 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503382 | 600 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503383 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503383 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503384 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503384 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503385 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503385 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503386 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.144 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.027025 |  | 2.9727
1503386 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1584 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.14188 |  | 11.0667
1503387 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.21 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.039411 |  | 4.3353
1503387 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.231 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.20691 |  | 16.139
1503388 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.695 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.96878 |  | 106.5655
1503388 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.9492 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 5.3689 |  | 418.7706
1503389 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.782 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14676 |  | 16.1436
1503389 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8602 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.77049 |  | 60.0984
1503390 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503391 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503392 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503392 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503393 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1503393 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1503394 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503394 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503395 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503395 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503396 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503396 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503397 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503397 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503398 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503399 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503399 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503399 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1503400 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503400 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503401 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503401 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503402 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503402 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503403 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503403 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503404 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503404 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503405 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1503405 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1503406 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503407 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503407 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503407 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503408 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503408 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503409 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503409 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503410 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503410 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503410 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503411 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503411 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503412 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503412 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503413 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503414 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503415 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503416 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503417 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1503418 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.851 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15971 |  | 17.5681
1503418 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9361 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.83848 |  | 65.4012
1503419 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503419 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503420 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503420 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503421 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.142 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.02665 |  | 2.9315
1503421 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1562 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.13991 |  | 10.913
1503422 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503422 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503423 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503424 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.959 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.17998 |  | 19.7976
1503424 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0549 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.94489 |  | 73.7012
1503425 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.653 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.12255 |  | 13.4806
1503425 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7183 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.64339 |  | 50.1845
1503426 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503426 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503427 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503427 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503428 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503428 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503429 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.031154 |  | 3.4269
1503429 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.16356 |  | 12.7575
1503430 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503430 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503431 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503431 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503432 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.206 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.038661 |  | 4.2527
1503432 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2266 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.20297 |  | 15.8315
1503433 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503433 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503434 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503434 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503435 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.657 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.1233 |  | 13.5631
1503435 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7227 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.64733 |  | 50.4919
1503436 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503436 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503437 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503437 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503438 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503438 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503439 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503439 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503440 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503440 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503441 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503441 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503442 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503442 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503443 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.269 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.23816 |  | 26.1973
1503443 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.3959 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.2503 |  | 97.5254
1503444 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503444 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503445 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503445 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503446 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.425 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.079761 |  | 8.7737
1503446 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4675 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.41875 |  | 32.6622
1503447 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503447 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503448 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503448 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503449 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503449 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503450 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503450 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503451 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503451 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503452 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503452 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503453 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503453 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503454 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503454 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503455 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.483 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.090646 |  | 9.9711
1503455 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5313 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.47589 |  | 37.1196
1503456 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503456 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503457 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503457 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503458 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.782 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14676 |  | 16.1436
1503458 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8602 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.77049 |  | 60.0984
1503459 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503459 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503460 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503460 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503461 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503462 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503462 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503463 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503463 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503464 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503464 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503465 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503466 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.202 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.036187 |  | 3.9805
1503466 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2121 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.18523 |  | 14.448
1503467 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.202 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.036187 |  | 3.9805
1503467 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2121 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.18523 |  | 14.448
1503468 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503468 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503469 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503469 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503470 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503470 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503471 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503471 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503472 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503472 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503472 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503473 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503473 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503474 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503475 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503475 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503475 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503476 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503476 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503477 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.149 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.026692 |  | 2.9361
1503477 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.15645 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.13663 |  | 10.6572
1503478 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.156 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.027946 |  | 3.0741
1503478 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1638 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.14305 |  | 11.1579
1503479 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503479 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503479 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503480 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503480 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503481 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1503481 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1503482 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503482 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503483 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503483 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503483 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503484 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503484 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503485 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503485 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503486 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.58 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.3315 |  | 36.4649
1503486 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.667 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.8371 |  | 143.2961
1503487 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.937 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.1071 |  | 121.7802
1503487 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.2275 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 6.1354 |  | 478.5596
1503488 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503488 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503489 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503489 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503490 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503490 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503491 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503491 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503492 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-30-F-310 | Install Blind - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1503493 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503494 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503494 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1503495 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503495 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP02 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503496 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503496 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503497 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503497 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503498 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1503498 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1503499 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.954 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.36671 |  | 40.3385
1503499 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.1494 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.9252 |  | 150.1692
1503500 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503500 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503501 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.952 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.54412 |  | 59.8527
1503501 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.0948 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 3.0154 |  | 235.2033
1503502 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503502 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503503 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503503 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503504 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503504 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503505 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.674 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.12649 |  | 13.9141
1503505 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7414 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.66408 |  | 51.7984
1503506 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503506 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503507 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 6.686 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.9962 |  | 219.587
1503507 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 7.3546 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 10.5402 |  | 822.1338
1503508 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503508 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503509 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1503509 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1503510 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503510 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503511 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 2.051 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.61237 |  | 67.3606
1503511 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 2.2561 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 3.2333 |  | 252.1981
1503512 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503512 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503513 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503513 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503514 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503514 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503515 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503515 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503516 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503516 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503517 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503517 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503518 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503518 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503518 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1503519 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503519 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503520 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503520 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503521 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503521 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503522 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503522 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503523 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503524 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503524 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503524 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503525 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503525 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503526 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503526 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503527 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503527 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503528 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503528 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503529 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503529 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503530 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503530 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503531 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503531 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503532 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503532 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503533 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503533 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503534 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503534 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503535 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503535 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503536 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.7 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.209 |  | 22.99
1503536 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.77 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.1035 |  | 86.0744
1503537 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.15 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.044786 |  | 4.9264
1503537 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.165 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.23647 |  | 18.4445
1503538 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503538 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503539 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503539 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503539 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1503540 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503540 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503541 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503541 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503542 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503542 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503542 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1503543 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503543 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503544 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503544 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503545 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503545 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503546 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503547 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503548 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 4.53 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.85016 |  | 93.5176
1503548 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 4.983 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 4.4633 |  | 348.1404
1503549 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503549 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503550 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503550 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503551 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 4.087 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.76702 |  | 84.3722
1503551 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 4.4957 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 4.0269 |  | 314.0948
1503552 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503552 | 600 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503553 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503553 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503554 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503554 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503555 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503555 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503556 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503556 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503557 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503557 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503558 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503558 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503559 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503559 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503560 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 8.543 | 0 | NA | NA | 0.57155 | 1 | 110 | 4.8828 |  | 537.1029
1503560 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 9.8244 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 27.0597 |  | 2110.653
1503561 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503561 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503562 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503563 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503563 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503563 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503564 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503564 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503565 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503565 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503566 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503566 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503566 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503567 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503567 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503568 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.302 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.054101 |  | 5.9511
1503568 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.3171 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.27693 |  | 21.6005
1503569 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.309 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.055355 |  | 6.0891
1503569 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.32445 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.28335 |  | 22.1012
1503570 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503570 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503570 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503571 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503571 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503571 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503572 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503572 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503573 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503573 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503574 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503574 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503575 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503575 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503576 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503576 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503577 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503577 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503578 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503578 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503579 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503579 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503579 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1503580 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503580 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503581 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503581 | 600 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503582 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503582 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503583 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503583 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503584 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503584 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503585 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503586 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503586 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503586 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503587 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503587 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503588 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503588 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503589 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503589 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503590 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503590 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503591 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503591 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503592 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503592 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503593 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503593 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503594 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503594 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503595 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.667 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.38122 |  | 41.9346
1503595 | 600 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.76705 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.1127 |  | 164.7905
1503596 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-30-F-310 | Install Inlines - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503596 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503597 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-30-F-310 | Install Inlines - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503597 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503598 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503598 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503599 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503599 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503600 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503600 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503601 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503601 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503602 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503602 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503603 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503603 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503604 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503604 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503605 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503605 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503606 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503606 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503607 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503607 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503608 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503608 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503609 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503610 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503610 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503611 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503611 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503612 | 400 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.255 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.047857 |  | 5.2642
1503612 | 600 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2805 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25125 |  | 19.5973
1503613 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503614 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.934 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.17529 |  | 19.2815
1503614 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0274 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.92026 |  | 71.7799
1503615 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503615 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503616 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503616 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503617 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503617 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503618 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503618 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503619 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503619 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503620 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503621 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503621 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503622 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503622 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503623 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503624 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503624 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503624 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503625 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503626 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503626 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503626 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1032 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503627 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.259 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048607 |  | 5.3468
1503627 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2849 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25519 |  | 19.9047
1503628 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503628 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503629 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503629 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503630 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503630 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503630 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503631 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503631 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503631 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503632 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503632 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503632 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503633 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503633 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503633 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503634 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503634 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503635 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503635 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503636 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503636 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503637 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503637 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503638 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503638 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503639 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503639 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503640 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503641 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503642 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503643 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503644 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503645 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503646 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503647 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503648 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503649 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.487 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.091397 |  | 10.0537
1503649 | 600 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5357 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.47983 |  | 37.427
1503650 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.996 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18692 |  | 20.5615
1503650 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0956 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.98134 |  | 76.5448
1503651 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503651 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503652 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.739 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.13239 |  | 14.5625
1503652 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.77595 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.67765 |  | 52.8569
1503653 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.739 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.13239 |  | 14.5625
1503653 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.77595 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.67765 |  | 52.8569
1503654 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503654 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503655 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.974 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.18279 |  | 20.1073
1503655 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0714 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.95967 |  | 74.854
1503656 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503656 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503657 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503657 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503658 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503658 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503659 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.487 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.091397 |  | 10.0537
1503659 | 600 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5357 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.47983 |  | 37.427
1503660 | 400 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.255 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.047857 |  | 5.2642
1503660 | 600 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2805 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25125 |  | 19.5973
1503661 | 400 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503661 | 400 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503662 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503662 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503663 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503663 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503664 | 400 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.642 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.12049 |  | 13.2535
1503664 | 600 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7062 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.63255 |  | 49.3391
1503665 | 400 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.642 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.12049 |  | 13.2535
1503665 | 600 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7062 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.63255 |  | 49.3391
1503666 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.22 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.041288 |  | 4.5417
1503666 | 600 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.242 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.21676 |  | 16.9075
1503667 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503667 | 600 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503668 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503668 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503669 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.442 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.082952 |  | 9.1247
1503669 | 600 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4862 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.4355 |  | 33.9687
1503670 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503670 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503671 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503671 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503672 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503672 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503673 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.917 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.1721 |  | 18.9306
1503673 | 600 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0087 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.90351 |  | 70.4734
1503674 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503674 | 600 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503675 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503675 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503676 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.142 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.02665 |  | 2.9315
1503676 | 600 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1562 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.13991 |  | 10.913
1503677 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503677 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503678 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503678 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503679 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.802 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15051 |  | 16.5565
1503679 | 600 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8822 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.7902 |  | 61.6354
1503680 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.157 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.029465 |  | 3.2411
1503680 | 600 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1727 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.15469 |  | 12.0658
1503681 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503681 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503682 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503682 | 600 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503683 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503683 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503684 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503684 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503685 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.886 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.16628 |  | 18.2906
1503685 | 600 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9746 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.87296 |  | 68.091
1503686 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503686 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503687 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503687 | 600 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503688 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503688 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503689 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503689 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503690 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 4.507 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.84584 |  | 93.0427
1503690 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 4.9577 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 4.4407 |  | 346.3728
1503691 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503692 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503693 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503694 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503695 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503696 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1503697 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.477 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.08952 |  | 9.8472
1503697 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5247 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.46998 |  | 36.6585
1503698 | 600 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503699 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.42 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.2665 |  | 29.3146
1503699 | 600 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.562 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.3991 |  | 109.1301
1503700 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503700 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503701 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.694 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13025 |  | 14.327
1503701 | 600 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7634 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.68379 |  | 53.3354
1503702 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503702 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503703 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.187 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.035095 |  | 3.8604
1503703 | 600 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2057 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.18425 |  | 14.3714
1503704 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503704 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503705 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503705 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503706 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503706 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503707 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503707 | 600 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503708 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503708 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503709 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.143 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.026837 |  | 2.9521
1503709 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1573 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.1409 |  | 10.9899
1503710 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503710 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503711 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503711 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503712 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503713 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503713 | 600 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503714 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.729 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.32449 |  | 35.6936
1503714 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.9019 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.7036 |  | 132.8774
1503715 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503715 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503716 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503716 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503717 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503717 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503718 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503718 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503719 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503719 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503720 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503720 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503721 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503721 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503722 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503722 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503723 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.135 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.21301 |  | 23.431
1503723 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.2485 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.1183 |  | 87.2272
1503724 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503724 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503725 | 600 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503726 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.302 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.24435 |  | 26.8786
1503726 | 600 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.4322 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.2828 |  | 100.0615
1503727 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503727 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503728 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503728 | 600 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503729 | 600 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503730 | 400 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503730 | 400 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503731 | 400 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503731 | 600 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503732 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.366 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.068688 |  | 7.5557
1503732 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4026 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.36061 |  | 28.1279
1503733 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503733 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503734 | 600 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503735 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.043 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.19574 |  | 21.5317
1503735 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.1473 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.0277 |  | 80.1568
1503736 | 400 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503736 | 400 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503737 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503737 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503738 | 400 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503738 | 600 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503739 | 400 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503739 | 400 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503740 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503740 | 600 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503741 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503741 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503742 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503742 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503743 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503743 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503744 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503744 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503745 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503745 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1503746 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503747 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503747 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503748 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503748 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503749 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503749 | 600 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503750 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503750 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503751 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.766 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14376 |  | 15.8133
1503751 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8426 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.75473 |  | 58.8688
1503752 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.846 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15877 |  | 17.4649
1503752 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9306 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.83355 |  | 65.0169
1503753 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.704 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13212 |  | 14.5334
1503753 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7744 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.69364 |  | 54.1039
1503754 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503754 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503755 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503755 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503756 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503756 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503757 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503757 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503758 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503758 | 600 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503759 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1503760 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.845 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15858 |  | 17.4442
1503760 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9295 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.83257 |  | 64.9401
1503761 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503761 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1503762 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503762 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1503763 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503764 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503764 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503765 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503766 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503766 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503767 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503767 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503768 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503768 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503769 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 3.481 | 0 | NA | NA | 0.37535 | 1 | 110 | 1.3066 |  | 143.7239
1503769 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 3.8291 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 6.9453 |  | 541.7329
1503770 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.419 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.23948 |  | 26.3427
1503770 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.48185 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.3272 |  | 103.5191
1503771 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.49 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.18392 |  | 20.2312
1503771 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.539 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 0.97765 |  | 76.2566
1503772 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503772 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503773 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-30-F-310 | Install Inlines - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503773 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503774 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503774 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503775 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-30-F-310 | Install Inlines - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503775 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503776 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503776 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503777 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503777 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503778 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503778 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503779 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503779 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503780 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503780 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503781 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503781 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503782 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503782 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503783 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503783 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503784 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503784 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503785 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503785 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503786 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503786 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503787 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503787 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503788 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503788 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503789 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.405 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.26368 |  | 29.0049
1503789 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.5455 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.3843 |  | 107.9773
1503790 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 6.154 | 0 | NA | NA | 0.18767 | 1 | 110 | 1.1549 |  | 127.0435
1503790 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 6.7694 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 6.0634 |  | 472.9483
1503791 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503791 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503792 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503792 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503793 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503793 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503794 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503794 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503795 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503795 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503796 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503796 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503796 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503797 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503797 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503798 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1503798 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1503799 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503799 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503799 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503800 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503801 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503801 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503801 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503802 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503802 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503803 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503803 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503803 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503804 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503804 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503805 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.109 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.019527 |  | 2.1479
1503805 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.11445 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.099951 |  | 7.7962
1503806 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503806 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503807 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503807 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503808 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503808 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503809 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503809 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503810 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503810 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503811 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503811 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503811 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1503812 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503812 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503813 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503813 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503814 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503814 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503815 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503815 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503816 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503816 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503817 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503817 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503818 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503818 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503819 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503820 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503820 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503820 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503821 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503821 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503822 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503822 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503823 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503823 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503824 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503824 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503825 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503825 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503826 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503826 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503827 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503827 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503828 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.525 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.45532 |  | 50.0853
1503828 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.6775 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.4041 |  | 187.5193
1503829 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503829 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503830 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.796 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.53623 |  | 58.9857
1503830 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.9756 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.8313 |  | 220.8424
1503831 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503831 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503832 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503832 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503833 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.386 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.11525 |  | 12.6773
1503833 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.4246 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.60851 |  | 47.4639
1503834 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503834 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 2 | 12 | CS | ZL01 | 2.9315 | 1 | 110 | 5.863 |  | 644.93
1503835 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503835 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503836 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.089571 |  | 9.8528
1503836 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.33 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.47294 |  | 36.889
1503837 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503837 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503838 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503838 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503839 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503839 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503840 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503840 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503841 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1503842 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503842 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503843 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.9 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.26871 |  | 29.5585
1503843 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.99 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.4188 |  | 110.6671
1503844 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503844 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503845 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503845 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503846 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1503847 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503847 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503848 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503848 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503849 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.9 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.26871 |  | 29.5585
1503849 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.99 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.4188 |  | 110.6671
1503850 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503850 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503851 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.523 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.093692 |  | 10.3061
1503851 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.54915 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.47958 |  | 37.4075
1503852 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.523 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.093692 |  | 10.3061
1503852 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.54915 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.47958 |  | 37.4075
1503853 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1503853 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1503854 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.159 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.028484 |  | 3.1332
1503854 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.16695 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.1458 |  | 11.3725
1503855 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503855 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503856 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 4.062 | 0 | NA | NA | 0.57155 | 1 | 110 | 2.3216 |  | 255.3801
1503856 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 4.6713 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 12.8662 |  | 1003.567
1503857 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503857 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503858 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503858 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503859 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503859 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503860 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503860 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503861 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503861 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503862 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503862 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503863 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503863 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503864 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503864 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1503865 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503866 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503866 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503866 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503867 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.419 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.23948 |  | 26.3427
1503867 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.48185 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.3272 |  | 103.5191
1503868 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503868 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503869 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503869 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503870 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.743 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.42466 |  | 46.7128
1503870 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.85445 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.3534 |  | 183.5673
1503871 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503871 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503872 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.743 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.42466 |  | 46.7128
1503872 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.85445 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.3534 |  | 183.5673
1503873 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503873 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503874 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503875 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503875 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503875 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1503876 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503876 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503877 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503877 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503878 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503878 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503879 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503879 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503880 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503880 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503881 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503881 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503882 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503882 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503883 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503883 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503884 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503884 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503885 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503885 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503886 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503886 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503887 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503887 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503888 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503888 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503889 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503889 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503890 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503891 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503891 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503892 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503893 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503893 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503894 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503894 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503895 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1503895 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1503896 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503896 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503897 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1503897 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1503898 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503898 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503899 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.166 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.029738 |  | 3.2711
1503899 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.1743 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.15222 |  | 11.8731
1503900 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503900 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503901 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503901 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503902 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503902 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503903 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503903 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 2 | 16 | CS | ZL01 | 3.848 | 1 | 110 | 7.696 |  | 846.56
1503904 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503904 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503905 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503905 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503906 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.49 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.18392 |  | 20.2312
1503906 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.539 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 0.97765 |  | 76.2566
1503907 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503907 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503908 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503908 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503909 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503909 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503910 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.628 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.23572 |  | 25.9289
1503910 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.6908 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 1.253 |  | 97.7329
1503911 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503911 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503912 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.5 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.18767 |  | 20.6441
1503912 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.55 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 0.9976 |  | 77.8128
1503913 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503913 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503914 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503914 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503915 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503915 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503916 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503916 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503917 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 3.112 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.92915 |  | 102.2068
1503917 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 3.4232 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 4.9059 |  | 382.6624
1503918 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503918 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503919 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1503919 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1503920 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503920 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503921 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503921 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 2 | 16 | CS | ZL01 | 3.848 | 1 | 110 | 7.696 |  | 846.56
1503922 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 3.481 | 0 | NA | NA | 0.37535 | 1 | 110 | 1.3066 |  | 143.7239
1503922 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 3.8291 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 6.9453 |  | 541.7329
1503923 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503923 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503924 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503924 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503925 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503925 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503926 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503926 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503927 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1503927 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1503928 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.628 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.23572 |  | 25.9289
1503928 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.6908 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 1.253 |  | 97.7329
1503929 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503929 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503930 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503930 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503931 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchXST | 8 | SchXST | NA | LM | 0.5 | 0 | NA | NA | 0.37535 | 1 | 110 | 0.18767 |  | 20.6441
1503931 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchXST | 8 | SchXST | NA | LM | 0.55 | 0 | NA | NA | 2.4184 | 0.75 | 78 | 0.9976 |  | 77.8128
1503932 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503932 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503933 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503933 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503934 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1503934 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1503935 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503935 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503936 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503936 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503937 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503937 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503938 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503938 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503938 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503939 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503939 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503940 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503940 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503941 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503941 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503942 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503942 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503943 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503943 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503944 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503944 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503944 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503945 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503945 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503945 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1503946 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503946 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503947 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503947 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503948 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503948 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503949 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503949 | 600 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503950 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503950 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503951 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503951 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503952 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503952 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503953 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503953 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503953 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1503954 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503954 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1503955 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503955 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503956 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503956 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503957 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503957 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503958 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503958 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503959 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1503959 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503960 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1503960 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1503961 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503962 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503963 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503963 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503964 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503964 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503965 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1503965 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1503966 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503966 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503967 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503967 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1503968 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503968 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503969 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1503969 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1503970 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1503970 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503971 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1503971 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1503972 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.543 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.8819 |  | 97.0092
1503972 | 600 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.7744 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 4.8874 |  | 381.2171
1503973 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503973 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1503974 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503974 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503975 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503975 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503976 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503976 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503977 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.209 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.41457 |  | 45.6027
1503977 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.4299 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.1765 |  | 169.7665
1503978 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503978 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503979 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.83 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15577 |  | 17.1346
1503979 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.913 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.81779 |  | 63.7873
1503980 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503980 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503981 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503981 | 600 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1503982 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503982 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1503983 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503984 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1503984 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1503984 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1503985 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503985 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1503986 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1503986 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | 0.75 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503987 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503987 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503988 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503988 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503989 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.259 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048607 |  | 5.3468
1503989 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2849 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25519 |  | 19.9047
1503990 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503991 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503991 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503992 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503992 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503993 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1503994 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503994 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1503995 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1503995 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1503996 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO1018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503996 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO1018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1503997 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.784 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14714 |  | 16.1849
1503997 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8624 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.77246 |  | 60.2521
1503998 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503998 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503999 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1503999 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504000 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504000 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504001 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504001 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504001 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504002 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504002 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504003 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504003 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1504004 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504005 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.942 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.17679 |  | 19.4467
1504005 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0362 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.92814 |  | 72.3947
1504006 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.542 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10172 |  | 11.1891
1504006 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5962 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.53402 |  | 41.6539
1504007 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.296 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.055551 |  | 6.1106
1504007 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3256 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.29164 |  | 22.7482
1504008 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504008 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504009 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504009 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504010 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504010 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504011 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.701 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13156 |  | 14.4715
1504011 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7711 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.69068 |  | 53.8734
1504012 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504012 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504013 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504013 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504014 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504014 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504015 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504015 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504016 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504016 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504017 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504017 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504018 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1504018 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504019 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1504019 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1504020 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504021 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504022 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504022 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504023 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504023 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504024 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504024 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504025 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504025 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504026 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504026 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504027 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504027 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504028 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504028 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504029 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504029 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504030 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504030 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504031 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504031 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504032 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504032 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504033 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504033 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1504034 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504034 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504035 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.423 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.064952 |  | 7.1447
1504035 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.44415 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.33816 |  | 26.3762
1504036 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.109 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.016737 |  | 1.8411
1504036 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.11445 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.087137 |  | 6.7967
1504037 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504037 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504038 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.743 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.11409 |  | 12.5497
1504038 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.78015 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.59397 |  | 46.3298
1504039 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.743 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.11409 |  | 12.5497
1504039 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.78015 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.59397 |  | 46.3298
1504040 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504040 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504041 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504041 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504042 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504042 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504042 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504043 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504043 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504044 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.367 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.056353 |  | 6.1988
1504044 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.38535 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.29339 |  | 22.8843
1504045 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504045 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504046 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.367 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.056353 |  | 6.1988
1504046 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.38535 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.29339 |  | 22.8843
1504047 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504047 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504048 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504048 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504048 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504049 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504049 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504050 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504050 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504050 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504051 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504051 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504052 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504052 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504053 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504053 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504054 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504054 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | XP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504055 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504055 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | XP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1504056 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504056 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504057 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504057 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504058 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504058 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504059 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504060 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.23 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.043165 |  | 4.7481
1504060 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.253 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.22662 |  | 17.676
1504061 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504062 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504063 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504064 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504065 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.495 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.092898 |  | 10.2188
1504065 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5445 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.48772 |  | 38.0418
1504066 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504066 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504067 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.206 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.036903 |  | 4.0594
1504067 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2163 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.1889 |  | 14.7341
1504068 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.591 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11091 |  | 12.2006
1504068 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6501 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.5823 |  | 45.4196
1504069 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504069 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504070 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504071 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504072 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.783 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14695 |  | 16.1643
1504072 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8613 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.77148 |  | 60.1753
1504073 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504073 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504074 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504074 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504075 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504075 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504076 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504076 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504077 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.261 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.23666 |  | 26.0321
1504077 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.3871 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.2424 |  | 96.9106
1504078 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.597 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.11204 |  | 12.3245
1504078 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6567 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.58821 |  | 45.8807
1504079 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504079 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504080 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504081 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.783 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14695 |  | 16.1643
1504081 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8613 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.77148 |  | 60.1753
1504082 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504082 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504083 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504083 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504084 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504084 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504085 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.56302 |  | 61.9322
1504085 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.3 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.9559 |  | 230.5565
1504086 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504086 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504087 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504087 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504088 | 600 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504089 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.403 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.075632 |  | 8.3196
1504089 | 600 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4433 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.39707 |  | 30.9714
1504090 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504090 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504091 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504091 | 600 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504092 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504092 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504093 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504093 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504094 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.958 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.36746 |  | 40.4211
1504094 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.1538 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.9292 |  | 150.4766
1504095 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.923 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.17322 |  | 19.0545
1504095 | 600 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0153 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.90942 |  | 70.9346
1504096 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504096 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504097 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504097 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504098 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504098 | 600 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504099 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504099 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504100 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504100 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504101 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504102 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504102 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504103 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.504 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.094587 |  | 10.4046
1504103 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5544 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.49658 |  | 38.7335
1504104 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504104 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504105 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504105 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504106 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.031154 |  | 3.4269
1504106 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.16356 |  | 12.7575
1504107 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504107 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504108 | 600 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504109 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.923 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.17322 |  | 19.0545
1504109 | 600 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0153 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.90942 |  | 70.9346
1504110 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504110 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504111 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.378 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.07094 |  | 7.8035
1504111 | 600 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4158 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.37244 |  | 29.0501
1504112 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504112 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504113 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.254 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.047669 |  | 5.2436
1504113 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2794 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25026 |  | 19.5205
1504114 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504114 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504115 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504115 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504116 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504116 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504117 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504118 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.519 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.097402 |  | 10.7143
1504118 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5709 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.51136 |  | 39.8863
1504119 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.465 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.087268 |  | 9.5995
1504119 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5115 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.45816 |  | 35.7363
1504120 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504120 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504121 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504121 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504122 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504122 | 600 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504123 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504123 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504124 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504124 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504125 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504125 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504126 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.742 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.13925 |  | 15.3179
1504126 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8162 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.73108 |  | 57.0243
1504127 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504127 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504128 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.911 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.17097 |  | 18.8067
1504128 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0021 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.89759 |  | 70.0123
1504129 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504129 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504130 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.642 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.12049 |  | 13.2535
1504130 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7062 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.63255 |  | 49.3391
1504131 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504131 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504132 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504133 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504133 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504134 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504135 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504135 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504136 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.565 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10604 |  | 11.6639
1504136 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6215 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.55669 |  | 43.4215
1504137 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504138 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504138 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504139 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504139 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504140 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504140 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504141 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1504141 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1504142 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504142 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504143 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1504143 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1504144 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.53 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.30292 |  | 33.3214
1504144 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.6095 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.6788 |  | 130.943
1504145 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504145 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504146 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504146 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504147 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504147 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1504148 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504148 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504148 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504149 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.815 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.54191 |  | 59.6097
1504149 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.9965 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.8613 |  | 223.1787
1504150 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.3 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.089571 |  | 9.8528
1504150 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.33 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.47294 |  | 36.889
1504151 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 2.051 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.61237 |  | 67.3606
1504151 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 2.2561 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 3.2333 |  | 252.1981
1504152 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504153 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504153 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504154 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504154 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504155 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.446 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.083702 |  | 9.2072
1504155 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4906 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.43944 |  | 34.2761
1504156 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504156 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504157 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504157 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504158 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.306 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.057428 |  | 6.3171
1504158 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3366 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.3015 |  | 23.5168
1504159 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504160 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504160 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504161 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.306 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.057428 |  | 6.3171
1504161 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.3366 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.3015 |  | 23.5168
1504162 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504163 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504163 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504164 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504165 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.256 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.045861 |  | 5.0447
1504165 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2688 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.23475 |  | 18.3104
1504166 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.249 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.044607 |  | 4.9067
1504166 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.26145 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.22833 |  | 17.8097
1504167 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504168 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504168 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504168 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504169 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504169 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504170 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504170 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504171 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504172 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504172 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504172 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504173 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504173 | 600 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504174 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504174 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504175 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504175 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504176 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504176 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504177 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504177 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | XP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1504178 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504178 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504179 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504179 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504180 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504180 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | XP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1504181 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504181 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504182 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504182 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504183 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504183 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | XP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1504184 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.18 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.48317 |  | 53.1491
1504184 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.357 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 2.6741 |  | 208.5768
1504185 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504185 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504186 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504186 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | XP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1504187 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504187 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504188 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504188 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504189 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.45 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.18426 |  | 20.2687
1504189 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.5175 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 1.0198 |  | 79.542
1504190 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504190 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504191 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.6 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.34293 |  | 37.7223
1504191 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.69 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.9005 |  | 148.2374
1504192 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 3.279 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.97901 |  | 107.6916
1504192 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4006 | ISO1010 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 3.6069 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 5.1692 |  | 403.1973
1504193 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.26 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.077628 |  | 8.5391
1504193 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.286 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.40988 |  | 31.9705
1504194 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504194 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504195 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504195 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1504196 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504196 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1504197 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.245 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.04389 |  | 4.8279
1504197 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.25725 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.22466 |  | 17.5236
1504198 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.199 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.035649 |  | 3.9214
1504198 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.20895 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.18248 |  | 14.2335
1504199 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.238 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.042636 |  | 4.69
1504199 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.2499 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.21824 |  | 17.0229
1504200 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.582 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.33264 |  | 36.5906
1504200 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.6693 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.8435 |  | 143.7902
1504201 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504201 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504202 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504202 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504203 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.26 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.077628 |  | 8.5391
1504203 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.286 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.40988 |  | 31.9705
1504204 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504205 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504205 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504205 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504206 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504206 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504207 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504207 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1504208 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504208 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504209 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504209 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1504210 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504210 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504211 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.5 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.28578 |  | 31.4353
1504211 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.575 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.5837 |  | 123.5311
1504212 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504212 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504213 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504213 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504214 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504214 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504215 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504215 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504216 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.7 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.40009 |  | 44.0094
1504216 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.805 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.2172 |  | 172.9436
1504217 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504217 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504218 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504218 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1504219 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504219 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504220 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504220 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504221 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504221 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1504222 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504223 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504223 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504223 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504224 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504224 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504225 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504225 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504226 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504226 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504227 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504228 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504228 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504228 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504229 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504229 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504229 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504230 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504230 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504230 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504231 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504231 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504232 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504232 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504233 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1504233 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1504234 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504234 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504235 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504235 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504236 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504236 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504237 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504237 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504238 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504238 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504238 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504239 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504239 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504240 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504240 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504241 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504241 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504242 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504242 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504243 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504243 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504244 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504244 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504245 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504245 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504246 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504246 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504247 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504247 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504248 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504248 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504249 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504249 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504249 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504250 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504250 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504251 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504251 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504252 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504252 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504253 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504253 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504254 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504254 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504255 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504255 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504256 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504256 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504257 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504258 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504258 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504258 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504259 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504259 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504260 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504260 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504261 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504261 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504262 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504262 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504263 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504263 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504263 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504264 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504264 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504265 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504265 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | XP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504266 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | XP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504266 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504267 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504267 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504268 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504268 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504269 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504269 | 600 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504270 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504270 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504271 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504271 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504272 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504272 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504273 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504273 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504274 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504275 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504275 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504275 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504276 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504276 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504277 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | XP01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504277 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504278 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504278 | 600 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504279 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504279 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504280 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504280 | 600 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504281 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504281 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1504282 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504282 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504283 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504284 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504284 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504284 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504285 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504285 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504285 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504286 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504286 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504286 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504287 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504287 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504288 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504288 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504289 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1504289 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1504290 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504290 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504291 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504291 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504292 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504292 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504293 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504293 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504294 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504294 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504294 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504295 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504295 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504296 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504296 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504297 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504297 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504298 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504298 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504299 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504299 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504300 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504300 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504301 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504301 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504302 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504302 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504303 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504303 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504304 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504304 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504305 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504305 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504305 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504306 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504306 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504307 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504307 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504308 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504308 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504309 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504309 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504310 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504310 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504311 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1504311 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504312 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1504312 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504313 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1504313 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504314 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504314 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504315 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504315 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504316 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504317 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504317 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504317 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504318 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504318 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504318 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504319 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504319 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504319 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504320 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504320 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504321 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504321 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504322 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1504322 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1504323 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504323 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504324 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504324 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504325 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504325 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504326 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504326 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504327 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504327 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504327 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504328 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504328 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504329 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504329 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504330 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504330 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504331 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504331 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504332 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504332 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504333 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504333 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504334 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504334 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504335 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504335 | 600 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504336 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504336 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504337 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504337 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504338 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504338 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504338 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504339 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504339 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504340 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504340 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504341 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504341 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504342 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504342 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504343 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504343 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504344 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504344 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504345 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.29 | 0.75 | 78 | 3.2175 |  | 250.965
1504345 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 1 | 0 | NA | NA | 2.34 | 0.75 | 78 | 1.755 |  | 136.89
1504346 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504346 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504347 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.941 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.28096 |  | 30.9051
1504347 | 600 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.0351 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.4834 |  | 115.7086
1504348 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504349 | 600 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504350 | 600 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504351 | 600 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504352 | 600 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504353 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504354 | 400 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504355 | 400 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | CS | XP01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504355 | 400 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504355 | 600 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504356 | 400 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504356 | 400 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504357 | 400 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504357 | 600 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | 0.75 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504358 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504358 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504359 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504359 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504360 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504360 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504361 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504361 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504362 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504363 | 400 | Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504363 | 400 | Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | 0.5 | Sch160 | NA | EA | 1 | 0.5 | NA | XP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504364 | 400 | Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504364 | 600 | Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | 1 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504365 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504365 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504366 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504366 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504367 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.779 | 0 | NA | NA | 0.21753 | 1 | 110 | 0.16946 |  | 18.6402
1504367 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.8569 | 0 | NA | NA | 1.4033 | 0.75 | 78 | 0.90186 |  | 70.3447
1504368 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504368 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504369 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.736 | 0 | NA | NA | 0.21753 | 1 | 110 | 0.1601 |  | 17.6113
1504369 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.8096 | 0 | NA | NA | 1.4033 | 0.75 | 78 | 0.85207 |  | 66.4618
1504370 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504370 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504371 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504371 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504372 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.718 | 0 | NA | NA | 0.21753 | 1 | 110 | 0.15619 |  | 17.1805
1504372 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.7898 | 0 | NA | NA | 1.4033 | 0.75 | 78 | 0.83124 |  | 64.8363
1504373 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.736 | 0 | NA | NA | 0.21753 | 1 | 110 | 0.1601 |  | 17.6113
1504373 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.8096 | 0 | NA | NA | 1.4033 | 0.75 | 78 | 0.85207 |  | 66.4618
1504374 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504374 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504375 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.208 | 0 | NA | NA | 0.21753 | 1 | 110 | 0.045246 |  | 4.9771
1504375 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.2288 | 0 | NA | NA | 1.4033 | 0.75 | 78 | 0.2408 |  | 18.7827
1504376 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504376 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504377 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchSTD | 6 | SchSTD | NA | LM | 3.601 | 0 | NA | NA | 0.21753 | 1 | 110 | 0.78333 |  | 86.1659
1504377 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchSTD | 6 | SchSTD | NA | LM | 3.9611 | 0 | NA | NA | 1.4033 | 0.75 | 78 | 4.1689 |  | 325.175
1504378 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.847 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.14812 |  | 16.2933
1504378 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.9317 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.81367 |  | 63.4664
1504379 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504379 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504380 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504380 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | XP01 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1504381 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504382 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504383 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504384 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504385 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504386 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504387 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504388 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504389 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504390 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504391 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504392 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504393 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504394 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504395 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504396 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504397 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504398 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504399 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504399 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504400 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504400 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504401 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504402 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504402 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504402 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504403 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.256 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.048044 |  | 5.2849
1504403 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2816 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.25223 |  | 19.6742
1504404 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504404 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504405 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504405 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504406 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504407 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.106 | 0 | NA | NA | 0.21753 | 1 | 110 | 0.023058 |  | 2.5364
1504407 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchSTD | 6 | SchSTD | NA | LM | 0.1166 | 0 | NA | NA | 1.4033 | 0.75 | 78 | 0.12272 |  | 9.5719
1504408 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504408 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504409 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504409 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504410 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2002 | Field | NA | 150-30-F-310 | Install valve - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
1504410 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1504411 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO1060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504411 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO1060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504412 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.2 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.034975 |  | 3.8473
1504412 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.22 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.19213 |  | 14.9862
1504413 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504414 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 6.567 | 0 | NA | NA | 0.18767 | 1 | 110 | 1.2324 |  | 135.5695
1504414 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 7.2237 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 6.4704 |  | 504.6882
1504415 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504415 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504416 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504416 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504417 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504417 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504418 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504419 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 4.526 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.84941 |  | 93.435
1504419 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 4.9786 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 4.4594 |  | 347.8329
1504420 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.244 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.045792 |  | 5.0371
1504420 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2684 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.24041 |  | 18.7519
1504421 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504421 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504422 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504422 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504423 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | 6 | SchSTD | NA | LM | 13.2264 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 11.8471 |  | 924.0706
1504423 | 300 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 13.2264 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1322.64
1504424 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504424 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504425 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504425 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504426 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | 6 | SchSTD | NA | LM | 16.2932 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 14.594 |  | 1138.3344
1504426 | 300 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 16.2932 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1629.32
1504427 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504427 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504428 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504428 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504429 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | 6 | SchSTD | NA | LM | 16.2932 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 14.594 |  | 1138.3344
1504429 | 300 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 16.2932 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1629.32
1504430 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504430 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504431 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504431 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504432 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 3.3501 | 0.75 | 78 | 2.5126 |  | 195.9809
1504432 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | 6 | SchSTD | NA | LM | 18.2919 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 16.3843 |  | 1277.9748
1504432 | 300 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 18.2919 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1829.19
1504433 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504433 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504434 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504434 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504435 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 2 | 12 | CS | XP01 | 2.431 | 1 | 110 | 4.862 |  | 534.82
1504435 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504436 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO1060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504436 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO1060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504437 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504437 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504438 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504438 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504439 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL150 | 6 | NA | CL150 | EA | 1 | 0 | NA | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
1504439 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1504440 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | NA | 150-30-F-310 | Install Blind - NB 6 CL150 | 6 | NA | CL150 | EA | 1 | 0 | NA | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
1504441 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504441 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504442 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504442 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504443 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504443 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504444 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.037535 |  | 4.1288
1504444 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.22 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.19706 |  | 15.3704
1504445 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.444 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.45867 |  | 50.4541
1504445 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.6884 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.408 |  | 187.8267
1504446 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504446 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504447 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504447 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504448 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504449 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.166 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.031154 |  | 3.4269
1504449 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.1826 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.16356 |  | 12.7575
1504450 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504450 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504451 | 400 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504451 | 600 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504452 | 400 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504452 | 600 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504453 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504453 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504454 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504454 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 2 | 12 | CS | XP01 | 2.431 | 1 | 110 | 4.862 |  | 534.82
1504455 | 600 | Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504455 | 600 | Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504456 | 400 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 2.069 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.36182 |  | 39.8003
1504456 | 600 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 2.2759 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.9876 |  | 155.032
1504457 | 400 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504457 | 600 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504458 | 400 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504458 | 400 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504459 | 400 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 2.069 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.36182 |  | 39.8003
1504459 | 600 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 2.2759 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.9876 |  | 155.032
1504460 | 400 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504460 | 600 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504461 | 400 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504461 | 400 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504462 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | XP01 | 1.781 | 1 | 110 | 1.781 |  | 195.91
1504462 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | 1.5 | Sch160 | NA | EA | 1 | 1.5 | CS | XP01 | 1.3 | 1 | 110 | 1.3 |  | 143
1504463 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | 1.5 | SchXST | NA | EA | 1 | 1.5 | CS | XP01 | 1.04 | 1 | 110 | 1.04 |  | 114.4
1504463 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL150 | 1.5 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504464 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504464 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504465 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchSTD | 6 | SchSTD | NA | LM | 4.847 | 0 | NA | NA | 0.21753 | 1 | 110 | 1.0544 |  | 115.9806
1504465 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchSTD | 6 | SchSTD | NA | LM | 5.3317 | 0 | NA | NA | 1.4033 | 0.75 | 78 | 5.6114 |  | 437.6904
1504466 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504466 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504467 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504467 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504468 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504468 | 600 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504469 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504469 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504470 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504470 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504471 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504471 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504472 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504472 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504473 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504473 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504474 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504474 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504475 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504475 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504476 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504476 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504477 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.021 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.5283 |  | 58.1135
1504477 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 3.3231 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 2.9021 |  | 226.3662
1504478 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.619 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.80776 |  | 88.8534
1504478 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 5.0809 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 4.4373 |  | 346.1057
1504479 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504479 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504480 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 2.619 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.458 |  | 50.3804
1504480 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 2.8809 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 2.5159 |  | 196.244
1504481 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504481 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504482 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504482 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504483 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504483 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504484 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.619 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.80776 |  | 88.8534
1504484 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 5.0809 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 4.4373 |  | 346.1057
1504485 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504485 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504486 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.146 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.72504 |  | 79.7545
1504486 | 600 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.5606 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 3.9829 |  | 310.6634
1504487 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504488 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.238 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.74113 |  | 81.5243
1504488 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 4.6618 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 4.0712 |  | 317.557
1504489 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504489 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504490 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | NA | 150-30-F-310 | Install valve - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
1504490 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1504491 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | NA | 150-30-F-310 | Install Blind - NB 3 CL150 | 3 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.56 | 0.75 | 78 | 1.17 |  | 91.26
1504492 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504492 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504493 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504493 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504494 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | XP01 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504494 | 600 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | 3 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504495 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504496 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504496 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504497 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504497 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504498 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 5.018 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.94174 |  | 103.5919
1504498 | 600 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 5.5198 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 4.9442 |  | 385.6442
1504499 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504499 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504500 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504500 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504501 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504501 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504502 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.765 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.14357 |  | 15.7927
1504502 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.8415 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.75374 |  | 58.7919
1504503 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504503 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504504 | 600 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504504 | 600 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504505 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504505 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504506 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504506 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504507 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.842 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.15802 |  | 17.3823
1504507 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.9262 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.82961 |  | 64.7095
1504508 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.381 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.071503 |  | 7.8654
1504508 | 600 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4191 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.37539 |  | 29.2807
1504509 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.333 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.15624 |  | 17.1862
1504509 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.38295 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 0.85753 |  | 66.8876
1504510 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1504510 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1504511 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | NA | 150-30-F-310 | Install valve - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
1504511 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 4.16 | 0.75 | 78 | 3.12 |  | 243.36
1504512 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5039 | ISO1051 | Field | NA | 150-30-F-310 | Install Blind - NB 10 CL600 | 10 | NA | CL600 | EA | 1 | 0 | NA | NA | 6.63 | 0.75 | 78 | 4.9725 |  | 387.855
1504513 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504513 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504514 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504514 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504515 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504515 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504516 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | YP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504516 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | YP01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504517 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504517 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | 1 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504518 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504519 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504521 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8108 | ISO4003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504523 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8112 | ISO4007 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504525 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8110 | ISO4005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504527 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8106 | ISO3097 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504529 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8104 | ISO3095 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504530 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 2.941 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.79029 |  | 86.9316
1504530 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 3.2351 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 4.1293 |  | 322.0817
1504531 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504532 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504532 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504532 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504533 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504533 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504534 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504534 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1504535 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.734 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.19724 |  | 21.696
1504535 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.8074 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 1.0306 |  | 80.3835
1504536 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 1.514 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.40683 |  | 44.7516
1504536 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 1.6654 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 2.1257 |  | 165.8047
1504537 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504537 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | XP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1504538 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 2.902 | 0 | NA | NA | 0.40947 | 1 | 110 | 1.1883 |  | 130.7106
1504538 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 3.3373 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 6.5764 |  | 512.9575
1504539 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504539 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504540 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504540 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504541 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | NA | 150-30-F-310 | Install valve - NB 6 CL150 | 6 | NA | CL150 | EA | 1 | 0 | NA | NA | 2.86 | 0.75 | 78 | 2.145 |  | 167.31
1504541 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 1 | 0 | NA | NA | 1.95 | 0.75 | 78 | 1.4625 |  | 114.075
1504542 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504542 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | 6 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 1.95 | 0.75 | 78 | 0.73125 |  | 57.0375
1504543 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 6 | CS | XP01 | 2.431 | 1 | 110 | 2.431 |  | 267.41
1504543 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504544 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.295 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.079271 |  | 8.7198
1504544 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.3245 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 0.41419 |  | 32.3067
1504545 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504545 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1504546 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504546 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1504547 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504547 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 2 | 16 | CS | XP01 | 3.0095 | 1 | 110 | 6.019 |  | 662.09
1504548 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504548 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504549 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 2.759 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.74138 |  | 81.552
1504549 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 3.0349 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 3.8737 |  | 302.1501
1504550 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504551 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504551 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504552 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504552 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504553 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504553 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP02 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504554 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.165 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.66586 |  | 73.2442
1504554 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.3397 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 3.6901 |  | 287.8276
1504555 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504555 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504556 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504556 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504557 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504557 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504558 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504559 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.9 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.24184 |  | 26.6027
1504559 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.99 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 1.2636 |  | 98.5629
1504560 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504560 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1504561 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504561 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1504562 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504562 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504563 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504563 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504564 | 400 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504564 | 600 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504565 | 600 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | NA | 150-30-F-310 | Install Blind - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504566 | 600 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504566 | 600 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504567 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504567 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504568 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1504568 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504569 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504569 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504570 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504570 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504571 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504571 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | ZL02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504572 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504572 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504572 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504573 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504573 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | NA | ZL02 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504574 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504574 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504575 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504575 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504576 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504576 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504577 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504578 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL02 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504578 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504578 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504579 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504579 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504580 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL02 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504580 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL02 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504581 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504581 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504582 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504582 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504583 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504583 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504584 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504584 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504585 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504585 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL02 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504586 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504586 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504587 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.17 | 1 | 110 | 1.17 |  | 128.7
1504587 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504588 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504588 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504589 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504590 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504591 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504591 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504592 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504592 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504593 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504594 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504594 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504595 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1504595 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1504596 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504596 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504597 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1504597 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504598 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504598 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | 0.5 | SchXXS | NA | EA | 1 | 0.5 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504599 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | 2 | Sch160 | NA | EA | 1 | 2 | CS | ZL01 | 1.69 | 1 | 110 | 1.69 |  | 185.9
1504599 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504600 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 8.85 | 0 | NA | NA | 0.57155 | 1 | 110 | 5.0582 |  | 556.4041
1504600 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 10.1775 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 28.0321 |  | 2186.5012
1504601 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504601 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504602 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504602 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504603 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.277 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.15832 |  | 17.4151
1504603 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.31855 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.87739 |  | 68.4363
1504604 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504605 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504606 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-30-F-310 | Install valve - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.46 | 0.75 | 78 | 4.095 |  | 319.41
1504606 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 1 | 0 | NA | NA | 3.38 | 0.75 | 78 | 2.535 |  | 197.73
1504607 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504607 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504608 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504608 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504609 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504610 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.491 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.46749 |  | 51.4243
1504610 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.7401 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.4543 |  | 191.4388
1504611 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504611 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504612 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504612 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504613 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504613 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | ZL02 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504614 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504615 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.454 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.085204 |  | 9.3724
1504615 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.4994 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.44732 |  | 34.8909
1504616 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | ZL02 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504616 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1504617 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.412 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.072049 |  | 7.9254
1504617 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.4532 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.39579 |  | 30.8715
1504618 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504618 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504619 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504619 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 6 | CS | ZL02 | 1.3715 | 1 | 110 | 2.743 |  | 301.73
1504620 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.273 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.047742 |  | 5.2516
1504620 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 0.3003 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.26226 |  | 20.4561
1504621 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | ZL02 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504621 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | ZL02 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504622 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 3 | CS | ZL02 | 1.3715 | 1 | 110 | 1.3715 |  | 150.865
1504622 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | 3 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.3 | 0.75 | 78 | 0.4875 |  | 38.025
1504623 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 3 | 3 | NA | NA | EA | 1 | 0 | NA | NA | 1.5 | 0.75 | 78 | 1.125 |  | 87.75
1504624 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.106 | 0 | NA | NA | 0.17488 | 1 | 110 | 0.19341 |  | 21.2756
1504624 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Field | NA | 150-20-F-210 | Install Spools - NB 3 SchSTD | 3 | SchSTD | NA | LM | 1.2166 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 1.0625 |  | 82.8735
1504625 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504626 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504626 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504627 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504627 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504628 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504628 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504629 | 600 | Proj_A | Area_10 | TR | TR-ZL02-8115 | ISO4019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504630 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8114 | ISO4020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504631 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504632 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504633 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504634 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504635 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504636 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504637 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504638 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 5.324 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.99917 |  | 109.9089
1504638 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 5.8564 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 5.2457 |  | 409.161
1504639 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504639 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504640 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.192 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.036033 |  | 3.9637
1504640 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2112 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.18917 |  | 14.7556
1504641 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504641 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504642 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.553 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.10378 |  | 11.4162
1504642 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.6083 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.54486 |  | 42.4993
1504643 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504643 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504644 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8102 | ISO2009 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504645 | 600 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504646 | 600 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504647 | 600 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504648 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1504649 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504650 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 10 | 10 | NA | NA | EA | 1 | 0 | NA | NA | 1.8233 | 0.75 | 78 | 1.3674 |  | 106.6607
1504651 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504652 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504653 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 1.907 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.89473 |  | 98.4205
1504653 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 2.193 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 4.9109 |  | 383.047
1504654 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504655 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504656 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504657 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504658 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504659 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504660 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8107 | ISO4002 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504661 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8086 | ISO2039 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504662 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504663 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504664 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504665 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504666 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504667 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504668 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504669 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504670 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504671 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504672 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504673 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504673 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1504674 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504674 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504675 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504676 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504677 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504678 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504679 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504680 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504681 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504682 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504683 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504684 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504685 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504686 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504687 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504688 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504689 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504690 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504691 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1504692 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1504693 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 16 | 16 | NA | NA | EA | 1 | 0 | NA | NA | 2.1107 | 0.75 | 78 | 1.583 |  | 123.4731
1504694 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504695 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504696 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504697 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504698 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504699 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504700 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504701 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504702 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504703 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504704 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504705 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504706 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504707 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504708 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504709 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504710 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504711 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504712 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504713 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504714 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504715 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504716 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504717 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1504718 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1504719 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 8 | 8 | NA | NA | EA | 1 | 0 | NA | NA | 1.7364 | 0.75 | 78 | 1.3023 |  | 101.5816
1504720 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 12 | 12 | NA | NA | EA | 1 | 0 | NA | NA | 1.9144 | 0.75 | 78 | 1.4358 |  | 111.9937
1504721 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8111 | ISO4006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504722 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8106 | ISO4001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504723 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8109 | ISO4004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504724 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8105 | ISO3096 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504725 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504725 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504726 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.614 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.35093 |  | 38.6025
1504726 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.7061 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.9448 |  | 151.6962
1504727 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 4.68 | 0 | NA | NA | 0.57155 | 1 | 110 | 2.6749 |  | 294.234
1504727 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 5.382 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 14.8237 |  | 1156.2515
1504728 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504728 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504729 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.676 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.5295 |  | 168.2415
1504729 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.0774 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 8.4761 |  | 661.1387
1504730 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.867 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.49553 |  | 54.5087
1504730 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.99705 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.7462 |  | 214.203
1504731 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.438 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.25034 |  | 27.5373
1504731 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.5037 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.3873 |  | 108.2133
1504732 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.719 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.41094 |  | 45.2039
1504732 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.82685 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.2774 |  | 177.6378
1504733 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.306 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.74644 |  | 82.1089
1504733 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.5019 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 4.1367 |  | 322.6633
1504734 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.894 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.36607 |  | 40.2672
1504734 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.0281 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 2.0259 |  | 158.0234
1504735 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504735 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504736 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504736 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504737 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 6.788 | 0 | NA | NA | 0.40947 | 1 | 110 | 2.7795 |  | 305.7422
1504737 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 7.8062 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 15.3827 |  | 1199.8469
1504738 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504738 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504739 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504739 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504740 | 600 | Proj_A | Area_10 | TR | TR-ZL01-8113 | ISO4018 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504741 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 2 | 2 | NA | NA | EA | 1 | 0 | NA | NA | 1 | 0.75 | 78 | 0.75 |  | 58.5
1504742 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504742 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504743 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 2.322 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.43578 |  | 47.9355
1504743 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 2.5542 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 2.2878 |  | 178.4508
1504744 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504744 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504745 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.233 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.043728 |  | 4.8101
1504745 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2563 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.22957 |  | 17.9066
1504746 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504747 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.247 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.044248 |  | 4.8673
1504747 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.25935 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.2265 |  | 17.6667
1504748 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.24 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.042994 |  | 4.7294
1504748 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.252 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.22008 |  | 17.166
1504749 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504749 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504750 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504750 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504751 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 1 | 1 | NA | NA | EA | 1 | 0 | NA | NA | 0.4 | 0.75 | 78 | 0.3 |  | 23.4
1504752 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.206 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.031631 |  | 3.4795
1504752 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.2163 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.16468 |  | 12.8451
1504753 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.199 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.030557 |  | 3.3612
1504753 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.20895 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.15909 |  | 12.4087
1504754 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 2.7 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.72553 |  | 79.808
1504754 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 2.97 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 3.7909 |  | 295.6887
1504755 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 2.701 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.7258 |  | 79.8376
1504755 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 2.9711 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 3.7923 |  | 295.7983
1504756 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 1.662 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.4466 |  | 49.1263
1504756 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 1.8282 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 2.3335 |  | 182.0128
1504757 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504757 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504758 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504758 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504759 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504759 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504760 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504760 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504761 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504761 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 2 | 16 | CS | ZL02 | 3.0095 | 1 | 110 | 6.019 |  | 662.09
1504762 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.856 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.23002 |  | 25.3021
1504762 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.9416 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 1.2018 |  | 93.7443
1504763 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504763 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504764 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 2 | 24 | CS | ZL02 | 4.7255 | 1 | 110 | 9.451 |  | 1039.61
1504764 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504765 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1504765 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504766 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1504766 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504767 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504767 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL02 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504768 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.45 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.12092 |  | 13.3013
1504768 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.495 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 0.63181 |  | 49.2815
1504769 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504769 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504770 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504770 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504771 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 8 | CS | ZL01 | 3.848 | 1 | 110 | 3.848 |  | 423.28
1504771 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504772 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.657 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.1233 |  | 13.5631
1504772 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.7227 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.64733 |  | 50.4919
1504773 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504773 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504773 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504774 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504774 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504775 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504775 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504775 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504776 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504776 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504777 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504777 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504777 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504778 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504778 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504779 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 SchXST | 1 | SchXST | NA | LM | 0.455 | 0 | NA | NA | 0.15355 | 1 | 110 | 0.069866 |  | 7.6852
1504779 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-20-F-210 | Install Spools - NB 1 SchXST | 1 | SchXST | NA | LM | 0.47775 | 0 | NA | NA | 1.0151 | 0.75 | 78 | 0.36374 |  | 28.3716
1504780 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504780 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL02 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504781 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504782 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL02 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504782 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504782 | 600 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504783 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504783 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504784 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL02 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504784 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504785 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504785 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504786 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504786 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504787 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504787 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504787 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504788 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504788 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504789 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504789 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504789 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504790 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504790 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504791 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.455 | 0 | NA | NA | 0.17914 | 1 | 110 | 0.08151 |  | 8.9661
1504791 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-20-F-210 | Install Spools - NB 1 Sch160 | 1 | Sch160 | NA | LM | 0.47775 | 0 | NA | NA | 1.1644 | 0.75 | 78 | 0.41723 |  | 32.5438
1504792 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504793 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504793 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504793 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504794 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504794 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504795 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504795 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504796 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504796 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | 1 | 3000psi | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504796 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | NA | 150-30-F-310 | Install valve - NB 1 3000psi | 1 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1504797 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504797 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504798 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504798 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504799 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504799 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504800 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504800 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504800 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504801 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504801 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | NA | ZL01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504802 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504802 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504803 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504803 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504804 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504804 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504805 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504806 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504806 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | 0.75 | 3000psi | NA | EA | 1 | 0.75 | NA | ZL01 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504806 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 3000psi | 0.75 | NA | 3000psi | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504807 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504807 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | 0.75 | SchXXS | NA | EA | 1 | 0.75 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504808 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | CS | ZL01 | 0.65 | 1 | 110 | 0.65 |  | 71.5
1504808 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504809 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504809 | 600 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504810 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504810 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504811 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504811 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504812 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504812 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504813 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504813 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 2 | 2 | CS | ZL01 | 0.78 | 1 | 110 | 1.56 |  | 171.6
1504814 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504814 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504815 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504815 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504816 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504816 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504817 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504817 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504818 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1504818 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1504819 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1504819 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
1504820 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504820 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504821 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.321 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.18347 |  | 20.1814
1504821 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.36915 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.0168 |  | 79.307
1504822 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.657 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.37551 |  | 41.3059
1504822 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.75555 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.081 |  | 162.3199
1504823 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504823 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504824 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504824 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1504825 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504825 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504826 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-30-F-310 | Install Blind - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504827 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504827 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504828 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | NA | 150-30-F-310 | Install Blind - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504829 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1504830 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1504830 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1504831 | 400 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.225 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.042226 |  | 4.6449
1504831 | 600 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2475 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.22169 |  | 17.2917
1504832 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.165 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.66586 |  | 73.2442
1504832 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.3397 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 3.6901 |  | 287.8276
1504833 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.507 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.28282 |  | 31.1106
1504833 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.6577 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.4848 |  | 115.8162
1504834 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504834 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504835 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.959 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.17998 |  | 19.7976
1504835 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.0549 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.94489 |  | 73.7012
1504836 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.207 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.68986 |  | 75.8847
1504836 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.3881 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 3.8231 |  | 298.2042
1504837 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.043 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.1677 |  | 128.4445
1504837 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.3495 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 6.4711 |  | 504.7482
1504838 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504838 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504839 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504839 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504840 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504840 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504841 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.871 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.0694 |  | 117.6307
1504841 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.1516 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 5.9263 |  | 462.2535
1504842 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.519 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.097402 |  | 10.7143
1504842 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.5709 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.51136 |  | 39.8863
1504843 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504843 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504844 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 4.182 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.78485 |  | 86.3334
1504844 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 4.6002 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 4.1205 |  | 321.3958
1504845 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504845 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504846 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504846 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504847 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | XP02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504847 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | 0.75 | 2000psi | NA | EA | 1 | 0.75 | NA | XP02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504847 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | NA | 150-30-F-310 | Install valve - NB 0.75 2000psi | 0.75 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504848 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | NA | XP02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504848 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 Sch160 | 0.75 | Sch160 | NA | EA | 1 | 0.75 | NA | XP02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504849 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | 0.75 | NA | CL3000 | EA | 1 | 0.75 | CS | XP02 | 2.47 | 1 | 110 | 2.47 |  | 271.7
1504849 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | 0.75 | CL3000 | NA | EA | 1 | 0.75 | NA | XP02 | 0.26 | 1 | 110 | 0.26 |  | 28.6
1504850 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 1.096 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.20569 |  | 22.6259
1504850 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 1.2056 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 1.0799 |  | 84.23
1504851 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504851 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504852 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504853 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504853 | 600 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504854 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504854 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504855 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP02 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504855 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504856 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 5.415 | 0 | NA | NA | 0.18767 | 1 | 110 | 1.0163 |  | 111.7875
1504856 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 5.9565 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 5.3353 |  | 416.1545
1504857 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504857 | 600 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504858 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504858 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504859 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504859 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504860 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504860 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504861 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504861 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504862 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504862 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504863 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504863 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504864 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504864 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504865 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504865 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504866 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 5.59 | 0.75 | 78 | 4.1925 |  | 327.015
1504866 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57
1504867 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504867 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504868 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.45 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.18426 |  | 20.2687
1504868 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.5175 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 1.0198 |  | 79.542
1504869 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504869 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504870 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.327 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.1339 |  | 14.7286
1504870 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.37605 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 0.74103 |  | 57.8005
1504871 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504871 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504872 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 5.59 | 0.75 | 78 | 4.1925 |  | 327.015
1504872 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57
1504873 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504873 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504874 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504874 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504875 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504875 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1504876 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504876 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504877 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1504877 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1504878 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504878 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504879 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 8.124 | 0 | NA | NA | 0.79335 | 1 | 110 | 6.4451 |  | 708.9655
1504879 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 9.3426 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 35.7744 |  | 2790.4057
1504880 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504880 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 2 | 32 | CS | ZL01 | 14.365 | 1 | 110 | 28.73 |  | 3160.3
1504881 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504881 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504882 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | YP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504882 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504883 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504883 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504884 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1504884 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1504885 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504885 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504886 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.2 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.037535 |  | 4.1288
1504886 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.22 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.19706 |  | 15.3704
1504887 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1504887 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 1 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.78 |  | 60.84
1504888 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504888 | 600 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | 2 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 1.04 | 0.75 | 78 | 0.39 |  | 30.42
1504889 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | YP01 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504889 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | YP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504890 | 400 | Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 0.14 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.026274 |  | 2.8902
1504890 | 600 | Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 0.154 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 0.13794 |  | 10.7593
1504891 | 400 | Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504891 | 600 | Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504892 | 400 | Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504892 | 600 | Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504893 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504893 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | XP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1504894 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504894 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | 2 | NA | CL2000 | EA | 1 | 2 | CS | XP01 | 4.42 | 1 | 110 | 4.42 |  | 486.2
1504895 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504895 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504896 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504896 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504897 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504897 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504898 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504898 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL01 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1504899 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.523 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.62362 |  | 68.5983
1504899 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.7514 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 3.4514 |  | 269.2055
1504900 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1504900 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1504901 | 400 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504901 | 600 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504902 | 400 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 3.625 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.68032 |  | 74.8347
1504902 | 600 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 3.9875 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 3.5717 |  | 278.5891
1504903 | 400 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504903 | 400 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504904 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504904 | 600 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504905 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP02 | 1.1765 | 1 | 110 | 2.353 |  | 258.83
1504905 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504906 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 5.125 | 0 | NA | NA | 0.18767 | 1 | 110 | 0.96183 |  | 105.8008
1504906 | 600 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 5.6375 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 5.0496 |  | 393.8674
1504907 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504907 | 600 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504908 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 2 SchXST | 2 | SchXST | NA | LM | 6.607 | 0 | NA | NA | 0.18767 | 1 | 110 | 1.24 |  | 136.3953
1504908 | 600 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | NA | 150-20-F-210 | Install Spools - NB 2 SchXST | 2 | SchXST | NA | LM | 7.2677 | 0 | NA | NA | 1.1943 | 0.75 | 78 | 6.5098 |  | 507.7623
1504909 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504909 | 600 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504910 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504910 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504911 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1504911 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 17.3162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 21.0498 |  | 1641.8809
1504911 | 300 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 17.3162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1731.62
1504912 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504912 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504913 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504913 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504914 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 11.742 | 0 | NA | NA | 0.29857 | 1 | 110 | 3.5058 |  | 385.6403
1504914 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 12.9162 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 18.5107 |  | 1443.8372
1504915 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504915 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504916 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504916 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504917 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 5.366 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.6021 |  | 176.2345
1504917 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 5.9026 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 8.4593 |  | 659.822
1504918 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.453 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.13525 |  | 14.8778
1504918 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.4983 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.71413 |  | 55.7025
1504919 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504919 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504920 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504920 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504921 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.137 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.33948 |  | 37.3423
1504921 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.2507 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.7924 |  | 139.8095
1504922 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504923 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504923 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | Threaded | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | 1 | 2000psi | NA | EA | 1 | 1 | NA | XP01 | 0.39 | 1 | 110 | 0.39 |  | 42.9
1504923 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-30-F-310 | Install valve - NB 1 2000psi | 1 | NA | 2000psi | EA | 1 | 0 | NA | NA | 0.39 | 0.75 | 78 | 0.2925 |  | 22.815
1504924 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504924 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | XP01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1504925 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | XP01 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1504925 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | XP01 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1504926 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504926 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1504927 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504927 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504928 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.435 | 0 | NA | NA | 0.26871 | 1 | 110 | 0.11689 |  | 12.858
1504928 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 0.4785 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 0.61075 |  | 47.6387
1504929 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504929 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504930 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504930 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1504931 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.446 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.18262 |  | 20.0885
1504931 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.5129 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 1.0107 |  | 78.835
1504932 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504932 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 2 | 24 | CS | XP01 | 4.7255 | 1 | 110 | 9.451 |  | 1039.61
1504933 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | XP01 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504933 | 600 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | 8 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 2.73 | 0.75 | 78 | 1.0238 |  | 79.8525
1504934 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504935 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504935 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504936 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504936 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504937 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.043 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.42708 |  | 46.9784
1504937 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.1994 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 2.3636 |  | 184.3607
1504938 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504939 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504939 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504940 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 11.271 | 0 | NA | NA | 0.40947 | 1 | 110 | 4.6151 |  | 507.6635
1504940 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 12.9617 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 25.5418 |  | 1992.262
1504941 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504941 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 2 | 24 | CS | XP01 | 4.7255 | 1 | 110 | 9.451 |  | 1039.61
1504942 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504942 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504943 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504943 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504944 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 7.749 | 0 | NA | NA | 0.40947 | 1 | 110 | 3.173 |  | 349.0271
1504944 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 8.9113 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 17.5604 |  | 1369.7133
1504945 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504945 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504946 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.809 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.74073 |  | 81.4802
1504946 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 2.0803 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 4.0995 |  | 319.7588
1504947 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504947 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504948 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504948 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504949 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504949 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504950 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.694 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.69364 |  | 76.3004
1504950 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.9481 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 3.8389 |  | 299.4314
1504951 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504951 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504952 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.435 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.17812 |  | 19.5931
1504952 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.50025 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 0.98578 |  | 76.8906
1504953 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504953 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504954 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504955 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504955 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504956 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504956 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504957 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 5.59 | 0.75 | 78 | 4.1925 |  | 327.015
1504957 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57
1504958 | 600 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Field | NA | 150-30-F-310 | Install Blind - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 5.59 | 0.75 | 78 | 4.1925 |  | 327.015
1504959 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504959 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504960 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.4 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.16379 |  | 18.0166
1504960 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.46 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 0.90646 |  | 70.704
1504961 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504961 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504962 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504963 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.65 | 0.75 | 78 | 0.4875 |  | 38.025
1504963 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 1 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.6825 |  | 53.235
1504964 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | XP01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1504964 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | 2 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 0.91 | 0.75 | 78 | 0.34125 |  | 26.6175
1504965 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.722 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.29564 |  | 32.52
1504965 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.8303 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 1.6362 |  | 127.6207
1504966 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 5.59 | 0.75 | 78 | 4.1925 |  | 327.015
1504966 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 4.42 | 0.75 | 78 | 3.315 |  | 258.57
1504967 | 600 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Field | NA | 150-30-F-310 | Install Blind - NB 12 CL150 | 12 | NA | CL150 | EA | 1 | 0 | NA | NA | 5.59 | 0.75 | 78 | 4.1925 |  | 327.015
1504968 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504968 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504969 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 2 | 24 | CS | XP01 | 4.7255 | 1 | 110 | 9.451 |  | 1039.61
1504969 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504970 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504970 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504971 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504971 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504972 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504972 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504973 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 7.1656 | 0.75 | 78 | 5.3742 |  | 419.1876
1504973 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 12 SchSTD | 12 | SchSTD | NA | LM | 18.4242 | 0 | NA | NA | 2.218 | 0.75 | 78 | 30.648 |  | 2390.5413
1504973 | 300 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-80-F-810 | Field Coating - NB 12 | 12 | NA | NA | LM | 18.4242 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 120 | 2210.898
1504974 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 10.479 | 0 | NA | NA | 0.40947 | 1 | 110 | 4.2908 |  | 471.9906
1504974 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 12.0508 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 23.747 |  | 1852.2681
1504975 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504975 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504976 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504976 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | 12 | NA | CL150 | EA | 0.5 | 0 | NA | NA | 4.42 | 0.75 | 78 | 1.6575 |  | 129.285
1504977 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504977 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | XP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504978 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504978 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504979 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.941 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.57953 |  | 63.7479
1504979 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 2.1351 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 3.0599 |  | 238.6721
1504980 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504980 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504981 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.453 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.13525 |  | 14.8778
1504981 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.4983 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.71413 |  | 55.7025
1504982 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 4.306 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.2856 |  | 141.4211
1504982 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 4.7366 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 6.7882 |  | 529.4807
1504983 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 11.742 | 0 | NA | NA | 0.29857 | 1 | 110 | 3.5058 |  | 385.6403
1504983 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 12.9162 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 18.5107 |  | 1443.8372
1504984 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1504984 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 17.3162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 21.0498 |  | 1641.8809
1504984 | 300 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 17.3162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1731.62
1504985 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504985 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504986 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504986 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504987 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504987 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504988 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504988 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504989 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504989 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504991 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1504991 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 17.3162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 21.0498 |  | 1641.8809
1504991 | 300 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 17.3162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1731.62
1504992 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1504992 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 19.5162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 23.7241 |  | 1850.4796
1504992 | 300 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 19.5162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1951.62
1504993 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 5.245 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.566 |  | 172.2605
1504993 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 5.7695 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 8.2685 |  | 644.9435
1504994 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1504994 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1504995 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504995 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504996 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1504996 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1504997 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504997 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1504998 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1504999 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1505000 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1505000 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 17.3162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 21.0498 |  | 1641.8809
1505000 | 300 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 17.3162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1731.62
1505001 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1505002 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1505003 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1505004 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 4.2237 | 0.75 | 78 | 3.1678 |  | 247.0864
1505004 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | 6 | SchXST | NA | LM | 19.5162 | 0 | NA | NA | 1.6208 | 0.75 | 78 | 23.7241 |  | 1850.4796
1505004 | 300 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-80-F-810 | Field Coating - NB 6 | 6 | NA | NA | LM | 19.5162 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 100 | 1951.62
1505005 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1505006 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 4.418 | 0 | NA | NA | 0.29857 | 1 | 110 | 1.3191 |  | 145.0995
1505006 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 4.8598 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 6.9648 |  | 543.2527
1505007 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505007 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505008 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505008 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505009 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505009 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505010 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505010 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505011 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505011 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505012 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505012 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505013 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505013 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505014 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505014 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505015 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505015 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505016 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505016 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505017 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.453 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.13525 |  | 14.8778
1505017 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.4983 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.71413 |  | 55.7025
1505018 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-50-F-510 | Erection of Pipe Supports - NB 6 | 6 | NA | NA | EA | 1 | 0 | NA | NA | 1.6538 | 0.75 | 78 | 1.2403 |  | 96.7444
1505019 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505019 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505020 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 1.537 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.4589 |  | 50.4794
1505020 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 1.6907 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 2.423 |  | 188.9949
1505021 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505021 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | 6 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 2.34 | 0.75 | 78 | 0.8775 |  | 68.445
1505022 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505022 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505023 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.453 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.13525 |  | 14.8778
1505023 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.4983 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 0.71413 |  | 55.7025
1505024 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505024 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 6 | CS | ZL01 | 2.9315 | 1 | 110 | 2.9315 |  | 322.465
1505025 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 6 SchXST | 6 | SchXST | NA | LM | 0.741 | 0 | NA | NA | 0.29857 | 1 | 110 | 0.22124 |  | 24.3365
1505025 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Field | NA | 150-20-F-210 | Install Spools - NB 6 SchXST | 6 | SchXST | NA | LM | 0.8151 | 0 | NA | NA | 1.9109 | 0.75 | 78 | 1.1682 |  | 91.1159
1505026 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.43 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.17607 |  | 19.3679
1505026 | 600 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.4945 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 0.97445 |  | 76.0068
1505027 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | YP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505027 | 600 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL300 | 12 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 4.94 | 0.75 | 78 | 1.8525 |  | 144.495
1505028 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | YP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505028 | 600 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL300 | 12 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 4.94 | 0.75 | 78 | 1.8525 |  | 144.495
1505029 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | YP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505029 | 600 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL300 | 12 | NA | CL300 | EA | 0.5 | 0 | NA | NA | 4.94 | 0.75 | 78 | 1.8525 |  | 144.495
1505030 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.84 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.34395 |  | 37.8349
1505030 | 600 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.966 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 1.9036 |  | 148.4784
1505031 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | YP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505031 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | YP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505032 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | YP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505032 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | YP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505033 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.416 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.17034 |  | 18.7373
1505033 | 600 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 0.4784 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 0.94272 |  | 73.5322
1505034 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505034 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505035 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-30-F-310 | Install Blind - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1505036 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1505036 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1505037 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | YP01 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505037 | 600 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505038 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1505038 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505039 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1505039 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505040 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1505040 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505041 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1505041 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505042 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.894 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.0825 |  | 119.0768
1505042 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.1781 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 5.9992 |  | 467.936
1505043 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505043 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505044 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505045 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1505045 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505046 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505046 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505047 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505047 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505048 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505048 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1505049 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.403 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.945 |  | 213.9484
1505049 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.9134 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 10.7789 |  | 840.7529
1505050 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505050 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1505051 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505051 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505052 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505052 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505053 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505053 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505054 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505054 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505055 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505055 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505056 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505056 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505057 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505057 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505058 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505058 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505059 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1505059 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505060 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505060 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1505061 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.687 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.32233 |  | 35.4562
1505061 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.79005 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 1.7691 |  | 137.9933
1505062 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 2 | 20 | CS | ZL01 | 5.915 | 1 | 110 | 11.83 |  | 1301.3
1505062 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505063 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.074 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.1854 |  | 130.3935
1505063 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.3851 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 6.5693 |  | 512.4072
1505064 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505064 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505065 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505065 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505066 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505066 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505067 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 11.3555 | 0.75 | 78 | 8.5166 |  | 664.2967
1505067 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | 12 | Sch80 | NA | LM | 19.5523 | 0 | NA | NA | 3.1137 | 0.75 | 78 | 45.6595 |  | 3561.4443
1505067 | 300 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | NA | 150-80-F-810 | Field Coating - NB 12 | 12 | NA | NA | LM | 19.5523 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 120 | 2346.276
1505068 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505068 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505069 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505069 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505070 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505070 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505071 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505071 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505072 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 11.3555 | 0.75 | 78 | 8.5166 |  | 664.2967
1505072 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | 12 | Sch80 | NA | LM | 19.5603 | 0 | NA | NA | 3.1137 | 0.75 | 78 | 45.6783 |  | 3562.9106
1505072 | 300 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Field | NA | 150-80-F-810 | Field Coating - NB 12 | 12 | NA | NA | LM | 19.5603 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 120 | 2347.242
1505073 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505074 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1505074 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505075 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505075 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505076 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505076 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505077 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505077 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1505078 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.43 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.9604 |  | 215.6459
1505078 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 3.9445 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 10.8644 |  | 847.4236
1505079 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505079 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505080 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.155 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.66014 |  | 72.6155
1505080 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.3282 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 3.6584 |  | 285.3569
1505081 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505081 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505082 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505082 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505083 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505083 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505084 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 11.3555 | 0.75 | 78 | 8.5166 |  | 664.2967
1505084 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | 12 | Sch80 | NA | LM | 18.0136 | 0 | NA | NA | 3.1137 | 0.75 | 78 | 42.0663 |  | 3281.1707
1505084 | 300 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-80-F-810 | Field Coating - NB 12 | 12 | NA | NA | LM | 18.0136 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 120 | 2161.632
1505085 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505085 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505086 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505086 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505087 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505087 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505088 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.524 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.29949 |  | 32.9442
1505088 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.6026 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.6598 |  | 129.4606
1505089 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505089 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505090 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505090 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505091 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505091 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505092 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505092 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505093 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 4.188 | 0 | NA | NA | 0.57155 | 1 | 110 | 2.3937 |  | 263.3017
1505093 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 4.8162 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 13.2653 |  | 1034.6968
1505094 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505094 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505095 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.447 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.20972 |  | 23.0697
1505095 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.51405 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 1.1511 |  | 89.786
1505096 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505096 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505097 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 6.804 | 0 | NA | NA | 0.57155 | 1 | 110 | 3.8888 |  | 427.771
1505097 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 7.8246 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 21.5514 |  | 1681.0117
1505098 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505098 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1505099 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505099 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | 10 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 4.16 | 0.75 | 78 | 1.56 |  | 121.68
1505100 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505100 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505101 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505101 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505102 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.577 | 0 | NA | NA | 0.46918 | 1 | 110 | 0.27072 |  | 29.779
1505102 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Field | NA | 150-20-F-210 | Install Spools - NB 10 Sch80 | 10 | Sch80 | NA | LM | 0.66355 | 0 | NA | NA | 2.9857 | 0.75 | 78 | 1.4859 |  | 115.8983
1505103 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505103 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505104 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505104 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505105 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505105 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 10 | CS | ZL01 | 5.915 | 1 | 110 | 5.915 |  | 650.65
1505106 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505106 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505107 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505107 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505108 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505109 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1505109 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505110 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1505110 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505111 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505111 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505112 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.77 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.72476 |  | 79.7236
1505112 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 2.0355 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 4.0111 |  | 312.8652
1505113 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505114 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1505114 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505115 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1505115 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505116 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL02 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1505116 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | 2 | NA | CL3000 | EA | 1 | 2 | CS | ZL02 | 5.46 | 1 | 110 | 5.46 |  | 600.6
1505117 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1505117 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1505118 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1505118 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1505119 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 6.532 | 0 | NA | NA | 0.26871 | 1 | 110 | 1.7552 |  | 193.0763
1505119 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 7.1852 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 9.1711 |  | 715.3477
1505120 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505121 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1505121 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505122 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | 1 | SchXST | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1505122 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505123 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505123 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL02 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505124 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | 1 | CL3000 | NA | EA | 1 | 1 | CS | ZL02 | 0.78 | 1 | 110 | 0.78 |  | 85.8
1505124 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | 1 | NA | CL3000 | EA | 1 | 1 | CS | ZL02 | 2.86 | 1 | 110 | 2.86 |  | 314.6
1505125 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505125 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505126 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 9.112 | 0 | NA | NA | 0.40947 | 1 | 110 | 3.7311 |  | 410.4188
1505126 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 10.4788 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 20.6492 |  | 1610.6372
1505127 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505127 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505128 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505128 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505129 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505129 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505130 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505130 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505131 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.3 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.17147 |  | 18.8612
1505131 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.345 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 0.95024 |  | 74.1187
1505132 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505132 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505133 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505133 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505134 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 4.6 | 0 | NA | NA | 0.57155 | 1 | 110 | 2.6291 |  | 289.2044
1505134 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 5.29 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 14.5703 |  | 1136.4865
1505135 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.382 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.3614 |  | 149.7576
1505135 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.7393 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 7.5449 |  | 588.5023
1505136 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505136 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505137 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505137 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505138 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 8 SchSTD | 8 | SchSTD | NA | LM | 8.022 | 0 | NA | NA | 0.26871 | 1 | 110 | 2.1556 |  | 237.1185
1505138 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | NA | 150-20-F-210 | Install Spools - NB 8 SchSTD | 8 | SchSTD | NA | LM | 8.8242 | 0 | NA | NA | 1.7019 | 0.75 | 78 | 11.2631 |  | 878.5241
1505139 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1505139 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1505140 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 8 | CS | ZL02 | 3.0095 | 1 | 110 | 3.0095 |  | 331.045
1505140 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | 8 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 3.38 | 0.75 | 78 | 1.2675 |  | 98.865
1505141 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.117 | 0 | NA | NA | 0.40947 | 1 | 110 | 0.45738 |  | 50.3114
1505141 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | NA | 150-20-F-210 | Install Spools - NB 12 SchSTD | 12 | SchSTD | NA | LM | 1.2845 | 0 | NA | NA | 2.6274 | 0.75 | 78 | 2.5313 |  | 197.4409
1505142 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 12 | CS | ZL02 | 4.7255 | 1 | 110 | 4.7255 |  | 519.805
1505142 | 600 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505143 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.6 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.34293 |  | 37.7223
1505143 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.69 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.9005 |  | 148.2374
1505144 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505144 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505145 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505146 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1505146 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505147 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505147 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505148 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505148 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505149 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505149 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1505150 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505150 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505151 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.812 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.4641 |  | 51.0509
1505151 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.9338 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.572 |  | 200.6146
1505152 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505152 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505153 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505153 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505154 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.021 | 0 | NA | NA | 0.57155 | 1 | 110 | 1.1551 |  | 127.0613
1505154 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 2.3241 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 6.4014 |  | 499.3129
1505155 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | Pipe to Pipe Field Run | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 11.3555 | 0.75 | 78 | 8.5166 |  | 664.2967
1505155 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | 12 | Sch80 | NA | LM | 19.4914 | 0 | NA | NA | 3.1137 | 0.75 | 78 | 45.5172 |  | 3550.3423
1505155 | 300 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-80-F-810 | Field Coating - NB 12 | 12 | NA | NA | LM | 19.4914 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 120 | 2338.962
1505156 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.827 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.47267 |  | 51.9939
1505156 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.95105 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.6195 |  | 204.3205
1505157 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505157 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505158 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505158 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505159 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505159 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505160 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505160 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505161 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505161 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505162 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.676 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.38637 |  | 42.5005
1505162 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.7774 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 2.1412 |  | 167.0141
1505163 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505163 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505164 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | 12 | Sch80 | NA | LM | 15.7101 | 0 | NA | NA | 3.1137 | 0.75 | 78 | 36.6872 |  | 2861.5981
1505164 | 300 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-80-F-810 | Field Coating - NB 12 | 12 | NA | NA | LM | 15.7101 | 0 | CS | NA | 0 | 0.75 | 78 | 0 | 120 | 1885.218
1505165 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 7.224 | 0 | NA | NA | 0.57155 | 1 | 110 | 4.1289 |  | 454.1767
1505165 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 8.3076 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 22.8818 |  | 1784.7779
1505166 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.077 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.61556 |  | 67.7116
1505166 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 1.2385 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 3.4114 |  | 266.0861
1505167 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | NA | 150-30-F-310 | Install valve - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 0.78 | 0.75 | 78 | 0.585 |  | 45.63
1505167 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505168 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | 1 | Sch160 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505168 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | 1 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505169 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505169 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END2 | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | 1 | SchXXS | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505170 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | 1 | CL6000 | NA | EA | 1 | 1 | CS | ZL01 | 0.91 | 1 | 110 | 0.91 |  | 100.1
1505170 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | Olet | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | 1 | NA | CL6000 | EA | 1 | 1 | CS | ZL01 | 3.77 | 1 | 110 | 3.77 |  | 414.7
1505171 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505171 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505172 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505172 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505173 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505173 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505174 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505174 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505175 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505175 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505176 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505176 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505177 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505177 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505178 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505178 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505179 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505180 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-30-F-310 | Install valve - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.69 | 0.75 | 78 | 1.2675 |  | 98.865
1505180 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 1 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.8775 |  | 68.445
1505181 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 2 | CS | ZL01 | 1.1765 | 1 | 110 | 1.1765 |  | 129.415
1505181 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | 2 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 1.17 | 0.75 | 78 | 0.43875 |  | 34.2225
1505182 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 9.078 | 0 | NA | NA | 0.57155 | 1 | 110 | 5.1885 |  | 570.7386
1505182 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 10.4397 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 28.7542 |  | 2242.8314
1505183 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505183 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505184 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505184 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505185 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.5 | 0 | NA | NA | 0.57155 | 1 | 110 | 0.28578 |  | 31.4353
1505185 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-20-F-210 | Install Spools - NB 12 Sch80 | 12 | Sch80 | NA | LM | 0.575 | 0 | NA | NA | 3.6724 | 0.75 | 78 | 1.5837 |  | 123.5311
1505186 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505186 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505187 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1505187 | 600 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1505188 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 7.683 | 1 | 110 | 15.366 |  | 1690.26
1505188 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505189 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505189 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505190 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 7.683 | 1 | 110 | 7.683 |  | 845.13
1505190 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 5.33 | 0.75 | 78 | 1.9988 |  | 155.9025
1505191 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | NA | 150-30-F-310 | Install valve - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 8.19 | 0.75 | 78 | 6.1425 |  | 479.115
1505191 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | 12 | NA | CL600 | EA | 1 | 0 | NA | NA | 5.33 | 0.75 | 78 | 3.9975 |  | 311.805
1505192 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 6.025 | 0 | NA | NA | 0.79335 | 1 | 110 | 4.7799 |  | 525.7899
1505192 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 6.9287 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 26.5314 |  | 2069.4479
1505193 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1505193 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1505194 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END2 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1505194 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1505195 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | NA | 150-29-S-290 | Shop handling - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.624 | 0 | NA | NA | 0.79335 | 1 | 110 | 0.49505 |  | 54.4553
1505195 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | NA | 150-20-F-210 | Install Spools - NB 16 Sch80 | 16 | Sch80 | NA | LM | 0.7176 | 0 | NA | NA | 5.1056 | 0.75 | 78 | 2.7478 |  | 214.3295
1505196 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | END1 | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 16 | CS | ZL01 | 14.365 | 1 | 110 | 14.365 |  | 1580.15
1505196 | 600 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Field | FLG | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | 16 | NA | CL600 | EA | 0.5 | 0 | NA | NA | 6.76 | 0.75 | 78 | 2.535 |  | 197.73
99999995 | 600 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Field | Field Weld Module Connect | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 11.3555 | 0.75 | 78 | 8.5166 |  | 664.2967
99999995 | 600 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Field | Field Weld Module Connect | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 12 | CS | ZL01 | 11.3555 | 0.75 | 78 | 8.5166 |  | 664.2967
99999995 | 600 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Field | Field Weld Module Connect | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 24 | CS | ZL01 | 11.3555 | 0.75 | 78 | 17.0332 |  | 1328.5935
99999995 | 600 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Field | Field Weld Module Connect | 150-10-F-110 | Field Butt Weld - NB 16 Sch80 | 16 | Sch80 | NA | EA | 2 | 32 | CS | ZL01 | 20.3905 | 0.75 | 78 | 30.5858 |  | 2385.6885
99999995 | 600 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Field | Field Weld Module Connect | 150-10-F-110 | Field Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | 1 | 16 | CS | ZL02 | 11.6532 | 0.75 | 78 | 8.7399 |  | 681.7122
99999995 | 600 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Field | Field Weld Module Connect | 150-10-F-110 | Field Butt Weld - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 20 | CS | ZL01 | 31.2637 | 0.75 | 78 | 23.4478 |  | 1828.9264
99999995 | 600 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Field | Field Weld Module Connect | 150-10-F-110 | Field Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 40.3455 | 0.75 | 78 | 30.2591 |  | 2360.2117
99999995 | 600 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Field | Field Weld Module Connect | 150-10-F-110 | Field Butt Weld - NB 24 Sch80 | 24 | Sch80 | NA | EA | 1 | 24 | CS | ZL01 | 40.3455 | 0.75 | 78 | 30.2591 |  | 2360.2117
99999996 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field | Field Weld Spool | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 4 | CS | XP01 | 1.6003 | 0.75 | 78 | 2.4004 |  | 187.2351
99999997 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | Deduct Shop Welds Reallocated | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | -2 | -4 | CS | XP01 | 1.1765 | 1 | 110 | -2.353 |  | -258.83
99999998 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication | Deduct Shop Welds - Correction for ftg to ftg welds | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | 2 | SchXST | NA | EA | -3 | -6 | CS | ZL02 | 1.1765 | 1 | 110 | -3.5295 |  | -388.245
99999998 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | Deduct Shop Welds - Correction for ftg to ftg welds | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | 8 | SchSTD | NA | EA | -5 | -40 | CS | ZL02 | 3.0095 | 1 | 110 | -15.0475 |  | -1655.225
99999998 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | Deduct Shop Welds - Correction for ftg to ftg welds | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | 12 | SchSTD | NA | EA | -4 | -48 | CS | ZL02 | 4.7255 | 1 | 110 | -18.902 |  | -2079.22
99999998 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | Deduct Shop Welds - Correction for ftg to ftg welds | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | 16 | SchSTD | NA | EA | -4 | -64 | CS | ZL02 | 8.8313 | 1 | 110 | -35.3253 |  | -3885.7867
99999998 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | Deduct Shop Welds - Correction for ftg to ftg welds | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | 24 | SchXST | NA | EA | -2 | -48 | CS | ZL02 | 17.7732 | 1 | 110 | -35.5463 |  | -3910.0967
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 33 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1650
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 33 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1650
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 0.75 | 0.75 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 15 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 750
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5052 | ISO1058 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5051 | ISO2065 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 19 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 950
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4016 | ISO3085 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3027 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 14 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 700
999999990 | 400 | Proj_A | Area_2 | TR | TR-YP01-8100 | ISO4026 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_2 | TR | TR-YP01-8099 | ISO4024 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4015 | ISO3083 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 17 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 850
999999990 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4019 | ISO3089 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 17 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 850
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2060 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2062 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 25 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1250
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2060 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 19 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 950
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 20 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1000
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2059 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5050 | ISO2035 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2061 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8053 | ISO3057 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 7 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 350
999999990 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4020 | ISO2042 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8048 | ISO3036 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 7 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 350
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8049 | ISO3037 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 7 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 350
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8050 | ISO3045 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 7 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 350
999999990 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8052 | ISO3056 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 7 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 350
999999990 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8085 | ISO2038 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8075 | ISO3054 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5001 | ISO3053 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5006 | ISO2046 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5007 | ISO3038 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5008 | ISO3047 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 32 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1600
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8051 | ISO3046 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 7 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 350
999999990 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5042 | ISO3077 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5040 | ISO3076 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3003 | ISO2037 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4014 | ISO1040 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4018 | ISO2027 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5041 | ISO3070 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1 | 1 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1.5 | 1.5 |  |  | EA | 22 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1100
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1.5 | 1.5 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 1.5 | 1.5 |  |  | EA | 22 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1100
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 10 | 10 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 750
999999990 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 4500
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 4500
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 2000
999999990 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 750
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 750
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 750
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-YP01-5015 | ISO2023 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 2000
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 750
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5011 | ISO1001 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 2000
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 750
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3021 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 12 | 12 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 14 | 14 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 14 | 14 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 14 | 14 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 14 | 14 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 14 | 14 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 14 | 14 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2084 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 1000
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3017 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 500
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 2500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO3013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 1000
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 1000
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3002 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 1000
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2080 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 16 | 16 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 250 | 1000
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2093 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8044 | ISO3051 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3058 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8038 | ISO3048 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8061 | ISO3068 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 16 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 800
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8037 | ISO1047 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_1 | DL | DL-XP01-8002 | ISO2006 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 16 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 800
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3060 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8057 | ISO3063 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3005 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8068 | ISO3081 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3003 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO3001 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO2085 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8064 | ISO3069 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8067 | ISO3064 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8058 | ISO3062 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8059 | ISO3067 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8060 | ISO3065 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO2081 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8063 | ISO3066 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8022 | ISO3084 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO1018 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 900
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3075 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 22 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1100
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8021 | ISO1034 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8065 | ISO3079 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8070 | ISO1018 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 7 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 350
999999990 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8020 | ISO1042 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8023 | ISO3086 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | DL | DL-ZL01-8035 | ISO3090 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_8 | LG | LG-XP01-4001 | ISO1014 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 900
999999990 | 400 | Proj_A | Area_8 | LG | LG-XP01-4017 | ISO3087 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 17 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 850
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8055 | ISO2007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 900
999999990 | 400 | Proj_A | Area_9 | TR | TR-XP01-8096 | ISO4021 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_8 | DL | DL-XP01-8025 | ISO3088 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 17 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 850
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8062 | ISO3078 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8036 | ISO3042 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8066 | ISO3080 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3043 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_6 | DL | DL-ZL01-8069 | ISO3082 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1031 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 17 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 850
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 12 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 600
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8017 | ISO1043 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8018 | ISO1044 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8019 | ISO1039 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 9 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 450
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8024 | ISO1037 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 9 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 450
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8071 | ISO1041 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8072 | ISO1038 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8073 | ISO1035 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_7 | DL | DL-ZL01-8016 | ISO1045 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 9 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 450
999999990 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 11 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 550
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 19 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 950
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 900
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8045 | ISO3034 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3027 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 19 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 950
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 14 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 700
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 20 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1000
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 16 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 800
999999990 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_10 | IA | IA-XP02-9001 | ISO3072 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 29 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1450
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 900
999999990 | 400 | Proj_A | Area_1 | DL | DL-ZL01-8084 | ISO2043 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 900
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2012 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2014 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_2 | DL | DL-ZL01-8013 | ISO2064 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8081 | ISO2001 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8080 | ISO2071 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8014 | ISO1036 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8012 | ISO2063 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8011 | ISO2070 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3032 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8010 | ISO2066 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5048 | ISO2059 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8009 | ISO2068 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 9 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 450
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5049 | ISO2062 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8008 | ISO2061 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5003 | ISO2016 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8007 | ISO2060 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2057 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 9 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 450
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8006 | ISO2052 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 16 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 800
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 18 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 900
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 22 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1100
999999990 | 400 | Proj_A | Area_3 | TR | TR-XP01-8097 | ISO4022 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8027 | ISO3035 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 25 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1250
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8029 | ISO1049 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 22 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1100
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8032 | ISO3041 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_3 | IA | IA-XP02-9010 | ISO2051 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8034 | ISO3044 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3039 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8040 | ISO3050 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5002 | ISO2017 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8042 | ISO3055 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 28 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1400
999999990 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8026 | ISO2047 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-ZL01-8030 | ISO3039 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 24 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1200
999999990 | 400 | Proj_A | Area_10 | DL | DL-ZL01-8077 | ISO2069 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_10 | GH | GH-YP01-3004 | ISO3093 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 14 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 700
999999990 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_3 | IA | IA-XP02-9006 | ISO2045 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_10 | BD | BD-XP01-6002 | ISO3094 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_1 | IA | IA-XP02-9003 | ISO2044 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 2 | 2 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 1500
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5037 | ISO2078 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 500
999999990 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 500
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 20 | 20 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 2000
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 24 | 24 |  |  | EA | 12 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 6000
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 24 | 24 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 2000
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 24 | 24 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 1000
999999990 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 24 | 24 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 500 | 2000
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8054 | ISO2049 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_9 | DL | DL-XP01-8056 | ISO2050 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO1060 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 16 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 800
999999990 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 20 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 1000
999999990 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5020 | ISO2013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_1 | FL | FL-YP01-8121 | ISO1055 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 5 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 250
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5022 | ISO2015 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 10 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 500
999999990 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8083 | ISO1003 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 15 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 750
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 13 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 650
999999990 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2053 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 8 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 400
999999990 | 400 | Proj_A | Area_3 | DL | DL-XP01-8047 | ISO3024 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 300
999999990 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 3 | 3 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 200
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4011 | ISO2030 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 19 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 950
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5053 | ISO3091 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3001 | ISO2031 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 100
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5032 | ISO4008 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5005 | ISO1002 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5004 | ISO2028 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 50
999999990 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 4 | 4 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 50 | 150
999999990 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2003 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 12 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 900
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4005 | ISO1013 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 150
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5054 | ISO2067 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 150
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO1012 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4007 | ISO2008 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 12 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 900
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 300
999999990 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 6 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 450
999999990 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 75
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 150
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 225
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 150
999999990 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 150
999999990 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 150
999999990 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 3 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 225
999999990 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 4 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 300
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 150
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 6 | 6 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 75 | 150
999999990 | 400 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 13 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 1300
999999990 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 19 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 1900
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4007 | ISO1011 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3020 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 200
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5024 | ISO1057 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 200
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 200
999999990 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5023 | ISO1056 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 200
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4004 | ISO3019 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5047 | ISO1024 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 200
999999990 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1046 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1008 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4003 | ISO1009 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 100
999999990 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication |  | 150-60-S-610 | Shop X-Ray - NB 8 | 8 |  |  | EA | 2 | 0 | NA | NA | 0 | 1 | 110 | 0 | 100 | 200
999999990 | 600 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Field |  | 150-60-F-610 | Field X-Ray - NB 12 | 12 |  |  | EA | 1 | 0 | NA | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500
999999990 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Field |  | 150-60-F-610 | Field X-Ray - NB 2 | 2 |  |  | EA | 1 | 0 | NA | NA | 0 | 0.75 | 78 | 0 | 750 | 750
999999990 | 600 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3028 | Field |  | 150-60-F-610 | Field X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 0.75 | 78 | 0 | 750 | 2250
999999990 | 600 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Field |  | 150-60-F-610 | Field X-Ray - NB 2 | 2 |  |  | EA | 3 | 0 | NA | NA | 0 | 0.75 | 78 | 0 | 750 | 2250
999999990 | 600 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Field |  | 150-60-F-610 | Field X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 0.75 | 78 | 0 | 1000 | 1000
999999990 | 600 | Proj_A | Area_9 | FL | FL-XP01-8117 | ISO2002 | Field |  | 150-60-F-610 | Field X-Ray - NB 6 | 6 |  |  | EA | 1 | 0 | NA | NA | 0 | 0.75 | 78 | 0 | 1000 | 1000
999999990 | 600 | Proj_A | Area_3 | BD | BD-XP01-6001 | ISO2076 | Field |  | 150-60-F-610 | Field X-Ray - NB 8 | 8 |  |  | EA | 1 | 0 | NA | NA | 0 | 0.75 | 78 | 0 | 1500 | 1500
999999991 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 0 | NA | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
999999991 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 0 | NA | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
999999991 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 0 | NA | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
999999991 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 2 | 0 | NA | NA | 5.6 | 1 | 110 | 11.2 |  | 1232
999999991 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 3 | 0 | NA | NA | 5.6 | 1 | 110 | 16.8 |  | 1848
999999991 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 1 | 0 | NA | NA | 5.6 | 1 | 110 | 5.6 |  | 616
999999991 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | 2 | SchXST | NA | EA | 3 | 0 | NA | NA | 5.6 | 1 | 110 | 16.8 |  | 1848
999999991 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 0 | NA | NA | 6 | 1 | 110 | 6 |  | 660
999999991 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 0 | NA | NA | 6 | 1 | 110 | 6 |  | 660
999999991 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 0 | NA | NA | 6 | 1 | 110 | 6 |  | 660
999999991 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 0 | NA | NA | 6 | 1 | 110 | 6 |  | 660
999999991 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 0 | NA | NA | 6 | 1 | 110 | 6 |  | 660
999999991 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 0 | NA | NA | 6 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 0 | NA | NA | 6 | 1 | 110 | 6 |  | 660
999999991 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 2 | 0 | NA | NA | 6 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | 3 | SchSTD | NA | EA | 1 | 0 | NA | NA | 6 | 1 | 110 | 6 |  | 660
999999991 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 4 SchSTD | 4 | SchSTD | NA | EA | 1 | 0 | NA | NA | 7 | 1 | 110 | 7 |  | 770
999999991 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 0 | NA | NA | 8.4 | 1 | 110 | 8.4 |  | 924
999999991 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | 4 | SchXST | NA | EA | 3 | 0 | NA | NA | 8.4 | 1 | 110 | 25.2 |  | 2772
999999991 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | 4 | SchXST | NA | EA | 3 | 0 | NA | NA | 8.4 | 1 | 110 | 25.2 |  | 2772
999999991 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | 4 | SchXST | NA | EA | 1 | 0 | NA | NA | 8.4 | 1 | 110 | 8.4 |  | 924
999999991 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchSTD | 6 | SchSTD | NA | EA | 1 | 0 | NA | NA | 8.8 | 1 | 110 | 8.8 |  | 968
999999991 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 2 | 0 | NA | NA | 12 | 1 | 110 | 24 |  | 2640
999999991 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 2 | 0 | NA | NA | 12 | 1 | 110 | 24 |  | 2640
999999991 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 3 | 0 | NA | NA | 12 | 1 | 110 | 36 |  | 3960
999999991 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 1 | 0 | NA | NA | 12 | 1 | 110 | 12 |  | 1320
999999991 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | 6 | SchXST | NA | EA | 3 | 0 | NA | NA | 12 | 1 | 110 | 36 |  | 3960
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | 8 | SchSTD | NA | EA | 3 | 0 | NA | NA | 9.8 | 1 | 110 | 29.4 |  | 3234
999999991 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | 8 | SchSTD | NA | EA | 1 | 0 | NA | NA | 9.8 | 1 | 110 | 9.8 |  | 1078
999999991 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 0 | NA | NA | 16 | 1 | 110 | 16 |  | 1760
999999991 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 8 SchXST | 8 | SchXST | NA | EA | 1 | 0 | NA | NA | 16 | 1 | 110 | 16 |  | 1760
999999991 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 0 | NA | NA | 14.6 | 1 | 110 | 14.6 |  | 1606
999999991 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 0 | NA | NA | 14.6 | 1 | 110 | 14.6 |  | 1606
999999991 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | 10 | Sch80 | NA | EA | 2 | 0 | NA | NA | 14.6 | 1 | 110 | 29.2 |  | 3212
999999991 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | 10 | Sch80 | NA | EA | 1 | 0 | NA | NA | 14.6 | 1 | 110 | 14.6 |  | 1606
999999991 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 3 | 0 | NA | NA | 19 | 1 | 110 | 57 |  | 6270
999999991 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 0 | NA | NA | 19 | 1 | 110 | 19 |  | 2090
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 0 | NA | NA | 19 | 1 | 110 | 38 |  | 4180
999999991 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 0 | NA | NA | 19 | 1 | 110 | 19 |  | 2090
999999991 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 0 | NA | NA | 19 | 1 | 110 | 19 |  | 2090
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 0 | NA | NA | 19 | 1 | 110 | 19 |  | 2090
999999991 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 0 | NA | NA | 19 | 1 | 110 | 38 |  | 4180
999999991 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 6 | 0 | NA | NA | 19 | 1 | 110 | 114 |  | 12540
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 0 | NA | NA | 19 | 1 | 110 | 19 |  | 2090
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 0 | NA | NA | 19 | 1 | 110 | 19 |  | 2090
999999991 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 0 | NA | NA | 19 | 1 | 110 | 19 |  | 2090
999999991 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 3 | 0 | NA | NA | 19 | 1 | 110 | 57 |  | 6270
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 1 | 0 | NA | NA | 19 | 1 | 110 | 19 |  | 2090
999999991 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | 12 | Sch80 | NA | EA | 2 | 0 | NA | NA | 19 | 1 | 110 | 38 |  | 4180
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 0 | NA | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
999999991 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | 12 | SchSTD | NA | EA | 3 | 0 | NA | NA | 12.2 | 1 | 110 | 36.6 |  | 4026
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 0 | NA | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
999999991 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | 12 | SchSTD | NA | EA | 2 | 0 | NA | NA | 12.2 | 1 | 110 | 24.4 |  | 2684
999999991 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | 12 | SchSTD | NA | EA | 1 | 0 | NA | NA | 12.2 | 1 | 110 | 12.2 |  | 1342
999999991 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | 16 | Sch80 | NA | EA | 2 | 0 | NA | NA | 17.6 | 1 | 110 | 35.2 |  | 3872
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | 16 | Sch80 | NA | EA | 6 | 0 | NA | NA | 17.6 | 1 | 110 | 105.6 |  | 11616
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | 16 | Sch80 | NA | EA | 1 | 0 | NA | NA | 17.6 | 1 | 110 | 17.6 |  | 1936
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 16 SchSTD | 16 | SchSTD | NA | EA | 3 | 0 | NA | NA | 15.6 | 1 | 110 | 46.8 |  | 5148
999999991 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 0 | NA | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | 20 | Sch80 | NA | EA | 2 | 0 | NA | NA | 41.2 | 1 | 110 | 82.4 |  | 9064
999999991 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 0 | NA | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
999999991 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 0 | NA | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
999999991 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 0 | NA | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
999999991 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 0 | NA | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | 20 | Sch80 | NA | EA | 4 | 0 | NA | NA | 41.2 | 1 | 110 | 164.8 |  | 18128
999999991 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | 20 | Sch80 | NA | EA | 1 | 0 | NA | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
999999991 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 24 Sch40 | 24 | Sch40 | NA | EA | 1 | 0 | NA | NA | 41.2 | 1 | 110 | 41.2 |  | 4532
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 24 Sch80 | 24 | Sch80 | NA | EA | 3 | 0 | NA | NA | 62.6 | 1 | 110 | 187.8 |  | 20658
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 24 Sch80 | 24 | Sch80 | NA | EA | 5 | 0 | NA | NA | 62.6 | 1 | 110 | 313 |  | 34430
999999991 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | NA | 150-70-S-710 | Shop Hydrotest - NB 24 SchXST | 24 | SchXST | NA | EA | 1 | 0 | NA | NA | 30.8 | 1 | 110 | 30.8 |  | 3388
999999992 | 400 | Proj_A | Area_2 | IA | IA-XP02-9002 | ISO2072 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_2 | IA | IA-XP02-9005 | ISO2074 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3032 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 1500
999999992 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3029 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 1500
999999992 | 400 | Proj_A | Area_10 | IA | IA-XP02-9009 | ISO3092 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_1 | DL | DL-XP01-8001 | ISO2036 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_9 | DL | DL-XP01-8015 | ISO2007 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_4 | DL | DL-XP01-8039 | ISO3049 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_3 | DL | DL-XP01-8046 | ISO3030 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_4 | DL | DL-XP01-8074 | ISO2048 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_3 | DL | DL-XP01-8043 | ISO3033 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 1000
999999992 | 400 | Proj_A | Area_10 | IA | IA-XP02-9007 | ISO3071 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_9 | DL | DL-XP01-8082 | ISO2022 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 1000
999999992 | 400 | Proj_A | Area_8 | DL | DL-XP01-8003 | ISO3074 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_5 | DL | DL-ZL01-8069 | ISO3059 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_6 | IA | IA-XP02-9001 | ISO3073 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1033 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_4 | DL | DL-XP01-8028 | ISO1048 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_4 | DL | DL-XP01-8033 | ISO3043 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_7 | DL | DL-XP01-8003 | ISO1032 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_10 | DL | DL-ZL02-8078 | ISO1059 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_4 | DL | DL-XP01-8041 | ISO3052 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 1000
999999992 | 400 | Proj_A | Area_3 | DL | DL-XP01-8079 | ISO3031 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_2 | IA | IA-XP02-9004 | ISO2073 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 1000
999999992 | 400 | Proj_A | Area_10 | IA | IA-XP02-9008 | ISO2058 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_4 | DL | DL-XP01-8031 | ISO3040 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 2 | 2 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 500 | 500
999999992 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2055 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 600
999999992 | 400 | Proj_A | Area_1 | FL | FL-XP01-8123 | ISO2040 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 600
999999992 | 400 | Proj_A | Area_5 | FL | FL-XP01-8124 | ISO3061 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 600
999999992 | 400 | Proj_A | Area_3 | DL | DL-XP01-8076 | ISO3025 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 600
999999992 | 400 | Proj_A | Area_2 | DL | DL-YP01-8005 | ISO2054 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 600
999999992 | 400 | Proj_A | Area_2 | DL | DL-YP01-8004 | ISO2052 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 600
999999992 | 400 | Proj_A | Area_9 | FL | FL-XP01-8119 | ISO1060 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 600
999999992 | 400 | Proj_A | Area_2 | FL | FL-YP01-8122 | ISO2005 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 1200
999999992 | 400 | Proj_A | Area_9 | FL | FL-XP01-8118 | ISO2004 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 3 | 3 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 600 | 1200
999999992 | 400 | Proj_A | Area_3 | BD | BD-XP01-6003 | ISO2075 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 4 | 4 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 700 | 700
999999992 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5046 | ISO1023 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 4 | 4 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 700 | 2100
999999992 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4012 | ISO2041 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 4 | 4 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 700 | 700
999999992 | 400 | Proj_A | Area_1 | GH | GH-ZL01-3002 | ISO2032 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 4 | 4 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 700 | 700
999999992 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5045 | ISO1053 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 4 | 4 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 700 | 2100
999999992 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5046 | ISO3010 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1029 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1027 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1017 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5046 | ISO1054 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 1800
999999992 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4009 | ISO1016 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 2700
999999992 | 400 | Proj_A | Area_8 | LG | LG-ZL01-4009 | ISO3012 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4009 | ISO1030 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 1800
999999992 | 400 | Proj_A | Area_9 | FL | FL-XP01-8120 | ISO2034 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4008 | ISO1026 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_1 | LG | LG-ZL01-4008 | ISO1028 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 2700
999999992 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4008 | ISO1025 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5045 | ISO1052 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5045 | ISO3011 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 6 | 6 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 900 | 900
999999992 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5043 | ISO3008 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 8 | 8 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1100 | 1100
999999992 | 400 | Proj_A | Area_10 | GHH | GHH-XP01-1001 | ISO1046 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 8 | 8 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1100 | 1100
999999992 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5044 | ISO3009 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 8 | 8 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1100 | 1100
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5009 | ISO1004 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 8 | 8 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1100 | 3300
999999992 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2026 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 10 | 10 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1500 | 1500
999999992 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5017 | ISO2010 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 10 | 10 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1500 | 3000
999999992 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2024 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 10 | 10 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1500 | 1500
999999992 | 400 | Proj_A | Area_1 | HPG | HPG-ZL01-5016 | ISO2025 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 10 | 10 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1500 | 1500
999999992 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1005 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 3400
999999992 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2018 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 5100
999999992 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2019 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 6 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 10200
999999992 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2021 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 5100
999999992 | 400 | Proj_A | Area_6 | HPG | HPG-ZL01-5047 | ISO2056 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 3400
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5013 | ISO1020 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO2033 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5036 | ISO2086 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_5 | HPG | HPG-ZL01-5025 | ISO2087 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5010 | ISO1019 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 3400
999999992 | 400 | Proj_A | Area_7 | LG | LG-ZL01-4002 | ISO1007 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_10 | LG | LG-ZL01-4002 | ISO1006 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3022 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_10 | LG | LG-XP01-4013 | ISO1050 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_10 | LG | LG-XP01-4010 | ISO2029 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 5100
999999992 | 400 | Proj_A | Area_10 | LG | LG-XP01-4001 | ISO1015 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 3400
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL02-5012 | ISO1021 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5047 | ISO3023 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_2 | HPG | HPG-ZL01-5025 | ISO2020 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 12 | 12 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 1700 | 1700
999999992 | 400 | Proj_A | Area_10 | HPG | HPG-ZL01-5014 | ISO1022 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 16 | 16 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2100 | 4200
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5014 | ISO2077 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 16 | 16 | NA | NA | EA | 6 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2100 | 12600
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5038 | ISO3007 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 16 | 16 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2100 | 6300
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5021 | ISO3006 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 16 | 16 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2100 | 2100
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2082 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 20 | 20 | NA | NA | EA | 4 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2700 | 10800
999999992 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5033 | ISO3004 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 20 | 20 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2700 | 2700
999999992 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5031 | ISO3016 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 20 | 20 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2700 | 2700
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5029 | ISO2083 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 20 | 20 | NA | NA | EA | 2 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2700 | 5400
999999992 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5027 | ISO2092 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 20 | 20 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2700 | 2700
999999992 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5028 | ISO3014 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 20 | 20 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2700 | 2700
999999992 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5030 | ISO2094 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 20 | 20 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2700 | 2700
999999992 | 400 | Proj_A | Area_4 | HPG | HPG-ZL01-5034 | ISO3018 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 20 | 20 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2700 | 2700
999999992 | 400 | Proj_A | Area_2 | HPG | HPG-YP01-5018 | ISO2011 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 24 | 24 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2880 | 2880
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5026 | ISO2091 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 24 | 24 | NA | NA | EA | 5 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2880 | 14400
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL01-5035 | ISO2090 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 24 | 24 | NA | NA | EA | 3 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2880 | 8640
999999992 | 400 | Proj_A | Area_3 | HPG | HPG-ZL02-5019 | ISO2089 | Spool Fabrication | NA | 150-80-S-810 | Shop Spools Coating - NB 24 | 24 | NA | NA | EA | 1 | 0 | CS | NA | 0 | 1 | 110 | 0 | 2880 | 2880
999999999 | 400 | Summary | Summary | Summary | Summary | Summary | Spool Fabrication |  | 150-50-S-510 | Pipe Supports Labor (shoes, lugs, guides, etc.) | 0 |  |  | of Labor hours | 0.05 | 0 |  |  | 0 | 0 | 0 | 963.9511 |  | 106034.6258
999999999 | 500 | Summary | Summary | Summary | Summary | Summary | Module |  | 150-70-F-710 | Hydrotest of module assembly | 0 |  |  | of Module Labor | 0.05 | 0 |  |  | 0 | 0 | 0 | 230.2252 |  | 25324.7765
999999999 | 500 | Summary | Summary | Summary | Summary | Summary | Module |  | 150-90-F-910 | Flushing & Drying Module Piping | 0 |  |  | of Module Labor | 0.03 | 0 |  |  | 0 | 0 | 0 | 138.1351 |  | 15194.8659
999999999 | 600 | Summary | Summary | Summary | Summary | Summary | Field |  | 150-40-F-410 | Bolt torquing and tensioning | 0 |  |  | of bolt-up labor | 0.15 | 0 |  |  | 0 | 0 | 0 | 198.3296 |  | 15469.7108
999999999 | 600 | Summary | Summary | Summary | Summary | Summary | Field |  | 150-70-F-710 | Field Hydrotest | 0 |  |  | of Field Labor | 0.05 | 0 |  |  | 0 | 0 | 0 | 285.076 |  | 22235.93
999999999 | 600 | Summary | Summary | Summary | Summary | Summary | Field |  | 150-90-F-910 | Flushing & Drying on Site | 0 |  |  | of Field Labor | 0.03 | 0 |  |  | 0 | 0 | 0 | 171.0456 |  | 13341.558
Piping Labor Detail - Trace back to the source MTO Line Item by MTO_ID
Example - Imaginary Project with made up quantities for Illustration Purposes
Go to Tab Index

## Piping Labor Summary Overview
Location | Code of Account (COA) & Description | Qty Units | Shop Quantity | FDI | Shop Hours | Shop Cost | Module Quantity | Module Hours | Module Cost | Field Quantity | Field Hours | Field Cost | Total Cost
Spool Fabrication | 150-80-S-810 - Shop Coating | Spools EA | 153 | 0 | 0 | 206200 | 0 | 0 | 0 | 0 | 0 | 0 | 206200
Spool Fabrication | 150-70-S-710 - Shop Hydrotest | EA | 153 | 0 | 2575.6 | 283316 | 0 | 0 | 0 | 0 | 0 | 0 | 283316
Spool Fabrication | 150-60-S-610 - Shop X-Ray | EA | 2167 | 0 | 0 | 164400 | 0 | 0 | 0 | 0 | 0 | 0 | 164400
Spool Fabrication | 150-50-S-519 - Shop Pipe Support (shoes, guides, etc.) | EA | 0 | 0 | 963.9511 | 106035 | 0 | 0 | 0 | 0 | 0 | 0 | 106035
Spool Fabrication | 150-29-S-290 - Shop Handling | M | 1796.798 | 0 | 848.0829 | 93289 | 0 | 0 | 0 | 0 | 0 | 0 | 93289
Spool Fabrication | 150-19-S-190 - Shop Threaded Joints | EA | 408 | 904.375 | 137.813 | 15159 | 0 | 0 | 0 | 0 | 0 | 0 | 15159
Spool Fabrication | 150-10-S-130 - Shop Olet Welds | EA | 210 | 1099.5 | 1014 | 111540 | 0 | 0 | 0 | 0 | 0 | 0 | 111540
Spool Fabrication | 150-10-S-120 - Shop Socket Welds | EA | 1817 | 2517.75 | 1595.1 | 175461 | 0 | 0 | 0 | 0 | 0 | 0 | 175461
Spool Fabrication | 150-10-S-110 - Shop Butt Welds | EA | 2879 | 40097.5 | 13108.4269 | 1441927 | 0 | 0 | 0 | 0 | 0 | 0 | 1441927
Spool Fabrication Total |  |  |  | 44619.125 | 20242.974 | 2597327 |  | 0 | 0 |  | 0 | 0 | 2597327
Module | 150-90-M-919 - Module Flushing, Chemical Cleaning - allowance | Lot | 0 | 0 | 0 | 0 | 0 | 138 | 15195 | 0 | 0 | 0 | 15195
Module | 150-70-M-719 - Module Hydrotest - allowance | Lot | 0 | 0 | 0 | 0 | 0 | 230 | 25325 | 0 | 0 | 0 | 25325
Module | 150-50-M-510 - Module Pipe Supports | EA | 0 | 0 | 0 | 0 | 83 | 162 | 17794 | 0 | 0 | 0 | 17791
Module | 150-40-M-410 - Module Flange Boltup | EA | 0 | 0 | 0 | 0 | 173 | 746 | 81495 | 0 | 0 | 0 | 81496
Module | 150-30-M-310 - Module Install Valves, blinds, inlines | EA | 0 | 0 | 0 | 0 | 74 | 282 | 31445 | 0 | 0 | 0 | 31446
Module | 150-20-M-210 - Module Erection of spools | LM | 0 | 0 | 0 | 0 | 715 | 3415 | 375758 | 0 | 0 | 0 | 375763
Module Total |  |  |  | 0 | 0 | 0 |  | 4973 | 547012 |  | 0 | 0 | 547016
Field | 150-90-F-919 - Field Flushing, Chemical Cleaning - allowance | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.0456 | 13342 | 13342
Field | 150-80-F-810 - Field Coating | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640.7836 | 0 | 59412 | 59412
Field | 150-70-F-719 - Field Hydrotest - allowance | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285.076 | 22236 | 22236
Field | 150-60-F-610 - Field X-Ray | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 10250 | 10250
Field | 150-50-F-510 - Field Pipe Supports | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 475.7192 | 37130 | 37106
Field | 150-40-F-419 - Field Bolt torquing and tensioning - allowance | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.3296 | 15470 | 15470
Field | 150-40-F-410 - Field Flange Boltup | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 839 | 1322.1975 | 103094 | 103131
Field | 150-30-F-310 - Field Install Valves, blinds, inlines | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 776.0025 | 60554 | 60528
Field | 150-25-F-250 - Field Installed piping | LM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640.7836 | 786.2873 | 61329 | 61330
Field | 150-20-F-210 - Field Erection of spools | LM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301.8388 | 2086.9609 | 162786 | 162783
Field | 150-10-F-110 - Field Butt Welds | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 254.3531 | 19839 | 19840
Field Total |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 6355.9718 | 565442 | 565428
Grand Total |  |  |  | 44619.125 | 20242.974 | 2597327 |  | 4973 | 547012 |  | 6355.9718 | 565442 | 3709771
Piping Labor Summary - Spool Fabrication, Module Yard and Field Quantities, Craft Labor Hours and Cost by Item Group
Example - Imaginary Project with made up quantities for Illustration Purposes See Interactive Power BI Report on the website for more estimate insights
Go to Tab Index

## Metrics by Location
Spool Fabrication Quantities and Metrics
Spool Fabrication Metric (SF) | SF Value | Area | Spool Fab Hrs | Labor Operations | Spool Fab Hours | Percent
Factored Diameter Inch - FDI | 44619 | Area_1 | 1453.2761 | Shop Butt Welds | 13108.4269 | 64.76%
Total Shop Fabrication Hours - Hrs | 20243 | Area_2 | 2593.1114 | Shop Hydrotest | 2575.6 | 12.72%
Total Shop Fabrication Cost - $ | 2597327 | Area_3 | 5697.4398 | Shop Socket Welds | 1595.1 | 7.88%
Shop Fabrication hours per meter of pipe thro'length - Hrs/LM | 7.6 | Area_4 | 3658.4957 | Shop Olet Welds | 1014 | 5.009%
Shop Fabrication hours per FDI - Hrs/FDI | 0.5 | Area_5 | 980.0458 | Shop Pipe Support | 963.9511 | 4.762%
Shop Fabrication Cost per FDI - $/FDI | 58 | Area_6 | 446.4423 | Shop Handling | 848.0829 | 4.19%
|  | Area_7 | 947.3952 | Shop Threaded Joints | 137.813 | 0.6808%
|  | Area_8 | 690.9783 | Shop X-Ray | Sub-Contract
|  | Area_9 | 239.673 | Shop Coating | Sub-Contract
|  | Area_10 | 2572.1653 | Total | 20242.974
|  | Allowances | 963.9511
|  | Total | 20242.974
Module Quantities and Metrics
|  |  |  | Labor Operations | Module Hrs | Percent
Module Piping Metric (MP) | MP Value | Area | Module Hrs | Module Erection of spools | 3415 | 68.67%
Module Pipe - thro'length - LM | 716 | Area_3 | 3060 | Module Flange Boltup | 746 | 15%
Module Hours - Hrs | 5084 | Area_2 | 1545 | Module Install Valves, blinds, inlines | 282 | 5.671%
Module Hours per M of pipe thro'length - Hrs/LM | 7.1 | Allowances | 368 | Module Hydrotest - allowance | 230 | 4.625%
Average pipe dia (Module Pipe) - inch | 15.5 | Total | 4973 | Module Pipe Supports | 162 | 3.258%
|  |  |  | Module Flushing, Chemical Cleaning - allowance | 138 | 2.775%
|  |  |  | Total | 4973
Field Quantities and Metrics
Field Piping Metric (FP) | FP Value | Area | Field Hrs | Labor Operations | Field Hrs | Percent
Field Pipe - thro'length - LM | 1943 | Area_1 | 942.8436 | Field Erection of spools | 2086.9609 | 32.83%
Field Hours - Hrs | 6356 | Area_2 | 181.291 | Field Flange Boltup | 1322.1975 | 20.8%
Field Hours per M of pipe thro'length - Hrs/LM | 3.3 | Area_3 | 533.5182 | Field Installed piping | 786.2873 | 12.37%
Average pipe dia (Field Pipe) - inch | 6.2 | Area_4 | 1143.8696 | Field Install Valves, blinds, inlines | 776.0025 | 12.21%
|  | Area_5 | 311.46 | Field Pipe Supports | 475.7192 | 7.485%
|  | Area_6 | 191.2156 | Field Hydrotest - allowance | 285.076 | 4.485%
|  | Area_7 | 308.5914 | Field Butt Welds | 254.3531 | 4.002%
|  | Area_8 | 225.7516 | Field Bolt torquing and tensioning - allowance | 198.3296 | 3.12%
|  | Area_9 | 196.4247 | Field Flushing, Chemical Cleaning - allowance | 171.0456 | 2.691%
|  | Area_10 | 1666.5548 | Field Coating | Sub-Contract
|  | Allowances | 654.4513 | Field X-Ray | Sub-Contract
|  | Total | 6355.9718 | Total | 6355.9718
Total Quantities and Metrics
Material Quantity Metric (QM) | QM Value
Total Pipe - throlength - LM | 2659
Large bore pipe (above 2 inch) - LM | 1970
Small bore pipe (2 inch & below) - LM | 689
Average pipe diameter - inch | 8.7
Large bore fittings & flanges (above 2 inch) - Ea | 1104
Small bore fittings & flanges (2 inch & below) - Ea | 2081
LB Fittings & Flanges frequency - M/Fitting | 2
SB Fittings & Flanges frequency - M/Fitting | 0.33
Large bore valves (above 2 inch) - Ea | 74
Small bore valves (2 inch & below) - Ea | 414
LB valve frequency - M/Valve | 27
SB valve frequency - M/Valve | 1.7
Piping Labor - Spool Fabrication, Module Yard and Field Quantities, Craft Labor Hours and Metrics
Example - Imaginary Project with made up quantities for Illustration Purposes See Interactive Power BI Report on the website for more estimate insights
Go to Tab Index

## Spool Fab Summary
Dia | COA | Description | Units | Shop Quantity | FDI | Shop Hours | Shop Cost
24 inch | 150-10-S-110 | Shop Butt Weld - NB 24 Sch40 | EA | 12 | 720 | 220.376 | 24241
24 inch | 150-10-S-110 | Shop Butt Weld - NB 24 Sch80 | EA | 51 | 3978 | 1693.1915 | 186251
24 inch | 150-10-S-110 | Shop Butt Weld - NB 24 SchXST | EA | 10 | 480 | 177.7317 | 19550
24 inch | 150-29-S-290 | Shop handling - NB 24 Sch40 | LM | 14.46 | 0 | 12.952 | 1425
24 inch | 150-29-S-290 | Shop handling - NB 24 Sch80 | LM | 103.42 | 0 | 120.425 | 13247
24 inch | 150-29-S-290 | Shop handling - NB 24 SchXST | LM | 12.399 | 0 | 14.4377 | 1588
24 inch | 150-60-S-610 | Shop X-Ray - NB 24 | EA | 22 | 0 | 0 | 11000
24 inch | 150-70-S-710 | Shop Hydrotest - NB 24 Sch40 | EA | 1 | 0 | 41.2 | 4532
24 inch | 150-70-S-710 | Shop Hydrotest - NB 24 Sch80 | EA | 8 | 0 | 500.8 | 55088
24 inch | 150-70-S-710 | Shop Hydrotest - NB 24 SchXST | EA | 1 | 0 | 30.8 | 3388
24 inch | 150-80-S-810 | Shop Spools Coating - NB 24 | EA | 10 | 0 | 0 | 28800
24 inch Total |  |  |  |  | 5178 | 2811.9139 | 349110
20 inch | 150-10-S-110 | Shop Butt Weld - NB 20 Sch80 | EA | 112 | 7280 | 2436.98 | 268068
20 inch | 150-10-S-110 | Shop Butt Weld - NB 20 SchXST | EA | 6 | 240 | 81.6725 | 8984
20 inch | 150-29-S-290 | Shop handling - NB 20 Sch80 | LM | 132.578 | 0 | 136.2819 | 14991
20 inch | 150-29-S-290 | Shop handling - NB 20 SchXST | LM | 2.414 | 0 | 2.4814 | 273
20 inch | 150-60-S-610 | Shop X-Ray - NB 20 | EA | 14 | 0 | 0 | 7000
20 inch | 150-70-S-710 | Shop Hydrotest - NB 20 Sch80 | EA | 12 | 0 | 494.4 | 54384
20 inch | 150-80-S-810 | Shop Spools Coating - NB 20 | EA | 12 | 0 | 0 | 32400
20 inch Total |  |  |  |  | 7520 | 3151.8158 | 386100
16 inch | 150-10-S-110 | Shop Butt Weld - NB 16 Sch80 | EA | 96 | 4608 | 1379.04 | 151694
16 inch | 150-10-S-110 | Shop Butt Weld - NB 16 SchSTD | EA | 14 | 336 | 123.6387 | 13600
16 inch | 150-10-S-110 | Shop Butt Weld - NB 16 SchXST | EA | 26 | 832 | 419.12 | 46103
16 inch | 150-29-S-290 | Shop handling - NB 16 Sch80 | LM | 111.045 | 0 | 88.0971 | 9691
16 inch | 150-29-S-290 | Shop handling - NB 16 SchSTD | LM | 43.76 | 0 | 25.7576 | 2833
16 inch | 150-29-S-290 | Shop handling - NB 16 SchXST | LM | 7.064 | 0 | 5.6042 | 616
16 inch | 150-60-S-610 | Shop X-Ray - NB 16 | EA | 45 | 0 | 0 | 11250
16 inch | 150-70-S-710 | Shop Hydrotest - NB 16 Sch80 | EA | 9 | 0 | 158.4 | 17424
16 inch | 150-70-S-710 | Shop Hydrotest - NB 16 SchSTD | EA | 3 | 0 | 46.8 | 5148
16 inch | 150-80-S-810 | Shop Spools Coating - NB 16 | EA | 12 | 0 | 0 | 25200
16 inch Total |  |  |  |  | 5776 | 2246.4576 | 283559
14 inch | 150-10-S-110 | Shop Butt Weld - NB 14 Sch80 | EA | 24 | 840 | 245.076 | 26958
14 inch | 150-29-S-290 | Shop handling - NB 14 Sch80 | LM | 16.032 | 0 | 10.8726 | 1196
14 inch | 150-60-S-610 | Shop X-Ray - NB 14 | EA | 6 | 0 | 0 | 1500
14 inch Total |  |  |  |  | 840 | 255.9486 | 29654
12 inch | 150-10-S-110 | Shop Butt Weld - NB 12 Sch80 | EA | 280 | 8400 | 2151.24 | 236636
12 inch | 150-10-S-110 | Shop Butt Weld - NB 12 SchSTD | EA | 74 | 1332 | 349.687 | 38466
12 inch | 150-29-S-290 | Shop handling - NB 12 Sch80 | LM | 304.543 | 0 | 174.0616 | 19147
12 inch | 150-29-S-290 | Shop handling - NB 12 SchSTD | LM | 77.687 | 0 | 31.8104 | 3499
12 inch | 150-60-S-610 | Shop X-Ray - NB 12 | EA | 106 | 0 | 0 | 26500
12 inch | 150-70-S-710 | Shop Hydrotest - NB 12 Sch80 | EA | 26 | 0 | 494 | 54340
12 inch | 150-70-S-710 | Shop Hydrotest - NB 12 SchSTD | EA | 8 | 0 | 97.6 | 10736
12 inch | 150-80-S-810 | Shop Spools Coating - NB 12 | EA | 34 | 0 | 0 | 57800
12 inch Total |  |  |  |  | 9732 | 3298.399 | 447124
10 inch | 150-10-S-110 | Shop Butt Weld - NB 10 Sch80 | EA | 74 | 1850 | 437.71 | 48148
10 inch | 150-10-S-110 | Shop Butt Weld - NB 10 SchSTD | EA | 8 | 120 | 33.4256 | 3677
10 inch | 150-29-S-290 | Shop handling - NB 10 Sch80 | LM | 45.668 | 0 | 21.4266 | 2357
10 inch | 150-29-S-290 | Shop handling - NB 10 SchSTD | LM | 5.322 | 0 | 1.7933 | 197
10 inch | 150-60-S-610 | Shop X-Ray - NB 10 | EA | 20 | 0 | 0 | 5000
10 inch | 150-70-S-710 | Shop Hydrotest - NB 10 Sch80 | EA | 5 | 0 | 73 | 8030
10 inch | 150-80-S-810 | Shop Spools Coating - NB 10 | EA | 5 | 0 | 0 | 7500
10 inch Total |  |  |  |  | 1970 | 567.3555 | 74909
8 inch | 150-10-S-110 | Shop Butt Weld - NB 8 SchSTD | EA | 58 | 464 | 174.551 | 19201
8 inch | 150-10-S-110 | Shop Butt Weld - NB 8 SchXST | EA | 62 | 744 | 238.576 | 26243
8 inch | 150-29-S-290 | Shop handling - NB 8 SchSTD | LM | 35.417 | 0 | 9.517 | 1047
8 inch | 150-29-S-290 | Shop handling - NB 8 SchXST | LM | 22.012 | 0 | 8.2621 | 909
8 inch | 150-60-S-610 | Shop X-Ray - NB 8 | EA | 53 | 0 | 0 | 5300
8 inch | 150-70-S-710 | Shop Hydrotest - NB 8 SchSTD | EA | 4 | 0 | 39.2 | 4312
8 inch | 150-70-S-710 | Shop Hydrotest - NB 8 SchXST | EA | 2 | 0 | 32 | 3520
8 inch | 150-80-S-810 | Shop Spools Coating - NB 8 | EA | 6 | 0 | 0 | 6600
8 inch Total |  |  |  |  | 1208 | 502.1062 | 67132
6 inch | 150-10-S-110 | Shop Butt Weld - NB 6 SchSTD | EA | 34 | 204 | 82.654 | 9092
6 inch | 150-10-S-110 | Shop Butt Weld - NB 6 SchXST | EA | 242 | 2178 | 709.423 | 78037
6 inch | 150-29-S-290 | Shop handling - NB 6 SchSTD | LM | 11.731 | 0 | 2.5518 | 281
6 inch | 150-29-S-290 | Shop handling - NB 6 SchXST | LM | 171.341 | 0 | 51.1575 | 5627
6 inch | 150-60-S-610 | Shop X-Ray - NB 6 | EA | 72 | 0 | 0 | 5400
6 inch | 150-70-S-710 | Shop Hydrotest - NB 6 SchSTD | EA | 1 | 0 | 8.8 | 968
6 inch | 150-70-S-710 | Shop Hydrotest - NB 6 SchXST | EA | 19 | 0 | 228 | 25080
6 inch | 150-80-S-810 | Shop Spools Coating - NB 6 | EA | 20 | 0 | 0 | 18000
6 inch Total |  |  |  |  | 2382 | 1082.5863 | 142485
4 inch | 150-10-S-110 | Shop Butt Weld - NB 4 SchSTD | EA | 19 | 76 | 31.9865 | 3519
4 inch | 150-10-S-110 | Shop Butt Weld - NB 4 SchXST | EA | 122 | 732 | 258.518 | 28437
4 inch | 150-29-S-290 | Shop handling - NB 4 SchSTD | LM | 10.831 | 0 | 2.0789 | 229
4 inch | 150-29-S-290 | Shop handling - NB 4 SchXST | LM | 85.427 | 0 | 21.1336 | 2325
4 inch | 150-60-S-610 | Shop X-Ray - NB 4 | EA | 40 | 0 | 0 | 2000
4 inch | 150-70-S-710 | Shop Hydrotest - NB 4 SchSTD | EA | 1 | 0 | 7 | 770
4 inch | 150-70-S-710 | Shop Hydrotest - NB 4 SchXST | EA | 8 | 0 | 67.2 | 7392
4 inch | 150-80-S-810 | Shop Spools Coating - NB 4 | EA | 9 | 0 | 0 | 6300
4 inch Total |  |  |  |  | 808 | 387.9169 | 50972
3 inch | 150-10-S-110 | Shop Butt Weld - NB 3 SchSTD | EA | 151 | 453 | 207.0965 | 22781
3 inch | 150-10-S-110 | Shop Butt Weld - NB 3 SchXST | EA | 12 | 54 | 19.032 | 2094
3 inch | 150-10-S-120 | Shop Socket Weld - NB 3 Sch160 | EA | 7 | 31.5 | 15.47 | 1702
3 inch | 150-10-S-120 | Shop Socket Weld - NB 3 SchXST | EA | 2 | 6 | 3.12 | 343
3 inch | 150-10-S-130 | Shop Olet Weld - NB 3 CL3000 | EA | 7 | 63 | 53.69 | 5906
3 inch | 150-29-S-290 | Shop handling - NB 3 SchSTD | LM | 105.754 | 0 | 18.494 | 2034
3 inch | 150-60-S-610 | Shop X-Ray - NB 3 | EA | 152 | 0 | 0 | 7600
3 inch | 150-70-S-710 | Shop Hydrotest - NB 3 SchSTD | EA | 11 | 0 | 66 | 7260
3 inch | 150-80-S-810 | Shop Spools Coating - NB 3 | EA | 11 | 0 | 0 | 6600
3 inch Total |  |  |  |  | 607.5 | 382.9025 | 56320
2 inch | 150-10-S-110 | Shop Butt Weld - NB 2 Sch160 | EA | 1 | 3.5 | 1.781 | 196
2 inch | 150-10-S-110 | Shop Butt Weld - NB 2 SchXST | EA | 1390 | 4170 | 1635.335 | 179887
2 inch | 150-10-S-120 | Shop Socket Weld - NB 2 Sch160 | EA | 58 | 174 | 98.02 | 10782
2 inch | 150-10-S-120 | Shop Socket Weld - NB 2 SchXST | EA | 30 | 60 | 35.1 | 3861
2 inch | 150-10-S-130 | Shop Olet Weld - NB 2 CL2000 | EA | 20 | 120 | 88.4 | 9724
2 inch | 150-10-S-130 | Shop Olet Weld - NB 2 CL3000 | EA | 128 | 768 | 698.88 | 76877
2 inch | 150-19-S-190 | Shop Threaded Connection - NB 2 SchXST | EA | 7 | 35 | 3.003 | 330
2 inch | 150-29-S-290 | Shop handling - NB 2 SchXST | LM | 428.165 | 0 | 80.3551 | 8839
2 inch | 150-60-S-610 | Shop X-Ray - NB 2 | EA | 931 | 0 | 0 | 46550
2 inch | 150-70-S-710 | Shop Hydrotest - NB 2 SchXST | EA | 34 | 0 | 190.4 | 20944
2 inch | 150-80-S-810 | Shop Spools Coating - NB 2 | EA | 34 | 0 | 0 | 17000
2 inch | 150-10-S-120 | Shop Socket Weld - NB 1.5 2000psi | EA | 8 | 18 | 8.32 | 915
2 inch | 150-10-S-120 | Shop Socket Weld - NB 1.5 CL3000 | EA | 20 | 45 | 20.8 | 2288
2 inch | 150-10-S-120 | Shop Socket Weld - NB 1.5 Sch160 | EA | 15 | 45 | 19.5 | 2145
2 inch | 150-10-S-120 | Shop Socket Weld - NB 1.5 SchXST | EA | 3 | 6.75 | 3.12 | 343
2 inch | 150-29-S-290 | Shop handling - NB 1.5 SchXST | LM | 3.46 | 0 | 0.60508 | 67
2 inch | 150-60-S-610 | Shop X-Ray - NB 1.5 | EA | 46 | 0 | 0 | 2300
2 inch Total |  |  |  |  | 5445.25 | 2883.6192 | 383048
1 inch | 150-10-S-110 | Shop Butt Weld - NB 1 SchXXS | EA | 1 | 3 | 0.585 | 64
1 inch | 150-10-S-120 | Shop Socket Weld - NB 1 2000psi | EA | 44 | 55 | 34.32 | 3775
1 inch | 150-10-S-120 | Shop Socket Weld - NB 1 3000psi | EA | 158 | 197.5 | 123.24 | 13556
1 inch | 150-10-S-120 | Shop Socket Weld - NB 1 CL3000 | EA | 371 | 463.75 | 289.38 | 31832
1 inch | 150-10-S-120 | Shop Socket Weld - NB 1 CL6000 | EA | 20 | 30 | 18.2 | 2002
1 inch | 150-10-S-120 | Shop Socket Weld - NB 1 CL800 | EA | 12 | 15 | 9.36 | 1030
1 inch | 150-10-S-120 | Shop Socket Weld - NB 1 Sch160 | EA | 300 | 375 | 273 | 30030
1 inch | 150-10-S-120 | Shop Socket Weld - NB 1 SchXST | EA | 30 | 37.5 | 23.4 | 2574
1 inch | 150-10-S-120 | Shop Socket Weld - NB 1 SchXXS | EA | 471 | 706.5 | 428.61 | 47147
1 inch | 150-10-S-130 | Shop Olet Weld - NB 1 CL3000 | EA | 24 | 72 | 68.64 | 7550
1 inch | 150-10-S-130 | Shop Olet Weld - NB 1 CL6000 | EA | 20 | 60 | 75.4 | 8294
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 1 2000psi | EA | 44 | 110 | 17.16 | 1888
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 1 3000psi | EA | 32 | 80 | 12.48 | 1373
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 1 CL3000 | EA | 91 | 227.5 | 35.49 | 3904
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 1 Sch160 | EA | 30 | 75 | 11.7 | 1287
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 1 SchXXS | EA | 38 | 95 | 14.82 | 1630
1 inch | 150-29-S-290 | Shop handling - NB 1 Sch160 | LM | 29.546 | 0 | 5.2929 | 582
1 inch | 150-29-S-290 | Shop handling - NB 1 SchXST | LM | 11.59 | 0 | 1.7797 | 196
1 inch | 150-60-S-610 | Shop X-Ray - NB 1 | EA | 497 | 0 | 0 | 24850
1 inch | 150-10-S-120 | Shop Socket Weld - NB 0.75 2000psi | EA | 22 | 20.625 | 14.3 | 1573
1 inch | 150-10-S-120 | Shop Socket Weld - NB 0.75 3000psi | EA | 42 | 39.375 | 27.3 | 3003
1 inch | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL3000 | EA | 58 | 54.375 | 37.7 | 4147
1 inch | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL6000 | EA | 2 | 1.875 | 1.56 | 172
1 inch | 150-10-S-120 | Shop Socket Weld - NB 0.75 CL800 | EA | 8 | 7.5 | 5.2 | 572
1 inch | 150-10-S-120 | Shop Socket Weld - NB 0.75 Sch160 | EA | 35 | 32.8125 | 27.3 | 3003
1 inch | 150-10-S-120 | Shop Socket Weld - NB 0.75 SchXXS | EA | 101 | 94.6875 | 78.78 | 8666
1 inch | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL3000 | EA | 9 | 13.5 | 22.23 | 2445
1 inch | 150-10-S-130 | Shop Olet Weld - NB 0.75 CL6000 | EA | 2 | 3 | 6.76 | 744
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 0.75 2000psi | EA | 20 | 37.5 | 5.2 | 572
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 0.75 3000psi | EA | 42 | 78.75 | 10.92 | 1201
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 0.75 CL3000 | EA | 55 | 103.125 | 14.3 | 1573
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 0.75 Sch160 | EA | 2 | 3.75 | 0.52 | 57
1 inch | 150-29-S-290 | Shop handling - NB 0.75 Sch160 | LM | 5.132 | 0 | 0.85369 | 94
1 inch | 150-60-S-610 | Shop X-Ray - NB 0.75 | EA | 163 | 0 | 0 | 8150
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 0.5 Sch160 | EA | 9 | 11.25 | 2.34 | 257
1 inch | 150-19-S-190 | Shop Threaded Connection - NB 0.5 SchXXS | EA | 38 | 47.5 | 9.88 | 1087
1 inch Total |  |  |  |  | 3152.375 | 1708.0013 | 220880
| 150-50-S-519 | Pipe Supports Labor (shoes, lugs, guides, etc.) | 5% of Labor hours |  |  | 963.9511 | 106035
Grand Total |  |  |  |  | 44619.125 | 20242.974 | 2597328
Pipe Spool Fabrication Quantities, Craft Labor Hours and Metrics
Example - Imaginary Project with made up quantities for Illustration Purposes See Interactive Power BI Report on the website for more estimate insights
Go to Tab Index

## Module Piping Summary
Dia | COA | Description | Units | Module Qty | Module Hours | Module Cost
24 inch | 150-20-M-210 | Install Spools - NB 24 Sch40 | LM | 17 | 96 | 10595
24 inch | 150-20-M-210 | Install Spools - NB 24 Sch80 | LM | 119 | 892 | 98042
24 inch | 150-20-M-210 | Install Spools - NB 24 SchXST | LM | 14 | 107 | 11754
24 inch | 150-30-M-310 | Install valve - NB 24 CL600 | EA | 1 | 18 | 1945
24 inch | 150-40-M-410 | Flange Bolt-Up - NB 24 CL300 | EA | 2 | 19 | 2116
24 inch | 150-40-M-410 | Flange Bolt-Up - NB 24 CL600 | EA | 14 | 144 | 15816
24 inch | 150-50-M-510 | Erection of Pipe Supports - NB 24 | EA | 22 | 57 | 6208
24 inch Total |  |  |  | 189 | 1333 | 146476
20 inch | 150-20-M-210 | Install Spools - NB 20 Sch80 | LM | 93 | 620 | 68285
20 inch | 150-20-M-210 | Install Spools - NB 20 SchXST | LM | 3 | 18 | 2024
20 inch | 150-30-M-310 | Install valve - NB 20 CL600 | EA | 3 | 46 | 5105
20 inch | 150-40-M-410 | Flange Bolt-Up - NB 20 CL600 | EA | 15 | 142 | 15573
20 inch | 150-50-M-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 14 | 1536
20 inch Total |  |  |  | 120 | 840 | 92523
16 inch | 150-20-M-210 | Install Spools - NB 16 Sch80 | LM | 102 | 520 | 57187
16 inch | 150-20-M-210 | Install Spools - NB 16 SchSTD | LM | 50 | 191 | 20990
16 inch | 150-20-M-210 | Install Spools - NB 16 SchXST | LM | 8 | 40 | 4562
16 inch | 150-30-M-310 | Install Blind - NB 16 CL300 | EA | 3 | 27 | 3045
16 inch | 150-30-M-310 | Install Blind - NB 16 CL600 | EA | 2 | 22 | 2516
16 inch | 150-30-M-310 | Install Inlines - NB 16 CL300 | EA | 4 | 36 | 4060
16 inch | 150-30-M-310 | Install valve - NB 16 CL300 | EA | 3 | 27 | 3045
16 inch | 150-30-M-310 | Install valve - NB 16 CL600 | EA | 1 | 11 | 1258
16 inch | 150-40-M-410 | Flange Bolt-Up - NB 16 CL300 | EA | 12 | 86 | 9460
16 inch | 150-40-M-410 | Flange Bolt-Up - NB 16 CL600 | EA | 15 | 111 | 12270
16 inch | 150-50-M-510 | Erection of Pipe Supports - NB 16 | EA | 17 | 35 | 3947
16 inch Total |  |  |  | 217 | 1106 | 122340
12 inch | 150-20-M-210 | Install Spools - NB 12 Sch80 | LM | 209 | 767 | 84362
12 inch | 150-20-M-210 | Install Spools - NB 12 SchSTD | LM | 15 | 41 | 4467
12 inch | 150-40-M-410 | Flange Bolt-Up - NB 12 CL600 | EA | 17 | 91 | 9967
12 inch | 150-50-M-510 | Erection of Pipe Supports - NB 12 | EA | 15 | 29 | 3159
12 inch Total |  |  |  | 256 | 928 | 101955
10 inch | 150-20-M-210 | Install Spools - NB 10 Sch80 | LM | 8 | 26 | 2784
10 inch | 150-20-M-210 | Install Spools - NB 10 SchSTD | LM | 6 | 14 | 1446
10 inch | 150-30-M-310 | Install Blind - NB 10 CL600 | EA | 2 | 14 | 1458
10 inch | 150-30-M-310 | Install valve - NB 10 CL600 | EA | 4 | 26 | 2918
10 inch | 150-40-M-410 | Flange Bolt-Up - NB 10 CL300 | EA | 0 | 4 | 430
10 inch | 150-40-M-410 | Flange Bolt-Up - NB 10 CL600 | EA | 9 | 42 | 4576
10 inch | 150-50-M-510 | Erection of Pipe Supports - NB 10 | EA | 6 | 12 | 1206
10 inch Total |  |  |  | 35 | 138 | 14818
8 inch | 150-40-M-410 | Flange Bolt-Up - NB 8 CL300 | EA | 0 | 4 | 344
8 inch Total |  |  |  | 0 | 4 | 344
3 inch | 150-40-M-410 | Flange Bolt-Up - NB 3 CL300 | EA | 0 | 2 | 128
3 inch Total |  |  |  | 0 | 2 | 128
2 inch | 150-20-M-210 | Install Spools - NB 2 SchXST | LM | 71 | 83 | 9212
2 inch | 150-30-M-310 | Install Blind - NB 2 CL150 | EA | 2 | 2 | 144
2 inch | 150-30-M-310 | Install valve - NB 2 CL150 | EA | 1 | 1 | 72
2 inch | 150-30-M-310 | Install valve - NB 2 CL300 | EA | 12 | 12 | 1371
2 inch | 150-30-M-310 | Install valve - NB 2 CL600 | EA | 19 | 32 | 3534
2 inch | 150-40-M-410 | Flange Bolt-Up - NB 2 CL150 | EA | 12 | 11 | 1300
2 inch | 150-40-M-410 | Flange Bolt-Up - NB 2 CL300 | EA | 24 | 24 | 2516
2 inch | 150-40-M-410 | Flange Bolt-Up - NB 2 CL600 | EA | 41 | 45 | 5148
2 inch | 150-50-M-510 | Erection of Pipe Supports - NB 2 | EA | 15 | 15 | 1650
2 inch Total |  |  |  | 197 | 225 | 24947
1 inch | 150-20-M-210 | Install Spools - NB 1 SchXST | LM | 0 | 0 | 48
1 inch | 150-30-M-310 | Install valve - NB 1 2000psi | EA | 8 | 3 | 344
1 inch | 150-30-M-310 | Install valve - NB 1 CL3000 | EA | 3 | 3 | 300
1 inch | 150-30-M-310 | Install valve - NB 1 CL600 | EA | 1 | 1 | 86
1 inch | 150-40-M-410 | Flange Bolt-Up - NB 1 CL300 | EA | 8 | 12 | 1030
1 inch | 150-40-M-410 | Flange Bolt-Up - NB 1 CL600 | EA | 4 | 6 | 643
1 inch | 150-50-M-510 | Erection of Pipe Supports - NB 1 | EA | 2 | 0 | 88
1 inch | 150-30-M-310 | Install valve - NB 0.75 2000psi | EA | 4 | 0 | 172
1 inch | 150-30-M-310 | Install valve - NB 0.75 3000psi | EA | 1 | 1 | 72
1 inch | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 0 | 2 | 114
1 inch | 150-40-M-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 0 | 1 | 64
1 inch Total |  |  |  | 31 | 29 | 2961
| 150-70-M-719 | Hydrotest of module assembly | 5% of Module Labor |  | 230 | 25325
| 150-90-M-919 | Flushing & Drying Module Piping | 3% of Module Labor |  | 138 | 15195
[5 empty] | 368 | 40520
Grand Total |  |  |  |  | 4973 | 547012
Module Piping Quantities, Craft Labor Hours and Metrics
Example - Imaginary Project with made up quantities for Illustration Purposes See Interactive Power BI Report on the website for more estimate insights
Go to Tab Index

## Field Piping Summary
Dia | COA | Description | Units | Field Qty | Field Hours | Field Cost
24 inch | 150-10-F-110 | Field Butt Weld - NB 24 Sch80 | EA | 2 | 60.5183 | 4720
24 inch Total |  |  |  |  | 60.5183 | 4720
20 inch | 150-10-F-110 | Field Butt Weld - NB 20 Sch80 | EA | 1 | 23.4478 | 1829
20 inch | 150-20-F-210 | Install Spools - NB 20 Sch80 | LM | 58.8087 | 292.3502 | 22803
20 inch | 150-30-F-310 | Install Blind - NB 20 CL600 | EA | 6 | 69.615 | 5430
20 inch | 150-30-F-310 | Install valve - NB 20 CL600 | EA | 6 | 69.615 | 5430
20 inch | 150-40-F-410 | Flange Bolt-Up - NB 20 CL600 | EA | 15 | 96.525 | 7530
20 inch | 150-50-F-510 | Erection of Pipe Supports - NB 20 | EA | 6 | 10.4715 | 816
20 inch Total |  |  |  |  | 562.0245 | 43838
16 inch | 150-10-F-110 | Field Butt Weld - NB 16 Sch80 | EA | 2 | 30.5858 | 2386
16 inch | 150-10-F-110 | Field Butt Weld - NB 16 SchSTD | EA | 1 | 8.7399 | 682
16 inch | 150-20-F-210 | Install Spools - NB 16 Sch80 | LM | 25.8761 | 99.0843 | 7729
16 inch | 150-30-F-310 | Install Inlines - NB 16 CL600 | EA | 6 | 51.48 | 4014
16 inch | 150-40-F-410 | Flange Bolt-Up - NB 16 CL600 | EA | 16.5 | 83.655 | 6527
16 inch | 150-50-F-510 | Erection of Pipe Supports - NB 16 | EA | 10 | 15.8299 | 1232
16 inch Total |  |  |  |  | 289.3748 | 22570
14 inch | 150-20-F-210 | Install Spools - NB 14 Sch80 | LM | 18.4368 | 60.2764 | 4701
14 inch | 150-40-F-410 | Flange Bolt-Up - NB 14 CL600 | EA | 9 | 40.365 | 3150
14 inch | 150-50-F-510 | Erection of Pipe Supports - NB 14 | EA | 6 | 9.0456 | 708
14 inch Total |  |  |  |  | 109.687 | 8559
12 inch | 150-10-F-110 | Field Butt Weld - NB 12 Sch80 | EA | 8 | 68.133 | 5314
12 inch | 150-10-F-110 | Field Butt Weld - NB 12 SchSTD | EA | 1 | 5.3742 | 419
12 inch | 150-20-F-210 | Install Spools - NB 12 Sch80 | LM | 141.3902 | 389.4335 | 30375
12 inch | 150-20-F-210 | Install Spools - NB 12 SchSTD | LM | 73.884 | 145.5936 | 11357
12 inch | 150-25-F-250 | Erection of Field Run Pipe - NB 12 Sch80 | LM | 92.3277 | 215.6085 | 16817
12 inch | 150-25-F-250 | Erection of Field Run Pipe - NB 12 SchSTD | LM | 18.4242 | 30.648 | 2391
12 inch | 150-30-F-310 | Install Blind - NB 12 CL150 | EA | 2 | 8.385 | 654
12 inch | 150-30-F-310 | Install Blind - NB 12 CL600 | EA | 4 | 24.57 | 1916
12 inch | 150-30-F-310 | Install valve - NB 12 CL150 | EA | 4 | 16.77 | 1308
12 inch | 150-30-F-310 | Install valve - NB 12 CL600 | EA | 14 | 85.995 | 6706
12 inch | 150-40-F-410 | Flange Bolt-Up - NB 12 CL150 | EA | 16.5 | 54.6975 | 4267
12 inch | 150-40-F-410 | Flange Bolt-Up - NB 12 CL300 | EA | 1.5 | 5.5575 | 433
12 inch | 150-40-F-410 | Flange Bolt-Up - NB 12 CL600 | EA | 69 | 275.8275 | 21516
12 inch | 150-50-F-510 | Erection of Pipe Supports - NB 12 | EA | 42 | 60.3043 | 4704
12 inch | 150-60-F-610 | Field X-Ray - NB 12 | EA | 1 | 0 | 1500
12 inch | 150-80-F-810 | Field Coating - NB 12 | LM | 110.7519 | 0 | 13291
12 inch Total |  |  |  |  | 1386.8976 | 122968
10 inch | 150-20-F-210 | Install Spools - NB 10 Sch80 | LM | 44.0404 | 98.6189 | 7693
10 inch | 150-30-F-310 | Install Blind - NB 10 CL600 | EA | 3 | 14.9175 | 1164
10 inch | 150-30-F-310 | Install valve - NB 10 CL600 | EA | 4 | 19.89 | 1552
10 inch | 150-40-F-410 | Flange Bolt-Up - NB 10 CL600 | EA | 12 | 37.44 | 2921
10 inch | 150-50-F-510 | Erection of Pipe Supports - NB 10 | EA | 15 | 20.5117 | 1600
10 inch Total |  |  |  |  | 191.3781 | 14930
8 inch | 150-10-F-110 | Field Butt Weld - NB 8 SchSTD | EA | 1 | 3.2165 | 251
8 inch | 150-20-F-210 | Install Spools - NB 8 SchSTD | LM | 38.9587 | 49.7265 | 3878
8 inch | 150-20-F-210 | Install Spools - NB 8 SchXST | LM | 24.2132 | 43.9184 | 3426
8 inch | 150-25-F-250 | Erection of Field Run Pipe - NB 8 SchSTD | LM | 19.1103 | 20.7853 | 1621
8 inch | 150-30-F-310 | Install Blind - NB 8 CL150 | EA | 1 | 2.73 | 213
8 inch | 150-30-F-310 | Install Inlines - NB 8 CL600 | EA | 2 | 8.19 | 638
8 inch | 150-30-F-310 | Install valve - NB 8 CL300 | EA | 1 | 3.315 | 259
8 inch | 150-30-F-310 | Install valve - NB 8 CL600 | EA | 11 | 45.045 | 3511
8 inch | 150-40-F-410 | Flange Bolt-Up - NB 8 CL150 | EA | 5.5 | 11.2613 | 879
8 inch | 150-40-F-410 | Flange Bolt-Up - NB 8 CL300 | EA | 1 | 2.34 | 183
8 inch | 150-40-F-410 | Flange Bolt-Up - NB 8 CL600 | EA | 35 | 88.725 | 6925
8 inch | 150-50-F-510 | Erection of Pipe Supports - NB 8 | EA | 18 | 23.4419 | 1829
8 inch | 150-60-F-610 | Field X-Ray - NB 8 | EA | 1 | 0 | 1500
8 inch | 150-80-F-810 | Field Coating - NB 8 | LM | 19.1103 | 0 | 2293
8 inch Total |  |  |  |  | 302.6949 | 27406
6 inch | 150-10-F-110 | Field Butt Weld - NB 6 SchSTD | EA | 1 | 2.5126 | 196
6 inch | 150-10-F-110 | Field Butt Weld - NB 6 SchXST | EA | 13 | 41.1811 | 3211
6 inch | 150-20-F-210 | Install Spools - NB 6 SchSTD | LM | 12.9041 | 13.5811 | 1059
6 inch | 150-20-F-210 | Install Spools - NB 6 SchXST | LM | 188.4751 | 270.1114 | 21068
6 inch | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchSTD | LM | 64.1047 | 57.4194 | 4478
6 inch | 150-25-F-250 | Erection of Field Run Pipe - NB 6 SchXST | LM | 249.1412 | 302.8587 | 23623
6 inch | 150-30-F-310 | Install Blind - NB 6 CL150 | EA | 1 | 2.145 | 167
6 inch | 150-30-F-310 | Install Inlines - NB 6 CL600 | EA | 4 | 12.87 | 1004
6 inch | 150-30-F-310 | Install valve - NB 6 CL150 | EA | 2 | 4.29 | 334
6 inch | 150-30-F-310 | Install valve - NB 6 CL600 | EA | 8 | 25.74 | 2008
6 inch | 150-40-F-410 | Flange Bolt-Up - NB 6 CL150 | EA | 9 | 13.1625 | 1026
6 inch | 150-40-F-410 | Flange Bolt-Up - NB 6 CL600 | EA | 61 | 107.055 | 8349
6 inch | 150-50-F-510 | Erection of Pipe Supports - NB 6 | EA | 94 | 116.5894 | 9095
6 inch | 150-60-F-610 | Field X-Ray - NB 6 | EA | 2 | 0 | 2000
6 inch | 150-80-F-810 | Field Coating - NB 6 | LM | 313.2459 | 0 | 31325
6 inch Total |  |  |  |  | 969.516 | 108943
4 inch | 150-10-F-110 | Field Butt Weld - NB 4 SchXST | EA | 1 | 2.2425 | 175
4 inch | 150-20-F-210 | Install Spools - NB 4 SchSTD | LM | 11.9141 | 10.9384 | 853
4 inch | 150-20-F-210 | Install Spools - NB 4 SchXST | LM | 93.9697 | 109.4208 | 8536
4 inch | 150-25-F-250 | Erection of Field Run Pipe - NB 4 SchXST | LM | 32.1585 | 31.891 | 2487
4 inch | 150-30-F-310 | Install Blind - NB 4 CL600 | EA | 6 | 15.21 | 1188
4 inch | 150-30-F-310 | Install valve - NB 4 CL600 | EA | 6 | 15.21 | 1188
4 inch | 150-40-F-410 | Flange Bolt-Up - NB 4 CL150 | EA | 2.5 | 2.925 | 228
4 inch | 150-40-F-410 | Flange Bolt-Up - NB 4 CL600 | EA | 32 | 46.8 | 3648
4 inch | 150-50-F-510 | Erection of Pipe Supports - NB 4 | EA | 27 | 30.375 | 2371
4 inch | 150-80-F-810 | Field Coating - NB 4 | LM | 32.1585 | 0 | 2573
4 inch Total |  |  |  |  | 265.0128 | 23247
3 inch | 150-20-F-210 | Install Spools - NB 3 SchSTD | LM | 116.3294 | 101.5928 | 7924
3 inch | 150-30-F-310 | Install Blind - NB 3 CL150 | EA | 1 | 1.17 | 91
3 inch | 150-30-F-310 | Install Blind - NB 3 CL300 | EA | 2 | 2.925 | 228
3 inch | 150-30-F-310 | Install Inlines - NB 3 CL300 | EA | 1 | 1.4625 | 114
3 inch | 150-30-F-310 | Install valve - NB 3 CL150 | EA | 4 | 4.68 | 364
3 inch | 150-30-F-310 | Install valve - NB 3 CL300 | EA | 2 | 2.925 | 228
3 inch | 150-40-F-410 | Flange Bolt-Up - NB 3 CL150 | EA | 20 | 15.6 | 1215
3 inch | 150-40-F-410 | Flange Bolt-Up - NB 3 CL300 | EA | 11 | 9.6525 | 751
3 inch | 150-40-F-410 | Flange Bolt-Up - NB 3 CL600 | EA | 5 | 4.875 | 380
3 inch | 150-50-F-510 | Erection of Pipe Supports - NB 3 | EA | 38 | 42.75 | 3338
3 inch Total |  |  |  |  | 187.6328 | 14633
2 inch | 150-10-F-110 | Field Butt Weld - NB 2 SchXST | EA | 7 | 8.4016 | 656
2 inch | 150-20-F-210 | Install Spools - NB 2 SchXST | LM | 400.8543 | 359.0504 | 28006
2 inch | 150-25-F-250 | Erection of Field Run Pipe - NB 2 SchXST | LM | 165.517 | 127.0763 | 9912
2 inch | 150-30-F-310 | Install Blind - NB 2 CL150 | EA | 6 | 2.925 | 228
2 inch | 150-30-F-310 | Install Blind - NB 2 CL300 | EA | 2 | 1.56 | 122
2 inch | 150-30-F-310 | Install Blind - NB 2 CL600 | EA | 2 | 2.535 | 198
2 inch | 150-30-F-310 | Install Inlines - NB 2 CL600 | EA | 1 | 1.2675 | 99
2 inch | 150-30-F-310 | Install valve - NB 2 CL150 | EA | 28 | 13.65 | 1064
2 inch | 150-30-F-310 | Install valve - NB 2 CL300 | EA | 8 | 6.24 | 488
2 inch | 150-30-F-310 | Install valve - NB 2 CL600 | EA | 96 | 121.68 | 9504
2 inch | 150-40-F-410 | Flange Bolt-Up - NB 2 CL150 | EA | 116.5 | 79.5113 | 6204
2 inch | 150-40-F-410 | Flange Bolt-Up - NB 2 CL300 | EA | 26 | 20.28 | 1581
2 inch | 150-40-F-410 | Flange Bolt-Up - NB 2 CL600 | EA | 227.5 | 199.6312 | 15552
2 inch | 150-50-F-510 | Erection of Pipe Supports - NB 2 | EA | 176 | 132 | 10313
2 inch | 150-60-F-610 | Field X-Ray - NB 2 | EA | 7 | 0 | 5250
2 inch | 150-80-F-810 | Field Coating - NB 2 | LM | 165.517 | 0 | 9930
2 inch | 150-20-F-210 | Install Spools - NB 1.5 SchXST | LM | 3.633 | 3.0101 | 234
2 inch | 150-30-F-310 | Install valve - NB 1.5 2000psi | EA | 4 | 1.56 | 122
2 inch | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL150 | EA | 0.5 | 0.34125 | 27
2 inch | 150-40-F-410 | Flange Bolt-Up - NB 1.5 CL300 | EA | 1 | 0.78 | 60
2 inch | 150-50-F-510 | Erection of Pipe Supports - NB 1.5 | EA | 2 | 0.75 | 58
2 inch Total |  |  |  |  | 1082.2496 | 99608
1 inch | 150-20-F-210 | Install Spools - NB 1 Sch160 | LM | 31.0233 | 27.0933 | 2116
1 inch | 150-20-F-210 | Install Spools - NB 1 SchXST | LM | 11.739 | 8.9376 | 698
1 inch | 150-30-F-310 | Install valve - NB 1 2000psi | EA | 36 | 10.53 | 824
1 inch | 150-30-F-310 | Install valve - NB 1 3000psi | EA | 95 | 55.575 | 4343
1 inch | 150-30-F-310 | Install valve - NB 1 CL300 | EA | 1 | 0.2925 | 23
1 inch | 150-30-F-310 | Install valve - NB 1 CL3000 | EA | 17 | 11.6025 | 901
1 inch | 150-30-F-310 | Install valve - NB 1 CL600 | EA | 12 | 7.02 | 552
1 inch | 150-30-F-310 | Install valve - NB 1 CL800 | EA | 6 | 3.51 | 276
1 inch | 150-40-F-410 | Flange Bolt-Up - NB 1 CL150 | EA | 9.5 | 6.4837 | 508
1 inch | 150-40-F-410 | Flange Bolt-Up - NB 1 CL300 | EA | 8 | 6.24 | 483
1 inch | 150-40-F-410 | Flange Bolt-Up - NB 1 CL600 | EA | 118 | 103.545 | 8059
1 inch | 150-50-F-510 | Erection of Pipe Supports - NB 1 | EA | 44 | 13.2 | 1030
1 inch | 150-20-F-210 | Install Spools - NB 0.75 Sch160 | LM | 5.3886 | 4.2233 | 330
1 inch | 150-30-F-310 | Install valve - NB 0.75 2000psi | EA | 17 | 4.9725 | 391
1 inch | 150-30-F-310 | Install valve - NB 0.75 3000psi | EA | 41 | 19.9875 | 1558
1 inch | 150-30-F-310 | Install valve - NB 0.75 CL800 | EA | 4 | 1.95 | 152
1 inch | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL150 | EA | 1 | 0.6825 | 54
1 inch | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL300 | EA | 1 | 0.78 | 60
1 inch | 150-40-F-410 | Flange Bolt-Up - NB 0.75 CL600 | EA | 8.5 | 7.4588 | 578
1 inch | 150-50-F-510 | Erection of Pipe Supports - NB 0.75 | EA | 2 | 0.45 | 36
1 inch Total |  |  |  |  | 294.5341 | 22972
| 150-40-F-419 | Bolt torquing and tensioning | 15% of bolt-up labor |  | 198.3296 | 15470
| 150-70-F-719 | Field Hydrotest | 5% of Field Labor |  | 285.076 | 22236
| 150-90-F-919 | Flushing & Drying on Site | 3% of Field Labor |  | 171.0456 | 13342
[5 empty] | 654.4513 | 51048
Grand Total |  |  |  |  | 6355.9718 | 565442
Field Piping Quantities, Craft Labor Hours and Metrics
Example - Imaginary Project with made up quantities for Illustration Purposes See Interactive Power BI Report on the website for more estimate insights
Go to Tab Index

## Labor Codes
COA | COA_Description | Location | COA Group | CBS | CBS_Description | Units
150-10-S-110 | Shop Butt Welds | Spool Fabrication | 10 | 400 | Shop | EA
150-10-S-120 | Shop Socket Welds | Spool Fabrication | 10 | 400 | Shop | EA
150-10-S-130 | Shop Olet Welds | Spool Fabrication | 10 | 400 | Shop | EA
150-15-S-150 | Shop PWHT | Spool Fabrication | 15 | 300 | Shop_Sub-Contract | EA
150-19-S-190 | Shop Threaded Joints | Spool Fabrication | 19 | 400 | Shop | EA
150-29-S-290 | Shop Handling | Spool Fabrication | 29 | 400 | Shop | M
150-30-S-310 | Shop Install Valves, blinds, inlines | Spool Fabrication | 30 | 400 | Shop | EA
150-40-S-410 | Shop Flange Boltup | Spool Fabrication | 40 | 400 | Shop | EA
150-50-S-510 | Shop Pipe Supports | Spool Fabrication | 50 | 400 | Shop | EA
150-50-S-519 | Shop Pipe Support (shoes, guides, etc.) | Spool Fabrication | 50 | 400 | Shop | Lot
150-60-S-610 | Shop X-Ray | Spool Fabrication | 60 | 300 | Shop_Sub-Contract | EA
150-70-S-710 | Shop Hydrotest | Spool Fabrication | 70 | 400 | Shop | EA
150-80-S-810 | Shop Coating | Spool Fabrication | 80 | 300 | Shop_Sub-Contract | Spools
150-90-S-910 | Shop Flushing, Chemical Cleaning | Spool Fabrication | 90 | 400 | Shop | Lot
150-95-S-950 | Shop Miscellaneous | Spool Fabrication | 95 | 400 | Shop | Lot
150-99-S-990 | Shop Spool handling and Loadout | Spool Fabrication | 99 | 400 | Shop | Spools
150-10-M-110 | Module Butt Welds | Module | 10 | 500 | Module | EA
150-10-M-120 | Module Socket Welds | Module | 10 | 500 | Module | EA
150-10-M-130 | Module Olet Welds | Module | 10 | 500 | Module | EA
150-15-M-150 | Module PWHT | Module | 15 | 500 | Module | EA
150-19-M-190 | Module Threaded Joints | Module | 19 | 500 | Module | EA
150-20-M-210 | Module Erection of spools | Module | 20 | 500 | Module | M
150-25-M-250 | Module Installed piping | Module | 25 | 500 | Module | M
150-30-M-310 | Module Install Valves, blinds, inlines | Module | 30 | 500 | Module | EA
150-35-M-350 | Module Dismantle Inlines prior to hydrotest | Module | 35 | 500 | Module | EA
150-36-M-360 | Module Reinstall Inlines after hydrotest | Module | 36 | 500 | Module | EA
150-40-M-410 | Module Flange Boltup | Module | 40 | 500 | Module | EA
150-40-M-419 | Module Bolt torquing and tensioning - allowance | Module | 40 | 500 | Module | Lot
150-45-M-450 | Module Unbolt Inlines prior to hydrotest | Module | 45 | 500 | Module | EA
150-46-M-460 | Module Reboltup Inlines after hydrotest | Module | 46 | 500 | Module | EA
150-50-M-510 | Module Pipe Supports | Module | 50 | 500 | Module | EA
150-60-M-610 | Module X-Ray | Module | 60 | 300 | Module Sub-Contract | EA
150-70-M-710 | Module Hydrotest | Module | 70 | 500 | Module | M
150-70-M-719 | Module Hydrotest - allowance | Module | 70 | 500 | Module | Lot
150-80-M-810 | Module Coating | Module | 80 | 300 | Module Sub-Contract | Lot
150-90-M-910 | Module Flushing, Chemical Cleaning | Module | 90 | 500 | Module | Lot
150-90-M-919 | Module Flushing, Chemical Cleaning - allowance | Module | 90 | 500 | Module | Lot
150-10-F-110 | Field Butt Welds | Field | 10 | 600 | Field | EA
150-10-F-120 | Field Socket Welds | Field | 10 | 600 | Field | EA
150-10-F-130 | Field Olet Welds | Field | 10 | 600 | Field | EA
150-15-F-150 | Field PWHT | Field | 15 | 600 | Field | EA
150-19-F-190 | Field Threaded Joints | Field | 19 | 600 | Field | EA
150-20-F-210 | Field Erection of spools | Field | 20 | 600 | Field | M
150-25-F-250 | Field Installed piping | Field | 25 | 600 | Field | M
150-30-F-310 | Field Install Valves, blinds, inlines | Field | 30 | 600 | Field | EA
150-35-F-350 | Field Dismantle Inlines prior to hydrotest | Field | 35 | 600 | Field | EA
150-36-F-360 | Field Reinstall Inlines after hydrotest | Field | 36 | 600 | Field | EA
150-40-F-410 | Field Flange Boltup | Field | 40 | 600 | Field | EA
150-40-F-419 | Field Bolt torquing and tensioning - allowance | Field | 40 | 600 | Field | Lot
150-45-F-450 | Field Unbolt Inlines prior to hydrotest | Field | 45 | 600 | Field | EA
150-46-F-460 | Field Reboltup Inlines after hydrotest | Field | 46 | 600 | Field | EA
150-50-F-510 | Field Pipe Supports | Field | 50 | 600 | Field | EA
150-60-F-610 | Field X-Ray | Field | 60 | 300 | Field Sub-Contract | EA
150-70-F-710 | Field Hydrotest | Field | 70 | 600 | Field | M
150-70-F-719 | Field Hydrotest - allowance | Field | 70 | 600 | Field | Lot
150-80-F-810 | Field Coating | Field | 80 | 300 | Field Sub-Contract | M
150-90-F-910 | Field Flushing, Chemical Cleaning | Field | 90 | 600 | Field | Lot
150-90-F-919 | Field Flushing, Chemical Cleaning - allowance | Field | 90 | 600 | Field | Lot
Piping Labor - Code of Accounts
Go to Tab Index